MINISTRY OF FINANCE

Podgorica, June 2020

MONTENEGRO

MINISTRY OF FINANCE

PUBLIC FINANCE MANAGEMENT REFORM PROGRAM 2016 - 2020

ANNUAL REPORT FOR 2019

TABLE OF CONTENTS

INTRODUCTION	2

SUMMARY OF RESULTS	4

INFORMATION ON THE PROGRESS IN IMPLEMENTING THE REFORM OBJECTIVES AND THE ACCOMPANYING INDICATORS FOR THE YEAR  2019	13

OBJECTIVE  1.  Sustainable fiscal framework, planning and budgeting of public expenditure	13

OBJECTIVE 2. EXECUTION OF THE BUDGET	21

OBJECTIVE 3. Development of the system of internal financial controls	33

OBJECTIVE 4 Transparent financial reporting and accounting	35

OBJECTIVE 5. Strengthening the capacities of external audit	39

REPORTING TABLE 	44

ANNEX 1	i

Performance Indicator Passports for the program of the public finance management reform for the period 2016-2020	i

INTRODUCTION

The implementation of the objectives of the Program is also important when it comes to the coordination of efforts to meet the criteria for opening or closing accession negotiations in a number of negotiation chapters, especially in the negotiation chapters: 5 - Public Procurement; 16 - Taxation; 17 - Economic and Monetary Policy, 29 - Customs Union, 32 - Financial Control, 33 - Financial and Budgetary Provisions.

In accordance with the Guidelines for Monitoring and Reporting on the Implementation of The Public Finance Management Reform Programme for the period 2016-2020 (hereinafter: the Program), the Ministry of Finance with the active participation of 14 different organizational units, whose representatives are part of the Coordination Group and the Operational Team, prepared the Annual Report on the implementation of the revised Program for 2019 and "Performance Indicators Passport", including Action plan for 2020. The Strategic Framework for Public Administration Reform of Montenegro implements two umbrella strategies, the Public Administration Reform Strategy (PAR) and the Public Finance Management Reform Program for the period 2016-2020, in connection with which full cooperation was achieved with the Ministry of Public Administration, through participation in the work of the Special Group for Public Administration Reform. The annual report of the Program, prior to its submission to the Government of Montenegro, was previously adopted by the Public Administration Reform Council, with a positive opinion of the General Secretariat of the Government of Montenegro. Also, the Annual Report was prepared in accordance with the obligation of the Ministry of Finance to regularly report to the Government starting in 2017 and inform the European Commission twice a year on the progress achieved through the implementation of the Program.

The purpose of the Annual Report on the implementation of the Program for 2019 is to provide information at the level of results and evaluation of performance indicators for further implementation and improvement of the Public Finance Management Program for January - December 2019, as well as highlighting the strengths and weaknesses of the system. and challenges for its further development and improvement. While the Action Plan for the Implementation of the Public Finance Management Reform Programme 2016-2020 for 2020, aims to show the degree of implementation of activities in which the best and least progress has been made, as well as the projected financial resources in individual objectives under the Program.

The overview of the set reform objectives shows a clear progress in the Annual Report on the Implementation of the Program for 2019, and the key results relate to:

- Development of the Analysis of the best practice and the draft of Concept of the improvement of the budget system and the medium-term budget framework;

- Drafting a new program classification;

- Drafting of the Manual for Program Budgeting;

- Development of the first phase of software solutions for the improvement of IT systems for budget planning and IT systems for centralized salariesl;

- The module for macroeconomic projections of public finances as well as strategic documents has been improved;

- Through the implementation of the reprogram of tax receivables, the total revenue amounts to € 63,917,439;

- Revenue collection from Tax Administration revenues for 2019 was exceeded by 80 mil. € above planned;

- The Law on the Fiscalization in the Trade ofProducts and Services was adopted;

- Customs Administration contributed to the increase of total budget revenues through the realized net collection of revenues in the amount of € 808,595,189.83;

- Harmonization of customs and excise legislation with EU legislation (Decree on Amendments to the Decree on the Implementation of the Customs Law, Customs Tariff Regulation for for 2019, Regulation on Amendments to the Regulation on the Conditions for Granting the Status of an Authorized Economic Operator in the Customs Territory of Montenegro) ;

- The Law on Public Procurement was adopted;

- The Law on Public-Private Partnership was adopted;

- Strengthening the capacity of internal auditors through training and certification as well as the quality of work;

- The Law on Public Sector Accounting was adopted;

- Improved audit process within the State Audit Institution, as well as improved administrative capacity;

- 90% of shortcomings in the audit manual were eliminated (development of the Manual for areas 1,2,3,5 and the Manual for the are 4 IPARD), as well as the increased level of efficiency in conducting audits.

SUMMARY OF RESULTS

Last year was reflected in the finalization of tender procedures for PFM projects within CAP 2014, and as such represents the continuation of achieving the target values by starting the implementation of the remaining activities planned by the Program, while the implementation of activities has been carried out from own funds and existing capacities. Also, it is important to emphasize that most activities are not set on an annual basis, but on a multi-year basis. Therefore, if performance indicators are set as an outcome, then they can be seen only by observing the entire period.

The analysis of the overall status of implementation of the set measures clearly indicates the achieved progress, and we can conclude that the partially realized projected activities set for 2019 are of primary importance for fulfilling the recommendations from the last EC Report. However, despite the challenges, for the Public Finance Reform Program for the period 2016-2020, it is pointed out that there is room for further progress in order to achieve the final results expected in 2020, which, judging by the activities that began in 2019, will result in great success in the future.

Partially realized

Number of indicators being followed in 2019

Total number of indicators

Not realized

Fully realized

Ratio between total number of indicators nd the number of indicators being followed in 2019

Total number of activities with the deadline in 2019

Therefore, in the Annual Report for 2019, out of a total of 41 performance indicators, the fulfillment of 39 success indicators is observed, of which 24 indicators have been met, and 15 indicators have not reached the target value. At the same time, we emphasize that there is no information available for 2 performance indicators for the reporting period, bearing in mind the fact that data are prepared on a semi-annual basis, which means that data for 2019 will be ready and available in June 2020, during the preparation of the semi-annual Report.

Also, the adopted Action Plan 2016-2020 defines a total of 98 activities, which are crucial for achieving the defined reform objectives. The new Action Plan for 2019 includes a total of 80 activities. In the reporting period, out of a total of 80 activities, included in the Action Plan for the implementation of the Program, the implementation of 66 activities is in progress, which as a percentage represents the degree of implementation: i) 42% of activities are fully realized (28); ii) 47% partially realized (31); and iii) 11% has not been realized (7).

Negative trend

Progress

Partially ralized

Not realized

Fully realized

PERCENTAGE OF THE ACHIEVED SUCCESS RESULTS

DEGREE OF REALIZATION OF ACTIVITIES

When it comes to Sustainable Fiscal Framework, Public Expenditure Planning and Budgeting, the set objectives are achieved through the implementation of the project "Improving the budget system and medium-term budget planning, Improving the IT system for budget planning and Improving the IT system for centralized salaries". It can be stated that compared to the previous period, limited progress has been made in this area, but still visible, given that the achievement of results is predominantly conditioned by the implementation of IPA projects, which were previously worked on with existing capacities for preparatory activities.

So far, the implementation of most activities and achieved results has been conditioned through projects co-financed from EU funds through the IPA instrument that began in 2019.

In the area of improving the model for macroeconomic projections, some indicators are partially and some fully met, which shows positive trendfs in terms of the implementation of the Action Plan for Public Finance Management Reform. The module for macroeconomic projections has been improved, updated with the latest data from international financial institutions and Monstat, which results in greater consistency and less deviation in terms of projected economic trends compared to those achieved. The newly developed model has significantly improved the financial programming process, and significantly improved the forecast of the potential GDP growth rate. Also, progress has been made in macroeconomic planning and quantification of the impact of some structural reform measures, where the Structural Reform Impact Assessment Module in the 2020-2022 Economic Reform Program was used for the first time. In the part related to further training of employees to work on the model in 2019, the indicator was partially met, which means that a number of employee trainings were conducted, while due to the complexity of the training model, they must continue with it in the future. In that way, the planned full operationalization of the model and complete training of the employees in the directorate for work on it will be achieved in accordance with the expert recommendations. The target value of real GDP growth for 2018, predicted by the model projection, is within the planned deviation in relation to the achieved growth rate, whereby this difference is only 0.2 percentage points. This shows that adapting the model to the needs of the work process in order to facilitate the use and greater practical application of the model has led to results that are reflected in the very low value of the deviation of real economic growth from the projected rate.

When it comes to the area of taxation, most of the predicted values of performance indicators for the reporting period have been met, as shown by key indicators: the share of submitted electronic tax returns has significantly increased (number of submitted e-returns for VAT 77.37% and profit 99.5% ), compared to last year, VAT 70% and profit 99%; revenue collection for 2019 was exceeded by 80 mil. € above planned (€ 73 million for 2018); for the previous four years, th e level of due tax debt was reduced by 210 mil. € (for 2019 € 378,142,829.1 while in 2018 it amounted to € 397,418,265); so far, through the implementation of the reprogram of tax receivables, the total revenue amounts to € 63,917,439 (a large shift compared to the total amount until 2018, which amounted to € 20,632,549.28), while in 2019 alone, € 19,526,984 was collected; The Law on Fiscalization in Trade in Products and Services was adopted, which provided the legal basis for the implementation of the electronic fiscalization project, all with the aim of improving duty collection and combating the gray economy and improving the business environment, while the implementation of e-fiscalization shall start at the beginning of 2021; The administrative and operational capacities of the Tax Administration have been strengthened through the completed Twinning project "Support to the Tax Administration" (4 components) which is based on the main project implemented within the project "Tax Administration Reform" in terms of strengthening the capacity of the Tax Administration in accordance with international standards. contribute to better readiness of employees to implement the main project (Integrated IT system); a Human Resources Management Strategy has been developed, and a Key Performance Indicator (KPI) has been set up to enable performance measurement at the strategic and operational levels.

The target value related to the harmonization of further domestic legislation with the acquis communautaire of EU is delayed comparing to planned. Although the performance indicator has not been fully met, a positive trend can be seen compared to last year, with the completion of proposals to amend the envisaged laws and the last legislative committee. They are currently submitted to the EC for an opinion. The reason for the delay in the adoption is the subsequent proposal to include the tax police in the Law on Tax Administration.

The Customs Administration continues to significantly contribute to the increase of total budget revenues by implementing activities for proper and timely collection of revenues, which resulted in a net collection of revenues in the amount of € 808,595,189.83, which is 5.17% or € 40 million more and represents a positive trend compared to 2018. The harmonization of customs and excise legislation with EU legislation has also achieved its target value by adopting all three regulations envisaged for the reporting period (Regulation on Amendments to the Regulation on the Implementation of the Customs Law, Regulation on Customs Tariff for 2019, Regulation on Amendments and Supplements Regulations on conditions for granting the status of authorized economic entity in the customs territory of Montenegro); In September 2019, the project "Support to the Customs Administration in the field of excise duties" was launched, The Customs Administration, through the project for accession to the Convention on Common Transit and the establishment of a computerized transit system (NCTS) that is compatible with the EU system, implements activities in accordance with the defined plans, e-manifest application for express shipments that allows shipments to be processed by customs even before they are delivered to the customs territory of Montenegro has been developed; Intensive work has also been done on strengthening the quality of risk profiling, with a focus on risks in the field of excise products, thus improving the customs risk management system; the number of business entities has increased (5 approvals based on accounting entries and 17 approvals based on invoices compared to 7 approvals based on the previous year); In November 2019, the validation mission of the CEFTA contracting parties concluded that the Customs Administration has fulfilled the conditions for the implementation of the institute of authorized economic operator (AEO) and can start issuing approvals to businessmen who meet the prescribed conditions.

Within the area of ​​public procurement, significant progress has been made in meeting the target values. The legislation of Montenegro has been harmonized with the acquis communautaire of EU through the adopted Law on Public Procurement, which is one of the conditions for closing Chapter 5 - Public Procurement in the negotiation phase of Montenegro. A new framework for investment policy in Montenegro has been established, through the adoption of the Law on Public-Private Partnership. There was an increase in the average number of bids for 2018, which is 3.14 compared to the previous year with 2.66 (the average is even above some countries in the EU), and indicates the currently pronounced participation of bidders in tender procedures and competition, while the data for 2019 will be available in May 2020. Furthermore, at the end of 2018, a contract was signed with the project contractor on the Implementation of the electronic public procurement system. During 2019, the initial phase lasting 6 months was completed and the development phase of the system began in order to introduce a modern electronic public procurement system.

During 2019, positive trends were achieved in the area of ​​State Aid Reform within the three Performance Indicators. Within the started implementation of the IPA project "Improvement and strengthening of the institutional and legal framework in the field of state aid and public procurement“, as well as through professional seminars, in order to raise public awareness on state aid, the number of state aid providers and beneficiaries  increased significantly, representatives from the private sectors and judges who have undergone seminars and trainings in the field of state aid. Therefore, although the target value was not achieved, a large shift compared to last year is evident (total number of trainings 5, final number of participants 56, while in 2018 it was 0). Also, the percentage of trained employees in the Agency for Protection of the Competition and members of the Council of the Agency also increased, thus achieving the target value of 70%, which indicates an upward trajectory compared to last year 0%. Also, the Agency ex officio initiated 2 proceedings, which, however, due to the complexity and complexity of the solution were not completed during 2019. Furthermore, the target value per indicator Number of legal acts analyzed and assessed by the Agency was achieved and exceeded for the analyzed period (total number of applications was 35 for 2019, while in 2018 it was 23).

Regarding the Reform of the Department for Debt Management, Debt Analysis, Cash Management and Cooperation with Foreign Countries, trainings have continued for employees in the front office on the implementation of the medium-term debt management strategy, for the preparation and implementation of bond issues on the international market, as well as financial derivatives and hedging, as well as a new SAP software solution for public debt management was implemented in order to more efficiently manage public debt through the consolidation of public debt records through a single database.

In the area of ​​Development of the system of internal financial controls, the capacities of internal audit were improved through training and certification of internal auditors (18 workshops were held, the number of deployed certified internal auditors increased from 94.05% in 2018 to 100.00% in 2019), as well as quality of work (the percentage of implemented recommendations increased to 84.46% in 2019 from 79.16% in 2018). The number of appointed internal auditors per unit in 2019 is at approximately the same level as in 2018 (2.1 and 2.21, respectively) as well as the percentage of appointed certified auditors who have continuous professional development (81.36% in 2019 .and 83.64% in 2018). In the area of ​​management and control, reporting has been improved, 93% of reporting entities have submitted reports on activities to improve management and internal controls. In addition, the capacities of managers and employees in financial services were improved through training (7 trainings were held for 83 participants). The percentage of ministries delegating responsibilities and authorities is very low (12%), but its growth is expected after the adoption of the Regulation on the transfer of tasks and tasks of financial management and internal controls in the public sector.

Within the area of ​​Transparent Financial Reporting and Accounting, a positive trend is continuously achieved. The Law on Accounting in the Public Sector was adopted in November 2019, while in December of the same year, work began on 5 bylaws with the help of local and international experts, which will be finalized by the end of 2020. The law stipulates that by 2022, the information system will be adjusted to the new accounting regulations, as well as that trainings will be conducted for all accountants to apply the new regulations, since the law will be applied on January 1, 2022. In order to implement the Strategy for the transition of the public sector to accrual accounting, so far a total of 120 accountants have been trained through three generations (2017-40, 2018-40, 2019-40 participants, the total number of participants is 120), and the result reflected in the actual values ​​the performance indicator is above the planned values ​​in 2019 and meets one of the key objectives of transparent financial reporting.

When it comes to the indicator that measures the implementation of the asset register and double asset accounting, it is necessary to make additional efforts, ie. to continue with trainings, in order to achieve the set objectives. On the other hand, the Property Administration has made efforts to intensify activities in this field, as follows:

- Testing of the functions of the web application ARS (Asset Registry System), which is currently not responding in all functions, which led to additional costs for the improvement and development of the application;

- A database of budgetary and extra-budgetary users has been developed in order to monitor the up-to-dateness of data by users on movable and immovable property;

- Continuous training for the proper use of the ARS application continued (9 trainings, in which about 200 employees were trained), which resulted in the creation of accounts for the use of the web application for all direct budget users who attended the training;

- Migration of data on real estate and movable property is planned by the end of 2020;

- The planned transition from the test environment to production is starting from March 2021.

When it comes to Strengthening the capacity of external audit, a positive trend was achieved in the values ​​of the Performance Indicators that are monitored and measured in 2019. Within the State Audit Institution, the percentage of implementation of the Annual Audit Plan increased by 2.68% compared to the planned (86%), which resulted in an increase in the coverage of public spending; the audit process has been improved through the newly adopted Instruction on the methodology of performing success audits in accordance with level IV of ISSAI standards; The administrative capacity of the audit staff in the field of accounting and public sector auditing has been improved through the organization of 13 trainings (3 at the domestic level and 10 at the regional and international level). Thus, all set indicators that are planned for this area in 2019 have been fulfilled. While within the Audit Authority a positive trend was achieved for 3 key indicators set in accordance with the plan, which is also expected for the remaining Indicators in the continuation of project implementation: the capacity of the institution was strengthened through 11 trainings per auditor;

the audit manual was improved, i.e. 90% of the shortcomings of the manual were eliminated, while the target value for 2019 was 50%, which enabled the successful development of the Manual for areas 1,2,3,5 and the Manual for area 4 IPARD; due to the use of audit software, the level of efficiency of conducting audits increased, which achieved 33.33% compared to 20% of the set target value for 2019). Within the two remaining unrealized Performance Indicators, the Implementation of the AP was postponed to 2020 due to lack of management (chief auditor), while data for 2019 are not available for the level of application of standards due to the dynamics of implementation of audit activities due to deadlines (II quarter of 2020).

GENERAL PROGRESS

The Report of the European Commission on Montenegro for 2019 states that additional efforts are needed in the area of public financial management reform, as well as that the The Public Finance Management Reform Programme 2016-2020 realizes with a certain delay. In addition, the Government of Montenegro, i.e. the Ministry of Finance, provides regular monitoring and reporting on implementation, but a framework for integrated monitoring and reporting has yet to be established.

- Dialogue with European Commission

In order to promote and assist in ensuring sound financial management and good implementation of Government policies, in 2019 the regular Dialogue on The Public Finance Management Reform Programme between the Government of Montenegro and the Directorate General for Neighborhood and Enlargement Negotiations (DG NEAR) continued. annual and follow-up meetings of the Special Working Group on Public Administration Reform (PAR). The importance of the Ministry of Finance, which is leading the reform of public financial management, was emphasized, as well as the fact that continuous progress in the implementation of reforms is necessary, given that it is a condition for withdrawing Sectoral budget support funds under IPA funds.

In accordance with the conclusions from the sixth meeting of the special working group PAR, and in order to prepare the necessary analysis of the current PFM program, the Ministry of Finance began communication with representatives of the EU Delegations in Montenegro regarding the monitoring and evaluation of PFM. The Ministry of Finance developed and submitted the application form "Assessment of the Public Finance Management Reform Programme" through the EU Integration Financial Instrument (EUIF) in November 2019. The experts will analyze the current Public Finance Management Reform Program 2016-2020, providing the Ministry of Finance with specific recommendations, as well as an overview of the new public financial management strategy 2021-2025. The project was approved at the meeting of the EUIF Steering Committee held on November 27, 2019. Therefore, in the coming period, the Ministry of Finance will begin the process of evaluating the selection of the most compatible expert for the successful implementation of the program.

Also, in connection with the operational conclusion of the Special Working Group on in 2018 (12), which refers to the participation of Montenegro in the Open Budget Index, the MoF has established communication with representatives of the International Budget Partnership (IBP), in order to obtain detailed information on procedures for Montenegro's participation in the Open Budget Survey. In this regard, representatives of the IBP, which conducts the survey in a total of 117 countries, informed the Ministry of Finance that the participation of new countries in the Survey is subject to a number of restrictions (mainly personnel and financial), which currently make it difficult for new countries to participate. In the second half of 2020, the planning of the Open Budget Survey for 2021 will begin, which would open possible opportunities for the participation of new countries. Therefore, the Open Budget Survey is prepared and initiated exclusively and only by budget experts outside the system of the executive authorities.

Additionally, as an instrument for the assessment of public financial management, the PEFA assessment was conducted in Montenegro for the third time for the period 2016-2018 (2009, 2013, 2019), and through the World Bank project in cooperation with the EU Delegation to Montenegro and the Ministry of Finance of Montenegro with the financial support of the SAFE Trust Fund. In order to fully understand the PEFA methodology, as well as the performance indicators and dimensions contained in it, 13-14 March 2019, a two-day training was held in Podgorica. After that, several data collection missions were conducted by relevant institutions in order to, in accordance with the standardized methodology, evaluate the existing PFM system of Montenegro and provide information on further reforms in this area in accordance with best practice. The first draft of the Report was submitted in June 2019, after which the mission of verifying the assessments by the competent authorities according to indicators was carried out. Furthermore, a formal “PEER review” was held in mid-October 2019, while the final version of the Report was published at the end of October 2019. According to the data, progress can be noted compared to the previous assessment within 11 indicators of performance in public finances and financial responsibility. The main improvements in performance indicators have been made in the areas of: (i) budget reliability (ii) extent of unreported government operations (iii) taxpayer registration and tax assessment (iv) procedures for contracting and reporting debt and issuing guarantees (v) improved procurement management (vi) effective internal controls (vii) strengthened internal audit, external audit and parliamentary scrutiny..

Given that the Sectoral Budget Support of the European Union represents support to Montenegro in the implementation of the Integrated Border Management Strategy (IBM) and the Public Administration Reform Strategy, it is important to note that Montenegro is the only country thanks to the efforts and results achieved under the IBM Strategy in the region which, after the first fiscal tranche, fulfilled all the conditions for obtaining the first variable tranche from the EU Sectoral Budget Support Program. Also, within the mentioned Strategy, the second variable tranche in the amount of EUR 3,868,000 was paid.

Sector budget support for IBM provided a total of 20 mil. € distributed in three tranches. The first fixed tranche in the amount of 8 mil. € was paid in December 2016, the first variable tranche in the amount of 8 mil. € was paid in November 2018, while the second variable tranche in the amount of EUR 3,868,000 was paid in November 2019. Taking this into account, the Ministry of the Interior received a total of 19,868,000 euros of support, which represents 99.34% of the allocated funds.

Also, for the needs of the implementation of the Public Administration Reform Strategy, Direct Budget Support for Public Administration Reform was approved through three tranches (€ 12 million - one fixed and two variable tranches). Through the first fixed and variable tranche, 6.1 million € was paid to Montenegro by December 2019.

Bearing in mind that the EU Sector Budget Support is a recognition of Montenegro's efforts to fully implement the Integrated Border Management Strategy (IBM) and the Public Administration Reform Strategy, it is important to note that satisfactory progress is needed in the areas of public financial management and budget transparency, which constitute two eligibility criteria.

From a macroeconomic and fiscal perspective, a number of implemented reforms have strengthened the stability of the public finance system, improved the investment and overall business environment, and significantly supported the country's economic growth and development. As a result of reform processes, macroeconomic stability has been preserved, and the Montenegrin economy recorded the strongest growth in the last decade of 5.1% in 2018, while the high growth trend continued in 2019, where according to preliminary data from Monstat, real economic growth of 3.6% was achieved., which is above the 3.1% estimate projected by the last Economic Reform Program 2020-2022 and above the projections of all international financial institutions. Most industries grew at a high rate in 2019, of which the largest growth was recorded in the sectors of tourism, construction, retail and transport. In particular, tourism recorded excellent results with € 1.1 billion in revenue at the annual level and a double-digit increase in overnight stays of 11.2% compared to 2018.

The growth model of Montenegro in the period 2020-2022 will be based on the continuation of investment activity, diversification of the domestic economy with strengthening of production and exports, moderate growth of private and state consumption and stabilization of imports. Further implementation of structural reforms will be in the function of sustainable economic growth and strengthening the fiscal capacity of the state.

| Macroeconomic indicators | 2019 |
| --- | --- |
| Arrivals in tourism, collective accommodation, growth in % | 20,1 |
| Overnight stays in tourism, collective accommodation, growth in % | 11,2 |
| Value of executed construction works, growth in % | 10,7 |
| Industrial production, growth in % | -6,3 |
| Mining and quarrying, growth in % | 20,8 |
| Manufacturing, growth in % | -10,0 |
| Electricity, gas and steam supply, growth in % | -7,1 |
| Retail turnover, constant prices, growth in % | 5,2 |
| Exports of goods, growth in % | 3,8 |
| Imports of goods, growth in % | 1,8 |
| Number of transported passengers at airports | 8,1 |
| Employment growth in %, administrative data | 7,1 |

| INTERNATIONAL INDICATORS | 2007 |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Doing Business | 84 | 77 |  | 65 | 56 | 56 | 51 | 44 | 36 | 461 | 51 | 42 | 50 | 50 |
| Corruption Perception Index - Transparency international | 84 | 85 |  | 69 | 69 | 66 | 752 | 67 | 76 | 61 | 64 | 64 | 67 | 66 |
| Economic freedom - Heritage Foundation | - | - |  | 94 | 68 | 76 | 72 | 70 | 68 | 66 | 65 | 83 | 68 | 92 |
| Economic Freedom of the World - Fraser Institute | 76 | 58 |  | 78 | 47 | 37 | 28 | 49 | 38 | 62 | 59 | 851 | 72 | 83 |
| Global Competitiveness Index – WEF | 82 | 65 |  | 62 | 49 | 60 | 72 | 67 | 67 | 70 | 82 | 773 | 71 | 73 |
| Freedom in the world - Freedom House | Partially free | Partially free |  | Partiaally free | free | Free | free | Free | free | Partially free | Partially free | Partially free | Partially free | Partially free |
| Credit rating - Standard & Poor’s | BB+ (Stable, 27.03. | BB+ (neg. 10.11.) |  | BB+ | BB (neg. 31.03.) | BB (neg. 13.12.) | BB- (Stable, June | BB- Negative | B+ Stable (November) | B+ Stable | B+ Negative | B+ Stable | B+ Stable | B+ Stable, April 2019, B+ Stable |

1 A significant change in the methodology of preparation of the Report has occurred;

1 Revised rank for 2017 is 90;

2 Revised rank for 2017 is 73

When it comes to the transparency of public finances, some progress has been made in this area in the past. Namely, the website of the Ministry of Finance regularly publishes data on budget execution on a monthly, quarterly and annual level. The report on budget receipts and expenditures is published once a month, while the analysis of consolidated public spending (data on the central budget and local government budgets) is published quarterly. Analyzes of macroeconomic developments and structural reforms are prepared twice a year, while projections of public finances and macroeconomic developments are updated twice a year. The Government Debt Report is published quarterly, while the Public Debt Report is published once a year.

Budget transparency remains a challenge, and accordingly, activities are planned by the PFM, the implementation of which will contribute to increasing the level of information contained in the budget, improving the presentation of multi-annual commitments and capital projects, better budget visualization and budget reporting, all with a view to more transparent use of public resources. In this regard, activities to improve the transparency and quality of budgeting, are implemented continuously and will continue in the future, predominantly through further implementation of the program budget and performance-based budget (within the EU co-financed project), then through the implementation of international standards in the domain of government statistics (ESA 2010), as well as the transition from cash to accrual accounting.

INFORMATION ON THE PROGRESS IN IMPLEMENTING THE REFORM OBJECTIVES AND THE ACCOMPANYING INDICATORS FOR THE YEAR 2019

OBJECTIVE 1.  Sustainable fiscal framework, planning and budgeting of public expenditure

Status of Indicator Realization

Observed number of activities: 32

Negative trend

Positive trend

Not realized

Partially realized

Fully realized

Status of Activity Realization

Number of performance indicators: 10

Achieving this objective is realized through the projects "Improvement of the budget system and medium-term budget framework, Improvement of IT systems for budget planning and IT systems for centralizedsalaries. The realization of the project began with the signing of the contract in December 2018.

In the part of the introduction of the program budget at the central level after the signing of the contract, the project team established relationships with people from key institutions and numerous stakeholders, then with development partners, especially with the EU, SIGMA, UNDP and the World Bank and other projects – especially with the project responsible for the development of the Budget Planning Information System.

After the end of the initial period, work began on the components and Medium-Term Budget Framework, Program Budgeting and Reporting and Component II of Development of the Management and Public Internal Control System in accordance with the work plan presented in the Initial Report. Although some of the activities have been postponed, others have been accelerated, which indicates that the expected results of the project can be reached even before the planned completion of the project. Activities for Component III Preparation of the Business Continuity Plan and Component IV Support for the transition to accrual accounting will begin in 2020 in accordance with the original plan.

In accordance with the reporting schedule, the first draft of the Progress Report was published on 22. May 2019, while the first draft of the Activity Report was presented on 17. July 2019, which resulted in a general conclusion of the Steering Committee that the project was making satisfactory progress. as well as that the project is progressing according to the planned dynamics, i.e. that all planned results can be achieved to a large extent in accordance with the project work plan presented in the Initial Report.

During the first year of project implementation, the following output results have been worked on:

- Best practice analysis, gap assessment and Action Plan;

- Integrated process procedure and methodology for policy-based planning and budgeting;

- Recommendations for amendments to budget legislation;

- Improved classification of the budget program;

- Manuals for the Medium Term Budget Framework and Program Budgeting;

- Capital Budgeting Manual;

- Medium-term budget framework and training for program budgeting;

- Capital budgeting training;

- Workplace support and counseling.

The preparation of the Best Practice Analysis and the draft Concept has been completed. A document for the discussion on budget legislation (Law on Budget and Fiscal Responsibility) has been prepared, which will be further discussed and will be developed during 2020. The first draft of the new program classification at four levels has been prepared, while meetings on these issues will continue during 2020. The Draft Program Budgeting Manual has been completed, while the Basic Budgeting Guidelines (the first part of the manual for the medium-term budget framework) have been prepared for discussion and further improvement.

Through the implementation of projects to date, excellent working relationships have been established with other development partners of state institutions and ongoing projects relevant to project development. Two expert groups for budget reform have been established: a basic expert group consisting of employees of the State Budget Directorate of the Ministry of Finance and an expanded expert group with additional representatives of the State Treasury, the Central Harmonization Directorate, the General Secretariat, four pilot ministries (tourism and sustainable development, economy, defense and agriculture and rural development), two Directorates - for transport and public works in charge of capital budgeting, and one member of the Parliamentary Committee for Economy.

The project team participated in a workshop and follow-up meetings on gender budgeting organized with MPs and other stakeholders as part of an OSCE-funded initiative. The aim of the participation was to gain insight into current developments in this area and to explore the possibility of integrating gender budgeting into budget systems and processes, which are currently being reshaped. In addition, the project team is working with a consultant working on a budget responsible for Roma, as part of an EU-funded regional initiative.

The project team participated in a workshop on the Government's Medium-Term Work Program organized by the General Secretariat of the Government in cooperation with SIGMA, with the aim of further coordinating ongoing reform initiatives for SPRV, strategic planning and program budgeting.

The project being implemented in the Ministry of Finance to modify the existing budget planning software will provide an opportunity to create a favorable IT environment for program budgeting and a medium-term budget framework. Within the mentioned project, activities are also realized according to the planned dynamics, i.e. after the analysis of the current situation, exchange of information and documents important for getting acquainted with the framework and analysis of application of best practices, connection and data exchange between the two projects, as well as interoperability other subsystems and IT solutions with which it is planned to establish adequate communication, adoption of a document representing the Business Model with a detailed overview of the functionality of the system, a test version of the IT system for budget planning. The first phase of system development, in the part of showing the budget spending limit for the three-year period, system development in order to electronically fill in budget requests by spending units and import data for further work on budget planning was realized, after which trainings were organized for representatives of the Ministry of Finance and all spending units, in order to fill the budget requirements for the next year, 2021, using the new IT system for budget planning.

In the second half of 2019, a discussion was held with three pilot ministries (agriculture and rural development, tourism and sustainable development and defense) to see how the proposed program classifications could work at the ministry level. Following the training on program budgeting, a series of discussions were held with budget analysts of the Budget Directorate to formulate a draft of the new program classification.

The draft manual for the development of the program budget was prepared on the basis of the Concept and several discussions and the manual includes:

- General introduction to program budgeting and explanation of key concepts and how they will be applied in Montenegro.

- Detailed instructions on how to formulate a program classification and how to determine program objectives.

- Detailed guidance on how to formulate medium-term specific objectives, performance indicators and annual objectives for each program and sub-program.

Regarding medium-term budgeting, it is proposed to introduce the methodology and process of the Medium-Term Budget Framework (MFS) in two phases:

- Introduction of a methodology for the preparation of the basic budget by the Ministry of Finance in 2020.

- Introduction of a methodology for the identification, cost and selection of proposals for new or amended public policy and capital projects by ministries and major spending units by 2021 according to the new program classification.

In the part of improving budget spending, due to numerous challenges and complexities that the realization of this segment requires, a number of documents were adopted within the project of centralized calculation of salaries. The summary document, which contains an overview of the completed activities, results and risks in the first year of the project and the forthcoming period, was also approved after the adopted changes at the suggestion of the beneficiary. A demo version of the Centralized Salary application is available on the server for access and testing for employees in the Salary Calculation and Control Division. After the procurement and installation of equipment, the implementation of the training plan and the gradual introduction of users by groups in accordance with the estimated dynamics will begin.

During this period, access to the test version of the application was provided, which enabled users in the directorate for calculation and control of salaries to access and test use of the system functionalities developed so far.

In addition, activities on the establishment of a comprehensive system of planning, coordination and monitoring of the implementation of Government policies continued. In 2018, the General Secretariat of the Government determined the Methodology for medium-term planning of ministries, which was prepared in cooperation with experts from SIGMA, OECD, Ministry of Finance, Ministry of Sustainable Development and Tourism, Ministry of Economy and Ministry of Agriculture and Rural Development. The methodology is a pilot project, applied during the preparation of medium-term work programs of the Ministry of Economy, the Ministry of Sustainable Development and Tourism and the Ministry of Agriculture and Rural Development, for the period 2019-2021.

In accordance with the new methodological approach, the pilot ministries are obliged to prepare the first annual reports on the implementation of medium-term work programs of the ministries by the end of the first quarter of 2020. The first annual reports will contain an analytical overview of progress in relation to general and specific sub-goals, an assessment of the overall progress in implementation, information on shortcomings and challenges, as well as a proposal of measures to overcome them.

On December 12, 2019, the Government adopted the Information: The first year of implementation of the legal framework for strategic policy planning, with recommendations for improving the planning system, which provides a detailed overview of the situation in the planning system based on the implementation of the appropriate legal framework. It is noticed that the quality of strategic documents and reports has significantly improved, but that the number of strategies is still high, which should be taken into account in the next planning cycles. The quality of reports has improved, but there is room for improvement in the area of performance and financial reporting.

Also, the European Commission's Report on Montenegro for 2019, published in May 2019, praises Montenegro's progress in the section "Political Criteria - Governance", emphasizing that: "the legal framework for strengthening strategic planning by central government bodies has been significantly improved“.

The share of medium-term sectoral strategies that include an estimate of costs for their implementation, as defined by the Performance Indicator, although in a growth trend compared to the previous year, is lower than the planned value for 2019. Planning has been improved due to the insistence on providing better information in the process of reviewing strategic documents, in the part of financial impact assessment. These data are important when setting spending limits in the Macroeconomic and Fiscal Policy Guidelines, and later in the annual Budget Law. However, having in mind the level of development of medium-term planning and activities for its improvement, primarily through trainings planned during 2020, its improvement is predominantly expected during 2020. Bearing in mind that in the coming period, work will be done on improving IT solutions in this field, it is expected that this Performance Indicator will be fully met.

The performance indicator related to the average discrepancy between the limits of budget expenditures set by the medium-term budget framework and the actual budget expenditures planned by the annual budget law shows a high degree of fulfillment and shows that the amount of budget expenditures planned by the Budget Law for 2019 slightly deviates from the amount of spending limit planned by the Macroeconomic and Fiscal Policy Guidelines for 2019-2021. The performance indicator related to the number of employees trained for medium-term planning is not met at the level of the target value, with the training process starting with training of employees in the State Budget Directorate. Bearing in mind that the achievement of this result is predominantly conditioned by the implementation of IPA projects, and that in the previous period, in accordance with the existing capacities, work was done primarily on preparatory activities. Fulfillment of this Performance Indicator is expected, in accordance with the planned dynamics of implementation during the next period, through the implementation of the project, when special emphasis will be put on the implementation of training, both for experts and managers.

| Name of the Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target value | Achieved | Target value | Achieved | Target value | Achieved |  |
| Share of new medium-term sectoral strategies in the total number of strategies which include the cost assessment for their implementation, including the funds from the donors | 60% | 80% | 70% | 85% | 75% | 90% | 85% |  |
| Average deviation between the budget expenditure limits determined by the medium-term budget framework and actual budget expenditures planned by the Law on the annual budget | 9% | 7% | 6% | 6% | 0,87% | 5% | 0,11% |  |
| Number of employees trained for medium-term planning based on the “top to bottom” principle | 0 | 52 | 0 | 35 | 0 | 52 | 17 |  |

The performance indicator that relates to the comprehensiveness of budget requirements meets the targeted value. However, budget requirements received in the format prescribed by the Ministry of Finance in the budget bulletin do not reflect the true picture of comprehensiveness and can often be of different quality. However, users of the budget submit their reasoning for the demanded funds in a “word” format, which is certainly an integral part of the request for funds from the budget, and this is certainly taken into account during the planning of the budget. Also, as part of the process of preparation and planning of the Law on the annual budget, the Ministry of Finance receives additional information from the consumer units, which it uses when considering the requirements as a whole and in this manner the value of the performance indicator is in total at a satisfactory level.

In order to more transparently present the medium-term budget framework in Montenegro, amendments to the Law on Budget and Fiscal Responsibility, adopted on August 1, 2018. It is defined that the estimate of receipts and expenditures expressed by economic classification, as well as a special part of the budget, which contains an overview of planned expenditures by budget users, contains the maximum level of budget spending that is binding for the law on the state budget for the first year. the third fiscal year, beginning in 2020, has been met. However, the main elements of the program budget are still not fully developed, as is the Performance Indicator. In this regard, through the project "Improvement of the Budgeting System, Multi – annual Budget Framework and Public Internal Financial Control System",  activities have been intensified on the development of other elements of the program budget, and in the coming period the target values are expected to be met.

The performance indicator related to the number of officials trained in accordance with the principles of program budgeting has not been met. Having in mind that during most of 2019, preparatory activities, analysis of the situation and concept development were done, trainings for representatives of the State Budget Directorate were held in 2019, while fulfillment of trainings for representatives of consumer units is expected during the first quarter of 2020. . years. The trainings will be related to the improvement of multi-year planning, program budgeting, revision of the program structure, definition of activities and Performance Indicator, etc., organizing the mentioned trainings for expert, but also managerial level of staff.

| Name of the Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Achieved | Target values | Achieved | Target values | Achieved |  |
| Share of consumer units of the first level which include comprehensive information in their budget requests | 40% | 75% | 70% | 80% | 80% | 90% | 90% |  |
| Level of information on the performance of the included in budget planning | Defined names of programs of all consumer units | Developed program structure at all budget users including the missions of consumer units, defined descriptions and program goals | Developed program structure in the part of defining names of the programs of all consumer units | Developed program structure in the part of defining names of the programs of all consumer units | Defined names of programs of all consumer units | Level 1 upgrade with defined set of Performance indicator for pilot projects | Defined names of programs of all consumer units |  |
| Number of employees trained for planning and monitoring expenditures in accordance with the principles of program budgeting | 0 | 20 | 0 | 35 | 0 | 70 | 17 |  |

In the part of capital budgeting, capital projects are presented individually, within homogeneous groups by areas, in the explanation of the annual Budget Law, which is an integral part of budget documentation and is submitted and considered in the Parliament of Montenegro as an integral part of the Law.

However, given the negative trend in the value of the Performance Indicator, which refers to the level of detail in the public presentation of the capital budget, in the coming period, intensive activities are planned in order to meet the target value. The aforementioned Concept of Integrated Planning and Budgeting Process presents the proposed key features and systems of capital budgeting, as well as the proposed reform approach, the necessary development of the regulatory framework and IT system to support the development of capital budgets. individual capital projects. Also, with the realization of the mentioned project, a more transparent presentation of capital projects is planned through the establishment of the register of public investments.

The indicator related to the realization of capital spending, i.e. the realization of the capital budget in 2019, has been fulfilled and shows a positive trend. Such a high degree of realization is the result of more intensive activities on already started significant projects in order to complete them and put the facilities into operation. Also, the intensified activities referred to new significant infrastructure projects in order to start the execution of works.

| Name of the Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Achieved | Target values | Achieved | Target values | Achieved |  |
| Level of details in the public presentation of the capital budget | Projects in the capital budget displayed grouped by fields (education, health, culture, sport…) | Display by all individual projects realized in the budget year | Projects in the capital budget displayed grouped by fields (education, health, culture, sport…) | Display by all individual projects realized in the budget year | Projects in the capital budget displayed grouped by fields (education, health, culture, sport…) | Display by all individual projects realized in the budget year | Projects in the capital budget displayed grouped by fields (education, health, culture, sport…) |  |
| The ratio of actual and capital expenditure in the current year in comparison to the capital budget plan | 70% | 80% | 82% | 80% | 91%/111% | 86% | 92%/112,3% |  |

Improving the model for macroeconomic projections

In the reporting period, activities related to improvement were implemented, i.e. the newly developed model for macroeconomic projections was updated, which resulted in setting a framework for further work on the model. Furthermore, it was adjusted to the needs of the work within the Directorate, in terms of corrections of existing system solutions of the model, so that it could be managed in an efficient and sustainable way. Namely, the module for macroeconomic projections was improved, supplemented with the latest data, in terms of external assumptions published by international financial institutions, as well as with the latest available data published by Monstat. Based on this, the model provides greater consistency and less deviation in terms of projected economic trends. A number of trainings for a number of employees were also carried out in the reporting period, as the complexity of the overall model still poses a major challenge for the Directorate's staff. In this way, the indicator in the action plan that refers to the training of employees in the use of the model is partially fulfilled, while the continuation of training is expected in the coming period, as it is a continuous process. Therefore, the Directorate plans to embark on a new project cycle that will explicitly seek expert assistance in model management and development of econometric knowledge, in order to significantly improve the knowledge and skills of existing employees in terms of macroeconomic modeling. Working on the model requires specific knowledge in the field of macroeconomics, econometrics and financial programming, and therefore continuous investments are needed in terms of sending employees to trainings in prestigious institutions. In order to further improve staff, it is necessary to increase the number of employees in the Directorate for Macroeconomic Analysis and Projections in order to distribute work on individual segments of the model evenly in accordance with the recommendations of experts who developed the existing model.

In the last Program of Economic Reforms for Montenegro for the period 2020-2022 the latest macroeconomic projections as well as the impact assessment of certain projects financed from public sources were presented. During the projection of macroeconomic indicators, the existing model of the Ministry of Finance was used, as well as the new model, which the Ministry of Finance developed through the project: "Support to the  Assessment of Macroeconomic Impact of Structural Reforms", within the support of IPA Program 2014 for Montenegro. The newly developed model has significantly improved the process of financial programming through structured econometric and behavioral equations through which trends in the development of key economic indicators and assessments of the impact of individual public policies on economic development are considered.

The latest program of economic reforms envisages a similar dynamics of macroeconomic developments in Montenegro by the Ministry of Finance with projections of all relevant international organizations. This is especially important bearing in mind that each of these institutions starts from different assumptions of economic trends on the global stage, as well as different internal factors due to the structure of the Montenegrin economy whose growth is mainly based on several key sectors. That is why the framework consensus reached in the latest projections for the next medium-term period is important.

The model has also significantly improved the forecast of the potential GDP growth rate, as the model provides tools that make it much easier to estimate the output gap and labor market performance indicators, taking into account the initial assumptions. This has significantly improved the implementation of the new model and facilitated its use in the process of work in the directorate, which continuously meets the expert recommendations in the field of implementation and full transition to the use of the new model by employees in the directorate.

The Macroeconometric Model for Montenegro (MMM) is used in the development of strategic documents. The novelty of this year's Economic Reform Program 2020-2022 is that the module for assessing the impact of structural reforms was used for the first time, which was highlighted at the initial meetings with EC representatives as a special progress in macroeconomic planning. The Program simulates the assessment of the impact of infrastructure projects on the Montenegrin economy. In this way, an assessment of the impact of infrastructure investments on macroeconomic indicators, such as GDP, investment, imports, employment and labor costs, was obtained and a quantitative expression of the net effects of these policies on economic growth was obtained. The model also contributes to adequate policy prioritization, which will be the focus in further developing capacity in the field of sectoral policies and assessing the impact of structural reforms.

| Name of the Performance Indicator | Planned 2014 | 2018 |  | 2019 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Achieved | Target values | Achieved |  |
| Implementation phases of the improved model for macroeconomic indicators projections and the impact of structural reforms | The existing model which is used in the Directorate for economic and development policy is based on the model of financial programming and the projection of specific parameters is based on an expert evaluation | A new model for macroeconomic indicator projections and impact of the structural reforms is built and the employees are trained | A new model for macroeconomic indicator projections and impact of the structural reforms is built and the employees are trained | Preconditions for the use of the new model by employees in the Directorate for Economic Policy and Development have been met | Preconditions for the use of the new model by employees in the Directorate for Economic Policy and Development have been met |  |
| Difference between the projected and achieved rate of GDP real growth | 1,8 p.p. | Less than 0,3 p.p. | Target value for 2018 was achieved (0,2 p.p.) | Less than 0,3 p.p. | Target value for 2019 was partially achieved, further recommendations were given |  |

CHALLENGES :

- Activities on the development of other elements of the program budget have been intensified, and the fulfillment of the target values is expected in the coming period.

- The performance indicator related to the number of officials trained in accordance with the principles of program budgeting has not been met. Having in mind that the realization of the stated result is predominantly conditioned by the realization of the previously mentioned IPA project, during 2019, work was done primarily on preparatory activities and analysis of the situation, while fulfillment is expected during the coming period.

- In the coming period, special emphasis will be placed on the implementation of trainings, both for employees of the Ministry of Finance and employees of budget users. The trainings will be related to the improvement of multi-year planning, program budgeting, capital budgeting, revision of the program structure, definition of activities and performance indicators, etc., organizing the mentioned trainings for expert, but also managerial level of staff.

- Having in mind the realization of the above-mentioned project, which in principle is proceeding according to the planned dynamics, it can be considered that the basic obstacles to progress and meeting the values of performance indicators have been overcome, and that preconditions have been created for progress in this area in the coming period.

- In order to fully implement and use the model, it is necessary to organize trainings in econometrics with special emphasis on the interpretation of the obtained results, hiring staff in charge of programming / coding econometric tools, as well as replacing old and purchasing new computer equipment that adequately meets the use of econometric software.

OBJECTIVE 2. EXECUTION OF THE BUDGET

Positive trend

Negative trend

Other

Not realized

Partially

Fully realized

Indicator Realization Status

Activity Realization Status

Observed number of activities: 22

NUMBER OF PERFORMANCE INDICATORS: 14

Tax Administration

In the previous period, positive results and effects in the field of revenue collection were achieved. In that sense, a higher share of submitted electronic tax returns (profit tax and value added tax - VAT) was achieved compared to last year, in order to create preconditions for fair and transparent market processes, of which the number of submitted e-tax returns 77.37% and profit 99.5%. When it comes to the collection of revenues for 2019, 80 mil. € above planned was realized.

BILLED

935 mill

BILLED 969 mill

BILLED 1.086 mill

BILLED

1. 177 mill

BILLED 4. 168 mill

Realization of billing above plan for 2016-2019

realization above the plan

During the previous 4 years,  realization of billing in the amount of 4.168 billion EUR exceeded the billing plan for 201 million of EUR

TOTAL

Special attention is paid to reducing the level of overdue tax debt. In the previous four years, the level of due tax debt decreased by 210 mil. €. Debt on 31.12.2019. amounted to € 378,142,829.1. At the end of 2018, it amounted to € 397,418,265.

During the previous four years, the level of due tax debt was reduced by

210 million EUR

Debt on the basis of concession reduced

by 5 million EUR

Income tax debt reduced by

13 milion EUR

Debt on 31st December 2019

378.142.829,1€

Tax and contribution debt reduced for

119 million EUR

Debt on the basis of GDP reduced for

68 million EUR

Debt on 31st December 2015

587.688.851€

TAX DEBT MOVEMENT

Furthermore, since 2017, the Tax Administration has started activities on the implementation of the reprogramming of tax receivables, which can best be seen through the total revenue on this basis in the amount of 63,917,439 € so far, during 2019, 19,526,984 € was collected. The settlement rate is 71.93%.

Degree of settlement of obligations

Collected during 2019

Collected during 2018

Collected during 2017

TOTAL COLLECTED

Local government

Legal entities

Natural person

RECAPITULATION OF PAYMENTS FROM THE REPROGRAM

Alignment of legislation with the acquis of EU is delayed compared to the planned progress. Draft Proposal of Amendments to the Law in the Field of Profit Tax, VAT and the Law on Tax Administration in the field of information exchange and mutual assistance, in cooperation with colleagues from the Spanish Tax Administration, in order to further harmonize with EU legislation, especially in the part of transfer pricing ( accurate presentation of actual profits, avoidance of tax fraud and evasion, as well as in the part of information exchange in order to react in a timely manner when performing tax obligations) has been prepared. The delay was due to the requested amendment of the Law on Tax Administration in part to introduce a new institute "tax police" which would have the authority to take certain actions and measures to detect crimes, prescribed by the Criminal Code of Montenegro, which as a possible consequence have total or partial tax evasion. Therefore, the said Bill was withdrawn from the procedure. After receiving the opinions of the Secretariat for Legislation, line ministries, the innovated text of the Bill in line with the suggestions of the European Commission will be sent to the European Commission again in March 2020 for an opinion, followed by the adoption procedure.

Also, in order to improve the collection of duties that will contribute to fiscal budget revenues, as well as combating the gray economy, better tax collection and improving the business environment in Montenegro, the Law on Fiscalization in the Trade of Products and Serviceswas adopted, providing a legal basis for project implementation. electronic fiscalization, which will enable the submission of data on turnover of products and services and fiscal invoices to the Tax Administration in real time, via an Internet connection and fiscal service. The mentioned Law brings many novelties, as well as issues, which should be regulated by bylaws, and which are still in the drafting stage. Furthermore, it was proposed that the implementation of the electronic fiscalization system should begin in early 2021, in order to familiarize taxpayers with the new procedures and obligations until the application of the law. A tender procedure was conducted for the selection of a company that will develop a software solution (conducted according to the rules of the World Bank). The first tender procedure failed due to the fact that the price of the bidder was significantly higher than that in the documentation for the tender procedure, and the second bidder did not submit the documentation in accordance with the rules of the tender procedure. The second tender procedure is in progress. The e-fiscalization project is set as 4 components of the main project "Tax Administration Reform". In this regard, as a result of the implementation of e-fiscalization and the implementation of the Tax Administration Reform project, there will be a complete reform of the Tax Administration.

In addition, in order to strengthen the administrative and operational capacity of the Tax Administration of Montenegro, in accordance with the standards and requirements arising from Chapter 16 - Taxes, in June 2019, the Twinning project "Support to the Tax Administration" funded by the European Union through pre-accession assistance instruments (IPA 2014). The project was successfully implemented in all components. Through four components, which include the development of a set of recommendations for further harmonization of the legal framework with the acquis communautaire in the field of taxes and excises, implementation of training programs for Tax Administration employees in basic business processes, laying the foundations for automatic information exchange and establishing the Central Liaison Office, as well as a detailed analysis of existing IT capacities and the definition of infrastructural needs for establishing interoperability and interconnection with EU tax administration systems.

Activities within objective 4.2 continued - Strengthening the administrative capacity of the Tax Administration. The Tax Administration, with the help of experts hired by the IMF (Multi-beneficiary IPA - the project is funded by the EC), continued cooperation in the form of providing technical assistance to strengthen the capacity of the PA. A Human Resources Management Strategy has been developed, and a key Performance Indicator (KPI) has been set to measure performance at the strategic and operational levels. Also, a risk management committee was formed, along with the already existing Reform Committee, which monitors the implementation of the Business Strategy 2019-2022 through the annual Action Plan (documents available on the website of the Tax Administration).

Having in mind the above mentioned, it is evident that the efforts on the improvement have contributed to a positive trend in budget execution, i.e. the value of the performance indicator related to the growth of the share of submitted electronic tax returns is above the expected value for 2019, while tax revenue planned tax revenues in the annual budget law exceeded by 80 mil. €, thus fulfilling the predicted value of the performance indicator and continuing the positive trend.

| Name of the Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Achieved | Target values | Achieved | Target values | Achieved |  |
| Growth in the share of submitted tax return requests (income tax, VAT) | 27% | VAT 50% | VAT 50% | VAT 65% | VAT 70% | 75% | 77,37% |  |
|  |  | PROFIT 95% | PROFIT 95% | PROFIT 97% | PROFIT 99% | 99% | 99,5% |  |
| Successfully implemented EU legislation regarding the common EU market | Screening process completed | Negotiations in the chapter 16 open | A certain level of legislative compliance has been achieved, greater level has been achieved in the field of VAT, compliance in the field of income tax (transfer prices), administrative co-operation and mutual help still remains | Law on amendments and supplements of the Law on the income tax of legal entities (IV quarter of 2018) Law on amendments and supplements of the Law on tax administration (IV quarter of 2018) | Draft versions on the amendment of the Law on VAT, Law on income tax and the Law on tax administration in the part of information exchange (automatic) and mutual help with a goal of further harmonization of domestic legislation with the EU acquis were prepared | Law on Amendments to the Law on Corporate Income Tax (IV quarter 2019) Law on Amendments to the Law on Tax Administration (IV quarter 2018) VAT Law (IV quarter) | All proposed amendments to the law passed the Legislative Committee. After which they were submitted to the EC for an opinion. |  |
| Share of collected tax revenues in relation to the planned tax revenues in the Law on the annual budget | 100% | More than 100% of the planned (24 million over the plan for the year 2017) and 34 million over the achievement in 2016 | More than 100% of the planned | 100% | More than the plan for the year 2018 73 million achieved which is 117 million above the value for the year 2017 | 100% | More than the plan for 2019., 80 million above the plan were achieved. |  |
| Share of the VAT revenues in the GDP | 13,5% | 13,5%20 | 13,0%[1] | 14,7% | 13,6%21 | 13,6% | 14,44% |  |

In order to eliminate the challenges, the importance of educating employees in the Tax Administration was recognized, both because of the improvement of the quality and efficiency of work processes, and because of the process of initiated reforms.

Activities related to the project “Tax Administration Reform in Montenegro” (RARP) continued. An initial report with an action plan, budget and implementation phases was prepared. activities on the development of the Document of functional requirements of the future IT system have started, activities on data cleaning (developed Strategy, action plan, training) have been started.

Also, the challenge of achieving the goal is fully reflected in the implementation of the project E - fiscalization and reform of the Tax Administration, which includes an integrated IT system and reengineering of business processes. In this regard, an initial Report with a detailed implementation plan was prepared in phases, as well as a budget for project implementation. Restructuring of the project "Reform of the Tax Administration in Montenegro (RARP)" in the amount of 14 mil. €, which started last year within which e-fiscalization is included as the 4th component. The final phase of describing the future functional requirements for the new IT system is underway. Development of TOR for dwh. The Strategy, Catalog and Action Plan for the data cleaning process were adopted as one of the most important preconditions for the successful implementation of the project. Quality control company was selected. The methodology for calculating the tax gap for VAT, profit and contributions has been developed.

Strengthening the Capacities of the Customs Administration

Objective: Strengthening the capacity of the Customs Administration in order to ensure efficient collection of revenues, security of the customs area and protection of society, as well as creating better conditions for the business environment

In order to efficiently collect revenues, the Customs Administration continuously conducts activities for proper and timely collection of revenues, based on the calculation of customs, tax, excise and other duties. The Customs Administration continues to significantly contribute to the increase of total budget revenues and, with the application of strong fiscal policy measures of the Government of Montenegro, records a continuous growth in the collection of revenues within its competence.

In 2019, the net collection of revenues in the amount of € 808,595,189.83 was realized, which is 5.17% or € 40 million more than in 2018, which exceeded the revenue plan by 2.06% or € 16 million.

Chart 1: Comparative Overview of Net Collected Revenues

Chart 2: Comparative overview of collection by type of revenue

- During 2019, in order to harmonize customs and excise legislation, as well as the implementation of modernized customs procedures at the national level, the following were adopted: the Regulation on Amendments to the Regulation on the Implementation of the Customs Law, which further harmonized the provisions relating to the transit procedure , status of goods and provision of customs debt, with the provisions of the Commission Delegated Regulation and the Commission Implementing Regulation (EU), i.e. with the bylaws of the Union Customs Law, which is one of the conditions for Montenegro's accession to the Convention on Common Transit Procedure and the Convention on Trade Facilitation ;

- Regulation on the Customs Tariff for 2019, which harmonizes the nomenclature of the customs tariff with the Combined Nomenclature of the European Union;

- Regulation on the Conditions for Granting the Status of an Authorized Economic Operator in the Customs Territory of Montenegro. With these changes, the institute of authorized business entity is fully harmonized with the provisions of the Delegated Regulation of the Commission and the Implementing Regulation of the Commission (EU).

In order to implement the Action Plan, the Customs Administration aims to Implement the IT system for excise duties at the national level, through the project "Support to the Customs Administration in the field of excise duties", which is funded by EUIF (for 14 months), in the reporting period initiated a new tender procedure. In this regard, the mentioned project started the implementation of the project in September 2019. The first meeting of the Project Steering Committee was held, at which the initial report "Inception Report" was adopted. The project is progressing according to the planned dynamics, which resulted in the development of basic modules in the new excise system. The project will implement a new national application for excise duties which will, among other things, enable electronic communication between the Customs Administration and excise taxpayers.

In connection with the Implementation of modernized customs procedures at the national level, the Customs Administration, through the project for accession to the Common Transit Convention and the the Implementation of the New Computerized Transit System (NCTS) compatible with the EU system, implements activities through three agreements: contract “Support in accession to the Convention on Common Transit and the Convention on Facilitation of Trade in Goods”, the contract “Implementation of NCTS”, which are implemented in accordance with the plans and the contract “Procurement of equipment for the functioning of NCTS” which was successfully implemented in 2019. In the previous period, a thorough assessment of the Montenegrin customs system was conducted by comparing the current situation with the requirements of the European Union and the requirements of the Conventions, through GAP analysis of the transit system, guarantee management system, risk management system, followed by functional and technical specifications. A functional specification for the Guarantee Management System was developed and adopted and the Enterprise Service Bus was installed, which represents a new platform and architecture of the Customs Information System. Along with Poland and Germany as the first EU members to implement NCTS phase 5 (the latest version of NCTS), the Customs Administration of Montenegro as well, within the mentioned project, will go directly to the implementation of the latest version of NCTS. The technical specification for NCTS phase 5 was officially accepted at the meeting of the Electronic Coordination Customs Group, which was held on November 18, 2019 in Brussels.

The Customs Administration, with the support of the German Office for Assistance and Cooperation (GIZ), has developed an "e-manifest" application that allows shipments delivered by express mail operators to be processed by customs and before being delivered to the customs territory of Montenegro, enabling faster delivery to the customer.

The Customs Administration has also created a modern and efficient Electronic Service for the Economy that enables electronic tracking of receivables and payments based on customs debt and bank guarantees. This service is available free of charge to all authorized users through the website of the Customs Administration.

In order to increase the level of information of natural persons, a new modern information service for natural persons has been created, through which they can be easily and quickly informed about customs procedures. A customs calculator is available at the service, through which individuals can quickly and easily calculate the amount of customs duties for goods ordered online.

In order to prepare for the implementation of automated procedures for reporting EU revenues (AB accounts), two study visits were realized, in March 2019 to the Financial Administration of the Republic of Slovenia and in November 2019 to the Financial Administration of the Czech Republic within the Customs 2020 program on “Traditional own funds and accounting procedures for classification of customs revenues into A&B accounts ”.

In order to implement activities related to the improvement of the customs risk management system, the Customs Administration adopted in March 2019 the "Instructions on the organization and binding procedures for risk management in customs procedures", which covers the entire system and process of risk analysis and provides uniform application procedure of work in this area in each customs office. Intensive work has also been done on strengthening the quality of risk profiling, with a focus on risks in the field of excise products. With the support of the World Bank project, a set of risk profiles for excise products has been developed in accordance with WCO standards and EU best practice. In 2019, the existing and new risk profiles for excise products were updated with the technical assistance of TAIEX experts. Within the NCTS project, the document "Design of the risk analysis system process" was prepared, which is the basis for the development of the technical specification. Intensive work has been done on improving the customs risk management system, at the national and regional level. The Customs Administration participated in the development of the CEFTA Risk Management Strategy, which was adopted by the Joint Committee of the Central European Free Trade Agreement in Tirana, on December 18, 2019. In December 2019, the nCEN network WCO was installed, which contributes to the efficient exchange of information between the countries of the Western Balkans, which relate to increasingly significant seizures of narcotics, precursors, psychotropic substances, cigarettes, goods infringing intellectual property rights and more.

In order to increase the number of business entities that have been issued approvals for simplified procedures, the Customs Administration has issued 5 approvals based on the book entry and 17 approvals based on the trade document or invoice.

In order to develop the authorized economic operator (AEO)  program, the validation mission of the CEFTA contracting parties concluded in November 2019 that the Customs Administration has fulfilled the conditions for the implementation of the institute of AEO and can start issuing approvals to businessmen who meet the prescribed conditions. With the entry into force of the Regulation on the Conditions for Granting the Status of an Authorized Economic Operator in the Customs Territory of Montenegro, the conditions for submitting applications for approval of AEO status by economic entities have been met. As part of the technical support of the IFC World Bank Group, an internal instruction for granting the status of authorized economic operator, AEO guidelines and other documents necessary for the application of the AEO Institute in practice have been developed. At the end of December 2019, 3 applications for approval of AEO status were submitted to the Customs Administration. At the regional level, the CEFTA parties adopted the Decision on the establishment of validation procedures for the mutual recognition of national programs of authorized economic operators (AEO) related to security and safety (AEOS).

Bearing in mind the above, it is evident that the activities contributed to a positive trend in achieving performance indicators, i.e. the rate of change in revenue collection compared to the previous year and harmonization of customs and excise legislation with EU legislation, which indicates that the real value of revenue collection is above the one from the previous year, as well as that three regulations were adopted during 2019 in order to harmonize legislation.

| Name of the Performance Indicator | Planned 2014 | 2018 |  | 2019 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Achieved | Target values | Achieved |  |
| Exchange rate of achieved revenue collection in regard to the previous year | 15% | 5% | 11,03% | 5% | 5,17% |  |
| Harmonizing customs and excises legislation with the EU legislation | Screening process for chapter 16 completed Taxation | 3 regulations adopted | 3 regulations adopted | 2 regulations adopted | 3 regulations adopted |  |

Public procurement

The institutional framework of public procurement in Montenegro was reformed, in such a way that on December 31, 2018, the Public Procurement Administration, with the reform of the state administration, ceased to exist and public procurement was entrusted to the Ministry of Finance, Public Procurement Policy Directorate. This significant change required revision and additional amendments to the Draft Law on Public Procurement, harmonization of the text with the European Commission, securing the consent of the European Commission, organizing a public hearing, organizing consultations with the largest contracting authorities on difficulties in implementing the Law on Public Procurement together resulted in the adoption of a new Public Procurement Law. Further harmonization of the legislative framework can be reflected in the adoption of the Law on Public-Private Partnership (PPP). By passing these two most important laws, the Ministry of Finance has created the basis for a new regulatory framework in the public procurement system, but also established the basis for further policy reforms in this area.

At the same time, in 2019, software solutions were developed that will ensure the efficient implementation of electronic public procurement from the date of application of the new Law on Public Procurement. From the introduction of the electronic public procurement system, it expects to improve the efficiency of the procurement process of goods, services and works, and to achieve savings in the public sector. E-procurement is not only an important segment of e-government reform within the European Union, but their development and level of compliance is subject to monitoring and evaluation of progress reports on Montenegro's transition to membership.

Another law that complements the legislative framework for public procurement was passed at the end of 2019. The Law on PPP regulates the forms of public-private partnership, conditions and procedure of proposing and approving public-private partnership projects, selection of the best bidder, and other issues of importance for public-private partnership. Also, this regulation for the first time introduced the institutes of concessions for public works and services, as well as forms of joint investment of the state and a private partner.

The Government of Montenegro has adopted an Action Plan - Public Procurement Policy and Public-Private Partnership Reform Agenda for the period 2019 - December 2020, in order to meet the final criteria for closing the negotiations in Chapter 5- Public Procurement, as well as meeting the obligations of the Economic Program reforms for Montenegro for the period 2019-2021. On this occasion, activities were undertaken to harmonize the legislative framework with the relevant EU regulations, the Treaty on the Functioning of the EU and the establishment of appropriate administrative and institutional capacities at all levels. The action plan contains 37 measures, including measures related to public-private partnerships. In addition, the determination of the measures of the Action Plan takes into account the dynamics of the implementation of obligations under the negotiating Chapter 5- Public Procurement and further provides the basis for the development of a new Strategy for Public Procurement Policy Development and Public-Private Partnership for 2021-2024, whose development is planned for 2020.

In accordance with the obligation to report annually, at the end of May 2019, the Ministry of Finance submitted to the Government for adoption the Annual Report on Public Procurement for 2018. The report contains all relevant information related to the public procurement system, which is an overview of the public procurement system in Montenegro, and is the result of data collected by contracting authorities who are required to keep records, process data and submit reports in electronic and written form.

Obligors to apply the Public Procurement Act in 2018 contracted a total of EUR 535,112,568.90 for procurement, of which EUR 449,373,407.93 was public procurement and EUR 85,739,160.97 was procurement of electricity and coal. The share of procurement and public procurement has a significant share in the gross domestic product (GDP) in Montenegro, with a share of procurement in 2018 of 11.58% of GDP and a share of public procurement of 9.7% of GDP.

In 2018, contracting authorities concluded 3771 public procurement contracts using public procurement procedures in the amount of EUR 364,782,721.50, and for small value procurements 94922 contracts in the amount of EUR 70,685,727.24 and for urgent procurements 1918 contracts worth 13,904 .959.19 euros. The increase in the average number of bids per one public procurement procedure to 3.14 bids per procedure in 2018 is a clear indicator of the upward trend of competitiveness growth.

Within the continuous support of the European Union, contracts for two technical assistance projects financed from IPA funds are being successfully implemented, namely: the project entitled "Improvement and strengthening of the institutional system and legal framework in the field of public procurement and state aid" and the project "Introduction of e-procurement in Montenegro ". Both projects are implemented according to the established dynamics, and the activities covered by them correspond to the strategic goals of the public procurement policy in Montenegro.

Respectable results were also achieved in the segment of continuous activities on professional training and development, where the Directorate for Public Procurement Policy in the course of 2019 trained 116 public procurement officers. In a total of four exam terms in 2019, 91 candidates passed the professional exam. The total number of certified employees from 2012 until today is 650. The Ministry of Finance has determined the Training Plan for 2019, with the aim of acquainting training participants with the provisions of the new laws in the areas of public procurement and public-private partnership.

| Name of the Performance Indicato | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Achieved | Target values | Achieved | Target values | Achieved |  |
| Level of harmonization and completion of the legislative framework in the public procurement procedures with the EU legislation | Negotiations opened in the negotiation chapter 5 | Negotiations opened in the negotiation chapter 5 | Negotiations opened in the negotiation chapter 5 | Further harmonization with the Directives package from the year 2014 in this field | Negotiations opened in the negotiation chapter 5 | Negotiations opened in the negotiation chapter 5 | Adoption of a new Law on Public Procurement by implementing the provisions in accordance with the new directives |  |
| Average number of bidders participating in public tenders | 3,1 bids per tender | 2,65 | 2,66 | 3,48 | 3,14 | 3,58 | n/a | N/A |
| Share of usage of the electronic public procurements in the total number of contracts on public procurements during the year | 0% (system of electronic public procurement does not exist) | 0% (system of electronic public procurement does not exist) | 0% (system of electronic public procurement does not exist) | Selection of the optimal bidder | A project of creating the public procurement e-system has been initiated | 30% | Pilot phase of e-system |  |

The first Performance Indicator related to the harmonization and completion of the legislative framework in public procurement procedures with EU legislation was met by the adoption of the Law on Public Procurement. The harmonization of the legislative framework in the field of public procurement in Montenegro with the acquis communautaire of EU is extremely important not only because of the need for public procurement procedures, which are very professional and complex procedures, to be legal, in line with public procurement principles, and therefore transparent, effective to enable effective market competition of economic entities, to enable equal treatment of all interested economic entities, without discrimination, especially small and medium enterprises, but also due to the fact that the same public procurement rules apply in the case of projects financed from European structural investment funds. This law represents a step forward in the harmonization of Montenegrin legislation with the acquis communautaire of EU in this area, which was assessed during the harmonization of the Draft Law with the European Commission. This new regulatory framework is the basis for Montenegro's further progress in the negotiating Chapter 5 - Public Procurement, and the text of the law is one of the conditions for closing this chapter in the negotiation phase of Montenegro.

In 2018, the average number of bids for 2018 is 3.14 and it is on the rise. This data indicates the currently expressed participation of bidders in tender procedures and the represented competition, because this average is above the same even in some EU member states. The Public Procurement Report for 2019, which contains, inter alia, data relating to the average number of bids in 2019, the Ministry of Finance prepares and submits to the Government for adoption by 31 May 2020, and therefore this datum is not available .

The implementation of an electronic public procurement system is one of the biggest challenges in meeting the public procurement target. The project started in November 2018 and lasts for 36 months. The project started in November 2018 and lasts for 36 months. In July 2020, the beginning of the Pilot phase is expected, in which several clients will take part, who would thus test the system and help eliminate possible shortcomings. After the final design of the system, the public procurement portal will replace the advanced IT system ESJN, with the expectation of starting from January 2021.

State aid reform

In the reporting period, the Sector for State Aid Control in the Agency for Protection of the Competition carried out a number of activities that contribute to increasing the efficiency, effectiveness and transparency of the state aid system process in Montenegro in accordance with EU standards.

Since there was a delay in the start of the IPA project "Improvement and Strengthening of the Institutional set-up and Legal Framework in the area of and Public Procurement and State Aid ", provided by the CAP 2014 Program, which was to begin in 2018, due to the change of project manager its implementation was postponed for the second quarter of 2019. Also, within the same project, and in order to strengthen administrative capacities and raise public awareness on the issue of state aid, a seminar for judges and prosecutors "State aid - the role of national courts" was held in June 2019 in Kolasin. 12 judges and 3 prosecutors underwent this type of training. Also, trainings were held for state aid providers in the Ministry of Culture, the Employment Service of Montenegro and the Municipality of Bar. In 2019, 31 state prosecutors underwent this type of training. Also, within the project "Strengthening the capacity to accelerate the process of negotiations with the EU" funded by the Norwegian Ministry of Foreign Affairs, and implemented by the United Nations Development Program (UNDP), on June 6, 2019, an expert seminar was held on "Training - law enforcement on state aid in the EU with an emphasis on aid to transport and infrastructure "in order to educate state aid providers and employees of the Agency. In addition to the employees of the Agency, this seminar was attended by representatives of the Ministry of Economy and other institutions who, despite not achieving the final target value, achieved an exceptional result compared to last year, which in this case is a big step forward (10 employees in total). Within all 5 conducted trainings for the reporting period, the number of trained officers is 56.

Performance Indicator set for 2019, which refers to the percentage of employees of the Agency for Protection of the Competition and members of the Agency's Council who go through professional seminars, in order to strengthen the legal framework, reduce illegal state aid and implement ex-post control through training, seminars and daily work with employees he achieved the target result. We note that within the project, trainings were held on the topic of state aid and concessions, state aid and media, as well as "on the job training" - State aid in the field of infrastructure (highway), which indicates that within this area activities are implemented in accordance with planned dynamics. However, the most intensive training is conducted daily for employees of the Agency for Protection of the Competition.

Regarding the number of completed proceedings initiated ex officio, there was a negative trend, noting that in the fourth quarter of 2019, 2 ex-officio cases were opened. Due to the volume and complexity of the work, we expect their closure in 2020.

The number of legal acts analyzed and evaluated by the Agency is also growing. Bearing in mind that the increase in the number of analyzed applications is accompanied by an increase in the level of awareness of institutions on the obligation to report state aid, we can say that the public has recognized the issue of state aid.

| Name of the Performance Indicator | Planned 2014 | 2018 |  | 2019 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Achieved | Target values | Achieved |  |
| Number of providers and users of the state aid, representatives of the private sector and judges which attend seminars and training in the field of state aid | 50 | 30 | 0 | 60 | 56 |  |
| Percentage of employees of the department and members of the commission for the control of state aid which attend expert seminars with a goal of strengthening the legal framework, reducing illegal state aid and conducting ex-post inspections | 30% | 50% | 0% | 70% | 70% |  |
| Number of finalized ex-officio subjects | 5 | do 2 | 0 No Ex-officio cases were initiated in the year 2018 | 2 | 0 (2 ex-officio cases were opened, we expect their finalization in the coming period) |  |
| Number of legal acts analyzed and assessed by the Agency | 11 | do 20 | 22 | 23 | 35 |  |

Debt Management, Debt Analysis, Cash Management and Foreign Cooperation Reform

Based on the recommendations of the expert teams of the International Monetary Fund and the World Bank, the Ministry of Finance has started the reform of the Department for Public Debt Management, Debt Analysis, Cash Management and Cooperation with Foreign Countries.

This organizational change has led to a gradual separation of business processes in a way that reflects the standards of functioning of the front office and back office in the financial sector. The separation of business processes is still ongoing, along with the training of new staff. Namely, both directorates face a significant outflow of staff, which requires continuous repetition of on-the-job training, both by employees in the Directorates and by external experts.

Accordingly, in 2019, employees in the front office attended trainings related to the development of a medium-term debt management strategy, training for the preparation and implementation of bond issues on the international market, as well as training related to financial derivatives and hedging. These trainings were conducted within the regular cooperation between Montenegro and the IMF, as well as using the services of independent experts.

In 2018, Montenegro adopted the Debt Management Strategy 2018-2020, which, as a guideline, defined the equalization of debt repayment through the improvement of indicators of average debt maturity. In 2018, thanks to successfully executed borrowing transactions, there was an improvement in the indicator of average debt maturity from 4.6, as it was in 2017, to 5.2, as it was in 2018, while in 2019 Montenegro also conducted successful transactions reflected in the issuance of Eurobonds, worth 500 mil. €, under, so far, the most favorable conditions, which relate to a maturity of 10 years and an annual interest rate of 2.55% per annum. Also, in 2019, Montenegro issued 143 million. € of domestic bonds, of which 50 mil. € with a maturity of 7 years and an annual interest rate of 3.5%, and 93 mil. € with a maturity of 5 years and an annual interest rate of 3%. These transactions enabled a further improvement of the debt quality indicator, so, according to preliminary data, the average debt maturity for 2019 will be 5.9 years, while according to preliminary data, the average interest rate will be 2.8%. At the same time, by issuing government bonds on the domestic market, another public debt management guideline was achieved regarding the development of the domestic government securities market, thus diversifying funding sources and laying the foundations for borrowing under more favorable conditions in the coming period.

In 2020, a new public debt management strategy will be developed to cover the period 2020-2022.

However, despite the significant number of implemented activities, the degree of realization of goals and performance indicators is conditioned by a number of factors, such as the need to finance the budget in a given year, the movement of reference interest rates, general trends in financial markets and the like. Namely, after, according to preliminary data, it reaches a maximum of 78.68% of GDP in 2019, public debt will begin to gradually decline to 73.1% of GDP in 2020, 65.8% GDP in 2021, and 63.2% of GDP in 2022. It is very important to emphasize that, in 2019, Montenegro realized a Eurobond transaction worth 500 mil. €, which are part of the total deposits made at the end of 2019, and which will be used to finance the budget and repay the debt in 2020. Therefore, the total public debt at the end of 2019 will amount to 78.68% of GDP, while the net public debt (i.e. public debt including deposits) will amount to 66.26% of GDP.

In addition to the above, continuous work is being done to improve efficiency in public debt management by consolidating public debt records through a single database by implementing a new SAP software solution for public debt management. During 2019, by using the new information system, the improvement of this system was considered, and the decision on possible improvement will be made in the following period.

The above indicates that the needs for financing the budget in 2020 are fully met, so the need for borrowing in 2020 will be less. This explains the declining trend of debt in 2020 and in the years to come.

| Name of the Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Achieved | Target values | Achieved | Target values | Achieved |  |
| Costs of servicing the public debt as a share of the GDP | 2.20% | 2.50% | 2,3 % | 1,9 % | 2,1% | 2,0% | 2,2% |  |
| The difference between the planned and achieved level of the debt of the public sector | 1,5% | 1,5% | Declining tendency in the year 2017 3,2% | 1,5% | Growth 3,07% | 1,5% | Realized difference in gross public debt 16.6% |  |

CHALLENGES:

- Establishment of a management structure in the PA, organizational scheme of bodies and risk management in regular operations, given that the implementation of two major projects (e-fiscalization and RARP - Tax Administration Reform) is underway.

- The challenge for continuing in the continuous realization of the positive trend of fulfilling performance indicators is reflected in the strengthening of IT systems and administrative capacities, which will be prevented by hiring qualified staff, improving existing staff and providing the necessary funds to strengthen and develop IT systems.

- In the forthcoming period, the challenge is to continue raising public awareness of the obligation to report state aid, as well as training and retaining professional administrative staff in the Agency for Protection of Competition.

- Given the negative trend in meeting the targets, the challenges in the coming period are reflected in external shocks that may result in new borrowing, rising public debt and price.

OBJECTIVE 3. Development of internal financial control systems

Within this goal, the Ministry of Finance implemented all planned activities, which contributed to the achievement of the set results. The most significant progress in the area of ​​internal audit has been made in the area of ​​strengthening the capacity of internal auditors through training and certification, which has increased the number of certified deployed internal auditors. As part of these activities, the Ministry of Finance has localized the Certification Program for Internal Auditors in the Public Sector, which has so far been organized in cooperation with the Center for Excellence in Finance (CEF) from Ljubljana and the Human Resources Administration. The program will be implemented by the Human Resources Administration in cooperation with the Ministry of Finance. In addition, in order to maintain and further develop the competencies and skills of deployed internal auditors, in cooperation with the Human Resources Administration, 18 workshops were held within the Program of Continuing Professional Development of Certified Internal Auditors in the Public Sector. All these activities contributed to the improvement of the quality of internal audit work, which is reflected in the growth of the percentage of implemented recommendations.

In order to ensure the coverage of public spending by the internal audit function, the adoption of the Law on Management and Internal Controls, full budget coverage is provided, both at the central and local level, by the internal audit function. Article 49 of the Law on Management and Internal Control in the Public Sector stipulates that the internal audit unit of an entity, which in accordance with the law supervises another entity, also performs internal audit of that entity, if no internal audit is established.

Having in mind the activities undertaken, it is evident that the values of most performance indicators have a positive trend.

| Name of the Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Achieved | Target values | Achieved | Target values | Achieved |  |
| Percentage of ministries which formally delegated responsibilities and authorizations to the managers which enhances the management authority | 6,25% | 30% | 11.11% | 16% | 18% | 50% | 12% |  |
| Percentage of budget users at a central and a local level which submit annual reports on financial management and control | 69% | 75% | 80% | 80% | 90% | 90% | 93% |  |
| Average number of appointed internal auditors by a unit | 1,76 | 2 | ≈2 | 2.3 | 2.21 | 2.5 | 2.1 |  |
| Percentage of appointed and certified internal auditors | 60% | 75% | 90,90% | 80% | 94.05% | 85% | 100.00% |  |
| Percentage of appointed certified auditors who have continuous professional development | 0% | 70% | 72,86% | 75% | 83.64% | 80% | 81,36% |  |
| Percentage of implemented and partially implemented recommendations of the internal audit until the end of the stated year, which were given in the previous year | 48% | 55% | 73,5% | 60% | 79,16% | 65% | 84,46% |  |

Regarding the Performance Indicator Percentage of ministries that have formally delegated responsibilities and authorities to managers, which improves managerial responsibility, has not been met, but after the adoption of the Regulation on transfer of tasks of financial management and internal controls in the public sector, tasks and tasks will be prescribed. to the heads of organizational units or other employees in the entity. The Ministry of Finance formed an interdepartmental working group (Ministry of Finance, Ministry of Public Administration and General Secretariat of the Government), which prepared the said Decree, as well as a team for drafting the Methodology for delegating responsibilities and powers, which in cooperation with the consultant, prescribed the manner of delegation in detail.

In addition to the above activities, through the implementation of the IPA project “Improvement of Budget System, multi-annual budget planning and Public Financial Internal Control System”, five pilot institutions (three ministries and two municipalities) were selected to provide technical support in the delegation of power process.

Also, during the reporting period, in cooperation with the Human Resources Administration, seven trainings in the field of management and internal controls were held, intended for managers in the public sector.

CHALLENGE:

- Implementation of delegating of responsibilities and decision-making powers to managers of organizational units

OBJECTIVE 4 Transparent financial reporting and accounting

The strategy for the transition of the public sector to accrual accounting adopted in 2015 recognized the training of accountants as one of the basic pillars of accounting reform.

In order to implement the Strategy for the transition of the public sector to accrual accounting, during 2019, work continued on strengthening human resources through training for accountants employed in the public sector.

In this regard, in 2019, the training for another 40 accountants from the public sector was completed, which began in October 2018. By the end of the third generation, by the end of 2019, a total of 120 trained accountants had been trained through three generations.

Within the same project, in the reporting period, a workshop for public sector accountants on the topic of "International Accounting Standards for the Public Sector" was realized, in which recognized international and domestic experts in the field of accounting took part.

Within the new accounting policies in 2019, the Law on Public Sector Accounting was adopted, which defines the transition from cash to the accounting principle of accounting, which will be implemented from January 1, 2022 and which will contribute to achieving the goal ,“Transparent financial reporting and accounting ". The benefits of adopting a law introducing accrual accounting in the Montenegrin public sector are manifold. The law provides a systematized legislative basis for accounting in the public sector, a report on the financial position of the public sector that Montenegro has not had so far, the introduction of the title of accountant in the public sector, which must have a certificate and define the conditions for obtaining this title. Also, the Law introduces a register of public sector entities, and provides more complete and better information on the efficiency and effectiveness of public spending, harmonization of the budget classification with the internationally recognized classification, and harmonization with international accounting and financial reporting standards.

The law prescribes that the deadline for the adoption of bylaws is one year from the day of the adoption of the law, since the law will be applied on January 1, 2022.

In the following period, the risk of losing the staff of trained accountants was recognized. In this regard, by the contract concluded with each of the participants, the Ministry of Finance obliged the participants to stay in the public sector for at least 3 years from obtaining the certificate, which reduced the risk of losing trained and professional staff. In this regard, the Ministry of Finance formed a working group for project localization in 2015, which is in charge of preparing a draft act which will formulate competencies in the localization process and which envisages localization of the project and training of accountants through the Human Resources Administration.

Property Administration

Bearing in mind that the establishment of a single record of state property is not only a legal obligation but also an obligation to the public, the Property Administration is implementing a project that provides a complete insight into each movable and immovable property in the state, as well as the possibility of reviewing total reporting and reporting. Therefore, the Sector for Real Estate Registry, Movable Property Records and Preparation of Data for Registration of State Property in cooperation with the Ministry of Finance and the Real Estate Administration has taken the necessary initiative to intensify activities to remove obstacles to the unified state register of fixed assets, ie web ARS (Asset Registry System) applications and migration of Excel spreadsheets of budget users and local self-government (Municipalities).

However, despite the activities undertaken, problems have been identified in establishing and maintaining records of state property. Namely, in 2019, the ARS functions were tested, which determined that the adopted Conceptual Design from 2014 does not correspond to all functions supported by the ARS application, which led to additional costs for the improvement and development of the application. Having in mind the above, there is a need for finishing in several phases, which further complicates the work of the ARS application, which is why all the funds would improve the keeping of records of state property. In this context, after consultations with the companies Prime Zone Ltd. and Sapiens Ltd., a request was sent to refine the application. Out of 30 requests, in the first phase, 5 requests were implemented, while the second phase of request processing is in the process, which also consists of 5 requests. Their testing and further implementation is expected during 2020.

Although the Register of Unified State Property does not yet exist, additional efforts have been made in the implementation of planned activities. Within the project "Expansion of the SAP system - implementation of the SAP FI - AA module and external applications for state property records" which is implemented by the Property Administration and representatives of the company "Atos" Ltd. Belgrade, and their subcontractor "Sapiens Evolution of Business" from Macedonia and "Prime Zone" Ltd. from Podgorica, the problem was solved during logging in to the ARS, i.e. the existing certificates were removed due to the fact that they hindered the work of the application. In that context, administrative rights and authorizations were given to the employee in the Sector for keeping the real estate register, records of movables and tasks for preparation of data for registration of state property, as technical support to the ARS application. Also, accounts for key users  have been created for the test version of the ARS application.

A particularly important activity in terms of complete insight into every asset of movable and immovable property in the country is the creation of a database of budgetary and extra-budgetary users, i.e. bodies (state bodies, local government bodies and public services), in order to monitor the timeliness in the process of submitting data by users, who are required by law to submit data on movable and immovable property, as well as taking measures provided by law. In this regard, a list of direct budget users was made (proposal of the Ministry of Finance for the establishment of a working group that would revise the list and implement it through the Legislation). Therefore, additional efforts to the above indicate that the Training Plan for future users of ARS - an external application for a single record of state property. In this regard, in the period September-December 2019, the Property Administration conducted a series of trainings for direct budget users (first-generation consumer units, independent consumer units) in order to properly use ARS, namely: Training for the use of ARS application and Trainings for filling in the Excel table for the so-called migration document.

In the previous period from November to December 2019, 9 groups were made for direct budget users, which consisted of 100 state bodies. At our request, the training was attended by at least 2 civil servants, which leads to the training being attended by about 200 civil servants. In this context, orders for the use of the Web application were created for all direct budget users who attended the training.

Pursuant to Article 56 of the Decree on the Organization and Manner of Work of the State Administration (Official Gazette of Montenegro, No. 87/18 and 02/19), the Minister of Finance issued a Decision on the Establishment of a Working Team for Drafting a Proposal for a Decree on Amendments to the Decree on the Manner of recording of real estate and movable property in state ownership, i.e. to legally regulate the one-time submission of data on already acquired assets in an Excel file adapted for the ARS application.

In the plan of activities of the PA of the ARS application - a single record of state property, marked December 31, 2019 as a cross-section of the state property, i.e. year for which the census shall be conducted. Direct budget users are obliged to submit Excel spreadsheets to the Property Administration by the end of March. The migration of data on real estate and movable property obtained from end users to the ARS application is planned for the end of 2020.

Data migration via Excel spreadsheet to the test version of the ARS application, Sector for keeping the Real Estate Register, records of movables and tasks for preparation of data for registration of state property, is performed only once, thus recording assets up to the date of migration of the property data. After this migration, end users will use the ARS application for each newly acquired asset, as a new way of keeping a single unified record of state property.

On the other hand, the Performance Indicator projected for 2019 has not been achieved. In order for this activity to be completed, it is necessary to continue with the trainings that started in 2019, which are trainings for indirect budget bodies (bodies that are part of ministries-funds, directorates, schools, faculties, etc.) and for local government (Municipalities).

After the trainings, the tables with data on the property of 30 bodies were processed, i.e. prepared for migration to the test version of the software solution for registration of movable and immovable property (ARS - Asset Registry System), out of a total of 40 bodies that submitted tables, while the rest needs to be processed by the authorities.

| Name of Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Achieved | Target values | Achieved | Target values | Achieved |  |
| Trained accountants in the public sector in relation to accrual accounting (based on CIPFA methodology) | 0 | 40 | 40 u 2016. godini | 40 | 80 | 20 | 40 |  |
| Assets register has been implemented along with the system for dual accounting for assets | Development of assets register commenced | Data on assets stored in the register | 0 | Data on assets stored in the register | 0 | Training (direct budget users) and migration of funds to ARS and commissioning of records | 9 groups 100 0 |  |

In the coming period, the implementation of data on state property in a single database - ARS is expected, which depends entirely on the bodies that will be in the records, so they are expected to fully cooperate and participate with proposals and suggestions. It is important to emphasize that 2020 is planned as a test year where the Property Administration in cooperation with users will refine and implement the fields in the ARS application. The planned transition from the test environment to production is March 2021.

CHALLENGES:

- sustainability of training for accountants;

- loss of staff of trained accountants;

- implementation of data on state property in a single database - ARS;

- transition from test environment to production.

OBJECTIVE 5. Strengthening the capacities of external audit

In 2019, the State Audit Institution started the implementation of a number of activities envisaged by the Public Finance Management Reform Program, which are being implemented in accordance with the defined deadlines. In this regard, the trend of achieving positive results within all three Performance Indicators continued in the reporting period.

| Name of the Performance Indicator | Planned 2014 | 2018 |  | 2019 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Target value | Achieved | Target value | Achieved |  |
| Percentage of realization of the SAI Annual audit plan | 60% | 83% | 86,27% | 86% | 88,68% |  |
| Application of the auditing methodology for conducting financial audit, regularity audit, and success audit in accordance with ISSAI standards | 2015 – Manual on the methodology of conducting financial audit and regularity audit in compliance with ISSAI 200 and ISSAI 400, Manual on the methodology of conducting success audit in compliance with ISSAI 300 and Guidelines for the control of audit quality | Guidelines for the audit of Annual financial reports of political subjects; Guidelines for the audit of the final account of the state budget. | Guidelines for the audit of annual financial reports of political subjects were adopted in January 2018. Guidelines for the audit of the final account of the state budget were adopted in September 2018. | n/a The activities listed in the action plan start from Q1 of 2019 | Instructions on the methodology of performing the performance audit in accordance with the IV level of the ISSAI standard were adopted in December 2019. |  |
| Number of organized training/seminars/workshops for auditors | A minimum of 3 trainings were organized | Additional 6 trainings were organized | 13 trainings (3 were organized at a local level and 10 were organized on a regional and international levels | Additional 7 trainings were organnized | 13 trainings (3 at the domestic level and 10 at the regional and international level) |  |

The performance indicator is above the planned value in 2019 and meets the goal in the implementation of the Annual Audit Plan, which is an additional contribution to strengthening the influence of the SAI in improving public financial management. The increase in the number of audits was manifested by an increase in the coverage of public spending.

Although the implementation of activities related to improving and harmonizing the work of the SAI with internationally accepted auditing standards is planned for 2020 through the implementation of the Project "Development and strengthening the capacities of the State Audit Institution and the Audit Authority of Montenegro" , implementation of activities began in 2019. Therefore, in order to improve the audit process, in the reporting period, a new Instruction on the methodology of performing performance audits in accordance with the IV level of the ISSAI standard was adopted. The aim of adopting the Instruction is to standardize methodological procedures in accordance with the organization of the SAI and harmonization with international auditing standards.

In the reporting period, 13 trainings were organized (3 at the domestic level and 10 at the regional and international level), which resulted in additional improvement of knowledge and skills of audit staff in the field of accounting and auditing of the public sector.

In order to further develop audit capacities, the Training Catalog in 2019 was adopted based on self-assessment of employees' needs for certain professional and specific knowledge, skills and abilities. In addition, in January 2019, amendments to the Rulebook on the program and manner of taking the exam for acquiring the title of state auditor were adopted and manuals for taking the exam for acquiring the title of state auditor were prepared.

However, in addition to the positive results, the challenge in the coming period is still considered to be the insufficient space capacity that affects the dynamics of hiring new staff, as well as the engagement of significant audit resources in conducting legally binding audits (annual audit of financial statements of political entities). In order to overcome these challenges, the state capital budget for 2019 plans funds to address the lack of office space for the needs of the State Audit Institution and the Statistical Office of Montenegro within the multi-year capital subproject "Facilities for the needs of the State Audit Institution and the Statistical Office of Montenegro".. In the reporting period, in accordance with the law, actions were taken to implement this activity. Having in mind the legal procedures that need to be implemented, the implementation of this activity will be a challenge in the coming period. Also, in order to overcome the challenges, in 2019 the SAI held several meetings with representatives of the competent committees in order to amend the Law on Financing of Political Entities and Election Campaigns, which, among other things, refers to amending the Law in the part of annual audits of financial statements.

Audit Authority

By strengthening its capacity, the audit authority further contributes to promoting the process of managing EU funds, accountability and transparency in spending, through the implementation of recommendations related to the effectiveness and stability of the system, all in order to protect Community and national interests.

Within its competencies, the audit authority, through the identified findings and recommendations given in the audit reports and through monitoring the implementation of recommendations, contributed to the strengthening of the system of internal controls in the use of EU funds. The results of audit work through audit reports contribute to more successful planning, execution and control of these funds and the overall process of using pre-accession funds in accordance with EU and national regulations. In addition to the above, the reports of the Audit Authority contribute to the improvement of the responsibilities of the holders of functions related to the implementation of funds and the transparency of their work.

The Public Finance Reform Program envisages the implementation of 5 activities of the Audit Authority. The implementation of the activities envisaged by the PFM began with the signing of the service contract. “Development and strengthening of the capacity of the State Audit Institution and the Audit Authority of Montenegro” worth € 648,500.00, with a planned duration of 18 months.

In the reporting period, the audit authority started with the implementation of project activities, which aim to contribute to the strengthening of the system of internal controls in the use of EU funds.

Target value for the indicator Number of organized trainings / seminars / workshops for auditors is fully met. During 2019, an average of 11 trainings per auditor were organized. Most of the trainings were organized within the project “Development and strengthening of the capacity of the State Audit Institution and the Audit Authority of Montenegro”.

Target value for the indicator The degree of improvement of the methodology for conducting the audit - the audit manual, has been fully met. This was achieved through 3 expert missions (out of 4 planned) to improve the manual for different types of audits in accordance with international auditing standards and developed the Manual for areas 1,2,3,5 and the Manual for area 4 IPARD, which were adopted and are being implemented from April 19, 2019..

The target value for the indicator Percentage of audits performed using audit software is fully met. The auditors of the Audit Authority used the audit software for 1/3 of the audits performed in 2019 (33.33%).

Target value for Performance Indicator The level of implementation of the Institutional Strategic and Action Plan has not been met, taking into account that top management has a key role in adopting strategic documents, that the Deputy Auditor General was appointed in December 2019, and the election of the Auditor General is planned for 2020. . The realization of this activity has been postponed for 2020.

Target value for the indicator The degree of application of the standard in order to ensure the quality of audit work has not been met. In order to meet this indicator, it is necessary to complete the audit activities that are conditioned by the deadlines for submission of financial statements and statements of expenditure to the European Commission by the audited entities (early 2020). However, during 2019, the Audit Authority worked on the development of the Manual on control and quality assurance of audit work. Its application will be realized by reviewing the degree of application of international auditing standards in relation to the conducted audit activities for the financial year 2019, which were completed in mid-March 2020, i.e. within the prescribed period. Therefore, the activity Degree of application of standards in order to ensure the quality of audit work will be realized in the first half of 2020.

| Name of Performance Indicator | PV 2014 | 2019 |  | Trend |
| --- | --- | --- | --- | --- |
|  |  | Target values | Achieved |  |
| Number of organized trainings/seminars/workshops for auditors | 3 trainings organized | Minimum 9 auditor trainings per auditor were organized | 11 trainings per auditor have been organized |  |
| Implementation of the Action Plan | n/a | Strategic Plan was adopted; Action plan was adopted | Activities have been delayed for 2020 |  |
| Improvement of the Auditors' handbook | Auditors' handbook has been prepared | 50% of deficiencies were remedied | 90% of deficiencies were remedied |  |
| Percentage of audits conducted by performing the auditing software | n/a | 20% | 33,33% |  |
| Level of application of standards with a goal of ensuring the quality of the work of the auditors | n/a | 30% | Data for 2019 could not be available this year due to the dynamics of the implementation of audit activities, which are conditioned by the prescribed deadlines. | N/A Data available durng the first quarter of 2020 |

Within the Audit Authority, a total of 32 positions were systematized, of which 20 vacancies are currently filled, and in the following period the need to hire an additional 12 employees for an indefinite period was expressed, filling all vacancies in such a manner.

Training of the Audit Authority employees is continuously carried out through the project “Development and strengthening of the capacity of the State Audit Institution and the Audit Authority of Montenegro”which includes all auditors of the Audit Authority, on the topics: system audit, audit of transactions, audit of annual accounts, sampling, control quality and insurance policies, FIDIC and PRAG.

In addition to the implemented activities within the project, the auditors of the Audit Authority participate in conferences, seminars and workshops organized by the institutions of the European Commission, the Human Resources Administration and professional associations of accountants and auditors of Montenegro.

CHALLENGES:

- Insufficient spatial capacities that affect the dynamics of admission of new staff to the SAI, as well as the engagement of significant audit resources in the implementation of legally binding audits (annual audit of financial statements of political entities).

- The audit authority is to strengthen the audit staff in terms of increasing the number of auditors and their competencies

- Further increase of the awareness of audit subjects in the responsible and transparent use of EU funds, by giving and monitoring the implementation of recommendations with the aim of effective and stable functioning of the management and control system and protection of financial and national interests of the Community.

- REPORTING TABLE

| Strategic goal 4.1._ A) Sustainable financial framework, planning and budgeting of public expenditure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OperatiVE GOAL 4.1.1. _ A.1. Medium-TERM BUDGET FRAMEWORK (MTBF), INCLUDING THE FISCAL STRATEGY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance Indicator 1 | Share of new medium-term sectoral strategies in the total number of strategies which include cost assessment for their implementation, including the potential funds from donors | SV (2014): 60% | TV 2017: 80% | Actual value in 2017: 70% | TV 2018: 85% | Actual value in 2018: 75% |  | TV 2019: 90% |  | Actual value in2019: 85% |  | TV 2020: 100% |  |  |  |
|  | Performance Indicator 2 | Average deviation between the limits of budget expenses determined by the medium-term budget framework and the real budget expenses planned by the Law on annual budget | SV (2014): 9% | TV 2017: 7% | Actual value in 2017: 6% | TV 2018: 6% | Actual value in 2018: 0,87% |  | TV 2019: 5% |  | Actual value in2019: 0,11% |  | TV 2020: 5% |  |  |  |
|  | Performance Indicator 3 | Number of employees trained for medium-term planning based on the “top to bottom” principle | SV (2014): 0 | TV 2017: 52 | Actual value in 2017: 0 | TV 2018: 35 | Actual value in 2018: 0 |  | TV 2019: 52 |  | Actual value in2019: 0 |  | TV 2020: 72 |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation | Priority |  | Planned starting date |  | Planned ending date |  | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 |  | 10 |  | 11 | 12 | 13 | 14 |
| *2) |  | A.1.3 Training of staff with a goal of improving medium-term planning of expenditure (target group: technical staff) | Training | Training materials prepared Certain number of employees trained. | IPA II | MF – BD (Ministry of finance) | 2 (A.1.5) |  | 2018 |  | 2019 |  | 2020 | 135.000,00 | Realization of funds will begin during 2019 from IPA II | Training material is prepaared. |
| *2) |  | A.1.4 Training for multi-annual budget planning with a goal of better compliance of program goals with the politics of the Government (target group: managerial staff) | Training | Training materials prepared Certain number of employees trained | IPA II | MF - BD | 2 (A.1.5) |  | 2018 |  | 2019 |  | 2020 | 50.000,00 | Realization of funds will begin during 2019 from IPA II | Training is planned for the third quarter of 2020 |
| *5) |  | A.1.7 Create an institutional and regulatory framework for strategic planning at the level of state administration/determining competences of state authorities for the implementation of the new planning process | Legal act (new / revised) | Regulation on amendments of the Regulation on organization and the mode of work of the state administration is adopted. Decision on amendments of the Rules of Procedure of the Government adopted |  | SGG | 2 (A.1.7) |  | IV Q 2016 |  | III Q 2018 |  | realized | 30.000,00 | SIGMA | Continuing of activities on the implementation of the medium-term planning of the work of ministries for all ministries in the year 2020 initiated as a pilot project for three ministries in the year 2019 under a new methodology |
|  |  | A.1.8 Improvement of planning and presentation of multi-annual assumed obligations in the budget | Legal act (new / revised) | Display of the multi-annual assumed obligations in the budget documentation. Display of multi-annual assumed obligations in the Law on the budget. | IPA II | MF - BD | 2 |  | IV Q 2017 |  | 2019 |  | 2020 | 300.000,00 | Realization of funds will begin during 2019 from IPA II |  |
| *6) |  | A.1.9 Develop and upgrade the existing IT system for budget planning in order to enable medium-term planning | Computerization | Specifications for the development and upgrade of the budget planning system prepared. Individual upgrades / enhancements / modules developed. | IPA II | MF - BD | 1 (A.2.9) (A.3.9) |  | 2018 |  | 2020 |  | 2020 | 15.000,00 | Realization of funds will begin during 2019 from IPA II |  |
| *7) |  | A.1.10 Improve the budget bulletin in the part of planning multi-annual assumed obligations | Guidelines/Manual | Budget circular prepared (every year) | IPA II | MF - BD | 1 (A.2.7) |  | II Q 2017 |  | 2019 |  | 2020 | 135.000,00 | Realization of funds will begin during 2019 from IPA II |  |
|  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  |  | 570.000,00 |  |  |
| Strategic goal 1._ A) Sustainable financial framework, planning and budgeting of public expenditure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OperatiVE GOAL 4.1.2_A.2. ANNUAL BUDGETING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance Indicator 4 | Share of first level consumer units which provide comprehensive information in their budget requests | SV (2014): 40% | TV 2017: 75% | Actual value in 2017: 70% | TV 2018: 80% | Actual value in 2018: 80% |  |  | TV 2019:90% |  | Actual value in2019: 90% | TV 2020: 100% |  |  |  |
|  | Performance Indicator 5 | Level of information on the performance of the included in planning of the budget | SV (2014): Defined names of programs of all consumer units. | TV 2017: Developed program structure at all budget units. | Actual value in 2017: Developed program structure in the part of defining the names of programs of all consumer units. | TV 2018: Developed program structure at all budget units. | Actual value in 2018. Developed program structure in the part of defining the names of programs of all consumer units. |  |  | TV 2019: Level 1 upgrade with set definition. The indicator is used for pilot projects |  | Actual value in 2019. Defined program names of all consumer units | TV 2020: Created set of indicators for all programs to monitor the success of achieving goals |  |  |  |
|  | Performance Indicator 6 | Number of employees trained for planning and monitoring expenses in accordance with the principles of program budgeting | SV (2014): 0 | TV 2017: 20 | Actual value in 2017: 0 | TV 2018: 35 | Actual value in 2018: 0 |  |  | TV 2019: 70 |  | Actual value in 2019: 17 | TV 2020: 130 |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation | Priority |  |  | Planned starting date |  | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | 9 |  | 10 | 11 | 12 | 13 | 14 |
| *2) |  | A.2.1 Evaluate the existing budget-related regulations and procedures and on the basis of findings and best practices and experiences in this field, amend the national legislative framework with the aim of establishing the preconditions for the full implementation of the program | Legal act (new / revised) | New / updated Decision on the mode and content of the program budget (in 2016 and if necessary in 2017 and subsequent years). Another (new) legal act is possible if necessary. | IPA II | MF - BD | 1 |  |  | Q II 2017 |  | 2018 | 2019 | 20.000,00 | Activity has been realized within the existing capacities, while a possible improvement in the following period will be realized from IPA II | Recommendations to amend the Decision were completed in December 2019, but a new Decision will be brought in 2020. Recommendations for amending the Law on Budget and Fiscal Responsibility have been prepared. The amendment to the law is planned for 2020 |
| *2) |  | A.2.2 Develop a detailed work plan for the implementation of program budgeting, including the follow-up plan of the activities. | Strategic / Plan document | Detailed Implementation Plan and Activities Plan prepared | IPA II | MF - BD | 1 (A.1.5) |  |  | 2018 |  | 2019 | 2019 | 20.000,00 | Realization of funds will begin during 2019 from IPA II | An agreed detailed plan is presented in the Introductory Report of the project. implementation and action plan. |
| *3) *4) *5) |  | A.2.3 Create a manual for program budgeting and update the manual in 2018. | Guidelines / Manual | Draft of the Manual prepared in Q2 2017. Updating of the Manual in Q2 2018 | IPA II | MF - BD | 1 |  |  | 2018 |  | 2019 | 2019 | 40.000,00 | Realization of funds will begin during 2019 from IPA II | The manual was developed and submitted in 2019. The manual will be updated if necessary in 2020 |
| *5) |  | A.2.4 Evaluate the existing program structures to identify the necessary changes through imposing / removing of programs or sub-programs | Legal act (new / revised) | Revised program structure prepared (draft). Revised program structure prepared (final) and implemented in the budget. | IPA II | MF - BD | 1 (A.2.5) (A.2.6) |  |  | 2018 |  | 2019 | 2019 | 60.000,00 | Realization of funds will begin during 2019 from IPA II | Implementation is scheduled for 2021 |
|  |  | A.2.5 Define missions, goals and descriptions of programs and sub-programs | Legal act (new / revised) | The missions, goals and descriptions of the programs / sub-programs are defined (and published in the budget documentation) for the 2017 budget and the required updates for the 2018 budget. | IPA II | MF - BD | 1 (A.2.4) (A.2.6) |  |  | 2018 |  | 2019 | 2020 | 180,000,00 | Realization of funds will begin during 2019 from IPA II |  |
|  |  | A.2.6 Define performance indicators for programs and sub-programs | Legal act (new / revised) | Performance indicators defined (and published in the budget documentation) | IPA II | MF - BD | 2 (A.2.4) (A.2.5) (C.1.4) (D.1.10) |  |  | 2019 |  | 2020 | 2020 2021 | 310,000.00 |  | Performance indicators will be defined in 2020 for pilot institutions and for other institutions in 2021. |
| *6) |  | A.2.7 Evaluate and modify the budget bulletin to reflect the changed program structures and introduce non-financial elements of the program budget | Legal act (new / modified) | Budget bulletin prepared (every year) | IPA II | MF - BD | 1 (A.1.11) |  |  | 2018 |  | 2019 | 2019 | 30,000,00 | Realization of funds will begin during 2019 from IPA II | The part of the circular related to the adopted new detailed program classifications will be completed in 2020. The part of the circular related to non - financial elements will be finalized in 2021. |
| *7) |  | A.2.8 Organize training for employees of the MF and budget organizations that will be involved in the implementation of the program budget | Training | Certain number of employees trained. | IPA II | MF - BD | 1 |  |  | 2018 |  | 2019 | 2020 | 170,000,00 | Realization of funds will begin during 2019 from IPA II | Training for employees in the MoF was held in 2019, while for employees in spending units will be in early 2020 |
|  |  | A.2.9 Evaluate and improve the functionality of an existing IT budget planning system | Computerization | Specifications for the development and upgrading of the budget planning system prepared. Individual upgrades / enhancements / modules developed. | IPA II | MF - BD | 1 (A.1.10) (A.3.9) |  |  | 2018 |  | 2020 | 2020 | See A1.10 | Realization of funds will begin during 2019 from IPA II |  |
|  |  | A.2.10 Improve budget transparency by providing better visual presentation | Computerization | Budget view designed and website created. The format of the Budget Law has been revised and updated. | IPA II | MF – BD | 2 |  |  | 2019 |  | 2020 | 2020 2021 | 20,000.00 |  | Recommendations and changes to the program classification were completed in 2019. In 2020, the budget presentation will be completed through a detailed program and amended organizational classification. Performance information and budget rationale will be covered in 2021. |
|  |  | A.2.11 In accordance with the best international standards, research and implement an improved presentation and visualization of annual reports (monthly and quarterly) | Computerization | Monthly and quarterly reports prepared and published on the MoF website. | IPA II | MF – BD | 2 |  |  | 2019 |  | 2020 | 2020 2021 | 45,000.00 |  |  |
|  |  | A.2.12 Improve the resources for better management of own EU funds | Training | Draft of the Manual prepared. Employees trained. | IPA II | MF – BD | 1 (B.1.6) (B.2.8) |  |  | 2017 |  | 2019 | realized | realized using the existing capacities |  |  |
|  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  |  | 895,000,00 |  |  |
| Strategic goal 1._ A) Sustainable financial framework, planning and budgeting of public expenditure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OperatiVE GOAL 4.1.3._A.3. CAPITAL BUDGET |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 7 | Level of details in the public presentation of the capital budget | SV (2014): Projects in the capital budget displayed as grouped by areas (education, health, culture, sports ...) | TV (2017): Projects in the capital budget displayed as grouped by areas (education, health, culture, sports ...) | Actual value in 2017: Projects in the Law on the budget displayed as grouped by areas, while in the description of the Law they are displayed by single projects | TV (2018): Projects in the capital budget displayed as grouped by areas (education, health, culture, sports ...) |  | Actual value in 2018: Projects in the Law on the budget displayed as grouped by areas, while in the description of the Law they are displayed by single projects |  | TV (2019): Overview of all individual projects implemented in the budget year and implementation of selected pilot projects by phases |  | Actual value in2019. Projects in the Law on Budget are presented grouped by areas, while in the Explanation of the Law they are presented by individual projects | TV (2020): Overview by individual projects and phases of project implementation |  |  |  |
|  | Performance indicator 8 | Ratio of actual and capital expenditure in the current year in comparison to the capital budget plan | SV (2014): 70% | TV (2017): 80% | Actual value in 2017i: 82 | TV (2018): 83% |  | Actual value in 2018: 91%/111% |  | TV (2019): 86% |  | Actual value in2019: 92% 112,3% | TV (2020): 90% |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation |  | Priority |  | Planned starting date |  | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 |
| *2) |  | A.3.1 Improve capital budget planning in the medium-term as a part of the MTBF | Legal act (new / modified) | New legal act / guidelines that prescribe the mode and content of capital budgeting. | IPA II | MF - BD |  | 1 |  | 2018 |  | 2020 | 2020 | 30,000,00 | Activity has been realized within the existing capacities, while a possible improvement in the following period will be realized from IPA II |  |
| *2) |  | A.3.2 Introduce the phases of capital projects in the preparation and planning of capital budgets (preparatory phase and construction phase) | Legal act (new / modified) | A new format of the law on budget (capital budget) prepared. | IPA II | MF - BD |  | 2 |  | 2018 |  | 2020 | 2020 | 25,000,00 | Realization of funds will begin during 2019 from IPA II |  |
| *3) *4) *5) |  | A.3.3 Improve the overview of projects in the capital budget through a detailed overview of individual projects by projects and economic classification | Legal act (new / modified) | A new format of the law on budget (capital budget) prepared. | IPA II | MF - BD |  | 1 |  | 2018 |  | 2020 | 2020 | 25,000,00 | Realization of funds will begin during 2019 from IPA II |  |
| *5) |  | A.3.4 Improve the descriptions of the capital budget in relation to the total estimated value and dynamics of the projects | Guidelines / Manual | Guidelines prepared. Explanation of each project prepared. | IPA II | MF - BD |  | 2 |  | 2018 |  | 2020 | 2020 | 15,000,00 | Realization of funds will begin during 2019 from IPA II |  |
|  |  | A.3. 5 Establish a public register of all projects financed from the capital budget | Computerization | Public register established. Registry published on the website of the MF. | IPA II | MF - BD MF - Treasury. MSDT - DPV MTMA - DT |  | 1 (D.1.7) |  | 2018 |  | 2020 | 2020 | 35,000,00 | Realization of funds will begin during 2019 from IPA II |  |
| *6) |  | A.3.6 Training of staff in competent ministries involved in the planning and implementation of capital projects in order of better planning of the cost of investment projects in the medium-term | Training | Training materials prepared. Certain number of employees trained. | IPA II | MF - BD |  | 2 |  | 2018 |  | 2019 | 2020 | 50,000,00 | Realization of funds will begin during 2019 from IPA II |  |
| *7) |  | A.3.7 Improve the overview of capital projects by separating the new projects from those that are already being implemented | Legal act (new / modified) | A new format of the law on budget (capital budget) prepared. | IPA II | MF - BD |  | 2 |  | 2018 |  | 2019 | 2020 | 10,000,00 | Realization of funds will begin during 2019 from IPA II |  |
|  |  | A.3.8 Evaluate and improve the functionality of an existing IT system for capital budget planning | Computerization | Specifications for the development and upgrading of the system for budget planning are prepared. Individual upgrades/improvements/modules developed | IPA II | MF - BD |  | 1 (A.1.10) (A.2.9) |  | 2018 |  | 2020 | 2020 | See A1.10 | Realization of funds will begin during 2019 from IPA II |  |
|  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  | 190,000,00 |  |  |
| Strategic goal 1._ A) Sustainable financial framework, planning and budgeting of public expenditure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OperativE GOAL 4.1.4._ A.4. iMPROVEMENT OF THE MODEL FOR MACROECONOMIC PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 9 | Implementation phases of the improved model for projections of macroeconomic Indicators and the impact of structural reforms | SV (2014): The existing model used in the Directorate for economic and development policy is based on the financial programming model, and the projection of the determined parameters is based on an expert assessment | TV (2017): Analysis and upgrading of the existing macroeconomic model for projections | Actual value in 2017: Target value for 2017 is fulfilled | TV (2018): A new model for projections of macroeconomic Indicators and the impact of structural reforms created and trained employees |  | Actual value in 2018: A new model for projections of macroeconomic Indicators and the impact of structural reforms created and trained employees |  | TV (2020): Completed implementation and full ability to use the model |  | Actual value in2019 Preconditions for the use of the new model by employees in the Directorate for Economic Policy and Development have been met | TV (2020): Full implementation and full ability to use the model |  |  |  |
|  | Performance indicator 10 | The difference between the projected and the realized rate of actual growth of GDP | SV (2014): 1,8 p.p. | TV (2017): Less than 0,5 p.p | Actual value in 2017: Target value for 2017 is not fulfilled | TV (2018): Less than 0,3 p.p |  | Actual value in 2018: 0,8 p.p. |  | TV (2020): Less than 0,2 p.p. |  | Actual value in2019. Target value for 2019 partially met, further recommendations given | TV (2020): less than 0,2 p.p. |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation |  | Priority |  | Planned starting date |  | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 |
| *2) |  | A.4.2 Improvement of the existing model for macroeconomic projections | Manual | Manual for using the new model | IPA II | MF - DEPD |  | 1 |  | Q III 017 |  | Q I 2018 | Realized/ Continuous | Not determined | / | - Work on improving the model is a continuous process. Realized |
| *2) |  | A.4.3 Training of employee for using the model (both modules) | Training | Certain number of employees trained | IPA II Budget of Montenegro | MF - DEPD Other competent ministries |  | 1 |  | Q III 2017 |  | Q III 2018 | Realized/ Continuous | Not determined | / | - After the outflow of staff, it is necessary to employ new staff and train them to work on the model. Realized |
| *3) *4) *5) |  | A.4.4 Collection and analysis of data for the requirements of module II of the model | Procedure | Creating of preconditions for improving the module II | IPA II | MF - DEPD Other competent ministries |  | 1 |  | Q II 2017 |  | Q I 2018 | Realized/ Continuous | Not determined | / | - Realized |
| *5) |  | A.4.5 Building of the module for the impact of structural reforms on macroeconomic effects Indicators | Manual | Manual for using the module II of the model | IPA II | MF - DEPD Other competent ministries |  | 1 |  | Q I 2018 |  | Q III 2018 | Realized/ Continuous | Not determined | / | - Realized |
|  |  | A.4.6 Implementation of the new model and full education of employees for the work in the model | Regulation / Procedures / Training courses/ Computerization | Application of the new model and training of employees of the DEP for working on the model, and of competent ministries for the usage of the model | IPA II | MF - DEPD |  | 1 |  | Q I 2018 |  | Q IV 2020 | 2024 | Not determined | / | - Adequate staff training; -engagement of experts for modelling and programming; - It is necessary to engage IT experts, mathematicians and engage analysts who have the necessary knowledge of modelling, programming and understanding of macroeconomics. |
|  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  | 200,000.00 |  |  |
| Strategic goal 2. _ B) Execution of the budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OperativE GOAL 4.1.3.1._ B.1. COLLECTION OF REVENUES – TAX ADMINISTRATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 11 | Growth of the share of submitted electronic tax returns (income tax, VAT) | SV (2014): 27% | TV (2017): PDV 50% REVENUE 95% | Actual value in 2017: VAT 50% REVENUE 95% | TV (2018): VAT 65% REVENUE 97% |  | Actual value in 2018: VAT 70% REVENUE 99% |  | TV (2020): VAT 80% REVENUE 99% |  | Actual value in2019. VAT 77,37 % REVENUE 99,5% | TV (2020): VAT 80% REVENUE 99% |  |  |  |
|  | Performance indicator 12 | Successfully implemented EU legislation regarding the common EU market | SV (2014): Screening process completed | TV (2017): Negotiations for chapter 16 opened | Actual value in 2017: A certain degree of legislative compliance has been achieved, a higher level of achievement has been achieved in the area of VAT, still remaining is compliance regarding income tax (transfer prices), administrative co-operation and mutual assistance | TV (2018): Law on amendments to the Law on income tax for legal entities (IV quarter 2018) - Law on amendments and supplements of the Law on tax administration (IV quarter 2018) |  | Actual value in 2018: Drafts of the Law on amendments to the Law on income tax for legal entities, as well as the Law on amendments and supplements of the Law on Tax Administration in order of further harmonization with EU legislation, especially in the area of administrative co-operation and information exchange. |  | TV (2020): Implemented planned activities from the Accession Program - Chapter 16 |  | Actual value in2019. Higher degree of compliance compared to the previous year; All proposed amendments to the law passed the Legislative Committee. After which they were submitted to the EC for an opinion. | TV (2020): Implemented channeled activities from the Accession Program - Chapter 16. |  |  |  |
|  | Performance indicator 13 | Share of collected tax revenues in relation to the planned tax revenues in the annual law on the budget | SV 2014: 100% (2015): 100% (2016): 100% | TV (2017): 100% | Actual value in 2017: More than 100% of the planned (24 million above plan for 2017) and 34 million above the achievement in 2016. | TV (2018): 100% |  | Actual value in 2018: Above the plan for 2018, 73 million were achieved and 117 million above the achievement in 2017. |  | TV (2020): 100% |  | Actual value in2019. Above the plan for 2019, 80 million were achieved above the plan | TV (2020): 100% |  |  |  |
|  | Performance indicator 14 | Share of VAT revenues in GDP | SV (2014): 13,5% | TV (2017): 13,5% | Actual value in 2017: 13,0% | TV (2018): 14,7% |  | Actual value in 2018: 13,6% |  | TV (2020): 14,6% |  | Actual value in2019i: 14,44% | TV (2020): 14,6% |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation |  | Priority |  | Planned starting date |  | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 |
|  |  | B.1.1 Further improvements in efficiency, taxpayer services and compliance with tax regulations through capacity building and system improvement within the Tax Administration. | Procedures, Computerization | Growth of the share of submitted electronic tax return requests (income tax, VAT) | IPA II | MF - PU. |  | 2 |  | 2018 |  | 2019 | 2020 | 1.000.000,00 | / | - Activity has not yet begun with realization, because it is conditioned by IPA funds |
|  |  | B.1.2 Improving the administrative and institutional capacities of the Tax Administration in the field of the application of the common VAT system of the EU | Legal act (new/revised), Computerization | Software implemented. | IPA II | MF - PU |  | 2 |  | 2019 |  | 2020 | 2025 | 2.000.000,00 | / | - The activity is realized with the predicted dynamics while the new deadline is related to the release of the VIES system, which must be in function at least half a year prior to the accession to EU |
|  |  | B.1.3 Improving the capacity of the Tax Administration and its IT systems in the field of risk analysis and inspection controls (e-controls) and implementation systems (e-fiscal measures) | Procedures, Computerization | Software implemented. | IPA II | MF - PU |  | 2 |  | 2017 |  | 2018 | 2020 | 500,000,00 | / | - The activity depends on the IPA funds; the incentive for this component is transferred within the "B 1.5" activity so that it can be implemented on time. E-fiscal measures will be financed from project funds under a contract with the World Bank in order of improvement of the Tax Administration |
|  |  | B.1.4 Strengthening the administrative and operational capacities of the Tax Administration in accordance with the EU standards and requirements defined in Chapter 16 - Taxation | Legal act (new/revised), Computerization | Updating the regulative / business processes defined in compliance with EU requirements | IPA II | MF - PU |  | 1 |  | Q II 2017 |  | 2018 (18 months) | June 2019 | 1.000.000,00 | 1.000.000,00 | - The completion of the project is scheduled for June 30th, 2019. |
|  |  | B.1.5 Tax Administration Reform | Business processes, Computerization | Implementation of the Integrated Revenue Management System (IRMS) in accordance with business processes |  | MF - PU |  | 1 |  | Q I 2017 |  | 2023(5 years) | 2023 (5 years) | 14.000.000,00 | 133.705,00 | - Restructuring of the project "Tax Administration Reform in Montenegro (RARP)", within which e-fiscal measures is planned as the 4th component. |
|  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  | 18.500.000,00 |  |  |
| Strategic goal 2. _ B) Execution of the budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operative GOAL 4.1.3.1._ B.1. COLLECTION OF REVENUES – CUSTOMS ADMINISTRATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 15 | The rate of change in the realized collection of revenues in relation to the previous year | SV (2014): 15% | TV (2017): 17,64 % | Actual value in 2017: 17,64 % | TV (2018): 5% |  | Actual value in 2018: 11,03% |  | TV (2020): 5% |  | Actual value in2019.: 5,17% | TV (2020): 5% |  |  |  |
|  | Performance indicator 16 | Harmonization of customs and excise legislation with EU legislation | SV (2014): Screening process completed chapter 16 Taxation | TV (2017): Law on amendments and supplements of the Law on customs Law on amendments and supplements of the Law on excises Regulations on the customs tariff for 2017 Regulations for implementing the Law on customs | Actual value in 2017: Four regulations adopted | TV (2018): Adoption of 3 regulations |  | Actual value in 2018: Three regulations adopted |  | TV (2020): Two regulations adopted |  | Actual value in2019.: Adoption of 3 regulations | TV (2020): Adoption of 2 regulations |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation |  | Priority |  | Planned starting date |  | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 |
|  |  | B.2.1 Implementation of IT system for excises at the national level | Procedures, Computerization | Procedures established. Software implemented. | IPA II | MF - UC. |  | 1 |  | 2019 |  | 2020 | 2020 | 299,000.00 |  |  |
| *2) |  | B.2.2 Implementation of modernized customs procedures at a national level | Procedures, Computerization | Procedures established. Software implemented. | IPA II | MF - UC. |  | 1 |  | 2018 |  | 2020 | 2020 | 3.300.000,00 | 0,000 | - The IPA 2014 project "Support to the Customs Administration" started with implementation in November 2018 and will last for 36 months. -The value of the project is EUR 3,300,000 |
| *2) |  | B.2.3 Training of officers in regard to the preparation for the implementation of automated reporting procedures on revenues EU (A-B accounts) | Training | Employees trained. | IPA II | MF - UC. |  | 2 |  | 2018 |  | 2020 | 2020 | Not determined | 0,000 | - Conducting training of officers within the framework of the CUSTOMS 2020 program |
| *3) *4) *5) |  | B.2.4 Improvement of the customs system of risk management | Training / Computerization | Employees trained. Software improvement | IPA II | MF - UC. |  | 2 |  | 2018 |  | 2020 | 2020 | Not determined | 0,000 | - Constant activities conducted with the continuous technical support of TAIEX and other EU expert assistance programs, which will ensure that the development of the risk analysis in the Customs Administration is in compliance with the best practices and guidelines of the EU and WCO in this area. |
| *5) |  | B.2.5 Increase the number of commercial entities that have been granted authorizations for simplified procedures | Preparation of commercial entities for obtaining authorizations | Increased number of commercial entities | IPA II | MF - UC. |  | 2 |  | 2018 |  | 2020 | 2020 | Not determined | 0,000 | - Continuation of the activities on affirmation of business entities to be entitled to use the simplified procedures. |
|  |  | B.2.6 Development of the AEO program | Regulative/ Procedures/ Training/ Computerization | The regulation has been updated. Procedures have been established. Software has been implemented. | IPA II | MF - UC. |  | 2 |  | 2018 |  | 2020 | 2020 | Not determined | 0,000 | - Implementation of the AEO program is a process that has been developing over the years. In 2018, preparatory activities for the development of the AEO program were carried out. In accordance with the defined plan, the Customs Administration continues to implement activities aimed at implementing the AEO program. |
|  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  | 3.300.000,00 | 0,000 |  |
| Strategic goal 2._ B) Execution of the budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operative GOAL 4.1.3.3._ B.3. PUBLIC PROCUREMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 17 | The level of harmonization and completion of the legislative framework in public procurement procedures with the EU legislation | SV (2014): Negotiations opened in the negotiation chapter 5 | TV (2017): Negotiations opened in the negotiation chapter 5 | Actual value in 2017: Negotiations opened in the negotiation chapter 5 | TV (2018): Further harmonization with the Directives package from 2014 in this field |  | Actual value in2018. Negotiations opened in the negotiation chapter 5 |  | TV (2019): Further harmonization with the package of Directives from 2014 in this area (implementation of the new Law on Public Procurement, introduction of the electronic system of Public Procurement ...) |  | Actual value in2019. Adoption of a new Law on Public Procurement by implementing the provisions in accordance with the new directives | TV (2020): Implemented planned activities from the Accession Program Chapter 5. |  |  |  |
|  | Performance indicator 18 | Average number of bidders participating in public tenders | SV (2014): 3,52 bids per tender | TV (2017): 3,2 | Actual value in 2017: 2,65 | TV (2018): 3,48 |  | Actual value in2018 3,14 |  | TV (2019): 3,58 |  | Actual value in2019. : n/a | TV (2020): 3,8 |  |  |  |
|  | Performance indicator 19 | Share of the use of electronic public procurement in the total number of public procurement contracts during the year | SV (2014): 0% (electronic public procurement system does not exist) | TV (2017): 0% (electronic public procurement system does not exist) | Actual value in 2017: 0% (electronic public procurement system does not exist) | TV (2018): Choice of the best bidder |  | Actual value in2018. The project of creating an e-public procurement system has started |  | TV (2019): 30% |  | Actual value in2019. Pilot phase of the e-system | TV (2020): 80% |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation |  | Priority |  | Planned starting date |  | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 |
| *2) |  | B.3.4 Provide training for public procurement employees of the state (such as public procurement officers, members of commission for opening and evaluating bids, as well as for inspectors, prosecutors and judges) | Training | Training materials prepared. Certain number of employees trained. | IPA II | MF - UJN |  | 2 |  | Q I 2017 |  | Q IV 2018 | Realized | 35,000,00 |  | Realized. |
| *2) |  | B.3.5 Material for training of specific target groups involved in public procurement | Training | Training materials prepared. Certain number of employees trained. | IPA II | MF - UJN |  | 2 |  | Q I 2017 |  | Q IV 2018 | IV Q 2019 III/IV Q 2020 | 50,000,00 |  | - There was a delay in implementation due to the new Law on Public Procurement. In accordance with this, the activity will be implemented during Q IV 2019 and it will refer to the preparation of the Manuals, guidelines and other instructions for the implementation of new legislation in this field. |
| *3) *4) *5) |  | B.3.6 Campaign for raising awareness | Training | Campaign started and completed. | IPA II | MF - UJN |  | 1 |  | Q III 2017 |  | Q IV 2018 | IV Q 2019 III/IV Q 2020 | 40,000,00 |  | - The delay in implementation was due to the new Law on Public Procurement. In this regard, it will be implemented continuously during 2019 (Q I-IV) and it will refer to the Development and implementation of the communication strategy with the goal of raising public awareness in the field of public procurement. |
| *5) |  | B.3.7 e-public procurements | Computerization | Software implemented. | IPA II | MF - UJN |  | 1 |  | Q I 2017 |  | 2020/2021 | 2020/2021 | 1.650.000,00 |  | The activities will be realized through an IPA project called “Implementation of electronic public procurement system in Montenegro The project started in November 2018. year and lasts 36 months.In July 2020, the beginning of the Pilot Phase in which will be attended by several customers who would test in this way system and assisted in removal possible shortcomings. After the final design of the system, the public procurement portal will replace the advanced IT system ESJN, with the expectation of January 2021. It's started testing of the electronic public procurement system by employees in Directorate for Public Procurement Policy of the Ministry of Finance, which will expand to six more clients |
|  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  | 1.775.000,00 |  |  |
| Strategic goal 2._ B) Execution of the budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operative GOAL 1._ B.4. REFORM OF THE STATE AID |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 20 | Number of providers and users of state aid, representatives of the private sector and judges attending seminars and trainings in the field of state aid | SV (2014): 50 | TV (2017): 50 | Actual value in 2017: 0 | TV (2018): 30 |  | Actual value in 2018: 0 |  | TV (2019): 60 |  | 56 | TV (2020): 100 |  |  |  |
|  | Performance indicator 21 | Percentage of officers of the Department and members of the Commission for control of state aid that attend professional seminars in order to strengthen the legal framework, reduce illegal state aid and execute ex-post controls | SV (2014): 30% | TV (2017): 30% | Actual value in 2017: 33% | TV (2018): 50% |  | Actual value in 2018: 0% |  | TV (2019): 70% |  | Actual value in2019: 70% | TV (2020): 80% |  |  |  |
|  | Performance indicator 22 | Number of completed ex-officio cases | SV (2014): 5 | TV (2017): 3 | Actual value in 2017: 0 | TV (2018): do 2 |  | Actual value in 2018: 0 |  | TV (2019): to 2 |  | Actual value in2019: 0 (2 ex-officio cases have been opened, we expect them to close in the coming period) | TV (2020): to 1 |  |  |  |
|  | Performance indicator 23 | Number of legal acts analyzed and assessed by the department | SV (2014): 11 | TV (2017): 20 | Actual value in 2017: 14 | TV (2018): do 20 |  | Actual value in 2018: 22 |  | TV (2019): to 23 |  | Actual value in2019: 35 | TV (2020): 25 |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation |  | Priority |  | Planned starting date |  | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 |
| *2) |  | B.4.1 Improving and strengthening the institutional basis and national legal system related to the implementation of rules and procedures for State aid; | Organizational/Managerial changes | Organizational change implemented, i.e. a special body (organizationally independent, part of MF or with some other ministry) | IPA II | MF - DP |  | 1 |  | Q II 2018 |  | Q IV 2020 | Q IV 2020 | 50,000,00 | Realization of funds will begin during 2019 from IPA II |  |
| *2) |  | B.4.2 Support through the negotiation process and fulfilment of obligations related to Chapter 8; | Legal act (new/revised) | Fulfilment of final determinants (benchmarks) | IPA II | MF - DP |  | 1 (B.4.3) |  | Q III 2018 |  | Continuous | Continuous | 150,000,00 | Realization of funds will begin during 2019 from IPA II |  |
| *3) *4) *5) |  | B.4.3 Conduction of monitoring of results achieved through analyses of national cases of State aid in customary EC law; | Guidelines/Manual | The analysis of 3-4 cases was performed. | IPA II | MF - DP |  | 1 (B.4.2) |  | Q III 2017 |  | Continuous | Continuous | 200,000,00 | Realization of funds will begin during 2019 from IPA II |  |
| *5) |  | B.4.4 Technical support for the software "Information system of state aid in Montenegro", creation of a special register for de Minimis State aid and establishment of an application for State aid providers: in order to be contained in a single IT component; | Computerization | Software implemented. | IPA II | MF - DP |  | 1 |  | Q IV 2018 |  | Q IV 2020 | Q IV 2020 | 200,000,00 | Realization of funds will begin during 2019 from IPA II |  |
|  |  | B.4.5 Strengthening administrative capacities through training and exchange of practical experiences | Training | Training materials prepared. Certain number of employees trained. | IPA II | MF - DP |  | 2 |  | Q III 2018 |  | Continuous | Continuous conduction | 100,000,00 | Realization of funds will begin during 2019 from IPA II |  |
|  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  | 700,000,00 |  |  |
| Strategic goal 2._ B) Execution of the budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operative GOAL 4. 1._ B.6. REFORM OF THE RENUMERATION SYSTEM IN THE PUBLIC SECTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 24 | Costs of servicing the public debt as a share of GDP | SV (2014): 2.2 % | TV (2017): 2.5 % | Actual value in 2017: 2,3 % | TV (2018): 1,9 % |  | Actual value in 2018: 2,1% |  | TV (2019): 2,0 % |  | Actual value in2019.:2,2% | TV (2020): 2,3% |  |  |  |
|  | Performance indicator 25 | The difference between the planned and realized level of the debt of the public sector | SV (2014): 1,5% | TV (2017): 1,5% | Actual value in 2017: Public debt is 3.2% lower than planned | TV (2018): 1,5% |  | Actual value in 2018: Public debt is 3.07% higher than planned |  | TV (2019): 1,5% |  | Actual value in2019. Realized difference in gross public debt 16.6% | TV (2020): 1,5% |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation |  | Priority |  | Planned starting date |  | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 |
| *2) |  | B.5.2 Training of staff in the Department for public debt in regard to the management of various financial operations, introduction and training for various financial derivatives, preparation and debt analysis, and improvement of debt management | Training | Materials for training prepared and available. Certain number of employees trained. | IMF SIGMA | MF – Treasury |  | 1 |  | Q I 2016 |  | Q IV 2018 | Realized / Continuous conduction | 50,000,00 | Donation |  |
| *2) |  | B.5.4 Upgrade the software mechanism for managing public debt and cash movement | Computerization | Upgrading the implemented software. |  | MF – Treasury |  | 3 |  | Q I 2016 |  | 2019 | 2020 | 500,000,00 | 0,000 |  |
|  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  | 780.000,00 | 0,000 |  |
| Strategic goal 1._ A) Sustainable financial framework, planning and budgeting of public expenditure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operative GOAL 4. 1._ B.6. REFORM OF THE SALARY SYSTEM IN THE PUBLIC SECTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation |  | Priority |  | Planned starting date |  | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 |
| *2) |  | B.6.2 Implementation of new software for calculation and control of remuneration in the public sector | Computerization | Software implemented. |  | MF - BD |  | 1 (B.6.1) |  | Q IV 2016 |  | 2018 | 2020 | 600,000,00 | Realization of funds will begin during 2019 from IPA II |  |
|  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  | 600,000,00 | 0,000 |  |
| Strategic goal 3._ C) Development of internal financial control in the public sector (PIFC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 26 | Percentage of ministries that formally delegated responsibilities and authorities to managers, which improves managerial accountability | SV (2014): 6,25% 2015: 6,3% 2016: 6,3% (Report: 2016: 22,22%) | TV (2017): 30% | Actual value in 2017: 11.11% | TV (2018): 16% |  | Actual value in 2018: 18% |  | TV (2019): 50% |  | Actual value in2019: 12% | TV (2020): 90% |  |  |  |
|  | Performance indicator 27 | Percentage of budget users at central and local levels who submit annual reports on financial management and control | SV (2014): 69% 2015: 76% 2016: 76% | TV (2017): 75% | Actual value in 2017: 80% | TV (2018): 80% |  | Actual value in 2018: 90% |  | TV (2019): 90% |  | Actual value in2019: 93% | TV (2020): 95% |  |  |  |
|  | Performance indicator 28 | The average number of appointed internal auditors per unit | SV (2014): 1,76 | TV (2017): 2 | Actual value in 2017: 2 | TV (2018): 2.3 |  | Actual value in 2018: 2.21 |  | TV (2019): 2.5 |  | Actual value in2019: 2.1 | TV (2020): 2,7 |  |  |  |
|  | Performance indicator 29 | Percentage of appointed and certified internal auditors | SV (2014): 60% | TV (2017): 75% | Actual value in 2017: 90,90% | TV (2018): 80% |  | Actual value in 2018: 94.05% |  | TV (2019): 85% |  | Actual value in2019: 100.00% | TV (2020):90% |  |  |  |
|  | Performance indicator 30 | Percentage of appointed certified auditors which have continuous professional development | SV (2014): 0% | TV (2017): 70% | Actual value in 2017: 74% | TV (2018): 75% |  | Actual value in 2018: 83.64% |  | TV (2019): 80% |  | Actual value in2019: 81,36% | TV (2020): 90% |  |  |  |
|  | Performance indicator 31 | Percentage of implemented and partially implemented recommendations of internal audit by the end of the year, which were given in the previous year | SV (2014): 48% (2016): 74,2% | TV (2017): 55% | Actual value in 2017: 73,5% | TV (2018): 60% |  | Actual value in 2018: 79,16% |  | TV (2019): 65% |  | Actual value in2019: 84,46% | TV (2020): 70% |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation |  | Priority |  | Planned starting date |  | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 |
| *2) |  | C.1.3 Defining mechanisms for delegating the responsibilities and authorizations | Legal act (new/revised) | A draft of the manual/rulebook which describes mechanisms for delegating responsibilities and authorities has been prepared | IPA II | MF - CHU MF – BD |  | 1 (C.1.2) |  | 2018 |  | 2019 | 2019 | 25,000,00 | 24.998,46 | - Realized. - Activities on creation of Methodology have started. |
| *2) |  | C.1.4 Conducting of training for managers | Training | Training materials prepared. Number of trained people. | IPA II | MF - CHU UZK |  | 2 (C.1.6) (C.1.7) |  | Q III 2017 |  | Continuous | Continuous | 20,000,00 | 12.000 | - The Ministry of Finance will continue to conduct trainings for managers in the following period. |
| *3) *4) *5) |  | C.1.5 Conducting of training for newly appointed internal auditors | Training | Training materials prepared. Number of trained people. | IPA II | MF - CHU UZK German Government. |  | 2 (C.1.5) (C.1.7) |  | Q III 2017 |  | Continuous | Continuous | 10,000,00 | 10.000 | - The Ministry of Finance will localize the Training Program in the following period and it will be implemented in co-operation with the Human Resources Management Authority. |
| *5) |  | C.1.6 Organizing and maintaining training for improving the expertise of existing internal audit capacities | Training | Training materials prepared. Number of trained people. | IPA II | MF / CHU UZK |  | 2 (C.1.5) (C.1.6) |  | Q III 2017 |  | Continuous | Continuous | 20,000,00 | 17.500 | - The Ministry of Finance will continue to conduct trainings for improving the expertise of internal audit in the following period. |
|  |  | C.1.8 Strengthening the capacities of the CHU for reviewing the quality of financial management and control and internal audit | Guidelines/Manual | Guidelines prepared. | IPA II SIGMA | MF – CHU |  | 1 (C.1.1) |  | Q II 2016 |  | 2020 | 2020 | 25,000,00 |  | - Implementation of the IPA project "Improvement of the budget system, multi-annual budget planning and system for public financial internal control” has begun, within which the assistance will be provided for the realization of this activity. |
| *6) |  | C.1.9 Updating of guidelines for establishing risk management | Guidelines/Manual | Guidelines for establishing risk management prepared | IPA II | MF - CHU |  | 1 |  | Q III 2018 |  | 2018 | Realized | 15,000,00 | 0.00 | - Guidelines will be updated in accordance with the level of development of process of risk management. |
|  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  | 175.000,00 |  |  |
| Strategic goal 4._D) Financial reporting and accounting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operative GOAL 4.3. _D.1. TRANSITION FROM CASH ACCOUNTING TO ACCRUAL ACCOUNTING AND FINANCIAL REPORTING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 32 | Trained accountants in the public sector regarding accrual accounting (based on the CIPFA methodology) | SV (2014): 0 | TV (2017): 40 | Actual value in 2017: 40 in 2016 | TV (2018): 40 |  | Actual value in 2018: 80 |  | TV (2019): 20 |  | Actual value in2019: 40 | TV (2020): 100 |  |  |  |
|  | Performance indicator 33 | Implemented register of assets and system for dual accounting of assets | SV (2014): Development of the asset register has begun | TV (2017): Data on assets stored in the register | Actual value in 2017: 0 | TV (2018): (direct and indirect users of the budget) and collecting information on the condition of the property |  | Actual value in 2018: 0 |  | TV (2019): Training course (indirect budget users) and migration of funds to ARS and commissioning of records |  | Actual value in2019: 9 groups 100 state bodies 0 migration | TV (2020): mplemented asset register and sufficient asset accounting system |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation |  | Priority |  | Planned starting date |  | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 |
| *2) |  | D.1.1 Provide general training on accrual accounting for accountants from the public sector | Training | Training materials are prepared and available. Certain number of employees trained. | UNDP CEF, CIPFA | MF - Treasury |  | 1 |  | Q I 2016 |  | Q IV 2020 | Realized / Continuous conduction | Not determined | Donation | Realized. |
| *2) |  | D.1.2 Develop new policies for accrual accounting | Legal act (new/revised) | Law on accounting in the public sector is adopted |  | MF - Treasury |  | 1 |  | Q I 2017 |  | Q IV 2020 | 2020 | Not determined | / | -Law on accounting in the public sector has been adopted in November 2019. |
| *3) *4) *5) |  | D.1.3 Adapt the accounting plan with new accounting requirements | Legal act (new/revised) | Updated classifications (organizational, functional, proprietor …) | UNDP | MF - Treasury |  | 2 (D.2.1) (D.2.2) (D.2.3) |  | Q I 2018 |  | 2020 | 2020 | Not determined | / | - Work on this activity is in progress. |
|  |  | D.1.4 Develop an IT system to support double-entry bookkeeping | Computerization | IT system implemented |  | MF - Treasury |  | 2 |  | 2019 |  | 2020 | 2020 | Not determined | Budget/Donation | Work on this activity is in progress. |
|  |  | D.1.5 Develop new implementation regulations and report forms | Legal act (new/revised) | New regulations and report forms approved. |  | MF - Treasury |  | 2 |  | 2019 |  | 2020 | 2020 | Not determined | Budget/Donation | Work on this activity is in progress. |
|  |  | D.1.6 Provide training for public sector accountants on new implementation regulations, forms and IT system | Training | Training materials are prepared and available. Certain number of employees trained. |  | MF - Treasury |  | 2 |  | 2020 |  | 2020 | 2020 | Not determined | Budget/Donation | Work on this activity will begin after the adoption of regulations and adjustment of IT systems |
| *5) |  | D.1.9 Provide training for accountants from the public sector on new implementation regulative and the usage of a new module for asset management | Training | Certain number of employees trained. |  | MF - PrA |  | 2 (D.1.8) |  | Q III 2015 |  | Q IV 2016 | 2020 | Not determined | / | - Realization of activities related to training of accountants in the public sector regarding the new implementation regulative and the usage of a new module for asset management will be specified in the following period. |
|  |  | D.1.10 Regulation changes, annual reports should include both asset data and performance indicators | Legal act (new/revised) | Regulation amended and approved. |  | MF - Treasury MF - DfP MF-PrA. |  | 2 (A.2.6) (C.1.4) (D.1.8) |  | 2019 |  | 2020 | 2020 | Nije određeno | / | The change in regulations began in June 2019, but due to the situation with the Corona pandemic virus, all activities were stopped. |
|  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  | 0.000 | 0.000 |  |
| Strategic goal 5._E) Development and strengthening of external audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operative GOAL 4.5.1._STRENGTHENING OF THE STATE AUDIT INSTITUTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 34 | Percentage of implementation of the Annual audit plan of the SAI | SV (2014): 60% (2017): 80% | N/A | N/A | TV (2018): 83% |  | Actual value in 2018: 86,27% |  | TV (2019): 86% |  | Actual value in2019: 88,68% | TV (2020):90% |  |  |  |
|  | Performance indicator 35 | Application of the auditing methodology for performing financial audit, regularity audit and success audit in accordance with ISSAI standards | SV (2014): 2015 – Instructions on the methodology of performing financial audits and regularity audits in compliance with ISSAI 200 and ISSAI 400, Instructions on methodology for performing the success audit in line with ISSAI 300 and the Guidelines for quality control audit | N/A | N/A | TV (2018): Guidelines for the of Annual financial statements Audit of political subjects; Guidelines for auditing the final account of the state budget. |  | Actual value in 2018: Guidelines for the annual financial statements audit of political subjects were adopted in January 2018. The guidelines for auditing the final account of the state budget were adopted in September 2018. |  | TV (2019): n/a The activities listed in the action plan start from Q1. 2019 |  | Actual value in2019.: Instruction on the methodology of performing the performance audit in accordance with the IV level of the ISSAI standard was adopted in December 2019. Guidelines for auditing the final account of the state budget were adopted in September 2018. | TV (2020): Adopted Manual for performing financial audit and regularity audit in accordance with ISSAI level IV and Improved Instruction on the methodology of performing performance audits in accordance with ISSAI Level IV AdoptedGuidelines for monitoring the implementation of recommendations given in audit reports. |  |  |  |
|  | Performance indicator 36 | Number of organized trainings / seminars / workshops for auditors | SV (2014): Minimum of 3 training sessions organized (2017): 9 additional trainings were organized | N/A | N/A | TV (2018): 6 additional trainings were organized |  | Actual value in 2018: 13 trainings (3 locally organized and 10 organized at regional and international levels) |  | TV (2019): 7 additional trainings were organized |  | Actual value in2019. i13 trainings (3 at the domestic level and 10 at the regional and international level) | TV (2020): 10 additionaltrainings were organized |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation |  | Priority |  | Planned starting date |  | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 |
|  |  | E.1.1 Analyze the Instruction on the methodology of performing financial audit and regularity audit and develop the Manual for financial audit and regularity audit in accordance with ISSAI standards | Manual | Draft Manual on Financial Audit and Regularity Audit in Accordance with ISSAI Standards prepared. | IPA II | SAI |  | 1 (E.1.5) |  | Q 1 2019 |  | Q II 2020 | Q II 2020 | 32,000.00 | 30,700.00 | The realization of activities is in progress. The activity is implemented within the Project "Development and Capacity Building of the State Audit Institution and the Audit Authority of Montenegro". The drafting of the Manual for Financial Audit and Regularity Audit is planned for I Q 2020. |
|  |  | E.1.2 Analyze the Instruction on the methodology of performing the performance audit and make recommendations for improving the methodology of the performance audit | Instructions | Recommendations for improving the methodology for the audit of success prepared. | IPA II | SAI |  | 1 (E.1.5) |  | Q I 2019 |  | Q II 2020 | Q II .2020 | 12,000.00 | 12,000,00 | The activity was implemented within the Project "Development and Capacity Building of the State Audit Institution and the Audit Body of Montenegro". A new Instruction on the methodology of performing the performance audit in accordance with the IV level of the ISSAI standard was adopted in December 2019. |
|  |  | E.1.3 Analyze the existing practice in monitoring the implementation of audit recommendations in the SAI in relation to EU best practice and develop guidelines for monitoring the implementation of recommendations from audit reports | Guidelines | Draft Guidelines for monitoring the implementation of audit recommendations prepared. | IPA II | SAI |  | 1 |  | Q I. 2019 |  | Q II 2020 | Q II 2020 | 24,000.00 | 0,00 | The activity is planned to be realized in accordance with the time dynamics determined by the project "Development and capacity building of the State Audit Institution and the Audit Authority of Montenegro". The first mission is planned to take place in early March 2020. |
|  |  | E.1.4 Develop a Human Resources Management Strategy and a Communication Strategy | Strategic / Plan document | Draft Human Resources Management Strategy prepared. Draft Communication Strategy prepared. | IPA II | SAI |  | 2 |  | Q I 2019 |  | Q II.2020 | Q II2020 | 40,000.00 | 24,227.85 | The realization of activities is in progress. The activity is implemented within the Project "Development and Capacity Building of the State Audit Institution and the Audit Authority of Montenegro". The adoption of the draft Communication Strategy in Q 1 of 2020 is planned. |
|  |  | E.1.5 Improving manual for the exam for state auditor; implementation of trainings (conducting 1 pilot audit and trainings related to the application of the Manual for financial audit and regularity audit) and improvement of audit capacity to apply IT tools | Manual / Instructions / Training / Computerization | SAI auditor training manuals prepared. A number of auditors trained. Improved IT tool implemented. | IPA II | SAI |  | 2 (E.1.1) (E.1.2) |  | Q I 2019 |  | Q II 2020 | Q II .2020 | 87,000.00 | 53,429.77 | The realization of activities is in progress. The activity is implemented within the Project "Development and Capacity Building of the State Audit Institution and the Audit Authority of Montenegro". Training related to the application of the IV level of the ISSAI standard is planned to be held in Q I 2020, while other trainings will be realized in accordance with the time dynamics defined by the project. |
| of |  | E.1.6 Develop the guidelines for revising the final account of the state budget and organize a workshop (training) for audit staff on the implementation of the audit guidelines for the final account of the state budget | Manual/Training | Draft of the Guidelines for the Audit of the final account of the budget is prepared. Certain number of employees trained. | SIGMA | SAI |  | 1 |  | Q I 2018 |  | Q II 2018 | Q II 2020 | 0,000 | 0,000 | - Training for audit staff on the implementation of the Guidelines for the audit of the final account of the state budget is planned to be organized in accordance with the time schedule planned by the Training Program for the period 2019-2020. Creation of the Training Program for the period 2019-2020. |

| *2) |  | E.1.8 Provide the necessary facilities for the work of the SAI in order to increase the audit capacities | Facilities | Facilities provided. |  | SAI | 1 | 2018 | 2019 | 2020 | 2.500.000,00 | 0,000 | - Activity is in progress. The capital budget of the for 2019 planned funds for resolving the lack of business facilities for the needs of the State Audit Institution and the Statistical Office within the multi-annual capital sub-project "Facilities for the needs of the State Audit Institution and the Statistical Office". In the previous period, the State Audit Institution has repeatedly tried to solve the issue of business facilities through an open public procurement procedure, in accordance with the Law on public procurement, but this was not implemented. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 2.695.000,00 | 0,000 |  |
| Strategic goal 4.5._E) Development and strengthening of external audit |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operative GOAL 4.5.2._AUDITING AUTHORITY |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 37 | Number of organized trainings / seminars / workshops for auditors | SV (2014): 3 trainings organized per auditor | N/A | N/A | TV (2018): A minimum of 5 auditor trainings have been organized per auditor | Actual value in 2018: 3 trainings have been organized on average per auditor | TV (2019): A minimum of 9 auditor trainings have been organized per auditor | Actual value in2019. godini: 11 trainings organizer per auditor | TV (2020): A minimum of 7 auditor trainings have been organized per auditor |  |  |  |
|  |  | Degree of implementation of the Strategic and Action Plan of the institution | SV (2014): n/a | N/A | N/A | TV (2018): The activities listed in the action plan will start in 2019 | Actual value in2018. godini: The activities listed in the action plan will start in 2019 | TV (2019) : Strategic plan adopted / Action plan adopted | Actual value in2019.: Activities have been postponed to 2020. | TV (2020): 20% of planned activities realized |  |  |  |
|  |  | Degree of improvement of the methodology for conducting the audit - audit manual | SV (2014): An audit manual has been prepared | N/A | N/A | TV (2018): The activities listed in the action plan will start in 2019 | Actual value in2018: The activities listed in the AP start in 2019 | TV (2019): 50% of deficiencies eliminated | Actual value in2019.: 90% of deficiencies eliminated | TV (2020): 100% defects eliminated |  |  |  |
|  |  | Percentage of audits performed using audit software | SV (2014): n/a | N/A | N/A | TV (2018): The activities listed in the action plan will start in 2019 | Actual value in2018.: The activities listed in the AP start in 2019 | TV (2019): 20% of audits conducted using software | Actual value in2019.: 33,33% | TV (2020): 50% of audits conducted using software |  |  |  |
|  |  | The degree of application of standards in order to ensure the quality of audit work | SV (2014): n/a | N/A | N/A | TV (2018): The activities listed in the action plan will start in 2019 | Actual value in2018.: The activities listed in the AP start in 2019 | TV (2019): 30% | Actual value in2019.: n/a Data for 2019 could not be available this year due to the dynamics of the implementation of audit activities that are conditioned by the prescribed deadlines. | TV (2020): 50% |  |  |  |
| MANAGEMENT OF PUBLIC FINANCES |  |  | Type of activity | Performance indicator/goal | Technical assistance required (IPA, IMF, UNDP…) | Agency/Directorate for implementation | Priority | Planned starting date | Planned ending date | New implementation deadline | Planned funds | Spent funds | RECOMMENDATIONS |
|  | SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
|  |  | E.2.1 Assessment of need for training, development and implementation of training programs for auditors | Strategic / Plan document Training | Number of organized trainings / seminars / workshops per auditor | IPA II | RT | 1 | 2019 | 2020 |  | 274,000.00 | 259,561.00 | The realization of activities is going according to plan, which is also expected in the continuation of the project implementation. |
|  |  | E.2.2 Improving the audit manual for different types of audits in line with international auditing standards | Guidelines / Manual | Degree of improvement of the methodology for conducting the audit - audit manual | IPA II | RT | 1 | 2019 | 2020 |  | 80,000.00 | 80,000.00 | Completely realized. |
|  |  | E.2.3 Improving skills for applying certain audit techniques (IT) | Computerization Training | Percentage of audits performed using audit software | IPA II | RT | 2 | 2019 | 2020 |  | 20,000.00 | 11,000.00 | The realization of activities is going according to plan, which is expected in the continuation of the project implementation. |
|  |  | E.2.4 Development of the strategic plan of the Audit Authority and the Action Plan for its implementation | Strategic/ Plan document | Degree of implementation of the Strategic and Action Plan of the institution | IPA II | RT | 2 | 2019 | 2020 |  | 70,000.00 | / | Realization of activities is expected in the II and III quarter of 2020. |
|  |  | E.2.5 Development of guidelines for quality assurance of audit work | Guidelines/ Manual | The degree of application of standards in order to ensure the quality of audit work | IPA II | RT | 2 | 2019 | 2020 |  | 31,000.00 | 22,000.00 | The activity has been realized and will be continued in the following period. |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 475,000.00 | 372,561.00 |  |

# ANNEX 1- Performance Indicator Passports for the program of the public finance management reform for the period 2016-2020

Chapter 6 of the Program for public finance management reform for the period 2016-2020 elaborates the system for monitoring and evaluation during the application of the Program whose goal is to evaluate the specific progress achieved by the realization of activities of the Action Plan for the implementation of the Program for the period 2016-2018 (hereinafter: AP)

The goal is the collection and unification of information on all defined Performance Indicators, including some of their key institutional and methodologic aspects, such as which institution is collecting data, how often, what is the equation for calculating the Indicator, what is the verification source, what are the starting measurements for the given Indicator and what are the target values projected for measuring the success of achievement of reform activities. Measuring and monitoring of Indicators should begin with the second planned report on realization of the Program for the period 2016-2020.

1 Sustainable fiscal framework, planning and budgeting of public expenditure

1.1 Mid-term budget framework, including the fiscal strategy

- 1.1.1. PASSPORT FOR THE PERFORMANCE INDICATOR 1.

| NAME OF THE PERFORMANCE INDICATOR | Share of new medium-term sectoral strategies in the total number of strategies that include cost assessment for their implementation, including potential donors |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Sustainable fiscal framework, planning and budgeting of public expenditure - Medium-term budget framework, including the fiscal strategy The Medium-Term Budget Framework reflects the policies and strategic objectives of the Government and contains fixed spending limits for all consumer units of the first level |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | In accordance with the PFM strategy, an activity is planned that relates to the development of a methodology for the development of strategic documents. According to the plan, it is planned that one of the minimum requirements includes the assessment of the fiscal impact, which indicates that after the adoption of adequate regulations all strategies will include an assessment of the fiscal impact. The data source for 2018 is the strategy adopted by the Government of Montenegro during 2018, and submitted to the Ministry of Finance for further opinion. |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance, State Budget Directorate Tanja Musterović tanja.musterovic@mif.gov.me Phone: 063262769 |  |  |  |
| FREQUENCY OF DATA COLLECTION | 1 x per year, during the first quarter. |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | Consideration is given to the strategies which are implemented for a period of 2 or more years, and the data will be calculated based on information from the budget sector on the assessment of the impact of the fiscal strategies which were submitted for further opinion, i.e. the Report on the analysis of the impact of regulations, until the possibility of automatic calculation of data. The data on adopted strategies are taken over from the General Secretariat of the Government. During 2019, 13 strategies were adopted based on the data of the General Secretariat of the Government. The effect is measured based on the data on the adopted strategies in the subject year, i.e. the subject of consideration will not be the strategies adopted in the previous period. The target value in 2020, and in the years after that, which is projected at the value of 100%, implies that any strategy adopted in 2020, and later, will include an assessment of the fiscal impact, while the strategies adopted in the previous the period shall be considered if there is would be a need for amendments and revisions of the Strategy. |  |  |  |
|  | FORMULA/EQUATION Number of adopted medium-term strategies which contain data on the total assessment of costs for their implementation in the fiscal year X100/ Total number of adopted medium-term strategies in the fiscal year |  |  |  |
| STARTING VALUE DATA | SV (2014): 60% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 80% | 85% | 90% | 100% |
| ACHIEVEMENT VALUE DATA | 70% | 75% | 85% |  |

# 1.1.2 PASSPORT FOR THE PERFORMANCE INDICATOR 2.

| NAME OF THE PERFORMANCE INDICATOR | The average deviation between the budget expenditure ceilings determined by the medium-term budgetary framework and the actual budget expenditures planned by the annual budget law |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Sustainable fiscal framework, planning and budgeting of public expenditure - Medium-term budget framework, including the fiscal strategy The Medium-Term Budget Framework reflects the policies and strategic objectives of the Government and contains fixed spending limits for all consumer units of the first level |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Official gazette, Law on the budget,(http://www.mf.gov.me/biblioteka/zakoni ), Guidelines of the macroeconomic and the fiscal policies for the three year period |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance, State Budget Directorate Tanja Musterović tanja.musterovic@mif.gov.me Phone: 063262769 |  |  |  |
| FREQUENCY OF DATA COLLECTION | 1x per year, the first quarter of the current year for the previous year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The guidelines for the macroeconomic and fiscal policies are used to define spending limits, which serve as the basis for the preparation of the Law on the Budget for the fiscal year. The fiscal policy guidelines were adopted annually for a period of three years. Restrictions are obligatory for the Law on the Budget for the first year and indicative for the second and third fiscal years. The guidelines are used as an indication of the budget framework and the limits of spending of the central state budget for the current budget, the state funds budget, capital budget, budget reserves, and budget spending limits for consumer units of the first level, with the exception of the costs for repayment of debt and interests, costs of co-financing and costs for financing material damages caused by natural disasters and other emergencies and unpredicted cases. The spending limit for the respective year is compared with the amounts planned in the Law on the Budget for the respective year, e.g. if we look for deviations in 2019, the data from the Law on the Budget for 2019 are compared with the data on the limits from the Guidelines for the period 2018-2021. |  |  |  |
|  | FORMULA/EQUATION (Amount as per Law on the Budget – amount of the spending limit/Amount as per Law on the Budget x100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 9% |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 7% | 6% | 5% | 5% |
| ACHIEVEMENT VALUE DATA | 6% | 0,87% | 0,11% |  |

# 1.1.3 PASSPORT FOR THE PERFORMANCE INDICATOR 3.

| NAME OF THE PERFORMANCE INDICATOR | The number of employees trained for medium-term planning based on the principle of "top to bottom" |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Sustainable fiscal framework, planning and budgeting of public expenditure - Medium-term budget framework, including the fiscal strategy The Medium-Term Budget Framework reflects the policies and strategic objectives of the Government and contains fixed spending limits for all consumer units of the first level |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | The Ministry of Finance, the State Budget Directorate and Consumer Units, the beneficiaries who attended trainings, based on the data maintained by the Ministry of Finance, the State Budget Directorate. The source of data is the Ministry of Finance |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance, State Budget Directorate Tanja Musterović tanja.musterovic@mif.gov.me Phone: 063262769 |  |  |  |
| FREQUENCY OF DATA COLLECTION | 1x per year, in the first quarter for the trainings conducted in the previous year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The Program for the public finance management reform and Action Plan predict the training for multi-annual budget planning with the goal of better linking of program objectives with Government policies. Training is planned for the managerial level and expert staff level by institutions identified as priorities, by 2020, when all institutions will be covered. (The President, The Parliament, Judiciary authorities, Ministries and independent bodies). The training will also be organized for the representatives of the State Audit Institution and the Committee of the Parliament for Economy and Finance. The performance indicator is measured based on the training completed in one calendar year, i.e. the number of participants who attended the training. The trainings started with the trainings of the employees in the Directorate for the State Budget in 2019, with the continuation planned for 2020. |  |  |  |
|  | FORMULA/EQUATION Number of persons who completed the training in accordance with the pre-defined program |  |  |  |
| STARTING VALUE DATA | SV (2014): 0 |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 52 | 35 | 52 | 72 |
| ACHIEVEMENT VALUE DATA | 0 | 0 | 17 |  |

# 1.2 Preparation of the annual budget

# 1.2.1 PASSPORT FOR THE PERFORMANCE INDICATOR 4.

| NAME OF THE PERFORMANCE INDICATOR | Share of first-level consumer units that provide comprehensive information in their budget requirements |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Sustainable fiscal framework, planning and budgeting of public expenditure - Preparation of the annual budget |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Requests for budget funds submitted to the Budget Directorate during the budget planning process |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance, State Budget Directorate Tanja Musterović tanja.musterovic@mif.gov.me Phone: 063262769 |  |  |  |
| FREQUENCY OF DATA COLLECTION | 1 x per year, after the requests for budget funds have been submitted by consumer units, that is, in the third quarter |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The precondition for creating an effective system of performance measurement of budget programs is the comprehensiveness of the information provided for budget planning for all programs in particular. In accordance with the Guidelines for the macroeconomic and fiscal policies, the Ministry of Finance sends a professional instruction on budget preparation, with detailed instructions on financial and non-financial data. The budget preparation tables include a filling instruction, a table for general information on the consumer unit, an administrative and legislative framework, tables for problems in financing, table of summary, information on expenditure for ongoing activities, information on expenditure for new activities, information on expenditure for salaries, explanation of current activities, explanation of new activities and data on overview of multi-annual obligations. Consumer units of the first level are the President of Montenegro, the Parliament, the Judiciary authorities, the Government - the General Secretariat of the Government and Ministries, independent consumer units and state funds. The performance indicator is measured in relation to the comprehensiveness of the information on the specified parts of the bulletin. Budget users often submit of the explanation for required funds in a “word” format, which is certainly an integral part of the request for budget funds and which is taken into account while planning the budget. Within the process of preparation and planning of the Law on the Budget, the Ministry of Finance also organizes meetings and conducts consultations with consumer units, or the so-called budget negotiations, which is a generally accepted international practice, and which organized in order to provide additional information in order to conceive a more realistic financial plan for the next year, in accordance with the fiscal capacities. In this way, the Ministry of Finance receives additional information from the consumer units, which it uses when considering the applications. In the following period, a more comprehensive filling of the budget bulletin is expected in accordance with the improvement of the same and the conduction of trainings with the goal of overall improvement of the budgeting process. |  |  |  |
|  | FORMULA/EQUATION Number of consumer units which provide comprehensive information / Total number of consumer units X 100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 40% |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 75% | 80% | 90% | 100% |
| ACHIEVEMENT VALUE DATA | 70% | 80% | 90% |  |

# 1.2.2 PASSPORT FOR THE PERFORMANCE INDICATOR 5.

| NAME OF THE PERFORMANCE INDICATOR | Level of performance information included in budget planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Sustainable fiscal framework, planning and budgeting of public expenditure - Preparation of the annual budget Creation of an effective system for measuring the performance of budget programs in order to increase the efficiency and transparency of public spending |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Law and explanation of the Law on the Budget for the fiscal year |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance, State Budget Directorate Tanja Musterović tanja.musterovic@mif.gov.me Phone: 063262769 |  |  |  |
| FREQUENCY OF DATA COLLECTION | 1x per year, the first quarter of the current year for the previous year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The Program for the Public Finance Management Reform predicts defining of missions, objectives and descriptions of programs and sub-programs, while by 2020 it is predicts defining of the Performance Indicator for programs and sub-programs. The legal basis is defined by the Law on the Budget and the fiscal responsibility, while the content and mode of preparation are defined by the Regulation. Increasing the level of information in the Program budget is given through the target values. Level 1 (2017) includes a developed program structure for all budget users including the missions of consumer units, defined program descriptions and objectives; Level 2 (2019) includes an upgrade of the Level 1 with the definition of a set of Performance Indicators for pilot projects, while Level 3 (2020) includes a set of Performance Indicators for all programs in order to monitor the achievement of objectives. |  |  |  |
|  | FORMULA/EQUATION n/a |  |  |  |
| STARTING VALUE DATA | SV (2014): Defined names of program for all consumer units |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | Level 1 | Level 1 | Level 2 | Level 3 |
| ACHIEVEMENT VALUE DATA | Developed program structure in the part of defining the name of the program for all consumer units | Developed program structure in the part of defining the name of the program for all consumer units | Defined program names of all consumer units |  |

# 1.2.3 PASSPORT FOR THE PERFORMANCE INDICATOR 6.

| NAME OF THE PERFORMANCE INDICATOR | Number of employees trained to plan and monitor expenditures in accordance with the principles of program budgeting |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Sustainable fiscal framework, planning and budgeting of public expenditure - Preparation of the annual budget Create an effective system for measuring the performance of budget programs in order to increase the efficiency and transparency of public spending |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Ministry of Finance, State Budget Directorate. |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance, State Budget Directorate. Tanja Musterović tanja.musterovic@mif.gov.me Phone: 063262769 |  |  |  |
| FREQUENCY OF DATA COLLECTION | 1x per year, the first quarter of the current year for the previous year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | In accordance with the Program of the public finance management reform and the Action Plan for the funds of IPA II, the organization of training is planned for employees of the Ministry of Finance and budget organizations which are involved in the implementation of the program budget. Training is planned for the managerial level and the expert staff level at institutions identified as priorities, by the year 2020, when all institutions will be covered. The training will also be organized for the representatives of the State Audit Institution and the Committee of the Parliament for Economy and Finance. The performance indicator is measured based on the training completed in one calendar year, that is, the number of participants who attended the training. During 2019, training was held for employees in the State Budget Directorate, while in 2020, training is planned for employees in budget spending units and other planned institutions. |  |  |  |
|  | FORMULA/EQUATION The total number of officers who attended training that started and ended during a calendar year |  |  |  |
| STARTING VALUE DATA | SV (2014): 0 |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 20 | 35 | 70 | 130 |
| ACHIEVEMENT VALUE DATA | 0 | 0 | 17 |  |

# 1.3Capital budget

# 1.3.1 PASSPORT FOR THE PERFORMANCE INDICATOR 7.

| NAME OF THE PERFORMANCE INDICATOR | The level of detail in the public presentation of the capital budget |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Sustainable fiscal framework, planning and budgeting of public expenditure - Capital budget Improve planning of the capital budget and reporting on the implementation of capital projects |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | The source of data is the annual Law on the Budget and the Official Gazette for the moment. Presentation of the capital budget that will be in accordance with the project for improvement of planning and reporting on realization of the capital budget on the website of the Ministry of Finance, i.e. the data will be presented on the Ministry of Finance webpage in the form of excel tables and corresponding diagrams. The above register will represent more detailed and elaborated data on the capital budget from the annual Law on the budget, so the source can also be the Law on the budget for the fiscal year. Webpage of the Ministry of Finance www.mf.gov.me |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance, State Budget Directorate Slobodanka Burić slobodanka.buric @mif.gov.me Phone: 063202933 |  |  |  |
| FREQUENCY OF DATA COLLECTION | 1x per year, in the first quarter |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The capital budget is an integral part of the annual Law on the Budget and contains an overview of capital projects that will be implemented in the next fiscal year. In order to implement a comprehensive reform of the budgeting process, it is also necessary to improve the process of planning capital projects by improving the presentation and coverage of information on planned projects in the budget as well as a report on their implementation. In accordance with the Program for public finance management reform from the funds of IPA II, establishment of a public register of all projects financed from the capital budget is planned. Namely, in the first phase, the overview is planned for all individual projects, while in the following period; the projects will be separated by stages of implementation (preparation phase and construction phase). At this point, through the explanation of the Law on the Budget, a detailed overview of all individual projects is given, while the improvement of the presentation of capital projects in the following period, in parallel, through the improvement of the presentation in the Law on the budget, will be shown in a public presentation that will be available on the website of the Ministry of Finance. Increasing the level of information in the public presentation of the capital budget is given through the target values. Level 1 (2017 and 2018) includes: Display by all individual projects that are implemented in the budget year. Level 2 (2019) includes: Display by all individual projects that are implemented in the budget year and realization of selected pilot projects in phases. Level 3 (2020) includes: Display by individual projects and project implementation phases |  |  |  |
|  | FORMULA/EQUATION n/a |  |  |  |
| STARTING VALUE DATA | SV (2014): Projects in the capital budget shown presented as grouped by fields (education, health, culture, sport ...) |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | Level 1 | Level 1 | Level 2 | Level 3 |
| ACHIEVEMENT VALUE DATA | Projects in the Law on the Budget are presented as grouped by areas, while in the Description of the Law they are shown by individual projects | Projects in the Law on the Budget are presented as grouped by areas, while in the Description of the Law they are shown by individual projects | Projects in the Law on Budget are presented as grouped by areas, while in the Description of the Law they are presented by individual projects |  |

# 1.3.2 PASSPORT FOR THE PERFORMANCE INDICATOR 8.

| NAME OF THE PERFORMANCE INDICATOR | The ratio of actual capital spending in the current year in comparison to the capital budget plan |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Sustainable fiscal framework, planning and budgeting of public expenditure - Capital budget Improve planning of the capital budget and reporting on the implementation of capital projects |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Official Gazette, Law on the final account of the budget, Law on the Budget for the fiscal year http://www.mf.gov.me/biblioteka/zakoni) |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance, State Budget Directorate Slobodanka Burić slobodanka.buric @mif.gov.me Phone: 063202933 |  |  |  |
| FREQUENCY OF DATA COLLECTION | 1x per year, in the second quarter of the current year for the previous year, after the adoption of the Law on the final account of the budget. In the first quarter we can have the preliminary data, i.e. the data which is not official. |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The Capital Budget is an integral part of the annual Law on the Budget, whose implementation is in charge of the Transport Administration and the Public Works Administration in co-operation with the Ministry of Finance. The data on actual costs of the capital budget are contained in the Law on the final account of the budget for the respective year. The Performance Indicator is measured as a part of the actual spending of the capital budget in accordance with the Law on the final account of the budget for the fiscal year in the amount of the capital budget planned by the Law on the budget for the fiscal year. |  |  |  |
|  | FORMULA/EQUATION Amount of actual spending in the capital budget Amount of the capital budget planned by the Law on the budgetx100=% |  |  |  |
| STARTING VALUE DATA | SV (2014): 70% |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 80% | 83 | 86% | 90% |
| ACHIEVEMENT VALUE DATA | 82 | 91% 111% | 92% 112,3% |  |

# 1.4 Improvement of the model for macroeconomic projections

# 1.4.1 PASSPORT FOR THE PERFORMANCE INDICATOR 9.

| NAME OF THE PERFORMANCE INDICATOR | Implementation phases of the improved model for projections of macroeconomic Indicators and the impact of structural reforms |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Sustainable fiscal framework, planning and budgeting of public expenditure - Improvement of the model for macroeconomic projections By improving projections of the macroeconomic indicators, which are the basis for projections of public finances and the creation of the Law on the budget, as well as other important strategic documents |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Data for monitoring of Indicators is collected at the national level through the implementation of projections incorporated in documents of national importance: Program of Economic Reforms; Guidelines for the Macroeconomic and Fiscal Policies: Updated projections of macroeconomic and fiscal indicators |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance, Directorate for Economic Policy and Development Iva Vuković, Director General of the Directorate for Economic Policy and Development iva.vukovic@mif.gov.me Phone:069820921 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Each of these documents is published annually, referring to the medium-term period. |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The new macroeconomic model has been developed on an econometric approach and the economy is observed through four sectors: actual, external, monetary and fiscal sectors. The model will include mechanisms which will enable the inclusion of long-term structural policies effects on the aggregate supply, as well as the short-term impact on demand. The developed Montenegrin macroeconomic model will consist of: 1) forecasting module, which will be used to generate predicted values of macroeconomic indicators for the purpose of developing the baseline scenario; 2) an impact assessment module to be used for policy simulations based on different policy scenarios (the “what if” analysis) |  |  |  |
|  | FORMULA/EQUATION n/a |  |  |  |
| STARTING VALUE DATA | SV (2014): The existing model used in the Directorate for Economic and Development Policy is based on the financial programming model, and the projection of the determined parameters is based on an expert assessment |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | Analysis and upgrading of the existing macroeconomic model for projections | A new model for projections of macroeconomic Indicators and the impact of structural reforms has been created and employees are trained | Assumptions fulfilled for the usage of the new model by employees of the Directorate for Economic Policy and Development | Full implementation and full ability of employees to use the model |
| ACHIEVEMENT VALUE DATA | Target value for 2017 was achieved | Target value for 2018 was achieved | Preconditions for the use of the new model by employees in the Directorate for Economic Policy and Development have been met |  |

# 1.4.2 PASSPORT FOR THE PERFORMANCE INDICATOR 10.

| NAME OF THE PERFORMANCE INDICATOR | The difference between the projected and the realized rate of real GDP growth |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Sustainable fiscal framework, planning and budgeting of public expenditure - Improvement of the model for macroeconomic projections Improvement of projections of macroeconomic Indicators, which are the basis for projections of public finances and the creation of the Law on the Budget, as well as other important strategic documents. At the same time, chapter III of the EU Directive 2011/85 concerning forecasts will also be fulfilled. The new model will enable the minimization of the differences between the plan and the realization, and in such a way it will contribute to the formation of assumptions for more realistic planning of the revenues side of the budget, which depends to a large extent on the growth of economic activity |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Data for monitoring of Indicators is collected at the national level. Estimate for the current year is published in the document: Projection of macroeconomic and fiscal indicators. Achievement is published by the Statistical Office on the website: http://monstat.org/cg/page.php?id=166&pageid=19 |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance Iva Vuković, Director General of the Directorate for Economic Policy and Development iva.vukovic@mif.gov.me Phone: 069820921 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Once a year The updated estimate is announced in October The achievement is announced in September of the current year for the previous year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The GDP estimate is based on a new econometric model that is based on the principles of the National Accounts System (SNA 2008) and the European System of National Accounts (ESA2010). The realization is also based on the mentioned methodologies. ESA 2010 defines the concepts, definitions and accounting rules that apply to the calculation of national accounts data in order to achieve international comparability. ESA 2010 presents a set of interconnected and consistent tables, accounts, classifications and balances that represent a statistical and documentary basis for the monitoring of economic activities. Gross domestic product (GDP) measures the total value of goods and services provided by resident institutional units. |  |  |  |
|  | FORMULA/EQUATION X p.p. = achieved rate of actual growth – projected rate of actual growth |  |  |  |
| STARTING VALUE DATA | SV (2014): 1,8 p.p. |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | Less than 0,5 p.p. | Less than 0,3 p.p. | Less than 0,2 p.p. | Less than 0,2 p.p. |
| ACHIEVEMENT VALUE DATA | The target value for 2017 is not achieved | 0,8 p.p. | Target value for 2019 was partially met, further recommendations given |  |

# 2 Execution of the budget

# 2.1 Collection of revenues – Tax Administration

# 2.1.1 PASSPORT FOR THE PERFORMANCE INDICATOR 11.

| NAME OF THE PERFORMANCE INDICATOR | Growth in the share of submitted electronic tax returns (income tax, VAT) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Collection of revenues – Tax Administration Strengthening the administrative capacities of the Tax Administration in order to improve collection of taxes, thus contributing to the fiscal revenue of the budget |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Data for monitoring of Indicators is collected at the national level https://eprijava.tax.gov.me/TaxisPortal (only financial statements can be viewed, not the statistics on the growth or decline of submitted e-applications) - Annual Report on the work of the Tax Administration: www.poreskauprava.gov.me - Internal quarterly and semi-annual reports of the competent department for e-applications (not published on the website) |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Tax Administration, Sector for planning of reporting and development of projects Lidija Šećković lidija.seckovic@tax.gov.me Phone: 067272353 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Quarterly |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | For the calendar year 2017, the data is given for the fiscal year 2016 concerning the REVENUE, because the maturity date is March 31, 2017, and when VAT is concerned, the data for the accounting periods which mature in 2017 are given. The VAT report is submitted up to 15th in the month for previous month. |  |  |  |
|  | FORMULA/EQUATION The total number of submitted VAT returns electronically submitted for the accounting periods of the calendar year The total number of submitted VAT applications for the accounting periods of the calendar year x100 The total number of submitted electronic applications for Income tax submitted for the accounting periods of the calendar year The total number of submitted applications for income tax applications for the accounting periods of the calendar year |  |  |  |
| STARTING VALUE DATA | SV (2014): 27% this is not a total figure as the paper mode of submission is used |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | VAT 50% INCOME 95% | VAT 65% INCOME 97% | VAT 75% INCOME 97% | VAT 80% INCOME 99% |
| ACHIEVEMENT VALUE DATA | VAT 50% INCOME 95% | VAT 70% INCOME 99% | VAT 77,37 % INCOME 99,5% |  |

# 2.1.2 PASSPORT FOR THE PERFORMANCE INDICATOR 12.

| NAME OF THE PERFORMANCE INDICATOR | Successfully implemented EU legislation regarding the common EU market |  |  |  |
| --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Collection of revenues – Tax Administration Strengthening the administrative capacity of the Tax Administration in order to improve collection of taxes, thus contributing to the fiscal revenue of the budget |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | At the national and international level -Official Gazette of Montenegro - Official Gazette of Montenegro - Progress Report (quarterly): www.poreskauprava.gov.me - EC report - Preparation of reports on the assessment of benchmarks - DG TAXUD report -Reports from Government sessions published by the Government of Montenegro on the adopted proposals: www.gov.me |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Tax Administration, Sector for planning of reporting and development of projects Lidija Šećković lidija.seckovic@tax.gov.me Phone: 067272353 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Quarterly upon request of the European Delegation to Montenegro |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | Document on the program of accession of Montenegro to the EU showing the status of compliance 1. Status a) Strategic framework, b) legislative framework c) administrative co-operation and mutual assistance. 2. Plans and requirements for all three areas mentioned above 3. Administrative framework - new institutions. Through reporting, the level of implementation of the plans and the requirements given in the document is monitored (the document can be found on the website of the Ministry of Foreign Affairs). www.mvp.gov.me The document on the program of accession of Montenegro to the EU provides deadlines for the adoption of the Acquis. This document contains everything, on the basis of which the degree of compliance of tax regulations can be measured by years, related to three basic laws: the Law on VAT, the Law on Income Tax and the Law on Tax Administration. - The stage of legislative compliance with the acquis based on the assessment at the beginning of the implementation of the IPA 2014 draft version of the prepared laws and bylaws for adoption for the purpose of further harmonization Basic directives for direct and indirect taxation: -Directive 2011/16 / EU related to mandatory automatic exchange of information in the field of taxation; VAT Directive; Directive 2006/112 / EC common VAT system with amendments; Council Directive 2008/9 / EC with amendments related to VAT refund. Directives relating to the profit tax; Directive 2003/49 / EU on a common system of taxation applicable in different Member States; Directive 2011/96 / EU on the common system of taxation applicable to the Council Directive of the European Union; Council Directive 2009/133 / EC. |  |  |  |
|  | FORMULA/EQUATION n/a |  |  |  |
| STARTING VALUE DATA | SV (2014): The screening process has been completed |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | Negotiations in chapter 16 - Taxation opened, activities conducted for the purpose of harmonization (assessment of the relevance of the acquis, responsible persons) | - Law on amendments and supplements to the Law on Income Tax of legal entities (IV quarter 2018) - Law on amendments and supplements to the Law on Tax Administration (IV quarter 2018) | - Law on amendments and supplements of the Law on VAT (IV quarter 2019) | Planned activities implemented from the Accession Program - Chapter 16. Taxes (Document on the program of accession of Montenegro to the EU) |
| ACHIEVEMENT VALUE DATA | -A certain level of legislative compliance has been achieved, a higher level of achievement has been achieved in the area of VAT; - there is harmonization to be done in the area of income tax (transfer prices) by the end of the IV quarter - Amendments to the Law on Tax Administration in the part of articles related to administrative cooperation and mutual assistance (until IV quarter). | Drafts were prepared to the Law on amendments and supplements to the Law on income tax of legal entities, and the Law on amendments and supplements to the Law on tax administration In order to further harmonize with EU legislation, especially in the area of administrative cooperation and information exchange. | Greater degree of compliance compared to the previous year All proposed amendments to the law passed the Legislative Committee. After which they were submitted to the EC for an opinion. | Greater degree of compliance compared to the previous year |

# 2.1.3 PASSPORT FOR THE PERFORMANCE INDICATOR 13.

| NAME OF THE PERFORMANCE INDICATOR | Share of collected tax revenues in relation to the planned tax revenues in the annual Law on the budget |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Collection of revenues – Tax Administration Strengthening the administrative capacity of the Tax Administration in order to improve collection of taxes, thus contributing to the fiscal revenue of the budget |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Data collection at the national level Annual Budget Plan of the Ministry of Finance on the basis of the Law on the Budget: www.mif.gov.me |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Tax Administration, Sector for planning of reporting and development of projects Lidija Šećković lidija.seckovic@tax.gov.me Phone: 067272353 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Quarterly, annually |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | FORMULA/EQUATION Collected tax revenues within a fiscal yearPlanned tax revenues in the Law on the annual budget x100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 100% (2015): 100% (2016): 100% |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 100% | 100% | 100% | 100% |
| ACHIEVEMENT VALUE DATA | More than 100% of the planned (24 million above plan for 2017) and 34 million above the achievement in 2016. | Above of the plan for 2018, 73 million were achieved or 117 million above the 2017 achievement. | Above the plan for 2019, 80 million were achieved above the plan |  |

# 2.1.4 PASSPORT FOR THE PERFORMANCE INDICATOR 14.

| NAME OF THE PERFORMANCE INDICATOR | Share of VAT revenues in GDP |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Collection of revenues – Tax Administration Strengthening the administrative capacity of the Tax Administration in order to improve collection of taxes, thus contributing to the fiscal revenue of the budget |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Data collection at the national level -Reports on the website of the Ministry of Finance: www.mif.gov.me Within the Directorate for Economic Policy and Development -Fiscal Strategy 2017-2020. where new projections are included with the included fiscal consolidation measures: www.mif.gov.me |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Tax Administration, Sector for planning of reporting and development of projects Lidija Šećković lidija.seckovic@tax.gov.me Phone: 067272353 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Quarterly |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | FORMULA/EQUATION Total VAT revenues in the fiscal year / GDP x 100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 13,5% |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 13,5% | 14,7% | 14;6% | 14,6% |
| ACHIEVEMENT VALUE DATA | 13,0% | 13,6% | 14,44% |  |

# 2.2 Collection of revenues – Customs Administration

# 2.2.1 PASSPORT FOR THE PERFORMANCE INDICATOR 15.

| NAME OF THE PERFORMANCE INDICATOR | The exchange rate in the realized collection of revenues in relation to the previous year |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Collection of taxes – Customs Administration Strengthening the capacities of the Customs Administration in order to ensure efficient collection of revenues, security of the customs area and protection of the society, as well as creating better conditions for the business environment |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Report on the work of the Customs Administration http://www.upravacarina.gov.me/uprava/Slobodan_pristup_informacijama |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Customs Administration Snežana Vučković, Department for customs legal affairs snezana.vuckovic@carina.gov.me Phone: 442 026 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Report on the work of the Customs Administration in the first quarter of the current year for the previous year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The Performance Indicator shows the rate of change in the collected collection of revenues from the Customs Administration in the reporting year in relation to the previous year. |  |  |  |
|  | FORMULA/EQUATION Achieved collection of revenue in the reporting year / Achieved collection of revenue in the previous year X 100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 15% |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 17,64 % | 5% | 5% | 5% |
| ACHIEVEMENT VALUE DATA | 17,64 % | 11,03% | 5,17% |  |

- 2.2.2 PASSPORT FOR THE PERFORMANCE INDICATOR 16.

| NAME OF THE PERFORMANCE INDICATOR | Harmonization of customs and excise legislation with EU legislation |  |  |  |
| --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Collection of taxes – Customs Administration Strengthening the capacities of the Customs Administration in order to ensure efficient collection of revenues, security of the customs area and protection of the society, as well as creating better conditions for the business environment |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Report on the work of the Customs Administration http://www.upravacarina.gov.me/uprava/Slobodan_pristup_informacijama |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Customs Administration Snežana Vučković, Department for customs legal affairs snezana.vuckovic@carina.gov.me Phone: 442 026 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Report on the work of the Customs Administration in the first quarter of the current year for the previous year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The impact indicator refers to the adoption of regulations related to the harmonization of customs and economic legislation with EU legislation. |  |  |  |
|  | FORMULA/ EQUATION Number of adopted harmonized regulations in the reporting year. |  |  |  |
| STARTING VALUE DATA | SV (2014): Screening process completed for chapters 29. ” Customs union and 16. “Taxation” |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | Law on amendments and supplements of the Law on Customs Law on amendments and supplements of the Law on Excises Regulations on the Customs tariffs for the year 2017 Regulations on amendments and supplements of the Regulation on implementing the Law on Customs | Adoption of 3 regulations | Adoption of 2 regulations | Adoption of 2 regulations |
| ACHIEVEMENT VALUE DATA | 4 Regulations Adopted | 3 Regulations Adopted | 3 Regulations Adopted |  |

# 2.3 Collection of revenues – Public procurements

# 2.3.1 PASSPORT FOR THE PERFORMANCE INDICATOR 17.

| NAME OF THE PERFORMANCE INDICATOR | Level of harmonization and completion of the legislative framework in the procedures public procurement with EU legislation |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Collection of revenues – Public procurements Harmonization of the public procurement system with EU legislation in the field of public procurement in order to establish an efficient, transparent and competitive public procurement system in Montenegro. |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Directives 23/2017,24/2017 and 25/2017 http://www.ujn.gov.me/category/direktive/ Law on Public Procurement ("Official Gazette of Montenegro", No. 042/11 dated 15.08.2011, 057/14 dated 26.12.2014, 028/15 dated 03.06.2015, 042/17 dated 30.06.2017) By-Laws http://www.ujn.gov.me/category/nova-podzakonska/ Strategy for the development of the public procurement system http://www.ujn.gov.me/strategija- razvvoja-sistema-javnih-nabavki-u-crnoj-gori-za-period-2016-2020-godine/ Reports on progress http://www.ujn.gov.me/category/eu-integracije/ |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Public Procurements Administration Dijana Ivanović, Department for monitoring of procedures of public procurement and management of electronic public procurements vukcevic.dijana@gmail.com Phone: 067373384 Sanja Poleksić, Department for professional specialization, training and international co-operation in the field of public procurement s.p@t-com.me Phone: 067400191 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Semi-annual through the report of the coordinating body for the realization of the AP strategy for the development of the public procurement system for the first and third quarters http://www.ujn.gov.me/category/koordinaciono-tijelo/ |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | September-October: Public Procurement Administration coordinates the analysis and, if necessary, revises the AP for the next year, in which all relevant parties are participating; December: If necessary, the Government of Montenegro adopts the revised AP for the next year. Using the AP as a mean of monitoring and implementation, the Coordinating Body will report to the Government on a semi-annual basis on the progress made in its implementation, in accordance with the following dynamics: January: Public Procurement Administration collects information on the implementation of the plan for the previous year from all relevant parties responsible for AP implementation; February: Public Procurement Administration is preparing a report on the implementation of the AP and submits it to the Government. The strategy for the development of the public procurement system in Montenegro for 2016-2020 was developed in a way to monitor all the activities necessary for the closing of Negotiation Chapter 5. Public Procurement, while the AP originates from this strategy. List of Directives: 1. Directive 2014/24 / EU of the European Parliament and of the Council of 26 February 2014 on public procurement and repealing of the Directive 2004/18 / EC (OJ L 94, 28.3.2014), as last amended by the Delegated regulation of the Commission) 2017/2365 of 18 December 2017 amending Directive 2014/24 / EU of the European Parliament and of the Council in regard to the application thresholds for procedures of awarding contracts (OJ L-337 of 19.12.2017); 2. Directive 2014/25/EU of the European Parliament and of the Council of 26 February 2014 on procurement by entities operating in the water, energy, transport and postal services sectors and repealing Directive 2004/17/EC (OJ L 94, 28 March 2014), as last amended by Commission Delegated Regulation (EU) 2017/2364 of 18 December 2017 amending Directive 2014/25/EU of the European Parliament and of the Council in respect of the application thresholds for the procedures for the award of contracts (OJ EU L-337 of 19 December 2017); 3. Council Directive 89/665/EEC of 21 December 1989 on the coordination of the laws, regulations and administrative provisions relating to the application of review procedures to the award of public supply and public works contracts (OJ L 395, 30 December 1989), as last amended by the Directive 2014/23/EU of the European Parliament and of the Council of 26 February 2014 on the award of concession contracts (OJ L 94, 28 March 2014); 4. Council Directive 92/13/EEC of 25 February 1992 coordinating the laws, regulations and administrative provisions relating to the application of Community rules on the procurement procedures of entities operating in the water, energy, transport and telecommunications sectors (OJ L 76, 23 March 1992), as last amended by the Directive 2014/23/EU of the European Parliament and of the Council of 26 February 2014 on the award of concession contracts (OJ L 94, 28 March 2014); 5. Articles 2, 12 and 13 of the Directive 2009/81/EC of the European Parliament and of the Council of 13 July 2009 on the coordination of procedures for the award of certain works contracts, supply contracts and service contracts by contracting authorities or entities in the fields of defense and security, and amending Directives 2004/17/EC and 2004/18/EC (OJ L 216, 20 August 2009), and the Commission Regulation (EU) 2017/2367 of 18 December 2017 amending Directive 2009/81/EC of the European Parliament and of the Council in respect of the application thresholds for the procedures for the award of contracts (OJ EU L-337 of 19 December 2017) |  |  |  |
| STARTING VALUE DATA | SV (2014): negotiations opened in negotiation chapter 5. Public procurement |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | Negotiations opened in negotiation chapter 5. | Further harmonization with the of the 2014 Directives package in this field | Further harmonization with the of the 2014 Directives package in this field (implementation of the new Law on Public Procurements, introduction of the electronic system of public procurements...) | Planned activities implemented from the Accession Program - Chapter 5. |
| ACHIEVEMENT VALUE DATA | Negotiations opened in negotiation chapter 5. | Negotiations opened in negotiation chapter 5. | Adoption of a new Law on Public Procurement by implementing the provisions in accordance with the new directives |  |

# 2.3.2 PASSPORT FOR THE PERFORMANCE INDICATOR 18.

| NAME OF THE PERFORMANCE INDICATOR | Average number of bidders participating in public tenders |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Collection of revenues – Public procurements Harmonization of the public procurement system with EU legislation in the field of public procurement in order to establish an efficient, transparent and competitive public procurement system in Montenegro. |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Annual Report on public procurement procedures conducted by the Public Procurement Administration: http://www.ujn.gov.me/category/izvjestaji/ |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Public Procurements Administration Dijana Ivanović, Department for monitoring of procedures of public procurement and management of electronic public procurements vukcevic.dijana@gmail.com Phone: 067373384 Sanja Poleksić, Department for professional specialization, training and international co-operation in the field of public procurement s.p@t-com.me Phone: 067400191 |  |  |  |
| FREQUENCY OF DATA COLLECTION | The Annual Report on public procurement procedures conducted by the Public Procurement Administration shall be submitted to the Government of Montenegro for approval by 31st May of the current year for the previous year. |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The Performance Indicator shows the number of bids received through the public procurement procedure, which means that the higher value of the Performance Indicator indicates greater competitiveness. |  |  |  |
|  | FORMULA/EQUATION Number of submitted bids within one calendar year / total number of procedures within that calendar year |  |  |  |
| STARTING VALUE DATA | SV (2014): 3,52 bids per tender http://www.ujn.gov.me/2015/06/godisnji-izvjestaj-o-javnim-nabavkama-u-crnoj-gori-za-2014-godinu/ |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 3,2 | 3,48 | 3,58 | 3,8 |
| ACHIEVEMENT VALUE DATA | 2,65 | 2,38 | n/a |  |

# 2.3.3 PASSPORT FOR THE PERFORMANCE INDICATOR 19.

| NAME OF THE PERFORMANCE INDICATOR | Share of the use of electronic public procurement in the total number of public procurement contracts during the year |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Collection of revenues – Public procurements Harmonization of the public procurement system with EU legislation in the field of public procurement in order to establish an efficient, transparent and competitive public procurement system in Montenegro. |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | The tender procedure for the selection of the most favorable bidder for the introduction of the electronic public procurement system in Montenegro is in progress. http://www.mif.gov.me/rubrike/CFCU_tenderi/Tenderi/Otvoreni/156772/Klarifikacije-za-ugovor-o-uslugama-Implementacija-Elektronskog-sistema-javnih-nabavki.html http://www.ujn.gov.me/category/izvjestaji/ |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Public Procurements Administration Dijana Ivanović, Department for monitoring of procedures of public procurement and management of electronic public procurements vukcevic.dijana@gmail.com Phone: 067373384 Sanja Poleksić, Department for professional specialization, training and international co-operation in the field of public procurement s.p@t-com.me Phone: 067400191 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Daily |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The e-system supports the complete public procurement procedure from the announcement of the electronic submission of bids till the awarding of the contract. Please note that the use of the electronic system will be mandatory for all obligators of the Law on Public Procurement. |  |  |  |
|  | FORMULA/EQUATION Number of contracts awarded by the e-system in one calendar year / total number of contracts awarded in one calendar year X 100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 0% (The electronic public procurement system does not exist) |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 0% (The electronic public procurement system does not exist) | Selection of the most favorable bidder | 30% | 80% |
| ACHIEVEMENT VALUE DATA | 0% (The electronic public procurement system does not exist) | Project of creating an e-system of public procurements has started | Piot phas of the e-system |  |

# 2.4 Reform of the State Aid

# 2.4.1 PASSPORT FOR THE PERFORMANCE INDICATOR 20.

| NAME OF THE PERFORMANCE INDICATOR | Number of providers and beneficiaries of state aid, representatives of the private sector and judges attending seminars and trainings in the field of state aid (all providers or potential beneficiaries of the aid, and other interested parties; number of beneficiaries is unspecified, from 30-100) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Reform of the State Aid Increasing the efficiency, effectiveness and transparency of the process of the system for control of state aid in Montenegro in order to comply with EU standards. |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Archive of the Agency for the Protection of the Competition, also the archive of the organizer of the project "Improvement and strengthening of the institutional and legal framework in the fields of state aid and public procurement", planned by the IPA 2014-2020 program. |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Agency for the Protection of the Competition Ivana Paprenica, drzavna.pomoc@azzk.me Phone: 063262830 |  |  |  |
| FREQUENCY OF DATA COLLECTION | After the seminars, an overview can be created at the end of each calendar year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The final number of seminar participants in one calendar year. The organizer of the project "Improvement and strengthening of the institutional and legal framework in the fields of state aid and public procurement", planned by the IPA 2014-2020 program, will organize seminars on the topics of state aid for different groups of providers and state aid beneficiaries aimed at raising the level of public awareness on state aid issues (refers to providers and state aid beneficiaries, representatives of the private sector and judges). The performance indicator is the total number of people who were present at the seminars they completed during a calendar year. |  |  |  |
|  | FORMULA/EQUATION n/a |  |  |  |
| STARTING VALUE DATA | SV (2014): 50 |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 50 | 30 | 60 | 100 |
| ACHIEVEMENT VALUE DATA | 0 | 0 | 56 |  |

# 2.4.2 PASSPORT FOR THE PERFORMANCE INDICATOR 21.

| NAME OF THE PERFORMANCE INDICATOR | Percentage of the employees of the departments and members of the commission for the control of the state aid which attend seminars with a goal of strengthening the legal framework, reducing of illegal state aid and conducting of ex-post controls |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Reform of the State Aid Increasing the efficiency, effectiveness and transparency of the process of the system for control of state aid in Montenegro in order to comply with EU standards. |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Archive of the Agency for the Protection of the Competition |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Agency for the Protection of the Competition Ivana Paprenica, drzavna.pomoc@azzk.me Phone: 063262830 |  |  |  |
| FREQUENCY OF DATA COLLECTION | An overview can be created at the end of each calendar year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The department for the state aid consists of 6 employees at the moment. The council of the Agency for the Protection of the Competition consists of 3 members. The subjects of seminars and trainings are solely the issues regarding state aid. |  |  |  |
|  | FORMULA/ EQUATION Number of people in the department for state aid + members of the council of the Agency for the Protection of the Competition which attended seminars (completed) within a calendar year / total number of people in the department for state aid + members of the council of the Agency for the Protection of the Competition within a calendar year X 100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 30% |  |  |  |
| Podaci o cilnim vrijednostima | 2017 | 2018 | 2019 | 2020 |
|  | 30% | 50% | 70% | 80% |
| ACHIEVEMENT VALUE DATA | 33% | 0% | 70% |  |

# 2.4.3 PASSPORT FOR THE PERFORMANCE INDICATOR 22.

| NAME OF THE PERFORMANCE INDICATOR | Number of completed ex-officio cases |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Reform of the State Aid Increasing the efficiency, effectiveness and transparency of the process of the system for control of state aid in Montenegro in order to comply with EU standards. |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Webpage of the Agency for the Protection of the Competition http://www.azzk.me/novi/joomlanovi/ |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Agency for the Protection of the Competition Ivana Paprenica, drzavna.pomoc@azzk.me Phone: 063262830 |  |  |  |
| FREQUENCY OF DATA COLLECTION | An overview can be created at the end of each calendar year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The level of awareness of relevant institutions of the need to report state aid is considered to be improving with the decreasing indicator (which means the institutions are better informed of the need to report state aid), i.e. the institutions approach the Agency / Commission before granting state aid (no need for ex officio cases). |  |  |  |
|  | FORMULA/EQUATION Number of completed ex officio cases within one calendar year |  |  |  |
| STARTING VALUE DATA | SV (2014): 5 |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 3 | Up to 2 | Up to 2 | Up to 1 |
| ACHIEVEMENT VALUE DATA | (0) No Ex-officio issues in 2017 | (0) No Ex-officio issues in 2018 | 0 (2 ex-officio cases have been opened, we expect them to be closed in the coming period) |  |

# 2.4.4 PASSPORT FOR THE PERFORMANCE INDICATOR 23.

| NAME OF THE PERFORMANCE INDICATOR | Number of legal acts, analyzed and assessed by the department (reporting state aid). |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Reform of the State Aid Increasing the efficiency, effectiveness and transparency of the process of the system for control of state aid in Montenegro in order to comply with EU standards. |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Webpage of the Agency for the Protection of the Competition http://www.azzk.me/novi/joomlanovi/ |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Agency for the Protection of the Competition Ivana Paprenica, drzavna.pomoc@azzk.me Phone: 063262830 |  |  |  |
| FREQUENCY OF DATA COLLECTION | After the case is completed, it is immediately published on the webpage of Agency for the Protection of the Competition |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The factual state of the number of analyzed state aid applications within one calendar year, a slight increase can be accompanied by an increase in the level of awareness of institutions on the obligation on reporting state aid. The Council of the Agency makes decisions in the forms of solutions and opinions. |  |  |  |
|  | FORMULA/EQUATION Number of legal acts analyzed and evaluated by the department within one calendar year |  |  |  |
| STARTING VALUE DATA | SV (2014): 11 |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 20 | Up to 20 | Up to 23 | Up to 25 |
| ACHIEVEMENT VALUE DATA | 14 | 22 | 35 |  |

# 2.5 Reform of the Department for managing the public debt, debt analysis, cash management and international co-operation

# 2.5.1 PASSPORT FOR THE PERFORMANCE INDICATOR 24.

| NAME OF THE PERFORMANCE INDICATOR | Costs of servicing the public debt as a share of the GDP |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Reform of the Department for managing the public debt, debt analysis, cash management and international co-operation Sound public debt monitoring and reporting, definition and establishment of clear procedures for debt management and debt analysis, cash management and transactions regarding debt repayment. |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | http://www.mf.gov.me/rubrike/drzavni-dug/ The data is posted on the webpages of the Ministry of Finance as a part of the Report on public debt. The Report features annual debt servicing costs, and the GDP used. |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance Katarina Živković, Head of the State Treasury Directorate Katarina.zivkovicc@mif.gov.me Phone: 020/202-167 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Once a year, in the second quarter of the previous calendar year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The Ministry of Finance has the authority to pay interest on the basis of state debt from funds held on the consolidated account within the treasury, in accordance with the Law on Budget and Fiscal Responsibility. The performance indicator serves to show the cost of debt in relation to the GDP. The total amount of interest in the fiscal year, from January 1st until December 31st, is calculated on the basis of the existing debt and estimates of future borrowing. Note: This Performance Indicator contains variables that are not in itself under the control of the Directorate for the state treasury. Movement of variable interest rates depends on movements of the market, while the movement of GDP is influenced by a number of factors over which the Directorate for the state treasury has no influence. |  |  |  |
|  | FORMULA/EQUATION Amount of paid interest / BDP X 100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 2.2 % |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 2.5 % | 1,9 % | 2,0 % | 2.3 % |
| ACHIEVEMENT VALUE DATA | 2,3% | 2,1% | 2,2 % |  |

# 2.5.2 PASSPORT FOR THE PERFORMANCE INDICATOR 25.

| NAME OF THE PERFORMANCE INDICATOR | Difference between the planned and achieved public sector debt level |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Execution of the budget - Reform of the Department for managing the public debt, debt analysis, cash management and international co-operation Sound public debt monitoring and reporting, definition and establishment of clear procedures for debt management and debt analysis, cash management and transactions regarding debt repayment. |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | http://www.mf.gov.me/rubrike/drzavni-dug/ The data is posted on the webpages of the Ministry of Finance as a part of the Report on public debt. The Report features annual debt servicing costs, and the GDP used. |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance Katarina Živković, Head of the State Treasury Directorate Katarina.zivkovicc@mif.gov.me Phone: 020/202-167 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Once a year, in the second quarter of the previous calendar year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The Ministry of Finance, in accordance with the Law on Budget and Fiscal Responsibility, prepares and publishes a report on the public debt. The performance indicator shows the relationship between the achieved level of public debt and the planned public debt for a given year. Public debt is calculated on the basis of the balance of external debt, internal debt, debt of state enterprises and debt of local self-governing bodies. Note: Movement of this performance indicator is conditioned by a number of factors that are largely beyond the control of the Directorate for the state treasury, such as the requirement to finance budget the year in a given year and other factors. |  |  |  |
|  | FORMULA/ EQUATION Total amount of debt / planned amount of debt X 100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 1,5% |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 1,5% | 1,5% | 1,5% | 1,5% |
| ACHIEVEMENT VALUE DATA | Public debt is 2.3% less than planned | Public debt is 3.07% higher than planned | Realized difference in gross public debt 16.6% |  |

# 3 Development of the system of internal financial controls

# 3.1 Management of public finance on an efficient, economic, effective and transparent manner to all consumer units

# 3.1.1 PASSPORT FOR THE PERFORMANCE INDICATOR 26.

| NAME OF THE PERFORMANCE INDICATOR | Percentage of ministries that formally delegate responsibilities and authorizations for decision making to the managers of organizational units |  |  |  |
| --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Development of the system of internal financial controls - Management of public finance on an efficient, economic, effective and transparent manner to all consumer units |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Annual reports on the implementation of planned activities on introducing and developing the system of financial management and controls Decisions by which responsibilities and authorizations have been delegated to the managers of organizational units for defined objectives |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance Nina Blečić E-mail: nina.blecic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA COLLECTION | Once a year, while adopting the Consolidate report which is published on the website of the Government of Montenegro, upon adoption until the end of quarter II of the current year for the previous year. |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The performance indicator relates to the ministries in which the heads of departments and general directors have been delegated with responsibilities and authorizations for the defined objectives and authorizations to manage determined budgets for their realization |  |  |  |
|  | FORMULA/EQUATION Number of ministries which delegated authorizations in relation to the total number of ministries x 100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 6,25% 2015: 6,3% 2016: 6,3% (Report: 2016: 22,22%) |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 30% | 16% | 50% | 90% |

# 3.1.2 PASSPORT FOR THE PERFORMANCE INDICATOR 27.

| NAME OF THE PERFORMANCE INDICATOR | Percentage of the budget beneficiaries on the central and the local levels which submit annual reports on financial management and control |  |  |  |
| --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Development of the system of internal financial controls - Management of public finance on an efficient, economic, effective and transparent manner to all consumer units |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Annual reports on the implementation of planned activities on introducing and developing the system of financial management and controls Data is available on the following link: www.gov.me/ResourceManager/FileDownload.aspx?rId=279138&rType=2 |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance Jelena Mirković E-mail: jelena.mirkovic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA COLLECTION | Once a year, while adopting the Consolidate report which is published on the website of the Government of Montenegro, upon adoption until the end of quarter II of the current year for the previous year. |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The Performance Indicator relates to budget beneficiaries at the central and local levels which are obliged in accordance with the Law on the system for internal financial control in the public sector to submit a report on the activities conducted within the entity. |  |  |  |
|  | FORMULA/EQUATION Number of budget beneficiaries at the central and local levels which submit annual reports in comparison to the total number of beneficiaries at the central and local levels which are obliged to submit annual reports X 100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 69% 2015: 76% 2016: 76% |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 75% | 80% | 90% | 95% |
| ACHIEVEMENT VALUE DATA | 77% | 90% | 93% |  |

# 3.1.3. PASSPORT FOR THE PERFORMANCE INDICATOR 28.

| NAME OF THE PERFORMANCE INDICATOR | Average number of appointed internal auditors per unit |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Development of the system of internal financial controls - Management of public finance on an efficient, economic, effective and transparent manner to all consumer units |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Register of appointed internal auditors Consolidated report on the system for internal financial controls in the public sector which is published in the II quarter of the current year for the previous calendar year |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance Miloš Baletić milos.baletic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA COLLECTION | Once a year, while adopting the Consolidate report which is published on the website of the Government of Montenegro, upon adoption until the end of quarter II of the current year for the previous year. |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The Regulation on amendments and supplements of the Regulation for establishing internal audit in the public sector, 30 budget beneficiaries (15 at the central and 15 at the local level) are obliged to establish a separate organizational unit for internal audit. Other budget beneficiaries must organize a separate internal audit unit or entrust the conduction of internal audit tasks to a budget user who has already established an internal audit unit. |  |  |  |
|  | FORMULA/EQUATION Average number of appointed internal auditors per unit = number of appointed internal auditors/number of established units for internal audit |  |  |  |
| STARTING VALUE DATA | SV (2014): 1,76 |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 2 | 2.3 | 2.5 | 2.7 |
| ACHIEVEMENT VALUE DATA | 2 | 2.21 | 2.1 |  |

# 3.1.4 PASSPORT FOR THE PERFORMANCE INDICATOR 29.

| NAME OF THE PERFORMANCE INDICATOR | Percentage of appointed and certified internal auditors |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Development of the system of internal financial controls - Management of public finance on an efficient, economic, effective and transparent manner to all consumer units |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Register of appointed internal auditors Consolidated report on the system for internal financial controls in the public sector which is published in the II quarter of the current year for the previous calendar year |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance Miloš Baletić milos.baletic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA COLLECTION | Once a year, while adopting the Consolidate report which is published on the website of the Government of Montenegro, upon adoption until the end of quarter II of the current year for the previous year. |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The Law on the system of internal financial control in the public sector states that in order for the internal auditor to establish a working relationship in regard to auditing, he/she must have passed the exam for the authorized internal auditor. An internal auditor may establish a working relationship in regard to auditing without passing the exam for the authorized internal auditor, provided that he/she passes this examination within one year from the date of the establishing of the employment relationship or within one year from the date of taking over the duties. |  |  |  |
|  | FORMULA/EQUATION number of certified auditors on an annual levelnumber of appointed internal auditors on an annual levelx100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 60% |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 75% | 80% | 85% | 90% |
| ACHIEVEMENT VALUE DATA | 90,90% | 94.05% | 100.00% |  |

# 3.1.5 PASSPORT FOR THE PERFORMANCE INDICATOR 30.

| NAME OF THE PERFORMANCE INDICATOR | Percentage of appointed certified auditors which have a continuous p0, rofess ional specialization |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Development of the system of internal financial controls - Management of public finance on an efficient, economic, effective and transparent manner to all consumer units |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Reports on continuous professional specialization |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance Miloš Baletić milos.baletic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA COLLECTION | Once a year, while adopting the Consolidate report which is published on the website of the Government of Montenegro, upon adoption until the end of quarter II of the current year for the previous year. |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | Internal auditors are obliged to continuously improve their knowledge and skills in order to help improve risk management, financial management and control by assessing their efficiency. |  |  |  |
|  | FORMULA/ EQUATION Number of internal auditors which were performing audits during the whole year and achieved a required number of points for continuous professional specialization / number of internal auditors which were performing auditing during the whole year X 100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 0% |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 70% | 75% | 80% | 90% |
| ACHIEVEMENT VALUE DATA | 74% | 83.64% | 81.63% |  |

# 3.1.6 PASSPORT FOR THE PERFORMANCE INDICATOR 31.

| NAME OF THE PERFORMANCE INDICATOR | Percentage of the implemented and partially implemented recommendations of the internal audit till the end of the year in subject, which were given in the previous year |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Development of the system of internal financial controls - Management of public finance on an efficient, economic, effective and transparent manner to all consumer units |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Annual reports of internal audit units Consolidated report on the system of internal financial control in the public sector of the current year for the previous year. The consolidated report is published on the website of the Government of Montenegro, after adoption by the end of the second quarter of the current year for the previous year. |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance Miloš Baletić milos.baletic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA COLLECTION | Once a year, while adopting the Consolidate report which is published on the website of the Government of Montenegro, upon adoption until the end of quarter II of the current year for the previous year. |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The percentage is calculated for all internal audit units that are required to submit the annual work report to the Directorate for central harmonization. Percentage is calculated for all recommendations given in the previous year. |  |  |  |
|  | FORMULA/ EQUATION Number of implemented or partially implemented recommendations / total number of recommendations in a single calendar year X 100 |  |  |  |
| STARTING VALUE DATA | SV (2014): 48% |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 55% | 60% | 65% | 70% |
| ACHIEVEMENT VALUE DATA | 73,5% | 79,16% | 84.46% |  |

4. Transparent financial reporting and accounting

# 4.1 The transition from cash accounting and financial reporting to accrual accounting

# 4.1.1 PASSPORT FOR THE PERFORMANCE INDICATOR 32.

| NAME OF THE PERFORMANCE INDICATOR | Trained accountants in the public sector for the application of accrual accounting in accordance with international accounting standards (based on the CIPFA methodology) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Transparent financial reporting and accounting - The transition from cash accounting and financial reporting to accrual accounting Improvement of the quality of the management of public finances and reporting by introducing basic preconditions for the key elements of accrual accounting |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Data of the Ministry of Finance on the number of attendants which were present at trainings |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Ministry of Finance Marija Uljarević marija.popovic@mif.gov.me Phone:063202964 |  |  |  |
| FREQUENCY OF DATA COLLECTION | December 31st every year |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | Ministry of Finance has started training public sector accountants to apply accrual accounting under international accounting standards since 2016. The training is conducted in accordance with the CIPFA (Chartered Institute of Public Finance and Accountancy) methodology. Trainees are accountants in consumer units of the budget of Montenegro and local self-governing units. The training is conducted in co-operation with the Centre for excellence in finance from Slovenia and the Human Resources Management Administration. The formula is created by the number of participants who only attended training during a single calendar year, regardless of whether they passed the exams and successfully completed the training, because at this stage of the accounting reform priority was given to familiarizing the accountant with international accounting standards. |  |  |  |
|  | FORMULA/EQUATION Number of people attending training in a single calendar year |  |  |  |
| STARTING VALUE DATA | SV (2014): 0 |  |  |  |
| TARGET VALUE DATA | Year 2017 | 2018 | 2019 | 2020 |
|  | 40 | 40 | 20 | 100 |
| ACHIEVEMENT VALUE DATA | 40 in 2016 | 80 | 40 |  |

# 4.1.2 PASSPORT FOR THE PERFORMANCE INDICATOR 33.

| NAME OF THE PERFORMANCE INDICATOR | Assets Register and the dual bookkeeping system for assets were implemented |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Transparent financial reporting and accounting - The transition from cash accounting and financial reporting to accrual accounting Improvement of the quality of the management of public finances and reporting by introducing basic preconditions for the key elements of accrual accounting |  |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Assets Administration and Assets Register System (ARS) |  |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Assets Administration Ranka Knežević, Email: ranka.knezevic@uzi.gov.me evidencija@uzi.gov.me Telefon:069/319-313 |  |  |  |
| FREQUENCY OF DATA COLLECTION | Daily – real time entry (with every purchase) |  |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | In 2016-2017 the Assets Administration developed a software tool and provided training for direct budget users. Upon completing training, users were obliged to provide assets details in the form of excel spreadsheets adapted to the ARS application to migrate the data into the register. Following the migration, users are obliged to record any purchase in the ARS (using records access application). The Assets Administration data on the number of users who attended training and provided assets information 195.66.166.90 |  |  |  |
| STARTING VALUE DATA | SV (2014): Development of the Asset Register commenced |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | Assets data entered in the register | Training (direct and indirect budget users) and gathering of assets data | Training (indirect budget users), migration into the ARS and becoming operational | The Assets Register and dual bookkeeping for assets are implemented |
| ACHIEVEMENT VALUE DATA | 0 | 0 | 9 groups 100 state bodies 0 migration |  |

# 5 Strengthening the capacities of external audit

# 5.1 Improvement of the process of auditing, strengthening of auditing capacities and the transparency of public spending – State Audit Institution

# 5.1.1 PASSPORT FOR THE PERFORMANCE INDICATOR 34.

| NAME OF THE PERFORMANCE INDICATOR | Percentage of realization of the Annual audit plan of the SAI |  |  |  |
| --- | --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Strengthening the capacities of external audit - Improvement of the process of auditing, strengthening of auditing capacities and the transparency of public spending – State Audit Institution |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | The data for monitoring the indicator are collected at the national level. SAI’s official webpages: www.SAI.co.me Database: SAI’s Annual Audit Plan; SAI’s Annual Report on Audits Done and Activities Undertaken for the period October of the previous year – October of the current year. Audit reports are posted on official SAI webpages: www.SAI.co.me |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | State Audit Institution Zoran Jelić zoran.jelic@SAI.co.me Phone : 020/407-407 Mihaela Popović mihaela.popovic@SAI.co.me Phone : 020/407-404 Marija Žugić, Department for international relations marija.zugic@SAI.co.me Phone: 020/407-430 |  |  |
| FREQUENCY OF DATA COLLECTION | Quarter IV of the current calendar year. |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | Under Article 9 of the Law on the SAI, Senate of the SAI adopts the Annual Audit Plan by the end of the current year for the next year. The Annual Audit Plan is an internal document of the SAI and it is regarded as a classified document until all the parties subject for auditing by the Plan are notified of the audit commencement |  |  |
|  | FORMULA/EQUATION %= number of conducted audits / number of planned audits X 100 |  |  |
| STARTING VALUE DATA | SV (2014): 60% SV (2017): 80% |  |  |
| TARGET VALUE DATA | 2018 | 2019 | 2020 |
|  | 83% | 86% | 90% |
| ACHIEVEMENT VALUE DATA | 86.27% | 88,68% |  |

# 5.1.2 PASSPORT FOR THE PERFORMANCE INDICATOR 35.

| NAME OF THE PERFORMANCE INDICATOR | Application of the audit methodology for financial, regularity and performance audits in accordance with ISSAI standards |  |  |
| --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Strengthening the capacities of external audit - Improvement of the process of auditing, strengthening of auditing capacities and the transparency of public spending – State Audit Institution |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | The data for monitoring the indicator are collected at the national level. SAI source: Draft reports prepared by the project teams and experts commissioned within the framework of IPA-funded project “Development and Building of SAI and AA Capacities”. SAI’s official webpages: http://www.SAI.co.me/1/index.php?option=com_content&view=article&id=93&Itemid=20&lang=sr http://www.SAI.co.me/1/index.php?option=com_content&view=article&id=139&Itemid=204&lang=sr |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | State Audit Institution Zoran Jelić zoran.jelic@SAI.co.me Phone : 020/407-407 Mihaela Popovic mihaela.popovic@SAI.co.me Phone : 020/407-404 Marija Žugić, Department for international relations marija.zugic@SAI.co.me Phone: 020/407-430 |  |  |
| FREQUENCY OF DATA COLLECTION | Quarter IV of the current calendar year. |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | No. of adopted and implemented methodologies for financial, regularity and performance audits in line with ISSAI standards for financial, regularity and performance audits compared to the number of planned methodologies. Description of methodologies: Audit methodology compliant with ISSAI level 3 – SAI has financial, regularity and performance audit methodologies compliant with ISSAI 200, 300 and 400. Audit methodology compliant with ISSAI level 4 – SAI has financial and regularity audit methodologies (manuals, guides) compliant with ISSAI 200 and 400, ISSAI 1000-1810 and ISSAI 4000) and performance audit methodology compliant with ISSAI 300 and ISSAI 3000, 3100 and 3200. |  |  |
|  | FORMULA/EQUATION n/a |  |  |
| STARTING VALUE DATA | SV (2015): Instruction on the methodology for financial and regularity audits compliant with ISSAI 200 and ISSAI 400, Instruction on the methodology for performance audits compliant with ISSAI 300 and Guidelines for Audit Quality Control SV (2017): Guidelines for assessing the application of fiscal responsibility criteria; Revised instruction on the methodology for performance audits compliant with ISSAI 300 |  |  |
| TARGET VALUE DATA | 2018 | 2019 | 2020 |
|  | Guidelines for Auditing Annual Financial Statements of Political Entities; Guidelines for Auditing Final Budget Accounts; | n/a The AP stars to be implemented as of Q1 2019 | Manual for Financial and Regularity Audits compliant with ISSAI 4th level adopted and applied. Manual for Performance Audits compliant with ISSAI 4th level adopted and applied. Guidelines for Monitoring the Implementation of Recommendations from Audit Reports adopted and applied. |
| ACHIEVEMENT VALUE DATA | Guidelines for the audit of annual financial statements of political entities were adopted in January 2018. The guidelines for auditing the final account of the state budget were adopted in September 2018. | Instruction on the methodology of performing the performance audit in accordance with the IV level of the ISSAI standard was adopted in December 2019. |  |

# 5.1.3 PASSPORT FOR THE PERFORMANCE INDICATOR 36.

| NAME OF THE PERFORMANCE INDICATOR | Number of organized trainings/seminars/workshops for auditors |  |  |
| --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Strengthening the capacities of external audit - Improvement of the process of auditing, strengthening of auditing capacities and the transparency of public spending – State Audit Institution |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | The data for monitoring the indicator are collected at the national level. Database of trainings/seminars/workshops delivered according to SAI’s Annual Training Plan and the trainings/seminars/workshops delivered within the framework of regional and international co-operation. SAI’s Training Plan SAI’s Annual Report on audits completed and activities conducted for the period: October of the previous year – October of the current year SAI’s official webpages: www.SAI.co.me |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | State Audit Institution Zoran Jelić zoran.jelic@SAI.co.me Phone : 020/407-407 Mihaela Popovic mihaela.popovic@SAI.co.me Phone : 020/407-404 Marija Žugić, Department for international relations marija.zugic@SAI.co.me Phone: 020/407-430 |  |  |
| FREQUENCY OF DATA COLLECTION | Quarter IV of the current calendar year. |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The SAI Senate adopts the Annual Training Plan. In addition to the trainings which are planned and implemented in accordance with the SAI Annual Plan, trainings are organized through regional and international co-operation as well. |  |  |
|  | FORMULA/EQUATION Number of trainings conducted in the current calendar year |  |  |
| STARTING VALUE DATA | SV (2014): A minimum of 3 trainings organized SV (2017): 9 additional trainings organized |  |  |
| TARGET VALUE DATA | 2018 | 2019 | 2020 |
|  | 6 additional trainings organized | 7 additional trainings organized | 10 additional trainings organized |
| ACHIEVEMENT VALUE DATA | 13 trainings (3 organized internally and 10 organized at an international level) | 13 trainings (3 organized internally and 10 organized at an international level) |  |

# 5.2 Strengthening of capacities and improvement of the auditing procedures – Audit Authority

# 5.2.1 PASSPORT FOR THE PERFORMANCE INDICATOR 37.

| NAME OF THE PERFORMANCE INDICATOR | Number of organized trainings/seminars/workshops per auditor |  |  |
| --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Strengthening the capacities of external audit - Strengthening the capacities and improvement of auditing procedures – Audit Authority |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Internal database on completed trainings of the employees of the Auditing Authority |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Audit Authority Radmila Prelević, authorized auditor radmila.prelevic@revizorskotijelo.me Phone: 067 313 199 |  |  |
| FREQUENCY OF DATA COLLECTION | January 31st N+1 for the year N |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | A greater number of audit training contributes to the strengthening the capacities of the institution and is measured by the number of trainings conducted during the calendar year per auditor. |  |  |
|  | FORMULA/EQUATION Number of audit trainings within a calendar year/number of auditors |  |  |
| STARTING VALUE DATA | SV (2014): 3 trainings organized per auditor |  |  |
| TARGET VALUE DATA | Year 2018 | 2019 | 2020 |
|  | A minimum of 5 audit trainings organized per auditor | A minimum of 9 audit trainings organized per auditor | A minimum of 7 audit trainings organized per auditor |
| ACHIEVEMENT VALUE DATA | 3 trainings organized per auditor on average | 11 trainings organized per auditor |  |

# 5.2.2 PASSPORT FOR THE PERFORMANCE INDICATOR 38.

| NAME OF THE PERFORMANCE INDICATOR | Level of implementation of the Strategic and Action plan of the institution |  |  |
| --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Strengthening the capacities of external audit - Strengthening the capacities and improvement of auditing procedures – Audit Authority |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Progress Report in implementing the Audit Authority’s Strategic Plan – Internal document |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Audit Authority Radmila Prelević, Authorized Auditor radmila.prelevic@ revizorskotijelo.me Telefon: 067 223 252 |  |  |
| FREQUENCY OF DATA COLLECTION | Quarter 1 N+1 for the year N |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The progress in implementing the AP accompanying the strategy is measured in percentages and shows managerial support for meeting the targets. |  |  |
|  | FORMULA/ EQUATION Realized number of AP activities / total number of AP activities X 100 |  |  |
| STARTING VALUE DATA | SV (2014): n/a |  |  |
| TARGET VALUE DATA | Year 2018 | 2019 | 2020 |
|  | n/a Activities stated in the AP start in 2019 | Strategic plan adopted Action plan adopted | 20% of planned activities realized |
| ACHIEVEMENT VALUE DATA | n/a Activities stated in the AP start in 2019 | Activities are delayed for 2020. |  |

# 5.2.3 PASSPORT FOR THE PERFORMANCE INDICATOR 39.

| NAME OF THE PERFORMANCE INDICATOR | Level of improvement of the audit methodology – Audit manual |  |  |
| --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Strengthening the capacities of external audit - Strengthening the capacities and improvement of auditing procedures – Audit Authority |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Working reports prepared by experts engaged in the IPA project "Development and capacity building of SAI and Audit Authority" with description of activities to improve the audit manual. |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Audit Authority Radmila Prelević, Authorized Auditor radmila.prelevic@ revizorskotijelo.me Telefon: 067 223 252 |  |  |
| FREQUENCY OF DATA COLLECTION | Once per year, dependent on the dynamic of the realization of the project |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The degree of improvement of the audit manual is measured by the percentage of the deficiencies identified by the project experts. |  |  |
|  | FORMULA/EQUATION Number of solved deficiencies of the manual / total number of deficiencies in the manual x 100 |  |  |
| STARTING VALUE DATA | SV (2014): Audit manual is prepared |  |  |
| TARGET VALUE DATA | Year 2018 | 2019 | 2020 |
|  | n/a Activities stated in the AP start in 2019 | 50% of deficiencies solved | 100% of deficiencies solved |
| ACHIEVEMENT VALUE DATA | n/a Activities stated in the AP start in 2019 | 90% of deficiencies eliminated |  |

# 5.2.4 PASSPORT FOR THE PERFORMANCE INDICATOR 40.

| NAME OF THE PERFORMANCE INDICATOR | Percentage of audits conducted by using the auditing software |  |  |
| --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Strengthening the capacities of external audit - Strengthening the capacities and improvement of auditing procedures – Audit Authority |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Reports on individual engagements of audit – internal documents |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Audit Authority Radmila Prelević, Authorized Auditor radmila.prelevic@ revizorskotijelo.me Telefon: 067 223 252 |  |  |
| FREQUENCY OF DATA COLLECTION | Quarter II of the N year for the previous year |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | The use of audit software tool is needed to increase audit efficiency. The indicator will be measured by the audits in which the software tool has been used as a share of the total number of audits. |  |  |
|  | FORMULA/ EQUATION Number of audits (in one calendar year) conducted using audit software tool / Total number of audits during the calendar year X 100 |  |  |
| STARTING VALUE DATA | SV (2014): n/a |  |  |
| TARGET VALUE DATA | Year 2018 | 2019 | 2020 |
|  | n/a Activities stated in the AP start in 2019 | 20% of audits conducted by using the software | 50% of audits conducted by using the software |
| ACHIEVEMENT VALUE DATA | n/a Activities stated in the AP start in 2019 | 33.33% |  |

# 5.2.5 PASSPORT FOR THE PERFORMANCE INDICATOR 41.

| NAME OF THE PERFORMANCE INDICATOR | Level of implementing standards to ensure audit quality |  |  |
| --- | --- | --- | --- |
| CORRESPONDING GOAL OR ACTIVITY | Strengthening the capacities of external audit - Strengthening the capacities and improvement of auditing procedures – Audit Authority |  |  |
| sOURCE OF DATA FOR MONITORING THE PERFORMANCE INDICATOR | Internal quality control register |  |  |
| PERSON IN CHARGE OF COLLECTING THE DATA | Audit Authority Radmila Prelević, Authorized Auditor radmila.prelevic@ revizorskotijelo.me Telefon: 067 223 252 |  |  |
| FREQUENCY OF DATA COLLECTION | Once a year |  |  |
| SHORT DESCRIPTION OF THE PERFORMANCE INDICATOR AND THE METHODOLOGY (FORMULA/EQUATION) | Quality control guidelines provide better quality and reliability of audit work. Performance Indicator is measured by the level of implementation of quality control guidelines. |  |  |
|  | FORMULA/EQUATION Number of audits covered by quality control / Total number of audits which are subject to quality control by the guidelines x 100 |  |  |
| STARTING VALUE DATA | SV (2014): n/a |  |  |
| TARGET VALUE DATA | Year 2018 | 2019 | 2020 |
|  | n/a Activities stated in the AP start in 2019 | 30% | 50% |
| ACHIEVEMENT VALUE DATA | n/a Activities stated in the AP start in 2019 | Data for 2019 could not be available this year due to the dynamics of the implementation of audit activities that are conditioned by the prescribed deadlines |  |

Public Finance  Management Reform Program for the period 2016-2020: http://www.mif.gov.me/biblioteka/strateska_dokumenta

At its session on June 28, 2018, the Government of Montenegro adopted an updated version of the Public Finance Management Reform Program for the period 2016-2020 with the Action Plan (http://www.mf.gov.me/biblioteka/strateska_dokumenta)

“Performance Indicator Passport”: http://www.mif.gov.me/biblioteka/strateska_dokumenta

The annual report for 2018 and the new AP for 2019 were adopted in May 2019. In February 2018, the Annual Report was adopted, which covers the implementation period from January 1 to December 31, 2017, while the Annual Report for 2016 was adopted in March 2017 and can be downloaded from the website of the Ministry of Finance:  http://www.mf.gov.me/biblioteka/strateska_dokumenta.

PAR Strategy: (http://www.mup.gov.me/ResourceManager/FileDownload.aspx?rid=250721&rType=2&file=Strategija%20reforme%20javne%20uprave%20u%20Crnoj%20Gori%202016-2020.godine.doc )

Conclusion No. 07-1966 of 6 July 2017 (adopted at the 32nd Session of the Government of Montenegro)

National IPA Program, Regional and Territorial Cooperation Program as well as the Education, Employment and Social Policy Program.

Agriculture and Rural Development Program.

The law on public procurement, (http://www.ujn.gov.me/wp-content/uploads/2018/02/Zakon-o-javnim-nabavkama-prečišćem-tekst-2017-godina-1.pdf )

Law on Public-Private Partnership,, (https://www.paragraf.me/nacrti_i_predlozi/predlog-zakona-o-javno-privatnom-partnerstvu.pdf ).

The data related to the internal audit for 2019 are of a preliminary nature.

The document was published in the "Official Gazette of Montenegro", No. 068/19; it is also available on the website of the State Audit Institution - www.dri.co.me

National IPA Program, Regional and Territorial Cooperation Program as well as the Education, Employment and Social Policy Program.

Agriculture and Rural Development Program.

Manuals adopted and implemented from April 19, 2019.

The seventh meeting of the Special Working Group for Public Administration Reform (PAR) formed between the European Commission and Montenegro held on September 27 and 28, 2018.

Direct budget support for the implementation of the Public Administration Reform Strategy amounts to 15 mil. €, and no national co-financing is envisaged for its implementation. Of this amount, 12 mil. € The program is planned to be allocated through three tranches. The remaining 3 mil. € represent complementary technical support, for which the Delegation of the European Union in Montenegro is in charge of contracting. Therefore, the first fixed tranche in the amount of 4 mil. € was paid to Montenegro on November 28, 2018, while the first variable tranche in the amount of 2.1 mil. € paid in December 2019.

Monstat: Data refer to 12 months

http://www.mif.gov.me/rubrike/Budzet_Ministarstva_finansija/

http://www.gsv.gov.me/stratesko_planiranje/politike

Law on Fiscalization in theTrade of Products and Services, ("Official Gazette of Montenegro", No. 46/2019).

The total value of the project in cooperation with the Tax Administration of Spain is € 1,000,000.00, with the EU contribution amounting to € 90,000.00 while the Government of Montenegro co-financed with € 100,000.00. The project is implemented by FIIAPP with the Tax Administration of Spain and the Tax Administration of Montenegro, as twinning partners.

The Parliament of Montenegro adopted the new Law on Public Procurement on December 30, 2019. (Official Gazette of Montenegro 074/19)

Law on Public-Private Partnership 12/27/2019 (Official Gazette of Montenegro 073/19)

The data will be contained in the Public Procurement Report for 2019, which was prepared by the Ministry of Finance by May 31, 2020 for the previous year, while the adoption will be in June 2020.

The final data on the mentioned values will be known at the end of March 2020, when the Public Debt Report for 2019 will be published. No significant deviations from preliminary data are expected.

According to preliminary data, the increase in gross public debt will amount to 16.6%. If we take into account the fact that, according to preliminary data, at the end of 2019, deposits amounted to 597.13 mil. €, so the value of gross public debt, at the end of 2019, will amount to 78.68% of GDP, while the value of net public debt will amount to 66.26% of GDP estimated for 2019.

On November 12, 2018, the Parliament of Montenegro adopted the “Law on Management and Internal Controls” (“Official Gazette of Montenegro”, No. 075/18 of November 23, 2018)

In 2016, Performance Indicator value was 22,22%.

The data for 2019.

The data for 2019 is of a preliminary character. The new Regulation on the Establishment of Internal Audit in the Public Sector ("Official Gazette of Montenegro", No. 070/19) has increased the number of units that are obliged to establish a special unit for internal audit. For this reason, the value of this indicator decreased compared to the previous year.

The data for 2019 is of a preliminary character.

The data for 2019 is of a preliminary character.

. The stated data is the real value, while in the last report the percentage of implementation of 73.5% referred to 2016, which was also stated

The data for 2019 is of a preliminary character.

Law on Accounting in the Public Sector, adopted by the Parliament of Montenegro on November 22, 2019, ("Official Gazette of Montenegro", No. 066/19 of December 6, 2019 ").

The Parliament of Montenegro passed the Law on State Property (ZDI), which entered into force in March 2009, which prescribes the obligation that the administrative body responsible for property affairs is obliged to establish a single register of real estate of state property, within 90 days from the date of expiration of the deadline set by the state and municipal authorities. According to these provisions, the state property register was to be operational by summer 2010.

In 2014, the external web application of the SAP system FI-AA submodule ARS was implemented

The implementer of the project is Atos Ltd from Belgrade. The project started on January 12, 2015 and lasted until 30.09.2015. The value of the project is 199,800.00 euros including VAT.

Employees in the Sector for keeping the real estate register, records of movables and tasks for preparation of data for registration of state property.

Bearing in mind that the trainings start in the middle of the year, the year of the training does not coincide with the calendar year, but the year extends to two calendar years.

Through cooperation with SIGMA, in 2019, draft Guidelines for proposing and selecting financial audits and regularity audits for the Annual Audit Plan were prepared.

In 2019, the following documents were prepared: the draft Manual for financial audit and regularity audit, which refers to the phases of planning and implementation of the audit, the draft of Communication Strategy

The document was published in the "Official Gazette of Montenegro", No. 068/19; it is also available on the website of the State Audit Institution - www.dri.co.me

The document was published in the "Official Gazette of Montenegro", No. 006/19; it is also available on the website of the State Audit Institution - www.dri.co.me

In November 2018, a contract on services "Development and capacity building of the State Audit Institution and the Audit Authority of Montenegro" was signed for a period of 18 months.

National IPA Program, Regional and Territorial Cooperation Program as well as the Education, Employment and Social Policy Program.

Agriculture and Rural Development Program.

The manuals were approved by the Auditor General of the Audit Authority by Decision No. 109/3 2019.

Having in mind that the Law on the final account of the budget for 2017 has not still been adopted, the data on actual expenditure has been taken over from the SAP system at the moment of creation. Performance Indicator passport is not official until the adoption of the Law on the final account of the budget.

Data is preliminary, as the actual data on GDP will be available in September 2019, for 2018. (MONSTAT quarterly reports on GDP).

Adoption of both drafts of the Law is expected during middle of 2019.

Draft of the Law on the final account of the budget of Montenegro for 2017. 13,0 represents the preliminary data until the official adoption of the Law in the Parliament (September), and until then, official data on the GDP for 2017 will be available.  http://www.gov.me/ResourceManager/FileDownload.aspx?rId=317590&rType=2

Data for the achievement of this performance indicator are available since February in the document „Report on revenues and expenditures of the budget“

Tokom izvjestajnog perioda podatak je bio preliminaran i iznosio je 2,38.

Podatak koji se odnosi na stvarnu vrijednost prosjecnog broja ponuda u 2019.godini ce biti dostupan u Godisnjem izvjestaju o javnim nabavkama za 2019.godinu,koji Ministarstvo finansija priprema i dostavlja Vladi na usvajanje najkasnije do 31.maja 2020.godine. Podatak je preliminaran.

Donation financed by SIGMA and MMF.

Actual value for 2018 for this Performance indicator is a preliminary value.

The data for 2018 is preliminary . While calculating the percentage of implementation, taken into account are only recommendations whose deadline for implementation was until the end of 2018.

Trainings are organized in co-ordination with the Human Resource Management Administration, and the funds are secured from the Budget of Montenegro as the realization of the IPA project begun at the end of 2018.

Funds given as a contribution for the implementation of the program for the training of newly appointed internal auditors.

Training has been organized in co-operation with the Human Resources Management Authority, with funds provided from the budget of Montenegro, since the realization of the IPA project started at the end of 2018.

Activity has been realized by the Ministry of Finance by using its own resources.

The first generation was financed by the Ministry of Finance of Slovakia and the UNDP, while the second generation was financed by USAID, and the third generation was again financed by the Ministry of Finance of Slovakia and the UNDP.

The Law on description of the Law does not feature all the information provided in budget requests. Comprehensive information is important when considering and negotiating budget requests.

Realization of the capital budget, without including the highway - 111%, and with the highway included it is - 91%

Data is preliminary, while the actual data on GDP will be available in September 2019, for the year 2018 (MONSTAT quarterly reports on GDP).

A formula has been submitted for the clearing and it is explained that for income, 95% represents the previous trend for income. When the e-submissions are concerned, it could not be processed as the obligation for submitting electronic applications started in January 2017.

Harmonization of the Law on tax administration is planned for the end of Q4 2018, in the part of administrative co-operation and mutual assistance and the Law on income tax (transfer prices).

Adoption of both drafts of Laws is expected by the middle of 2019.

Zakon o izmjenama i dopunama zakona o porezu na dobit pravnih lica (IV kvartal 2019);

Zakon o izmjenama i dopunama Zakona o poreskoj administraciji  (IV kvartal 2018);

Zakon o PDV-u (IV kvartal).

Draft of the Law on the final account of the budget of Montenegro for 2017. 13,0 represents the preliminary data until the official adoption of the Law in Parliament (September), and until then official data on the GDP for 2017 will be available. http://www.gov.me/ResourceManager/FileDownload.aspx?rId=317590&rType=2

Data for achievement of this performance indicator is available since February in the document „Report on revenues and expenditures of the budget“

Official data on achieved values for 2018 will be available by adopting the Annual report on conducted procedures for public procurements for 2018 until May 31st of the current year.

The data will be contained in the Public Procurement Report for 2019, which was prepared by the Ministry of Finance by May 31, 2020 for the previous year, while the adoption will be in June 2020.

According to preliminary data, the increase in gross public debt will amount to 16.6%. If we take into account the fact that, according to preliminary data, at the end of 2019 deposits amounted to EUR 597.13 million, so the value of gross public debt, at the end of 2019, will amount to 78.68% of GDP, while the value net public debt will amount to 66.26% of GDP estimated for 2019.

Reports have been delivered to the CHU of the Ministry of Finance. This performance indicator exists in the Strategy for the reform of the public administration, and the results are available on the link: www.gov.me/ResourceManager/FileDownload.aspx?rId=279138&rType=2

Reports have been delivered to the CHU of the Ministry of Finance.

Number of beneficiaries of the budget is changing in accordance with the amendments of the regulation on organization and the mode of work of the state administration and the Law on the budget for the current year.

Actual value of this performance indicator in 2017 is a preliminary value.

Actual value of this performance indicator in 2018 is a preliminary value. Percentage is calculated on the basis of submitted reports up to the day of submission.

Data for 2019.

Actual value of this performance indicator in 2018 is a preliminary value.

The data for 2019 is of a preliminary character. The new Regulation on the Establishment of Internal Audit in the Public Sector ("Official Gazette of Montenegro", No. 070/19) has increased the number of units that are obliged to establish a special unit for internal audit. For this reason, the value of this indicator decreased compared to the previous year.

Data for 2019 are of a preliminary character.

Number of achieved points is determined on the basis of the Instruction for continuous professional specialization of authorized internal auditors in the public sector.

Data for 2019 are of a preliminary character.

The stated figure is an actual value, while in the previous report, the percentage of implementation of 73,5% referred to 2016, which was mentioned.

Data for 2018 are preliminary. While calculating the percentage of implementation, taken into consideration were only recommendations whose implementation deadline was until the end of 2018.

Data for 2019 are of a preliminary character.

Bearing in mind that the trainings start in the middle of the year, the year of training does not coincide with the calendar year, but the year extends to two calendar years.

The asset data has been entered into the register. The data (spreadsheets) submitted to the Assets Administration have been modified, tested and migrated to the ARS trial version. During migration and trials we noted some problems in the operation of this application (at times it prevents users from accessing the application) and we notified the application developers, “ATOS doo Belgrade”, of the issue. We are currently receiving assistance regarding the software tool and we expect that the issue will be resolved shortly. Once it is resolved, we will ensure the final migration of data and when this is complete, the application will be active for all users who have provided data in a timely manner.

The migration of data on real estate and movable property obtained from end users to the LFS application is planned for the end of 2020.

The application of the stated formula will begin after the mentioned plans have been adopted.

During 2019 deficiencies in the audit manual will be identified, after which the mentioned formula will be implemented.

Data for this Performance Indicator will be available during Q1. 2020.