ACRONYMS

AMM			Association of Managers of Montenegro

PAR AP		Public Administration Reform Action Plan

AURUM		Public Administration Reform Strategy 2011 – 2016

APDPFAI		Agency for Personal Data Protection and Free Access to Information

GPD			Gross-domestic product

CAF 			Common Assessment Framework

CPR			Central personnel records

DEU			Delegation of the EU to Montenegro

SAI 			State Audit Institution

DT			Digital transformation

EDMS			Electronic document management system

EFQM			European Foundation for Quality Management

eID			Electronic identity

EC			European Commission

EU			European Union

EUPAN			European Public Administration Network

GSB	Single information system for electronic exchange of data between state authorities and state administration authorities

GSG			General Secretariat of the Government

ILIAS			E-learning/training platform

IPA III			Instrument of Pre-Accession Assistance

IS			Information systems

ISO			International Organisation for Standardisation

ISPI			Reporting on mid-term work programmes of ministries

IT			Information technology

LSGU			Local self-government unit

SISEDE			Single information system for the electronic data exchange

MEA			Ministry of European Affairs

CEA			Commission for Economic Affairs

HRIS			Human resource information system

KPMG			Consulting and audit company

CPS			Commission for Political System

LSG			Local self-government

MED			Ministry of Economic Development

MESPH			Strategic planning portal in the EU integration IT system

MF			Ministry of Finance

MLESD			Ministry of Labour, Employment and Social Dialogue

Standard Cost Model	Standard cost model

MONSTAT 		Directorate for Statistics of Montenegro

MIA 			Ministry of Internal Affairs

MJ 	Ministry of Justice

MHMR 		Ministry of Human and Minority Rights

MH			Ministry of Health

NGO			Non-governmental organisation

OGP			Open Government partnership

CCMNE		Chamber of Commerce of Montenegro

MPAEU		Montenegro’s Programme of Accession to the EU

PFRP 			Public Finance Reform Programme

GWP			Government Work Programme

ReSPA			Regional School of Public Administration

WG			Working group

RIA			Regulatory Impact Assessment

PAR			Public administration reform

SBS			Sector budget support

SIGMA	Joint OECD/EU Support for Improvement in Governance and Management

FAI			Free access to information

HRA			Human Resources Authority

UN			United Nations

UNDP			UN Development Programme

LCSSE			Law on Civil Servants and State Employees

UoM			Union of Municipalities of Montenegro

LFAI			Law on Free Access to Information

LAP			Law on Administrative Procedure

EA			Employment Agency

CONTENTS

| I | INTRODUCTORY SUMMARY |  | 4 |
| --- | --- | --- | --- |
| II | INTRODUCTION |  | 7 |
| III | MONITORING AND ACHIEVEMENTS IN THE AURUM IMPLEMENTATION |  | 9 |
|  | 3.1 3.2 3.3 | DIALOGUE WITH THE EU SIGMA MONITORING REPORT INFORMATION ON PROGRESS IN ACHIEVING OPERATIONAL GOALS | 11 12 13 |
| IV | BUDGET |  | 38 |
|  | 4.1 | EU SUPPORT FOR PUBLIC ADMINISTRATION REFORM - IPA III (SECTOR BUDGET SUPPORT) | 38 |
| V | RECOMMENDATIONS |  | 41 |
| VI | REPORTING TABLE |  | 43 |

I	INTRODUCTORY SUMMARY

The primary monitoring results for the Action Plan 2022-2024 implementation period, compared to 2024, with reference to 183 activities and 53 indicators that have been tracked and measured, indicate an increase in performance indicators compared to 2023 and 2022, confirming that reform activities are proceeding more quickly.

EU BUDGET SUPPORT

2024 EUROPEAN COMMISSION REPORT

The European Commission’s 2024 Report states that Montenegro has made limited progress in reforming its public administration. According to the Report, Montenegro is moderately prepared to implement the acquis in this field.

II	INTRODUCTION

The reform of public administration in Montenegro represents one of the most important strategic priorities of the state in the context of its social, economic and political development. Establishing an administrative system that meets EU standards is necessary to meet the criteria from Chapter 23 (Judiciary and Fundamental Rights) and Chapter 24 (Justice, Freedom and Security), which implies that the improvement of public administration is one of the main priorities on the European road.

The entire process is directed towards the modernisation and improvement of the functioning of state and local institutions, in accordance with the principles of efficiency, transparency and responsibility. The guiding idea of this process is to ensure a better quality of public services for citizens and the economy, as well as a better, more transparent and more inclusive process of creating public policies.

The Public Administration Reform Strategy (AURUM) includes five strategic goals, namely:

I Citizen-oriented organisation and operation of the public administration;

II Citizens and businesses use high-quality services of the public administration;

III Professional public administration;

IV Transparent and open public administration;

V Policy planning with and for citizens.

Reforming public administration not only helps to increase public confidence in institutions, but it also makes sure that different social groups are included in decision-making through transparent and participatory processes.

The Ministry of Public Administration has produced reports on the execution of the Action Plan 2022-2024 in compliance with the Methodology for the formulation and monitoring of strategic documents,  Public Administration Reform Strategy 2022-2026 for the year 2022, as well as for the year 2023. These reports track the Public Administration Reform Strategy’s implementation status and offer information on performance indicator trends and the degree of strategic activity realisation.

In certain ways, the three-year Action Plan monitoring process is completed by the Report on the implementation of the Action Plan 2022-2024 for the year 2024, which allows continuity in tracking the accomplishment of goals and activities. The conclusions drawn from these three reports serve as the foundation for the 2025–2026 Action Plan’s activity definition. Because they are related, the Action Plan 2025–2026 and the Report for 2024 will be considered simultaneously during the Government of Montenegro session.

The report on the implementation of the PAR for 2024 was developed by the Coordination Structure, established in July 2024. The coordination structure with six coordination bodies aims at the timely collection of data on the implementation of strategic and operational goals, as well as the provision of a platform for timely intervention in case of delays in the implementation of planned activities. The work of the Coordination Team began with the holding of the first meeting in July 2024, after which it was intensified during the year with a special focus on fulfilling the indicators from the Sector Budget Support and defining the tasks for the next period.

The horisontal themes of the AURUM refer to the creation of public administration based on equality, inclusion, anti-discrimination and equal opportunities for all.

The MPA’s commitment to these topics is also reflected in a series of activities included in the upcoming Action Plan that seek to make gender equality a major priority of the public administration reform. The Ministry’s ultimate goal is to establish, in the near future, policies and conditions that acknowledge and actively advance gender equality at all levels of public administration, working with all pertinent institutions. In keeping with this, in February 2025, training was held for representatives of the Ministry of Public Administration, which is part of the regular general training programme of the Human Resources Administration.

Since the activities in the PAR area must keep pace with latest technological advancements, the Ministry of Public Administration will devote special attention to the development of artificial intelligence in the upcoming period, as it has enormous potential for enhancing public services, streamlining administrative processes and facilitating better decision-making. In this context, the MPA has inititated the process of evaluating the Montenegrin institutions’ preparedness for the use of artificial intelligence and drafting a future strategy for the development of artificial intelligence in Montenegro. It is important to note that within its competences, the MPA implements the Digital Transformation Strategy 2022-2026 and the Cyber Security Strategy 2022-2026, which together form a comprehensive strategic framework in the direction of strengthening the efficiency and security of public services in the digital environment.

The Ready4EU training programme was created to make sure that Montenegro’s public administration was prepared for the challenges that come with joining the European Union. It is a HRA project that is being carried out with assistance from MED, MPA, and ReSPA. This programme aims to assist civil workers in learning fundamental administrative skills and EU knowledge in response to the intensified discussions between Montenegro and the EU. Employees in public administration are thereby getting ready for their future positions in EU agencies, organisations, and advisory bodies.

Published: October 18, 2024 08:30 a.m.

Author: Ministry of Public Administration

CAF team of the Ministry of Public Administration held a meeting

The creation of a quality management model is one of the main issues for enhancing public administration in Montenegro. Being a trailblazer in this field, the Ministry of Public Administration aims to inspire other organisations to incorporate this idea into their work by setting an example. The Ministry finished the evaluation process in 2024 and was designated as effective user by CAF based on the evaluator’s report and evaluation. MPA is the first institution in Montenegro to earn this esteemed distinction, therefore this achievement marks a significant advancement.

III	MONITORING AND ACHIEVEMENTS IN THE PAR STRATEGY IMPLEMENTATION

With reference to 183 activities and 53 indicators that were tracked and measured, the primary findings of the monitoring for the Action Plan 2022–2024 implementation period are displayed in the graphs below. These findings demonstrate that, in contrast to the outcomes attained in 2022 and 2023, notable advancements were made in the area of activity implementation in 2024.

It is crucial to note that the Public Administration Reform Strategy was put into action during the 2022–2024 reporting year under a dynamic political environment. Significant political changes occurred during this time, including two government reorganisations, which directly affected how public administration operated and, in turn, how well the Strategy was implemented in 2022–2024. The dynamics of implementing reform measures paralleled changes in the structure and makeup of the executive branch, with some actions being slowed down or modified to fit the changing conditions. The public administration reform process had difficulties in maintaining continuity, coordinating across institutions, and guaranteeing stability in the execution of intended policies under such circumstances.

An overview of the reorganisation of the Government is shown in the following graphic:

Through effective coordination and cooperation with other institutions, as well as monitoring and reporting on reform processes, the Ministry of Public Administration, in particular the Directorate for Strategic Planning in Public Administration, International Cooperation, and IPA Funds, which is in charge of overseeing the implementation of the 2022-2026 PAR Strategy with the Action Plan 2022-2024, worked diligently on the implementation of public administration reform in Montenegro.

Notwithstanding the difficulties encountered throughout the Strategy’s implementation and oversight, extra effort was taken to ensure that the reform initiatives were carried out in a manner that aligned with the objectives specified in the strategic document. Compared to the adoption of the Report for the year 2023 in July 2024, the reporting procedure for the year 2024 proceeded more quickly, which is another indication of this development.

An administrative-operational organisation - the Coordination Team for monitoring the implementation of the public administration reform was established in July 2024 with the goal of improving monitoring and reporting.

In order to ensure more effective management of the entire process and oversight of the execution of reform activities, the coordination team was established.  According to the five strategic goals of the AURUM, the coordination structure is made up of six coordination organisations, including a particular coordination body for the local self-government system.  A coordinator and secretary are selected to each coordinating body. This procedure led to the adoption of the Information on the work of the coordination team for the implementation of public administration reform in December 2024, which gives an overview of the outcomes attained and the work done by this group.

While the efforts of the Coordination Team are innovative and have undoubtedly enhanced officials' reporting skills, they have also introduced challenges. As a result, efforts will be made in the near future to strengthen this team by: enhancing coordinators’ and secretaries’ abilities; cutting the number of members; encouraging coordinators to be more proactive; and enhancing coordination between coordinators and body secretaries. The EU Delegation in Montenegro’s “Support for coordination, monitoring and reporting on the Public Administration Reform Strategy and the Public Finance Reform Management Programme” initiative offers expert assistance for the coordination team’s and the Council’s work. The idea of public administration reform, including public financial management, is greatly aided by this project, which puts The Centre for Excellence in Finance (CEF) into practice.

The Council for Public Administration Reform, which keeps an eye on both public administration and public finance management (PFM) reforms from a political standpoint, is particularly significant in this regard. The Prime Minister chairs the Council. The release of announcements and information from the sessions helped to make this government body’s operations more transparent. The Council convened three sessions during the reporting period: the II session in April 2024, the III session in December 2024, and the IV session in March 2025.

The fourth session of the Council, held on March 7, 2025, was an opportunity to acquaint Council members with the main findings and recommendations of the Public Administration Report prepared by the SIGMA organisation. At this session, the Draft Action Plan of the Public Administration Reform Strategy 2022-2026 was also adopted for the period 2025-2026. Also, on the agenda was Information on activities in the field of public finance management reform in the period December 2024-March 2025, as well as oral information on the activities of the Ministry of Public Administration regarding the preparation of the Law on Local Self-Government.

3.1 DIALOGUE WITH THE EU

The Public Administration Reform Special Group represents the platform of the negotiation process between Montenegro and the European Commission in the field of public administration reform. The aim of the meetings is to analyse the situation in the field of public administration, address challenges and discuss what needs to be done in order to bring the Montenegrin public administration system into line with European Union standards as much as possible. At the meetings of the Special Group, the degree of fulfillment of indicators of Sector Budget Support, within the framework of the IPA III financial aid mechanism for public administration reform and public finance management, is considered. The XII meeting of the Special Group was held on November 20, 2024, for the first time in Brussels, which is the result of efforts to improve the dialogue between Montenegro and the EU in this important area. The result of the meeting in Brussels are the Operational Conclusions, which were adopted by the Government of Montenegro on December 19, 2024, and which were previously agreed with the European Commission.

Timely implementation of the measures from the Operational Conclusions is crucial for strengthening the capacity of institutions towards fulfilling the conditions for EU membership, while commitment to fulfilling the Operational Conclusions will continue to be a priority of the Government of Montenegro in the coming period.

According to the Report of the European Commission for 2024, Montenegro has made limited progress in the field of public administration reform. The Report states that Montenegro is moderately ready for the application of the acquis in this area. When it comes to the Commission's recommendations from 2023, it was assessed that they were partially adopted and remain in force. Additionally, the report states that in the coming year, Montenegro should:

- Adopt and implement amendments to the Law on Free Access to Information, in line with the principles of good public administration, and introduce measures to reduce the high number of requests for information and related appeals;

- Amend and implement the Law on Civil Servants and State Employees and the Law on Local Self-Government to ensure that recruitment follows the principles of merit, competence and transparency;

- Put in place a unified, comprehensive and transparent system for capital investment planning and management.

After the publication of the European Commission’s report for Montenegro, the Ministry of European Affairs coordinated the process of developing the Action Plan for the fulfillment of the recommendations from the Report, which was adopted in February 2025, with the aim of more efficiently fulfilling the Commission’s recommendations. Regarding the implementation of recommendations in the field of public administration reform, the Action Plan defines specific activities related to the adoption of legal solutions, improvement of the implementation of the strategic framework and monitoring of the Strategy, as well as cooperation with NGOs in the field of strategic planning in public administration.

3.2 OECD/SIGMA MONITORING REPORT

The OECD/SIGMA report serves as the foundation for the European Commission’s assessment on Montenegro’s public administration reform for 2024. The goals of OECD/SIGMA (a joint initiative between the OECD and the EU), are to improve public administration in countries undergoing European integration, assess the effectiveness, accountability, and transparency of institutions, and assess country’s capacity to apply European standards. The legislative framework, institutional capacity, and policy implementation are all analysed as part of the SIGMA monitoring process. The findings are then used to offer recommendations and assistance to countries undergoing public administration reform.

Since the research conducted by OECD/SIGMA coincides with the planned evaluation, the findings of the OECD/SIGMA monitoring were taken as recommendations of the external evaluator and thus were treated in the formulation of challenges and recommendations in the Report for 2024, as well as when defining and re-defining activities in the Action Plan 2025-2026. The reformulated OECD/SIGMA SIGMA Principles of Good Management served as the methodological basis for monitoring.

As for the monitoring process itself, i.e. during the preparation of this report, which lasted from February to November 2024, the MPA was in the role of coordinator, and all relevant institutions, as well as local experts engaged by the OECD/SIGMA organisation, actively participated in it.

As stated in the report, Montenegro has achieved some progress in areas such as the strategic framework for the continuous improvement of public administration, the development and coordination of policies and the implementation of the RIA form, where compared to the average of the countries of the Western Balkans, Montenegro achieves better results. However, there are challenges in other sectors, especially in terms of human resource management, service delivery and digitisation.

The OECD/SIGMA report summarises the key systemic challenges for progress in public administration reform:

- Implementation of the Public Administration Reform Strategy 2022-2026 is low.

- HRA capacities are weak, and top management structure is unstable, with significant deficiencies in merit-based recruitment.

- The organisational typology established in the law is not respected, and accountability based on clear objectives and the performance management of agencies is absent.

- The quality and digital accessibility of services remains low.

- There is relatively low implementation of oversight institutions’ recommendations and lack of parliamentary support for these institutions.

In this regard, OECD/SIGMA concludes that in the coming period it is necessary to ensure the timely implementation of reform plans and goals and, if necessary, to re-define them through a thorough analysis of what has been achieved. Also, it is necessary to provide competitive conditions for the employment of candidates for positions of senior management staff, and to ensure the stability of these positions to the greatest extent possible. At the same time, in order to achieve the progress that has been achieved at the regional level in this area, it is necessary to speed up reforms in the direction of improving the quality and online availability of public services for citizens.

3.3 INFORMATION ON PROGRESS IN ACHIEVING OPERATIONAL OBJECTIVES

CITIZEN-ORIENTED ORGANISATION AND OPERATION OF THE PUBLIC ADMINISTRATION

The first strategic goal is aimed at adjusting the structure and functioning of the public administration in order to better respond to the expectations and demands of citizens. Within this goal, activities are planned that include optimisation of internal processes, strengthening of external and internal supervision over the work of public administration bodies, increasing responsibility and streamlining procedures.

To achieve this strategic goal, in the context of strengthening the responsibility of public administration bodies and external supervision over their work, a negative trend of the set indicators is evident. A significant increase in the amount of funds forcibly collected in cases represented by the Protector of Property and Legal Interests is a burden on the state budget, as indicated by the Protector in his Report adopted by the Government of Montenegro at the session on February 13, 2025. Also, the challenge for reaching this strategic goal is the negative trend of the indicator, which is measured by the average duration of the dispute in the Administrative Court, caused by an unusually large influx of cases during 2022, 2023 and 2024.

In the context of improving the responsibility of public administration and external supervision of its work, the Public Administration Reform Strategy envisages strengthening the function of the Ombudsman, i.e. increasing the percentage of implemented recommendations that this institution submits to public administration bodies. After the great growth achieved by this indicator in 2023, the trend of the indicator, despite a slight decline, is still positive and has exceeded the target value for 2024.

An important segment of the organisation of public administration is the concept of good management, which implies the establishment of a series of mechanisms to achieve the goals of public administration bodies, all within the framework of the approved budget and expected performance. Although managerial accountability remains a challenge for the public administration system in Montenegro, the indicator that measures the formal delegation of authority for financial management and internal control to senior management shows a significant growth trend.

In order for the public administration organisation to achieve the highest possible level of internal consistency, the fact that the indicator measuring the compliance of all laws with the Law on Public Administration has been fully implemented is encouraging.

More than 3,000 public administration employees will use a new Information System for electronic document management and management of the process of electronic sessions of the Government of Montenegro - eDMS/eSV, which was established with the goal of modernising the work of public administration bodies, expediting the process, and improving the administration’s responsiveness to the needs of citizens. It began operations in January 2025. The 2024 target value was surpassed by the associated performance indicator, which calculates the proportion of public administration entities with eDMS in place. One unit combines the new eDMS/eSV and CA (digital signature platform) solutions.

The use of intermunicipal cooperation is a mechanism that can guarantee the reasonable and high-quality completion of tasks that fall within the purview of municipalities. The number of jobs where inter-municipal collaboration was established in 2024 exceeded the intended figure, even though the prior legal framework was vague and did not specify the specifics of the inter-municipal cooperation mechanism. This mechanism will be strengthened by the new Law on Local Self-Government.

The following is a tabular overview of the performance indicators:

| OPERATIONAL OBJECTIVE 1.1 | Functional public administration with efficient oversight of its implementation and application of the managerial accountability concept |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | BASELINE VALUE | VALUE FOR 2022 | VALUE FOR 2023 | VALUE FOR 2024 |  | TREND |  | TARGET VALUE BY 2024 |  |
| Amount collected by means of enforcement procedure in labour cases handled by the Protector of Property and Legal Interests | €10,412,089 | €15,226,148.67 | € 14,143,973.4 | €18,803,866.30 |  |  |  | Unchanged as compared to the baseline value |  |
| Percentage of institutions having established a reporting system at the level of outcome indicators and objectives which would enable monitoring of the achievement of results with indicators of the programme-based budget implementation | No system in place | The indicator will be tracked through indicator 45 | The indicator will be tracked through indicator 45 | The indicator will be tracked through indicator 45 |  |  |  | 100% of ministries have outcome reporting in place |  |
| Average duration of administrative disputes in the Administrative Court | 17 months | 17.7 months | 17.2 months | 19.2 months |  |  |  | 12 months |  |
| Percentage of recommendations implemented by state authorities based on the Ombudsman’s annual work report | 19.88% | 19.3% | 53.1% | 52.5% |  |  |  | Over 40% of implemented recommendations |  |
| Percentage of ministries which delegate financial management and internal control authority to senior management in accordance with the Decree | 8.3% | 28% | N/A | 42% |  |  |  | 50% |  |
| Number of administrative authorities having been subjected to administrative oversight by the line ministry | 0 | 0 | N/A | N/A |  |  |  | 30% |  |
| Percentage of laws which are harmonised with the Law on Public Administration | 66.7% | 83.3% | 83.3% | 100% |  |  |  | 95% |  |
| OPERATIONAL OBJECTIVE 1.2 |  | Paperless administration |  |  |  |  |  |  |  |  |
| INDICATOR |  | BASELINE VALUE | VALUE FOR 2022 | VALUE FOR 2023 |  | VALUE FOR 2024 |  | TREND |  | TARGET VALUE BY 2024 |
| Percentage of state authorities which have established electronic document management system |  | 38% | 40% | 38% |  | 55% |  |  |  | 50% |
| Percentage of state authorities performing fully electronic exchange (externally) of documents via eDMS |  | 0 | 1.29% | 0 |  | 0% |  |  |  | 20% |

| OPERATIONAL OBJECTIVE 1.3 | Strengthening functional and financially independent municipalities to ensure more equal development of all LSGUs |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | BASELINE VALUE | VALUE FOR 2022 | VALUE FOR 2023 | VALUE FOR 2024 | TREND | TARGET VALUE BY 2024 |
| Number of tasks involving inter-municipal cooperation | 20 | N/A | N/A | 31 |  | 24 |
| Ratio of debt to their total revenue (at the level of all municipalities) | 33.5% | 28.28% | 22.2% | N/A |  | 32% |

ACHIEVEMENTS

- The conditions have been created to strengthen the legal security of the subjects of Inspectorial Oversight, as well as all citizens, by building mechanisms that will ensure comprehensive, uniform, proportionate and efficient behavior of inspectors, professionalism and quality of work of inspection authorities, through the adoption of amendments to the Law on Inspectorial Oversight.

- The Government approved the Proposal Law on Amendments to the Law on Administrative Dispute. The proposal law amends the requirements of holding an oral hearing (Article 14) and costs of litigation (Article 20).

- The Report of the Protector of Property and Legal Interests has been improved with an assessment of the situation and recommendations for improving the work of those bodies that are recognised for the largest number of cases before the courts.

- To modernise public administration, increase efficiency and speed up work processes, as well as strengthen flexibility, transparency and data security, a new Information System for electronic document management (eDMS) and management of the process of electronic Government sessions (eSV) was established.

- In 2024, 439 users of the eDMS system were trained. Trainings were held for enrollment officers, eSV administrators, trainers and application administrators.

IMPLEMENTATION IN PROGRESS

- As regards systematic regulation of all issues of importance for the organisation and functioning of the Government, in mid-June 2022, the Working Body drafted the Draft Law on the Government. The draft was harmonised with the comments of SIGMA and the Venice Commission, which gave a positive assessment with suggestions and recommendations for improvement. The text of the Law was harmonised with the GRECO recommendations and sent back to the European Commission for its opinion.

- A major step forward in the field of public administration organisation is the fact that the interdepartmental working group started work on the Draft Law on Public Institutions on the basis of the Analysis with identified challenges and recommendations on the need to establish a normative framework for public institutions

- Based on the conclusions of the Analysis of the functioning of local self-government, the Draft Law on Local Self-Government was prepared, which is expected to be adopted in Q1 2025. The Draft Law went through an inclusive process of public discussion that included all relevant stakeholders from the local self-government level, the Association of Municipalities of Montenegro, experts from the State Audit Institution, the Ombudsman, the Administrative Court of Montenegro, as well as the non-governmental sector and the academic community. The Draft Law is currently undergoing harmonisation within the Secretariat for Legislation and is anticipated to receive approval from the Government of Montenegro in the near future.

- By establishing the Registry of  State authorities and Institutions at the state and local levels, citizens, bodies and institutions, the private and public sector, the academic community and researchers are given access to numerous data on bodies and institutions. The register is functional at the central level. The process of entering data by local self-governments is ongoing.

- The report on handling of administrative matters at the central level for the year 2023 is in the final stage and is expected to be available soon. The process of collecting data for the preparation of this report for the year 2024 has begun, also at the central level. After the adoption of a new methodology, which was done in cooperation with SIGMA experts, the report focuses on individual administrative procedures, which enables a more precise analysis of data and the formulation of recommendations. The report for the year 2022 could not be prepared at the central level, since as much as 41 authorities failed to submit any data on the state of administrative matters, due to a cyber attack on the Government’s IT infrastructure.

- The Draft Law on Management and Internal Controls in the Public Sector is harmonised with the comments of the European Commission.

- The development of the Methodology for the Development of the Gender Equality Plan in all Ministries was initiated through the “United in Gender Equality” project implemented by UNDP and will be addressed by the Action Plan for 2025-2026.

- In the course of the public discussion on the Law on Local Self-Government, a proposal was put forth to the Ministry of Public Administration by all local self-government units, the Union of Municipalities, and the Union of the Administration and the Judiciary, advocating for the regulation of the civil service system at the local level through a distinct law. After analysing the submitted proposals and explanations, with consultations with experts, by forming a working body, the Ministry started work on the Law on Local Civil Servants and State Employees.

- In 2024, the implementation of the “Municipalities for the EU” project began,  which aims to build the capacity of local authorities to face challenges related to the EU acquis and accession reforms. It is necessary to ensure that local governments are equipped with the necessary institutional, financial and human resources for the effective implementation of EU policies and standards at the local level.

- “Conducting e-Government Assessment in Local Self-Governments in Montenegro” project, funded by the EU, has begun. During the designated timeframe, the groundwork for evaluating e-Government commenced, encompassing a thorough examination of the institutional, organisational, regulatory, technical, and administrative capacities of local self-governments. This effort aims to deliver an extensive insight into the preparedness and necessary resources for delivering high-quality e-Government services to both citizens and the business community.  Following the evaluation, the initiative is anticipated to progress with tangible assistance for digital transformation in six local self-governing bodies.

CHALLENGES

- Solving the issue of abuse of the right to free access to information is a prerequisite for speeding up the proceedings of the Administrative Court. It is expected that this challenge will be addressed by the adoption of the new Law on Free Access to Information, as well as amendments to the Law on Administrative Dispute.

- Improving the transparency of the work of the Administrative Inspectorate is a challenge that will be addressed by the new Action Plan.

- The improvement of the Analysis of the impact of the proposed organisational changes with a focus on the justification of the establishment of new authorities or mergers/abolitions will be recognised by a new action document.

- The development of the Methodology for the development of the work programme of state administration bodies with indicators of the performance of the bodies and the development of the Methodology for the preparation of reports on the work of the bodies with reference to the realisation of goals and performance indicators, as well as the organisation of trainings for the application of these methodologies, will be realised through activity 5.1.1 “Development of an amended methodology for medium-term planning of the work of the Government and ministries” and will be recognised by a new action document for the period 2025-2026.

- The development of a platform of institutions that reflect commitment to the affirmation of human rights, gender equality, the richness of diversity and the importance of inclusiveness will be recognized in the new Action Plan 2025-2026.

- Given that the integration of eDMS with other information systems is a key step towards achieving the digital transformation of public administration and public services; significant challenges on the way to this goal are the unwillingness of institutions to adapt their internal procedures to the electronic way of doing business, the lack of technical prerequisites for establishing the system, as well as the resistance of employees to changing established work practices.

- The introduction of eDMS at the local level, in municipalities where there is no system for electronic document management, remains a challenge for the next period, and will be the main topic of the above-mentioned project, which is implemented in cooperation with UNOPS.

- The activity related to raising the capacity of Representatives of Property and Legal Interests of Local Self-Government Units has not been implemented. This challenge will be targeted by the new Action Plan for the period 2025-2026.

- There is significant room for improving coordination and data exchange between central and local authorities, especially as regards the consultation mechanism of local authorities in the preparation of public policies, which is often missing. Solving this challenge requires a systemic, horisontal approach, which first of all implies a higher level of digitisation of systems and services, both at the local and central levels.

II CITIZENS AND BUSINESSES USE HIGH-QUALITY SERVICES OF THE PUBLIC ADMINISTRATION

During the reporting period, significant progress was made in the implementation of measures that contribute to the modernisation of public administration and the improvement of the quality of its services. Special focus was on improving the quality management system, increasing the number of digitised services, establishing secure platforms for electronic data exchange and raising citizens’ awareness of the benefits of digital services.

The concept of quality management in public administration enables constant improvement of the work of institutions, which results in better satisfaction of service users, optimal use of resources and reduces the possibility of errors and abuses. By introducing quality standards, the public administration can better monitor and evaluate its effectiveness, thereby strengthening citizens’ trust. In this regard, the positive trend of indicators related to the introduction of quality management systems in public administration bodies is of particular importance.

Also, the growth of the citizens’ satisfaction index with public services (Balkan barometer) further supports the thesis that the development of services is moving in the right direction.

The new eGovernment Portal will additionally contribute to the modernisation of public administration, increase efficiency in service provision and strengthen citizens’ trust in institutions. The number of digitised services available on this portal is growing significantly.

However, as regards the indicator that measures the percentage of electronically submitted applications in relation to the total number of applications submitted by users for the use of the pilot service, of the planned 4 pilot services (eJob, eStudent, eProfessional exam and eNGO), it is possible to report only for the eStudent service (electronically submitted applications for admission to faculties), where the value of the indicator remained unchanged in relation to 2023. The fact that the remaining pilot services (eJob, eProfessional exam) have not been developed, that is, they are at the very beginning of their functionality (eNGO), is an incentive for all involved institutions to contribute to a faster and more efficient development of services for citizens.

The SISEDE platform (Single information system for the electronic data exchange) provides communication between existing information systems and registriess and a faster exchange of information between citizens and the administration, enabling the automated exchange and use of large amounts of data from state registries; thus the provision of services electronically has been significantly improved. Although the indicator measured by electronically connected registries in metaregistry remains unchanged, the platform is expanding to additional institutions and registers, which will cover an even wider range of services and enable faster and more efficient data exchange.

The following is a tabular overview of the performance indicators:

| OPERATIONAL OBJECTIVE 2.1 | Efficient service delivery and introduction of service delivery quality management |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | BASELINE VALUE | VALUE FOR 2022 | VALUE FOR 2023 | VALUE FOR 2024 | TREND | TARGET VALUE BY 2024 |
| Number of institutions with introduced quality management system | 0 | 1 | 1 | 15 |  | 5 |
| Citizens’ satisfaction with public services (Balkan barometer) | 2.9 | 3 | 2.8 | 4 |  | 3.5 |
| Percentage of administrative acts cancelled by the Administrative Court | 20.33% | 28% | N/A | N/A |  | 20% |

| OPERATIONAL OBJECTIVE 2.2 | Full interoperability of information systems and increased number of electronic services with high level of sophistication |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | BASELINE VALUE | VALUE FOR 2022 | VALUE FOR 2023 | VALUE FOR 2024 | TREND | TARGET VALUE BY 2024 |
| Number of digitalised services on a single portal in areas defined in line with EU methodology “eGovernment Benchmark” | 0 (2020) | 0 | 0 | 32 |  | 10 digitised services on a single portal |
| Percentage of electronically submitted requests compared to the total number of requests submitted by users for pilot service use | 0 | 85.3 | 86.14% | 86.14% |  | 15% per pilot service |
| Number of electronic exchanges from registries in metaregistry | 8 (2021) | 12 | 16 | 16 |  | 30 |

ACHIEVEMENTS

- In July 2014, the Government adopted Quality Management Roadmap for the public administration of Montenegro with a promotion plan for the period 2024-2026.

- The Ministry of Public Administration concluded the evaluation procedure in 2024, and the institution was awarded the CAF Effective User certificate based on the evaluator’s assessment and report. The Ministry of Public Administration is the first organisation in Montenegro to achieve this certification.

- In the Ministry of Public Administration, the Institute for Metrology, and the Municipality of Zeta, a thorough examination of the work process was conducted using the CAF self-assessment model, leading to the identification of recommendations that are being executed through improvement plans. This analysis facilitated the recognition of crucial aspects for enhancing services aimed at citizens by means of improved regulation, process modernisation, digital transformation, and the advancement of human resources.

- The Ministry of Public Administration, alongside representatives from various institutions, has outlined the business processes related to the services overseen by the ministries. In this context, during the prior period, a total of 10 Guides on administrative procedures were developed. Guides have been released from the expertise of the Ministry of Public Administration and the Ministry of Sports and Youth. The remaining eight guides are set to be released soon, specifically for the Ministry of Energy, the Ministry of European Affairs, the Ministry of Culture and Media, the Ministry of Human and Minority Rights, the Ministry of Labour, Employment and Social Dialogue, the Ministry of Regional Investment Development and Cooperation with NGOs, the Ministry of Social Welfare, Family Care and Demography, and the Ministry of Tourism.

- At the conclusion of 2024, a finalised solution for the certification body (GovME CA) was established, facilitating the generation of secure electronic signatures to enhance the digitisation of services. This infrastructure plays a crucial role in ensuring the security and safeguarding of data during the digital transformation of public administration, and it is linked to the eDMS and eSV system.The quantity of administrative fees and charges eligible for payment via the national system for electronic billing and collection control (NS NAT) has been expanded.

- The eGovernment portal is nearing completion, with a launch scheduled for March 2025.

603 administrative fees/taxes are eligible for payment electronically starting today. The Ministry of Public Administration continues to facilitate transactions for both citizens and businesses using digital tools.

Marash Dukaj

Minister

Eplacanje.gov.me

To solve the persisting challenge in the process of establishing full interoperability, the Ministry of Public Administration implemented platforms aimed at enhancing digitalisation and automation of business processes (IBM-BPM Platform) and facilitating data integration (X-Road Platform) throughout 2024.  The IBM-BMP platform empowers institutions to autonomously develop intricate electronic services for both citizens and the economy. The X-Road platform signifies progress in achieving interoperability, facilitating secure data exchange among the information systems of various organisations.

- In February 2025, the Plan for the comprehensive rollout of transactional public electronic services at both national and local levels for the years 2025-2027 was approved. The digitisation service plan outlines a total of 57 services scheduled for rollout in 2025, followed by 70 services in 2026, and 35 services set for 2027.

- A promotional video for eGovernment has been released on the MPA YouTube channel, aimed at enhancing citizens’ understanding of digital services.

IMPLEMENTATION IN PROGRESS

- The Quality Management Network is in progress - a registry of institutions that use some of the quality management standards has been created and contact persons have been identified.

- Mapping work processes to enhance efficiency and establish a management system is achieved through the application of the CAF self-assessment model, alongside globally acknowledged quality standards (ISO:9001).

- The ongoing expansion of the SISEDE platform to more institutions and registries aims to encompass a broader array of services, facilitating quicker and more efficient data exchange. This platform currently comprises 23 institutions, with 57 registries officially recorded in metaregistry.  In 2024, over 9 million inquiries were processed via the SISEDE platform, enhancing the efficiency and transparency of public institutions’ operations.

- The Capital City of Podgorica showcases a commendable application of the SISEDE System, reflecting a notable rise in inquiries by 400,000 in comparison to 2023. The integration of additional local self-government units is currently in progress.

- Anticipations indicate that 32 services are set to be implemented on the eGovernment Portal, encompassing offerings associated with NGOs, the Ministry of Culture and Media, and the Directorate for Diaspora.

CHALLENGES

- The initiative to create a methodology for implementing quality management within the public administration system has been discontinued. To achieve this goal, the CAF manual 2020 and ISO 9001:2015 standards serve as guides for implementing quality management standards.

- In the realm of public administration, there exists a notable lack of understanding regarding the advantages of implementing a quality management system.  A significant number of institutions fail to acknowledge the advantages of these models in enhancing work efficiency and user experience. Furthermore, there exists a lack of understanding and expertise within the institutions concerning the execution of the quality system. The obstacles to putting this principle into practice are related to financial constraints and limitations in staffing.

- In relation to the digitisation of services for citizens and the businesses, enhancing the technical and personnel capacities of institutions is essential to guarantee their complete integration into digital systems. Furthermore, it is essential to persist in educating and increasing awareness regarding the benefits of electronic services, targeting both the general public and public administration employees.

- The Implementation Plan for Transactional Public Electronic Services 2025-2027 highlights several critical challenges hindering the advancement of sophisticated services. These include outdated software solutions, the absence of system integration (with over 100 systems in public administration), inadequate infrastructure, and lack of internal resources and reliance on external suppliers for digital service development.

- The persistent lack of digital skills among public administration employees and citizens poses a significant barrier to digital transformation, necessitating systemic interventions through investments in education and infrastructure.

- A significant obstacle that hinders the utilisation of the current SISEDE system is the insufficient collaboration among institutions.

- There is a lack of acknowledgment regarding the importance of professional education in IT audit among stakeholders, coupled with a low level of awareness among authorities about the necessity of implementing effective internal IT controls.

- Additionally, the management of IT risks by authorities is inadequate, complicating the planning of audit engagements.

III PROFESSIONAL PUBLIC ADMINISTRATION

Under the strategic goal of “Professional Public Administration,” a set of indicators has been established to assess progress towards developing a citizen-oriented professional, accountable, and efficient public administration. The fundamental principles for achieving this objective involve improved planning within public administration and the application of merit-based criteria in the recruitment and compensation of officials. Furthermore, ongoing professional development for employees should empower officials to enhance their skills and knowledge while also adapting to the evolving challenges and needs of the public. Consequently, allocating resources towards civil servants translates to enhanced services for the public and a stronger economy.

The progress in personnel planning is evaluated based on the proportion of enhanced HR plans that have been developed and approved by state authorities, specifically local self-government bodies. Following the restructuring of the public administration, 14 state authorities failed to implement a HR plan, resulting in a minor decrease in two indicators compared to 2023. The circumstances for local self-government bodies remain unchanged; they continue to neither formulate nor approve HR plans.

Furthermore, the metrics assessed by the average number of candidates responding to job postings and competitions within the Human Resources Administration are experiencing a downturn. This trend indicates that the existing framework and methodology have failed to achieve the intended level of competitiveness, highlighting barriers that are steering this process towards outcomes that fall short of expectations. This decline highlights the necessity for further analyses and modifications within the employment framework to foster an environment conducive to attracting highly qualified talent and enhancing competitiveness.

The professionalisation of officials hinges significantly on the implementation of a fair and merit-based evaluation system for their performance. The relevant indicator shows a notable growth trend compared to 2023, yet it has not achieved the target value. The relevant metric, assessing the proportion of officials promoted according to their grades and performance, remains constant, as the data for 2024 has not yet been released.

Source: Report on the work of the Human Resources Administration for 2023

The increasing strategic planning of trainings by state authorities and local self-government bodies, along with the rising percentage of newly employed officers receiving training in their first year, suggests that these efforts have yielded positive outcomes. It is essential to maintain a continuous commitment to ensuring that the professional development of officers remains a priority for both state and local authorities.

Indicator

Within the PAR Strategy 2022-2026, the ratio of employees in public administration at both central and local levels to the total number of employees indicator, is monitored.

The assessment of employee satisfaction follows a cyclical approach, with surveys conducted at both central and local levels alternating over a two-year period. In 2023, the survey was conducted at the central level across 40 authorities, whereas in 2024, the assessment of satisfaction was extended to all local self-government units, indicating that this indicator has been addressed.  Nonetheless, the survey’s acquisition of 28.8% valid responses from local self-government units adds a layer of complexity to the interpretation of the results. This suggests that assessing employee satisfaction is a multifaceted endeavor that will necessitate focused attention moving forward.

The ratio of employees in public administration at both central and local levels to the total number of employees in Montenegro

Established value

Projected value PAR strategy

The ratio of employees in public administration at both central and local levels to the total number of employees in Montenegro

Total employees in public administration

Total employees in Montenegro

The strategy for reforming public administration aims to outline essential work processes, assess efficiency, and evaluate employee numbers by conducting functional analyses of institutions. It will also identify necessary organisational, personnel, and other changes based on the findings from these analyses. Nevertheless, given the substantial organisational changes within the public administration since 2022, the functional analyses have yet to be finalised, resulting in the value of this indicator remaining static.

The indicator that measures the ratio of employees in public administration at both central and local levels to the total number of employees is crucial for achieving optimal public administration. This ratio has been consistently declining since 2022. The value for 2024 is still under the target, suggesting that this indicator has been achieved to a satisfactory degree.

Presented here is a comprehensive table detailing the performance metrics:

| OPERATIONAL OBJECTIVE 3.1 | Efficient HR planning system based on identified needs, depoliticisation and improving human resources recruitment procedure and further digitalisation of civil service system; |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | BASELINE VALUE | VALUE FOR 2022 | VALUE FOR 2023 | VALUE FOR 2024 | TREND | TARGET VALUE BY 2024 |
| Percentage of authorities which developed their HR plan with improved quality through CPR Percentage of local self-government authorities and services at the local level which developed their HR plans through CPR in accordance with the LCSSE and in accordance with the Law on Local Self Government | 28.5% of state authorities (2021) 0% of local government bodies and services (2021) | 82% of state authorities 0% | 92% of state authorities 0% | 86% of state authorities 0% |  | 30% of local government bodies and services |
| Percentage of public institutions with adopted HR plan | 0 | 0 | 0 | 0 |  | Establishing a baseline |
| Percentage of HR plans adopted by state authorities and local self-government authorities | 63% of HR plans of state authorities 37% of HR plans of local government bodies (2020) | 82% of HR plans of state authorities 63% of HR plans of local government bodies | 92% of state authorities | 86% of state authorities N/A |  | 100% of HR plans of state authorities and local government bodies |
| Average number of candidates per notice | Internal notice 1.1 Public notice 4.8 (2020) | Internal notice 2.1 Public notice 6.9 | Internal notice - 1.92 Public notice – 11.51 | Internal notice - 0.54 Public notice -4.37 |  | Internal notice -1.6 Public notice - 5 |
| Average number of candidates per competition | 2.14 (2020) | 2.46 | 3.14 | 1.68 |  | 4 candidates |
| Number of HR functions where records are kept through HRIS alone | 0 | 3 | 3 | N/A |  | 3 records |
| Percentage of local self-governments with developed HRIS | 0 | 0 | 0 | 0 |  | 30% |

| OPERATIONAL OBJECTIVE 3.2 | Public administration attractive employer – efficient system of assessment, promotion and rewarding based on merits and continuous development |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | BASELINE VALUE | VALUE FOR 2022 | VALUE FOR 2023 | VALUE FOR 2024 | TREND | TARGET VALUE BY 2024 |
| Percentage of assessed civil servants in state authorities | 63.38% (2019) | 46.6% | 29% | 54.09% |  | 100% |
| Percentage of civil servants promoted or rewarded based on their performance assessment | 0 | 0.01% | N/A | N/A |  | 10% |
| Percentage of state authorities, state administration authorities and local self-government units with strategic training planning | State authorities, public administration bodies and local self-government units do not strategically plan training | 29% of state authorities strategically plan trainings 16% of local self-government units strategically plan trainings | 29.5% of state authorities strategically plan trainings 68% of local self-government units strategically plan trainings | 63% of state authorities strategically plan trainings; 32% of local governments |  | 50% |
| Percentage of new civil servants who were trained during their first year of work at initial positions of civil servant posts | Established training programme for new employees | 2 training cycles implemented | 4.2% | 10.7% |  | 50% |
| Percentage of institutions measuring satisfaction of state level civil servants and local level civil servants | 0% | 0% | 40 bodies included in the research | All local self-government units included in the survey |  | 50% of state administration bodies |

| OPERATIONAL OBJECTIVE 3.3 | Optimal public administration |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | BASELINE VALUE | VALUE FOR 2022 | VALUE FOR 2023 | VALUE FOR 2024 | TREND | TARGET VALUE BY 2024 |
| Number of institutions with amended organisational and functional structure based on functional analyses recommendations | 0 | 0 | 0 | 0 |  | The value will be established after functional analyses |
| Share of the total number of employees at the central and the local level in the total number of employees in Montenegro | 26% | 23% | 21.7% | 21.1% |  | 23.7% |

ACHIEVEMENTS

- After coordination with the European Commission, the Government approved the Draft Law on Amendments to the Law on Civil Servants and State Employees. Professionalisation, meritocracy and depoliticisation are the main goals of the changes to the Law.

- The activity concerning the improvement of the skills of the officials responsible for the development of the innovative HR plan was successfully implemented.

- The Human Resources Administration has prepared the Methodology for surveying employee satisfaction in state authorities and local self-government bodies. The Administration informed the Government of Montenegro about the results of these researches, as well as the proposed measures, such as the adoption of individual action documents with the aim of achieving a higher degree of satisfaction among civil servants and local and state employees.

- Employee satisfaction measurement has been put into practice across all local government units.

- In an effort to enhance the professional growth of civil servants moving forward, the Human Resources Administration has updated the assessment system and released a comprehensive Manual for the evaluation, monitoring of work, and professional growth of civil servants and state employees, which includes special training plans as an added incentive.

- The e-application for My personal file has been enhanced, providing a platform for all civil servants and state employees to access their recorded information, apply for training opportunities, and review the training sessions they have participated in.

- Twenty employees of the Ministry of Public Administration have successfully completed training in ICT project management.

- Regular publications provide data on the number of employees in public administration at both the central and local levels.

- Supervision of the implementation of contracts related to temporary and occassional employment has been enhanced by establishing a dedicated Commission tasked with analysing and monitoring service contracts as well as contracts for temporary and ocassional employment within consumer units funded by the state budget.

- The programme for newly appointed officials is operating effectively, with a total of 73 participants in 2024, comprising 58 female participants and 15 male participants.

- To tackle the issue of staff training for upcoming roles of IT engineers in public administration, the University of Montenegro successfully accredited the Master’s study programme in Information Security at the Institute for Interdisciplinary and Multidisciplinary Studies in 2024. This programme comprises an academic study curriculum totaling 120 ECTS credits. Instruction will be conducted in English. Upon completing the studies, the designation obtained is Master - Information Security.

IMPLEMENTATION IN PROGRESS

- The implementation of the Competency Framework is anticipated in the second quarter of 2025. The implementation of the Competency Framework across all categories of civil servants guarantees that employees have the precise skills and abilities required to effectively carry out their responsibilities during recruitment and assessment processes. This structured method allows for improved alignment of jobs with requirements, which directly aids in the more effective realisation of strategic objectives, enhancing public administration and establishing a basis for a more transparent and accountable governance.

- To enhance the civil service framework at the local level, and drawing from the findings of the Analysis regarding the operation of the local self-government system, a Working Group has been established to develop the legislation concerning local civil servants and state employees.

- The integration of HR Plans with the Budget has been achieved by updating the Guidelines for their preparation. The revisions to the 2019 guidelines now include a directive that drafts of HR Plans should be developed concurrently with the proposal for the Budget Law for the relevant year in which the HR Plan is implemented. The guidelines can be found on the Human Resources Administration’s website.

- To enhance the selection process for registered candidates within the Human Resources Administration, an updated concept of the Regulation on the verification of knowledge, abilities, and competencies has been developed, alongside a technical concept for the electronic application system for candidates - the tender procedure has commenced.

- To enhance the quality of the Internal Organisation Act, efforts commenced on developing job catalogues, an analysis of existing job descriptions was conducted, and two workshops took place with representatives from state authorities.

- To enhance the HR function across all tiers of administrative management, initiatives commenced on creating an application solution for managing the Human Resources Network via the HRIS.

- The Human Resources Administration is persistently engaged in enhancing and updating the Information System for the electronic assessment of candidates. Starting in February 2025, individuals will have the opportunity to access the results of the aptitude assessment and the selection list via this system. They will also be able to track their status and receive prompt updates regarding the results of the evaluation process.

- Initiatives within the Training Programme aimed at developing essential skills related to gender equality have commenced, focusing on the education of both male and female trainers in this area. The initiative is carried out under the project “United in Gender Equality,” which is executed by UNDP and funded by the European Union.

- The initiation of the Ready4EU training programme, executed in collaboration with the HRA, Ministry of European Affairs, the Ministry of Public Administration, and ReSPA, has commenced. The training programmes are structured to equip civil servants for their roles within the institutions of the European Union.

- The Human Resources Administration consistently executes over 20 diverse training initiatives, encompassing general, specialised, and accredited programmes.

- Amendments to the Law on Public Sector Salaries and Labour Law are in progress. The Law on Public Sector Salaries must tackle the current condition of the salary framework, which has been adversely affected by various collective agreements, resulting in significant disparities within that framework. The Labour Law ought to incorporate modifications in the personnel planning of budget-funded institutions.

CHALLENGES

- The advancement of officials’ professional skills through the creation of an effective online learning platform continues to pose a challenge, which will be tackled by a forthcoming action document, as the ILIAS platform is currently inactive. Furthermore, the circumstances regarding the advancement of the internal mobility module for officials remain unchanged.

- To effectively carry out the Analysis of Human Resources Units Operations, it is essential to first establish the Methodology for conducting the analysis for human resources units operations.

- A number of trainings within the Human Resources Administration were not carried out as planned in the Action Plan, owing to various technical and organisational challenges. The ongoing challenge of insufficient staffing is a recurring concern highlighted by the Human Resources Administration.

- The initial phase of the analysis regarding HR policy and the employment process within Montenegro’s health system has been completed only. The undertaking of thorough functional assessments within the sector continues to pose a systemic challenge for the upcoming period.

- Enhancing the digital competencies of personnel within public administration poses a horisontal challenge for achieving the strategic objectives of reform in this sector.

IV TRANSPARENT AND OPEN PUBLIC ADMINISTRATION

The fourth strategic goal focuses on enhancing the transparency and openness of public administration to citizens. The objective is to enhance the operations of the Agency for Personal Data Protection and Free Access to Information, while also improving the overall legal protection framework concerning free access to information (FAI). The objective is also to enhance the enforcement of the LFAI by the relevant authorities, ensuring the proper exercise of the right to access information and facilitating access to that information in line with the current institutional and legal framework. Furthermore, there are intentions to enhance awareness and develop the competencies of users of the LFAI, alongside efforts to boost the reuse of information and increase the accessibility of open data.

Significant advancements have been made towards enhancing the effectiveness of the legal protection framework in the realm of FAI, as well as bolstering the capabilities of the Agency Agency for Personal Data Protection and Free Access to Information. The proportion of decisions annulled by the Administrative Court concerning the total judgements in administrative disputes linked to the Agency’s decisions has fallen to 1.43%. Nonetheless, the difficulty in this domain is highlighted by the unfavorable trajectory of the metric, which is assessed by the proportion of rulings from the Administrative Court in administrative disputes arising from the Agency’s failure to issue a decision. There is a noticeable rise to 87%, with 26.2% of cases resulting in a directive for the Agency’s Council to render a decision, while in 73.8% of instances, the Agency’s Council did reach a decision, leading to the suspension of proceedings by the Administrative Court of Montenegro. The count of authorities submitting requests for access to information in the information system has remained consistent with the previous reporting period, totaling 1,475.

Nonetheless, efforts to enhance the enforcement of the LFAI by those responsible for its implementation and to bolster the capacity of law users have led to significant progress in ensuring the proper realisation of the right to access information. The advancement is indicated by the reduction in the proportion of annulled decisions made by the Agency compared to the overall number of appeals, with a noted decline in this metric to 15.49%. The Agency has annulled 1,041 decisions made by authorities from a total of 6,717 cases that were resolved.

The issue at hand is the unfavorable trend of the indicator, which is assessed by the proportion of upheld appeals resulting from the administration’s silence compared to the total number of appeals. Notably, there has been a significant rise to 35.34%, translating to 2,374 upheld appeals due to the administration’s silence out of a total of 6,717 decided cases.

To enhance the reuse of information and boost the availability of open data, efforts were undertaken to improve legislation and practices in this domain.

The Law on Free Access to Information (LFAI) was adopted and new Open Data Portal was established, which commenced operations on December 15, 2024.

Notable advancements have been achieved regarding the accessibility of open data, reflected in the rise of datasets on the Open Data Portal (http://www.data.gov.me) to a total of 456.

Published: December 16, 2024 12:33 p.m.

Author: Ministry of Public Administration

Dukaj – New Open Data Portal launched

The newly launched Open Data Portal offers advantages not just for the general public, but also for the IT sector, business representatives, academic institutions, NGOs, and the media. Data that is published proactively ought to be readily available and machine-readable to enhance business efficiency and improve quality of life through their merger and reuse. Additionally, 36 FAI institutions publish data on this Portal, as evidenced by the upward trend of the indicator at 2.18%. Nonetheless, a challenge exists regarding the quantity of high-value datasets with FAI made available through the Portal.

In the realm of oversight, a total of 85 inspections were conducted in 2024 across various entities, such as ministries, local governments, and public institutions, focusing on the proactive dissemination of information and adherence to the Law on Free Access to Information. There was a noticeable enhancement in the proactive dissemination of information aligned with established standards, making it easier for citizens, NGOs, and the economic sector to access relevant data. Nonetheless, some authorities failed to disclose all the information required by the Law, and they were instructed to rectify the noted discrepancies within a specified timeframe. The Agency refrained from filing any misdemeanor charges during the designated timeframe; however, its inspections played a pivotal role in enhancing transparency and ensuring the public had greater access to information.

The following is a tabular presentation of the performance indicators:

| OPERATIONAL OBJECTIVE 4.2 | Improvement of the application of the FAI Law by those obliged to apply the Law and strengthening of the capacities of the users of the Law with a view to ensuring adequate exercise of the access to information right |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | BASELINE VALUE | VALUE FOR 2022 | VALUE FOR 2023 | VALUE FOR 2024 | TREND | TARGET VALUE BY 2024 |
| Share of upheld appeals against administrative silence in relation to the total number of appeals | 23.15% (2020) | 23.5% | 29.5% | 35.34% |  | 15% |
| Share of decisions of the authorities annulled by the Agency in relation to the total number of appeals | 53.19% (2020) | 38% | 26.36% | 15.49% |  | 45% |

| OPERATIONAL OBJECTIVE 4.3 | Improvement of information reuse and increasing the availability of open data |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | BASELINE VALUE | VALUE FOR 2022 | VALUE FOR 2023 | VALUE FOR 2024 | TREND | TARGET VALUE BY 2024 |
| Number of datasets on the Open Data Portal www.data.gov.me | 146 (2021) | 197 | 0 | 456 |  | 500 |
| Number of institutions publishing the data on the Open Data Portal | 1.5% of institutions subject to FAI | 1.5% | 0 | 2.18% |  | 10% of institutions subject to FAI |
| Number of published high-value datasets with APIs on the Open Data Portal | 0 | 0 | 0 | N/A |  | At least 10 |
| Share of authorities which publish proactively the information in line with the FAI Law | The baseline value will be determined based on the APDPFAI Work Report in March 2021 | The baseline value will be determined in 2023 for all ministries, GSG, CC Podgorica, municipalities of Nikšić and Herceg Novi | 47 inspections of 47 subjects of application | 85 inspections |  | 65% of ministries and other (selected) administrative bodies 65% of local governments |

ACHIEVEMENTS

- New Law on Free Access to Information (LFAI) was established by the Government of Montenegro on December 13, 2024 with the aim of improving the availability of data for the general public and harmonising it with European standards. By adopting the new Law, the goal is to solve the problems that were recognised in practice during the period of application of the current LFAI.

- With the support of SIGMA, an Analysis of the appeal procedure and other procedures carried out by APDPFAI was prepared.

- With the aim of strengthening the capacity of APDPFAI, 8 people were employed. Special training of the Council of Europe was conducted in November 2024.

OPEN DATA PORATAL

Focal point of access for public sector data in an open format, and a place to interact with data users, business sector, IT community and other stakeholders.

A training plan was developed within the HRA General Training Programme. In 2024, 120 participants attended training on free access to information. Together with the previous period, the total number of participants on this topic is 306.

- Four employees from the APDPFAI completed trainer training for the application of LFAI through an abbreviated programme. In 2024, two iterations of the Training of Trainers programme (TOT) took place, with a total of 27 participants involved.

- In order to assist authorised individuals within the authorities, a network of these persons has been established, facilitating daily communication through a Viber channel. Additionally, meetings for the exchange of information among authorised officials from the ministries were conducted.

- The Open Data Portal commenced its operations on December 15, 2024.  The Ministry of Public Administration has developed the new Open Data Portal, with assistance from EU and UNDP offices in Montenegro as part of the collaborative project, “E-services and digital infrastructure as a measure of response to COVID-19.” The framework for the creation of the new Open Data Portal has been established, and all subsequent required processes have been carried out in line with UNDP standards. In this context, we have met another requirement for advancing the democratisation of the whole society.

- Activities were conducted to enhance the Portal by identifying and revising previously published data sets, ensuring their accuracy, relevance, and availability. More than 450 datasets in an accessible format can be found on the Portal.

- A two-day training session for administrators of the Open Data Portal was conducted by the Ministry of Public Administration in collaboration with ReSPA. Oscar Corcho, a full professor at the University of Madrid, addressed the participants regarding the significance of open data. To bring the Open Data Portal into reality, it is essential that information is clear and readily available. Representatives from various ministries, administrations, agencies, and institutes participated in the training.

- The initiation of the co-creation process for the National Action Plan for Open Government Partnership for the period 2026-2029 has begun. The initiation of this process was marked by the release of the suggested Calendar for the preparation of the NAP 2026-2029, which allows for the active involvement of all pertinent stakeholders and promotes an inclusive dialogue.

IMPLEMENTATION IN PROGRESS

- Currently, an analysis of the APDPFAI information system is in progress. A data entry plan will be established in relation to the release of government data in an open format, as outlined in a forthcoming action document.

- The ongoing enhancement of APDPFAI is achieved with the assistance of SIGMA. A round table was convened to discuss strategies for addressing current obstacles in accessing public information.

- APDPFAI consistently enhances user experience by providing better access to information for citizens via the website. A Manual has been developed for the proactive dissemination of data on the websites of entities required to adhere to the Law, along with a self-assessment questionnaire to evaluate the compliance of authorities in meeting the obligations set forth by the LFAI.

- The arrangement of educational initiatives for primary authorities, with the highest volume of requests for free access to information, is currently in progress. A workshop was conducted in collaboration with SIGMA for school secretaries and directors, acknowledging the heightened volume of requests that schools are experiencing.

- A Draft Manual for information officers in authorities has been created and will be accessible on the Agency’s website following verification. Nonetheless, the recognition for the most proactive authority has yet to be established, with plans for its implementation set for 2026.

CHALLENGES

- The connection between the appeal procedure and the relevant section of the IT system was not achieved due to missing funds.

- The formation of the FAI Council.

- The objectives of the APDPFAI Communication Strategy were not fulfilled, leading to the discontinuation of this initiative.

- The enhancement of the methodology for the yearly submission of APDPFAI to the Parliament has been discontinued, as the reporting format is mandated by legislation.

- Creating a decision search engine for FAI Agency and courts.

- Strategic plan for identifying target users and establishing partnerships.

- The assessment indicates that creating working groups for LFAI at the authority level is deemed unnecessary. The implementation of this activity will occur via the establishment of the FAI Council.

- A Quality Management Model in FAI area for state authorities which includes a self-evaluation component, an action plan, and training initiatives for staff should be planned for the upcoming Strategy implementation period.

- Development of robust fiscal transparency for authorities, by formulating a plan to enhance budget transparency in alignment with global and regional standards.

- Identifying high-value open data sets through pilot initiatives in crucial sectors like public finance, geo-location, health, and transport, while also launching a campaign to highlight the significance of open data.

- Enhancing the awareness of public administration entities regarding the dissemination of information related to gender equality on the Open Data Portal.

V POLICY PLANNING WITH AND FOR CITIZENS

The execution of the fifth strategic goal enhances the quality of public policies, guaranteeing their transparency and foundation on analytical data. The primary emphasis is on enhancing the consultative process and aligning medium-term budget planning with strategic planning and sectoral policies by creating a cohesive strategic management system. Enhancing public consultations fosters greater transparency in decision-making and improves the preparation of regulatory impact assessements (RIA). These assessments, along with impact studies, will be accessible to the public via the eGovernment portal.

Efforts have been made to enhance the data-driven planning framework that fosters the development of sustainable policies, with advancements achieved in reinforcing methodological standards for reporting on the execution of strategic documents. Employees in the public administration have become more aware of the application of established methodological criteria in the process of reporting on the implementation of strategic documents, as well as the quality of the reports themselves. The ongoing positive trend of the indicator in 2024 further supports this, revealing that 58.82% of submissions regarding the execution of strategic documents are completely in accordance with the established methodology.

Furthermore, there has been a notable rise in the understanding and knowledge among employees in the ministries regarding the significance of assessing strategic documents, leading to an increase in the evaluation rate of these documents to 62%. This advancement fosters the development of more effective public policies moving forward, ensuring they are better aligned with the needs of the populace.

Nonetheless, the obstacle to achieving this strategic objective is a minor decline in the proportion of new strategic documents that completely adhere to the methodological standards, which currently stands at 66.66%. Considering that the restructuring of the public administration, marked by a notable rise in the number of ministries, resulted in a shift of responsibilities among institutions, along with staff changes, there was a degree of interruption in the strategic planning process within each ministry. It is crucial to highlight that there is a lack of available data concerning the metrics that indicate the proportion of ministries whose yearly work programmes include well-defined objectives and indicators, as well as those whose annual reports reflect the outcomes based on these established objectives and indicators. The factors contributing to this situation include the restructuring of the public administration, the ineffectiveness of the IT system resulting from attacks on government infrastructure, and the postponement of the methodological framework for medium-term planning. This has led to challenges in adopting a more proactive stance in developing a work programme with clearly defined objectives and measurable indicators.

To enhance public consultations, the Report on the implementation of the Regulation concerning the election of representatives from non-governmental organisations in the working bodies of public administration and the conduct of public consultations for the preparation of laws and strategies for 2023, published in December 2024, has been updated. Nevertheless, the analysis of the data reveals a notable difficulty in carrying out public consultations. Among the 70 acts being developed within the ministries, only 23 acts underwent the public consultation process during the initial preparation stage, representing a percentage of 32.86%. Conversely, for approximately 67.14% of acts, this procedure was not carried out. The Report for 2024 is set to be finalised by the conclusion of 2025.

Advancements have been observed in the establishment of strategic planning within ministries, highlighted by a rise in the number of ministries that now possess dedicated units for this purpose, totaling 6 at present. The challenge arises concerning the enduring financial viability of the proposal to create strategic planning units, especially considering the notable rise in the number of ministries following the recent restructuring of the public administration, which now totals 25.

A notable outcome was attained through the ongoing execution of the Professional Education Programme for civil servants focused on strategic planning. This initiative expanded the number of civil servants in ministries who received training in strategic planning and were acknowledged as members of the informal Network of Civil Servants for Strategic Planning. The formalisation of the Network of Civil Servants for Strategic Planning faces challenges due to the ongoing changes in the organisation of public administration, particularly the risks linked to the establishment of the policy coordination function within the ministries.

A crucial aspect of policy development involving citizens and for citizens is the regulatory impact assessement (RAI). In this domain, notable advancements have been achieved in broadening the scope and enhancing the ability to assess the impacts of regulations, which aids in fostering improved and more transparent decision-making. This approach allows individuals to engage more actively in policy-making, ensuring that regulations are more closely aligned with their needs. As a result, this fosters greater trust in institutions and enhances overall quality of life.

Below is a table showcasing the performance indicators:

| OPERATIONAL OBJECTIVE 5.1 |  | Strengthening the data-based planning system that leads to sustainable policies and achievement of Government priorities |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR |  | BASELINE VALUE |  | VALUE FOR 2022 |  | VALUE FOR 2023 |  | VALUE FOR 2024 |  | TREND |  | TARGET VALUE BY 2024 |
| Percentage of new strategic documents fully aligned with the methodological criteria |  | 69% (2020) |  | 50% |  | 76.33% |  | 66.66% |  |  |  | 75% |
| Percentage of reports on implementation of strategic documents that are fully aligned with the methodology |  | 52% (2020) |  | 38% |  | 51.06% |  | 58.82% |  |  |  | 65% |
| Percentage of ministries with Annual Work Programmes that contain clear objectives and indicators |  | 18% (2019) |  | 0% |  | 0% |  | 0% |  |  |  | 80% |
| Percentage of ministries with annual performance reports that present the result as per the set objectives and indicators |  | 0% |  | 0% |  | 0% |  | 0% |  |  |  | 80% |
| Percentage of strategic documents followed up by evaluation |  | The baseline value will be determined after the analysis (2022) |  | 31% |  | 60% |  | 62% |  |  |  | 40% |
| Percentage of policy consultations conducted in line with the legal framework and SIGMA principles compared to the number of Government acts subject to public consultation |  | 0 |  | 23.1% |  | 32.86% |  | N/A |  |  |  | 100% |
| OPERATIONAL OBJECTIVE 5.2 | Enhanced institutional coordination for stronger policy impacts |  |  |  |  |  |  |  |  |  |  |  |
| INDICATOR | BASELINE VALUE |  | VALUE FOR 2022 |  | VALUE FOR 2023 |  | VALUE FOR 2024 |  | TREND |  | TARGET VALUE BY 2024 |  |
| % of ministries that set up the strategic planning units | 30% (2021) |  | 22.2% |  | 26.3% |  | 24% |  |  |  | 70% |  |
| % of ministries that have civil servants who are members of the Strategic Planning Network | 50% (2021) |  | 87.5% |  | 89.5% |  | 100% |  |  |  | 70% |  |

| OPERATIONAL OBJECTIVE 5.3 | Expand the scope of RIA and strengthen the capacities for its implementation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | BASELINE VALUE | VALUE FOR 2022 | VALUE FOR 2023 | VALUE FOR 2024 | TREND | TARGET VALUE BY 2024 |
| Percentage of laws with RIAs that implement the Standard Cost Model | 18% (2020) | 18.5% | 18.75% | 27.04% |  | 20% |
| Percentage of high-quality RIAs against the total number of RIAs delivered to the MF for its opinion | 68.72% (2020) | 82.49% | 83.15% | 89.86% |  | 77% |

ACHIEVEMENTS

The majority of initiatives aimed at enhancing policies for and with citizens took place in 2022 and 2023. Nonetheless, the achievements were acknowledged in the 2024 SIGMA report, which validates advancements in this domain.

- In reference to the Evaluation of Principles of Public Administration document released by SIGMA for the year 2024 In relation to its Western Balkan counterparts, Montenegro distinguishes itself in two significant areas: the coordination of policies and the planning and monitoring of those policies. The effective implementation of the policy planning system was notably highlighted. The findings demonstrate the country’s success in aligning policies and establishing a framework for accurate planning, execution, and oversight of public policies, marking a notable advancement in the reform of public administration.

Source: Report on the evaluation of public administration principles in Montenegro for 2024 (OECD/SIGMA)

- To align national policies with sustainable development objectives, a set of national sustainable development indicators has been established for monitoring at the national level. This framework facilitates the integration of sectoral strategies with the overarching National Strategy for Sustainable Development 2030. A summary of the indicators can be found at the following link: Indicators for Achieving Sustainable Development Goals (sdgmontenegro.me)

- Regarding the Public Administration Principles Assessment Report released by SIGMA, Montenegro achieved the highest rating among the Western Balkans for the Indicator - Use of evidence and impact assessment in policy making, along with the quality and accessibility of laws. Montenegro has seen notable advancements in the implementation of Regulatory Impact Assessment (RIA) recently. The findings indicate that RIA was applied to 96% of the draft laws passed by the Government in 2023, totaling 43 out of 45 laws, whereas the application rate for secondary legal acts stood at 63%. The findings demonstrate a notable level of uniformity in the implementation of the process, with Montenegro attaining considerable alignment with established practices in this domain.

- The manuals and guidelines for RIA are regarded as clear and comprehensive, as evidenced by the SIGMA survey results among public servants, where 70% of respondents highlight the availability and usefulness of these resources.

- To enhance the institutional capabilities of the pertinent departments, particularly in developing skills for conducting economic and financial analyses using the Standard Cost Model, the Ministry of Finance organised a total of 52 training sessions from 2018 to 2024. From 2018 to 2024, a total of 300 officials received training. Among them, men accounted for 29.33% (88 men) while women represented 70.66% (212 women of the 300 trained officials).

- A RIA Network was formed at both the state and local levels, comprising officials who have received training in regulatory impact assessment, along with those who demonstrated strong performance in regulatory impact assessments during the preparation of the relevant report.

- RIA monitoring for by-laws has been established. The Ministry of Finance conducted a comparison between the data on decisions, regulations, and decrees published in the Official Gazette of Montenegro and the records of the number of such submissions made to the Ministry of Finance. During the session on October 17, 2024, the Government of Montenegro approved the Analysis of the implementation of the RIA for bylaws for the years 2022 and 2023.

IMPLEMENTATION IN PROGRESS

- A Draft Methodology has been created outlining the framework for medium-term plans, along with a summary of the responsibilities of essential institutions that require the establishment of coordination elements. The alignment of the planning process with the budget process is detailed. The preliminary document was presented to the Ministry of Finance and MED for feedback.

- Short animations were created regarding strategic planning; however, they remain unpublished due to the current inoperability of the javnepolitike.me website.

- The Information on the establishment of the coordination system for strategic partners has been approved. Additionally, an enhanced information system for strategic planning - ISPI, offers the capability to connect with IT systems utilised for programme budgeting. In the upcoming timeframe, it is essential to define particular technical specifications for their linking, serving as a prerequisite for their practical implementation.

- Strategic planning units have been set up in six ministries to date. During discussions with SIGMA and in the evaluation of the strategic planning framework, a different approach was proposed. This involves identifying essential policy coordination roles to be integrated into the existing positions within the ministries, thus mitigating the financial sustainability risks linked to the earlier approach.

- In collaboration with SIGMA, a draft version of the Regulatory Impact Assessment Manual (RIA) and a Regulatory Impact Analysis Report aimed at developing a comprehensive RIA were created and shared with members of the RIA network on October 8, 2024. Subsequently, the text was refined based on the recommendations from the representatives of the RIA network and the business sector. Efforts have commenced to revise the Instructions regarding the preparation of the RIA. Simultaneously, efforts are underway to enhance the Ministry of Finance’s opinion format.

- The training programme for trainers within the RIA Network is currently in progress, aimed at advancing to the subsequent stage of executing a comprehensive Regulatory Impact Assessment. The training addresses essential elements of Regulatory Impact Assessment, specifically focusing on the updated sections in the comprehensive RIA format.

- In 2024, discussions took place with the representatives of the Parliament. Training focused on enhancing the ability to prepare RIA during the enactment of laws and amendments will take place in 2025.

CHALLENGES

- The ongoing reorganisation of public administration, coupled with unstable political conditions, has resulted in a lack of effective coordination in finalising the Methodology for Medium-Term Planning for Government and Ministries. This situation has hindered the ability to conduct training sessions for the development of medium-term work programmes for the ministries and to prepare for the 2023-2025 cycle, as well as to compile a list of standard costs for strategy preparation. The organisation of expert assistance for the completion of activities has commenced, facilitated by the EUforPFM project, which is set to launch at the close of 2024.

- The issue arises concerning the long-term financial viability and the necessity to create units dedicated to strategic planning, especially considering the notable rise in the number of ministries following the recent restructuring of the public administration, which now totals 25. This also complicated the formalisation of the Network of Civil Servants for Strategic Planning, particularly regarding the risks linked to the establishment of the policy coordination function within the ministries.

- It is essential to carry out initiatives aimed at establishing the policy coordination role within the ministries, while also clarifying the specifics of this function to outline the guidelines for aligning national policy planning with IPA support programming.

- The analysis of connections between strategic documents at both the national and local levels, along with improvement recommendations, was set aside. It is essential to first identify the local needs and establish the method and direction for supporting the fulfillment of those needs.

- Advancing and involving the eGovernment platform, focused on developing public policies collaboratively with citizens.

- Training sessions for officials involved in the development of laws and strategies regarding the standards for conducting public consultations were not held because of insufficient technical and organisational resources.

- The utilisation of eParticipation and ePetition digital platforms for citizen engagement in public policy development remains constrained and ineffective. Therefore, efforts must be made to enhance awareness and increase participation among the relevant public and governmental bodies.

IV BUDGET

A programme budget has been established in Montenegro, specifically a sub-programme focused on reforming public administration. The allocated budget for the Ministry of Public Administration in this subprogramme for 2024 was €905,290, with €755,068 utilised.

Resources are allocated for executing the PAR Strategy 2022-2026 by all institutions responsible for reform goals and activities, which guarantees enhanced financial and fiscal sustainability. A substantial portion of the activities outlined for the AP 2022-2024 is being executed in collaboration with partners-donors.

A total expenditure of €4,408,595 was incurred for the activities carried out in AP during the 2022-2024 period.

4.1 EU SUPPORT TO PUBLIC ADMINISTRATION REFORM – IPA III (SBP

AURUM 2022–2026 and PFM 2022–2026 implementation support was facilitated by the EU via IPA III, specifically the sector budget support (SBP) instrument outlined in the Action Document - EU Support to Public Administration Reform, totaling EUR 16.6 million. A total of EUR 13.1 million is earmarked for direct financial assistance to the budget, with an additional EUR 3.5 million allocated for supplementary support in executing reform processes. This initiative aims to enhance citizens’ quality of life and foster economic development by establishing a professional, efficient, and digitised public administration that is accessible to everyone.

The additional assistance within the sector budget support for PAR enhances the achievement of established goals via the execution of targeted projects. Under the IPA III framework, this assistance is carried out through three essential projects that are progressing as anticipated:

- EU4PA - Technical assistance to Montenegro in support of public services provision and human resources management: The value of the project is EUR 1.3 million, it started in November 2023 and lasts until November 2026. The objective of the project is to establish a public administration that is efficient, accountable, and transparent, delivering top-notch services to both citizens and the economy. The project encompasses two key elements: enhancing the official framework and delivering services. The present emphasis is on creating a competency framework applicable to all civil servants and state employees.

- Support to Coordination, Monitoring, and Reporting on Public Administration Reform Strategy and the Public Financial Management Reform Programme 2022-2026: The project is valued at EUR 700,000, commenced in September 2023, and will continue for a duration of three years. The emphasis during the previous period was on enhancing the effectiveness of the Coordination Team responsible for executing public administration reform, improving negotiations with the European Commission, fostering dialogue with donors, and monitoring as well as developing capacities for transparency in public administration reform. Particular emphasis is placed on the creation of annual reports and reporting on outcomes.

- EU4PFM - EU for Public Finance Management (PFM) in Montenegro: The value of the project is EUR 1.5 million and it started in November 2024.

In the context of overseeing the execution of the AURUM, significant emphasis is placed on tracking the indicators related to Sector Budget Support, which are essential prerequisites for the allocation of financial aid within the PAR framework. The indicators facilitate ongoing evaluation of advancements in executing reform initiatives, alongside adherence to established goals and benchmarks.

Considering their significance, SBP indicators will be featured in a dedicated Report on financial assistance for public administration reform in 2024, as outlined in the Government of Montenegro’s work programme for Q2. This document will offer a comprehensive analysis of the outcomes attained, highlight possible challenges, and suggest additional measures to enhance the reform process, thereby promoting transparency and accountability in the execution of public administration.

Following the insights gained from IPA II, MPA, in its role as the process coordinator, engaged in various activities aimed at achieving the target values of SBP indicators and enhancing collaboration among pertinent institutions. In this context, a Working Team was established in May 2024 to oversee the achievement of the indicators outlined in the Annual Action Programme for Montenegro for 2022 in the form of SBP. Four meetings of the Working Team took place, focusing particularly on defining and developing the Employment Plan within the pilot sectors of environmental protection and employment and social policy, aligned with the newly established indicators. The Government of Montenegro is nearing the completion of the Employment Plan adoption process.

The Ministry of Public Administration, in collaboration with the pertinent institutions and the EU Delegation in Montenegro, organised efforts related to the supplementary programming of the Action Document from 2022, focusing on the reform of public administration and the management of public finances. In December 2024, the amendments to the 2022 Action Document were officially signed. This initiative involved the allocation of an extra EUR 2.6 million for direct budget assistance, focused on enhancing human resources in two essential pilot sectors identified as priority funding areas following EU accession: environmental protection and employment and social policy. The workforce in these two pilot sectors will be crucial in enhancing the administrative and personnel capabilities of Montenegrin institutions, facilitating the effective preparation and execution of multi-year IPA operational programmes for the 2024-2027 period. For the first time, these programmes will be executed under a model of independent management, eliminating the need for prior oversight from the EU Delegation. This shift necessitates additional resources and skills for successful execution.

In this context, the new responsibility of the Working Team, under the coordination of the Ministry of Public Administration, pertains to the preparation of the Request for the initial variable tranche via the SBP, in line with the successful achievement of the established indicators.

The action document outlines six performance indicators that serve as the basis for tracking progress towards the established objectives. The extent to which the indicators are achieved is a prerequisite for the disbursement of the allocated financial resources, facilitated through two variable tranches. The process of gathering verification sources and preparing materials for the request for the initial variable tranche, scheduled to be submitted to the EC in Q2 2025, is currently in progress.

The Ministry of Public Administration is working on the annual document detailing financial assistance for the public administration reform, aiming to deliver a thorough summary of the financial backing in this sector.

Table of performance indicators for the payment of variable tranches

| Indicator | Target values Year 3 (2024) | Target value Year 5 (2026) |
| --- | --- | --- |
| Number of organisations that have implemented a quality management system and are prepared for the certification process | A minimum of five institutions, concerning the baseline value, have implemented a quality management system and are prepared for the certification process. | A minimum of 15 institutions have implemented a quality management system and are now prepared for the certification process, compared to the baseline value. |
| Proportion of strategic documents associated with programme budgets | At least 50% of the implemented strategies include an Action Plan, with their budgets aligned to the national programme budget as per the Methodological Guidelines for Costing of Government Strategies (ReSPA). | At least 80% of the strategies that have been adopted include an Action Plan with a budget that is connected to the national programme budget. |
| Percentage of ministries that assign financial management and internal control responsibilities to senior management as per the applicable Regulation | At least 50% of ministries | At least 80% of ministries |
| Improved transparency of public finances | Prepared and published half-yearly and annual reports on budget performance, including gender indicators | Macro-fiscal guidelines (medium-term budgetary frameworks) include medium-term programme-based policy information, information on non-financial performance and expenditure plans |
| Average number of qualified candidates per notice and per competition | Public notices: 7 Public competitions: 4 | Public notices: 9 Public competitions: 6 |
| The timeframe for the employment process in the two pilot sectors, starting from the Decision to initiate the procedure for filling the position by the head of the public administration body until the employment decision is reached. (baseline value: around 12 months) | 6 months *Target Value - Year 4 (2025) | 4 months |
| The recruitment of civil servants in two pilot sectors was conducted in accordance with the established Employment and Competency Plan. | Created an Employment Plan focused on two pilot sectors aimed at generating a minimum of 100 new or additional jobs. A framework outlining competencies for all civil servants has been put in place. *Target Value - Year 4 (2025) | 90% of the personnel outlined in the Employment Plan for the two pilot sectors have been hired, and all recruitment processes have adhered to the Competency Framework. |
| Proportion of capital initiatives for which a cost-benefit assessment has been conducted following the updated methodology | A novel methodology for evaluating costs and benefits has been sanctioned, aligning with best international standards. | At least 50% of the total capital projects outlined in the annual national budget should have a cost-benefit analysis conducted in line with the updated methodology. |

Enhancing coordination in public administration reform support – meeting held with project representatives and partners

4.1.1 Coordination of financial support

In June 2024, MPA, acting as the coordinator for public administration reform in Montenegro, collaborated with relevant institutions to prepare the Report on Financial Support for Public Administration Reform for 2023, aiming to deliver a thorough overview of the financial assistance in this sector.  Furthermore, to enhance the collaboration of donor assistance for public administration reform, and considering that numerous projects aimed at supporting this reform are presently underway, MPA convened a coordination meeting with representatives from organisations involved in the ongoing projects in the realm of public administration reform. The meeting took place in December 2024, particularly considering the preparations for the upcoming AP for the 2025–2026 period, as part of the AURUM 2022–2026. The meeting was attended by project representatives, international partners engaged in close collaboration with the Ministry, and members of the Delegation from the European Union. Through the organisation of this coordination meeting, the synergy of all projects was guaranteed, demonstrating an effective strategy in the alignment of activities and the financial viability of the reform.

Furthermore, as part of the Government of Montenegro’s work programme for 2025, MPA is set to develop a new Report on Financial Support for Public Administration Reform 2024, which is expected to be completed by the end of Q2 2025. The endorsement of this document promotes transparency in the allocation of financial resources, adherence to reform objectives, and facilitates prompt identification of implementation challenges, thereby enhancing effective management.

V RECOMMENDATIONS

STRATEGIC GOAL I CITIZEN-ORIENTED ORGANISATION AND OPERATION OF THE PUBLIC ADMINISTRATION

MPA and LSGs

- Ensure the functionality of the eDMS system at the central level

- Intensify activities on digitalisation of municipalities

- Strengthen the function of the Protector of Property and Legal Interests at the local level

ALL DEPARTMENTS

- Ensure the implementation of the recommendations of the Protector of Property Legal Interests and the Ombudsman

- Promote the role of the Agency for Peaceful Resolution of Labour Disputes to reduce the expenditure of Budget funds for labour disputes

STRATEGIC GOAL II CITIZENS AND BUSINESSES USE HIGH-QUALITY SERVICES OF THE PUBLIC ADMINISTRATION

ALL DEPARTMENTS

- Form a dedicated team of organisations that have begun applying the CAF model, which will provide guidance and support to other organisations.

- Enhance management engagement in the advancement and execution of the quality framework.

- Facilitate education and advocacy for the advantages of quality management via training sessions, seminars, and sharing of best practices among organisations.

- Establish the necessary conditions for all new services to interface with the updated eGovernment portal.

- Strengthen interdepartmental collaboration in the development of new e-Services.

- It is essential to expedite efforts to enhance the digital competencies of employees within public administration. This is particularly important for IT personnel, who should receive specialised training focused on emerging technologies, including artificial intelligence.

STRATEGIC GOAL III Professional public administration

MPA

- Improvement of the normative framework in the field of the civil service system

HRA

- Providing an adequate mechanism for monitoring career development, from trainee positions to leadership skills

ALL DEPARTMENTS

- Strengthen supervision over the creation of HR Plans by ensuring stronger inter-institutional coordination of this process

- Ensure greater participation of senior management personnel in trainings, their participation in designing trainings and initiating specific training programmes

- Plan and implement continuous education at all levels

STRATEGIC GOAL IV Transparent and open public administration

MPA

- Intensify activities on the formation of the FAI Council

- It is recommended to develop a detailed plan to identify high value open data sets, launch pilot initiatives in key areas, organise an awareness campaign and implement activities through the next action document, with monitoring and evaluation of progress.

APDPFAI

- Intensify activities on improving the functioning of the APDPFAI information system and connecting the appeals procedure with the part of the IT system related to appeals

ALL DEPARTMENTS

- Ensure prompt action on all requests, adhering to principles of transparency and accessibility, to prevent any appeals from citizens.

STRATEGIC GOAL V Policy planning with and for citizens

GSG

- It is essential to enhance collaboration among central government bodies and ministries in strategic planning, along with improving communication regarding the methodological standards for the development of strategic documents

- It is necessary to additionally strengthen the obligation to carry out the evaluation of strategic documents through the establishment of more effective procedural solutions at the Government level

- It is essential to reevaluate the organisational framework of institutions to facilitate the integration of policy coordination roles within ministries. The established functions would subsequently be allocated to the current roles within the ministries, thereby mitigating the risk associated with financial sustainability.

- It is essential to enhance the knowledge of civil servants regarding the application of the Methodology for the formulation of policies, drafting, and monitoring the execution of strategic documents. This should particularly emphasise the aspects of reporting on the execution of these documents to further elevate the quality of reports.

- Enhance efforts to revitalise the ISPI information system, facilitating coordination and linkage among strategic planning (including umbrella and sectoral strategic documents, as well as the medium-term work plans of the Government and ministries), the programme budget, and donor assistance.

- It is advised that, as part of the EU4PFM initiative, efforts should be made to establish a methodological framework for the medium-term planning of government and ministry activities. This will ensure the provision of clear guidelines and a timeline for the development of ministry work programmes, grounded in well-defined objectives and corresponding performance indicators.

MF

- Promote enhanced participation of all regulatory stakeholders in the implementation and utilisation of regulatory impact assessments (RIA)

MPA

- Ensure the establishment of a mechanism to track adherence to the stipulations from public consultations, in line with applicable laws, during the evaluation of all proposed legislation and strategies presented to the Government for approval.

VI ACTION PLAN IMPLEMENTATION REPORTING TABLE

STRATEGIC GOAL I CITIZEN-ORIENTED ORGANISATION AND OPERATION OF THE PUBLIC ADMINISTRATION

| Operational objective 1.1 Functional public administration with efficient oversight of its implementation and application of the managerial accountability concept |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| Amount collected by means of enforcement procedure in labour cases handled by the Protector of Property and Legal Interests | €10,412,089.00 | €15,226,148.67 | € 14,143,973.40 | €18,803,866.30 |  | Unchanged compared to the baseline value | -3% of the initial value |
| Percentage of institutions having established a reporting system at the level of outcome indicators and objectives which would enable monitoring of the achievement of results with indicators of the programme-based budget implementation | No system is in place | The indicator will be tracked through indicator 45 | The indicator will be tracked through indicator 45 | The indicator will be tracked through indicator 45 |  | 100% of ministries have outcome reporting in place | 100% of ministries have outcome reporting in place, 50% of state authorities and public institutions |
| Average length of administrative disputes in Administrative Court | 17 months | 17.7 months | 17.2 months | 19.2 months |  | 12 months | 6 months |
| Percentage of recommendations implemented by state authorities based on the Ombudsman’s annual work report | 19.88% | 19.3% | 53.1% | 52.5% |  | Over 40% of implemented recommendations | Over 60% of implemented recommendations |
| Percentage of ministries which delegate financial management and internal control authority to senior management in accordance with the Decree | 8.3% | 28% | N/A | 42% |  | 50% | 80% |
| Number of administrative authorities having been subjected to administrative oversight by the line ministry | 0 | 0 | N/A | The indicator cannot be tracked within the current organisational structure |  | 30% | 50% |
| Percentage of laws which are harmonised with the Law on Public Administration | 66.7% | 83.3% | 83.3% | 100% |  | 95% | 100% |

|  | Activity |  | Outcome indicator |  | Competent institutions |  | Start | End |  | Indicator implementation status |  | New deadline |  | Funds planned |  | Funds realised | Source of funding |  | Recommendations |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1.1 | Drafting of the Proposal for the Law on the Government |  | The proposal of the Law has been approved by the Government |  | MPA |  | Q1 2022 | Q3 2024 |  | The working group prepared the Draft Law on the Government. In February 2025, it was sent to the EC for an opinion |  | Q4 2025 |  | €5,000 |  | €8,000 | Budget of Montenegro |  | The activity will be acknowledged in AP 2025-2026 |  |
| 1.1.2. | Adoption of the Law on Public Institutions |  | - Conducted an analysis highlighting identified challenges and providing recommendations for the establishment of a normative framework for public institutions - The Proposal Law on Public Institutions has received approval. |  | MPA |  | Q1 2023 | Q4 2024 |  | Analysis conducted An interdepartmental Working Group for the Law on Public Institutions was established. Work on the Draft Law has begun |  | Q4 2025 |  | €18,000 |  | €8,000 | Budget of Montenegro |  | The activity will be acknowledged in AP 2025-2026 |  |
| 1.1.3 | Establish Registry of State authorities and Institutions at the central and local levels |  | - Enhanced Registry of State authorities available at www.drzavniorgani.me - Registry of public services has been established, with local self-government as its founder. - Identification of relevant contacts within competent institutions for data entry into registries |  | MPA UoM LSU SIGMA |  | Q2 2022 | Q4 2024 |  | - Established Registry of State authorities at the central level - Registry at the local level established; Local governments are currently entering data |  |  |  | €35,000 |  | €8,400 | Budget of Montenegro |  |  |  |
| 1.1.4 | Draft amendments to the Law on Inspectorial Oversight |  | Law on Inspectorial Oversight is amended to introduce a combined method of work and efficiency of inspectorial oversight |  | MPA |  | Q2 2022 | Q4 2024 |  | The Law on Amendments to the Law on Inspectorial Oversight with more effective Inspectorial Oversight was adopted |  |  |  | €5,000 |  | No funds were spent | Budget of Montenegro |  | Government changes (42nd and 43rd) caused a delay in the implementation of this activity |  |
| 1.1.5 | Upgrade of the Single Inspection Information System (SIIS) includes a new module that allows business operators under supervision to conduct self-assessments by completing checklists and submitting them directly to the database. |  | -ToR developed to include the necessary upgrade - SIIS upgrade tender published -New SIIS module developed |  | Directorate for Inspection Affairs |  | Q1 2023 | Q1 2024 |  | The allocation of IPA funds facilitated the establishment of technical conditions, enabling the acquisition of state-of-the-art equipment. As a result, inspectors are now equipped with some of the latest and highest quality computer technology for their tasks. Facilitated the self-assessment of supervised entities through the completion of checklists. |  |  |  | €60,000 |  | €50,000 | Budget of Montenegro |  |  |  |
| 1.1.6 | Strengthening the personnel capacities of the Administrative Inspectorate |  | - At least 6 training events for the officers of the Administrative Inspectorate have been carried out - The number of Administrative Inspectorate staff members increased |  | HRA MPA |  | Q2 2022 | Q4 2024 |  |  |  | Q4 2026 |  | €16,000 |  |  | Budget of Montenegro |  | The activity will be acknowledged in AP 2025-2026 |  |
| 1.1.7 | Improving the transparency of the Administrative Inspectorate |  | A fragmented monitoring programme of the Administrative Inspectorate was developed |  | Administrative Inspectorate |  | Q1 2022 | Q4 2022 |  |  |  | Q4 2025 |  | €5,000 |  |  | Budget of Montenegro |  | The activity will be acknowledged in AP 2025-2026 |  |
| 1.1.8 | Improvement of the system of reporting on the work of the Administrative Inspectorate |  | The methodology for the development of the annual work report of the Administrative Inspectorate has been enhanced, incorporating details on recurring inspections and the outcomes of those evaluations. |  | Administrative Inspectorate |  | Q2 2022 | Q4 2023 |  | The methodological aspects of the report from the Department of Administrative Inspectorate have seen enhancements. The Report for 2024 is currently being crafted with an enhanced framework. |  |  |  | €15,000 |  | €5,000 | Budget of Montenegro |  |  |  |
| 1.1.9 | Develop analysis of the reasons/grounds for payment of additional enforcement costs in lost cases and implement recommendations in institutions identified as being involved in a higher number of disputes |  | - Comprehensive analysis of the reasons for paying enforcement costs in lost cases and concrete recommendations for improvement are developed - Dialogue and cooperation with the institutions identified as being involved in a higher number of disputes are improved |  | Protector of Property and Legal Interests MF MJHMR Agency for Peaceful Settlement of Disputes SIGMA |  | Q2 2022 | Q4 2024 |  | The narrative section of the Protector’s Quarterly Report includes an examination of the data. |  |  |  | €18,000 |  | No funds were spent | Budget of Montenegro Donor funds - direct assistance SIGMA |  |  |  |
| 1.1.10 | Improve the structure of reporting of the Protector of Property and Legal Interests on the costs of enforced payment in lost court cases |  | Report is improved and includes situation assessment and recommendations for improvement of work of the authorities recognised as being involved in a higher number of court cases, case-law, overview of costs, legal opinions relevant to the public interest |  | Protector of Property and Legal Interests |  | Q3 2022 | Q3 2024 |  | Improved reporting structure |  |  |  | €2,000 |  | No funds were spent | Budget of Montenegro |  |  |  |
| 1.1.11 | Improve the analysis of impact of the proposed organisational changes with the focus on justifiability of establishing new or merging/abolishing authorities |  | Regulatory impact assessment (RIA) is improved *activity related to 3.3.7 and 5.1.1 |  | MPA, MF, SIGMA |  | Q1 2022 | Q3 2022 |  |  |  | Q3 2025 |  | €10,000 |  |  | Budget of Montenegro Donor funds - direct SIGMA assistance |  | The activity will be acknowledged in AP 2025-2026 |  |
| 1.1.12 | Harmonisation of special laws with the Law on Public Administration |  | Information Brief on the level of harmonisation of special laws with LSA is developed and adopted |  | MPA |  | Q1 2023 | Q4 2024 |  | All laws are harmonised with the Law on Public Administration |  |  |  | €10,000 |  | No funds spent | Budget of Montenegro |  |  |  |
| 1.1.13 | Develop methodology for developing the work programme of state administration authorities including performance indicators |  | - Prepared methodology for state administration bodies - Methodology promoted for public institutions as well |  | MPA SIGMA |  | Q2 2022 | Q4 2022 |  |  |  | Q3 2025 |  | €25,000 |  |  | Budget of Montenegro Donor funds Direct SIGMA assistance |  | The activity will be acknowledged in AP 2025-2026, through the implementation of activity 5.1.1. |  |
| 1.1.14 | Develop methodology for developing the work programme of authorities including an overview of implementation of objectives and performance indicators |  | Adopted methodology to encourage results-oriented reporting |  | MPA – Directorate for Normative Affairs MF SIGMA |  | Q2 2022 | Q3 2022 |  |  |  | Q3 2025 |  | €12,000 |  |  | Budget of Montenegro Donor funds - direct SIGMA assistance |  | The activity will be acknowledged in AP 2025-2026, through the implementation of activity 5.1.1. |  |
| 1.1.15 | Analyse available data and upgrade necessary data and information in two pilot institutions |  | Analysis covering two pilot institutions MPA and HRA is published |  | MPA, HRA |  | Q2 2022 | Q4 2024 |  |  |  |  |  | €25,000 |  |  | Budget of Montenegro |  | Activities will be acknowledged in AP 2025-2026 |  |
| 1.1.16 | Increase availability of data held by two pilot institutions |  | Number of datasets on the websites of two pilot institutions MPA and HRA |  | MPA, HRA |  | Q3 2022 | Q4 2024 |  |  |  |  |  | €25,000 |  |  | Budget of Montenegro |  |  |  |
| 1.1.17 | Improve organisation of work and communication based on available data in two pilot institutions |  | Plan for improving communication in two pilot institutions MPA and HRA is developed |  | MPA, HRA |  | Q1 2023 | Q3 2024 |  |  |  |  |  | €45,000 |  |  | Budget |  |  |  |
| 1.1.18 | Organise training on application of methodology for developing work programmes and reporting on the work of authorities, including an overview of implementation of objectives and performance indicators |  | - At least 70 employees are trained in developing work programmes and reporting on the work of authorities, including an overview of implementation of objectives and performance indicators - 37 employees in the first training event - 37 employees in the second training event |  | HRA, GSG, MPA |  | Q4 2022 | Q4 2024 |  |  |  | Q4 2025 |  | €12,000 |  |  | Budget of Montenegro |  |  |  |
| 1.1.19 | Improve the normative framework governing administrative disputes |  | - The legislation concerning Administrative Dispute has been revised to address the expenses associated with disputes and the management of oral hearings, aiming to shorten the duration of administrative disputes. - Training sessions for judges regarding the application of the recent legislation |  | MJHMR Judicial Training Centre Administrative Court |  | Q2 2022 | Q4 2024 |  | The Government approved the Proposal Law on Amendments to the Law on Administrative Disputes |  |  |  | €12,000 |  | €45,000 | Budget of Montenegro |  |  |  |
| 1.1.20 | Develop Analysis with recommendations on the length of administrative disputes in administrative matters |  | - Analysis of ping-pong cases is developed - Identification of institutions with the highest percentage of annulled acts - Administrative procedure training for identified institutions is delivered |  | Administrative Court MPA, HRA SIGMA |  | Q3 2022 | Q2 2024 |  | Report on proceedings in administrative matters for the year 2022, with reference to the year 2021 |  | Q3 2026 |  | €25,000 |  |  | Budget of Montenegro Donor funds - direct SIGMA assistance |  |  |  |
| 1.1.21 | Improvement of the structure of annual reporting by including overview of the situation regarding implementation of recommendations given by Ombudsman |  | - Ombudsman’s annual report is improved concerning implemented recommendations and violations of citizens’ rights and freedoms by state authorities - Proactive work of Ombudsman through promotion of human rights and freedoms in the context of recommendations given to state authorities |  | Ombudsman |  | Q2 2022 | Q1 2023 |  | - The annual report has been improved - Field visits and thematic meetings with institutions are held on an annual basis |  |  |  | €7,000 |  | No funds were spent | Budget of Montenegro |  |  |  |
| 1.1.22 | Develop and present Information Brief on unimplemented Ombudsman’s recommendations given to state authorities from previous reporting periods, in order to determine the way to improve the implementation rate |  | - Information Brief adopted and presented - Intensive dialogue with the institutions frequently violating citizens’ rights and failing to follow Ombudsman’s recommendations is established |  | Ombudsperson, Parliamentary Committee, SIGMA |  | Q2 2023 | Q2 2024 |  | - In the annual overview of the Ombudsperson’s activities, the report is structured to include details on recommendations that have been fully implemented, partially implemented, and those that remain unimplemented. The document is submitted to the Parliament and is accessible to the public. - Annual field visits and thematic meetings are conducted with institutions recognised for frequently infringing upon citizens’ rights. |  |  |  | €7,000 |  | No funds were spent | Budget of Montenegro Donor funds - direct SIGMA assistance |  |  |  |
| 1.1.23 | Develop plan of Ombudsman’s visits to the authorities having failed to implement recommendations, including methods of follow-up reporting |  | Plan of Ombudsman’s visits to the authorities having failed to implement recommendations, including methods of follow-up reporting is developed |  | Ombudsman Parliamentary Committee SIGMA |  | Q2 2024 | Q4 2024 |  |  |  | April 2026 |  | €8,000 |  |  | Budget of Montenegro |  | The activity will be acknowledged in AP 2025-2026 |  |
| 1.1.24 | Amend the legal framework on internal controls in the public sector |  | Law on Management and Internal Controls in the Public Sector is amended with respect to managerial accountability |  | MF – Directorate for Central Harmonisation |  | Q1 2022 | Q2 2024 |  | Draft Law prepared |  | Q2 2025 |  | €5,000 |  |  | Budget of Montenegro |  | The activity will be acknowledged in AP 2025-2026 |  |
| 1.1.25 | Raise senior management awareness of managerial accountability |  | - At least 50 managers and employees are trained on the importance of implementation of managerial accountability in the public administration - One roundtable meeting on senior management awareness of managerial accountability is held - In 2022, 25 managers |  | HRA, MF, AMM |  | Q3 2022 | Q4 2023 |  | - A training session centered on the theme of managerial accountability was held for both managers and employees at the local level. The invitation was sent to the central institutions; however, the training could not proceed because there were not enough applicants. - In late November 2023, the Ministry of Finance convened a Conference on Managerial Accountability aimed at increasing the awareness of managers in the public administration sector. |  |  |  | €16,000 |  | €2,500 | Budget of Montenegro |  |  |  |
| 1.1.26 | Organise training for internal auditors to improve their skills for evaluating the implementation of managerial accountability |  | At least 60 internal auditors are equipped with skills for evaluating the implementation of managerial accountability |  | HRA MF |  | Q1 2023 | Q4 2023 |  | As part of the continuous professional development efforts for certified internal auditors in the public sector, four training sessions were held for internal auditors from different internal audit units at both central and local levels. The sessions centered around the themes of Managerial Accountability Audits and the Development of Internal Audit Soft Skills, attracting 104 participants. |  |  |  | €2,000 |  | €2,000 | Budget |  |  |  |
| 1.1.27 | Review the quality of management and internal control to evaluate the situation |  | Reports including situation assessment, identified problems and recommendations for improvement are adopted |  | MF |  | Q4 2022 | Q2 2023 |  | In February 2024, reports on the quality of management and internal controls were conducted, accompanied by an assessment of the current situation and recommendations for enhancement. |  |  |  | €2,000 |  | No funds were spent | Budget of Montenegro |  |  |  |
| 1.1.28 | Promote public administration based on diversity, non-discrimination policies and equal opportunities |  | Regulatory framework governing and affirming diversity, equality, inclusion is promoted (Law on the Prohibition of Discrimination, Law on Gender Equality, Law on Same Sex Life Partnership) |  | MPA MJHMR Line ministries |  | Q2 2022 | Q4 2024 |  | The activity is consistently carried out during all public engagements, alongside the involvement of representatives from the Ministry of Public Administration in working groups aimed at enhancing the strategic and regulatory framework of the MJHMR. |  | Q2 2026 |  | €15,000 |  |  | Budget of Montenegro |  | The activity will be acknowledged through AP 2025-2026 |  |
| 1.1.29 | Develop public administration communications plan affirming diversity, equality, non-discrimination policies and equal opportunities, while considering sector-specific approach to these matters |  | Communications plan developed and adopted |  | MPA MJHMR Line ministries |  | Q1 2023 | Q4 2024 |  | Activity implemented |  |  |  | €30,000 |  |  | Budget of Montenegro |  |  |  |
| 1.1.30 | Develop a platform of institutions reflecting the commitment to affirmation of human rights, gender equality, value of diversity and improtance of inclusion |  | - Websites of institutions are upgraded - Communications plans of institutions are improved - Three roundtable meetings are held - Promotional activities– video, iconography, etc. |  | MPA MJHMR Line ministries |  | Q1 2024 | Q4 2024 |  |  |  | Q2 2026 |  | €40,000 |  |  | Budget |  | The activity will be acknowledged in AP 2025-2026 |  |
| 1.1.31 | Develop methodology for developing gender equality plans in all ministries |  | Methodology for developing gender equality plans in ministries is developed |  | MJHMR GSG |  | Q2 2022 | Q4 2024 |  | The implementation of activities is ongoing through the project “United in Gender Eqality”. |  | Q4 2026 |  | €7,000 |  | €5,000 | Budget of Montenegro |  | The activity will be acknowledged in AP 2025-2026 |  |
| 1.1.32 | Develop gender equality plans in 3 pilot ministries |  | At least 3 ministries have developed individual gender equality plans |  | MJHMR |  | Q3 2022 | Q4 2024 |  | The implementation of activities is ongoing through the project “United in Gender Eqality”. |  | Q4 2026 |  | €18,000 |  | €12,000 | Budget of Montenegro |  | The activity will be acknowledged in AP 2025-2026 |  |
| Operational objective 1.2 Paperless administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INDICATOR |  | Baseline value |  | Value for 2022 |  |  | Value for 2023 |  | Value for 2024 |  | Trend |  | Target value by 2024 |  |  | Target value by 2026 |  |
| Percentage of state authorities which have established electronic document management system |  | 38% |  | 40% |  |  | 38% |  | 55% |  |  |  | 50% |  |  | 80% |  |
| Percentage of state authorities performing fully electronic exchange (externally) of documents via eDMS |  | 0 |  | 1.30% |  |  | 0% |  | 0% |  |  |  | 20% |  |  | 40% |  |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.2.1 | Analyse challenges and advantages of eDMS | Analysis of technical eDM systems which are in place is carried out | MPA | Q1 2022 | Q1 2023 | An analysis of the pilot phase was conducted to formulate a plan for the subsequent integration of additional institutions into this framework |  | €27,000 | €80,000 | Budget of Montenegro Donor funds - Direct assistance from SIGMA |  |
| 1.2.2. | Redesign eDMS and link it to e-government portal | - Development of technical specification for eDMS redesign - UX/UI system redesign based on user experience | MPA | Q4 2023 | Q3 2024 | The redesign of the system was done within the framework of activity 1.2.4 Information on the implementation of the Information System for electronic document management and management of the process of electronic sessions of the Government of Montenegro |  | €30,000 | €30,000 | Budget of Montenegro |  |
| 1.2.3 | Improve employees’ knowledge of eDMS | - Minimum 150 public administration employees successfully completed eDMS training - eDMS is linked to electronic Government sessions | MPA | Q1 2024 | Q3 2024 | A total of 439 users have been trained on the eDMS system linked to the electronic sessions of the Government. |  | €30,000 | €30,000 | Budget of Montenegro |  |
| 1.2.4 | Implement document management system in authorities with the highest volume of interaction with the citizens | - Analysis identifying administrative and technical requirements for establishment of eDMS is developed - Document management system implemented in additional 16 state authorities | MPA State authorities implementing the system (pilot in selected agencies, administrations, fund) | Q2 2023 | Q4 2024 | - Developed document, “Creation and maintenance of information system for eDMS and management of the process of electronic sessions of the Government.” - The system has been implemented in over 20 authorities |  | €430,000 | €430,000 | Budget of Montenegro |  |
| 1.2.5 | Introduce eDMS at the local level in four selected LSGUs having no electronic document management system in place | - Situation analysis regarding current status to identify requirements for establishment of eDMS (technical and administrative requirements) - eDMS is introduced in two selected LSGUs - eDMS training is organised for a minimum of 60 LSGU employees | MPA LSGUs HRA | Q1 2023 | Q4 2024 |  | Q4 2025 | €250,000 |  | Budget of Montenegro | The activity will be acknowledged through AP 2025-2026 |
| 1.2.6 | Strengthen the capacity of MPA IT Department staff members | Minimum 10 specialised training events for IT personnel | MPA - Directorate for Digitalisation and e-Services Specialised IT training providers | Q1 2023 | Q4 2024 |  | Q4 2026 | €47,000 | €30,000 | Budget of Montenegro | The activity will be acknowledged through AP 2025-2026 |

| Operational objective 1.3 Strengthening functional and financially independent municipalities to ensure more equal development of all LSGUs |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| Number of tasks involving inter-municipal cooperation | 20 | N/A | N/A | 31 |  | 24 | 30 |
| Ratio of debt of all municipalities to their total revenue (at the level of all municipalities) | 33.50% | 28.3% | 22.2% | N/A |  | 32% |  |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.3.1 | Screen the functioning of the local self-government | Screening of current LSGUs tasks is implemented for all areas, including situation assessment, level of implementation and proposed measures for future functioning of LSGUs, challenges faced by LSGUs in performing: delegated and entrusted tasks, transfer of powers to municipalities under strategic documents without ensured funding by central-level authorities, cost-benefit analysis of core LSGU tasks, with recommendations for improvement and options for introducing soft poly-typic functioning system | MPA UoM LSGUs | Q1 2022 | Q3 2023 | At the session held in January 2024, the Government of Montenegro adopted the Screening of the Local Self-Government System | Q1 2024 | €30,000 | €5,448 | Budget of Montenegro | SIGMA expert support provided |
| 1.3.2 | Adopt a plan with recommendations based on findings of the screening activity under 1.3.1 | Plan with recommendations is adopted | MPA UoM LSGUs | Q4 2022 | Q2 2023 | The plan is an integral part of the Screening of the Local Self-Government System. | Q1 2024 | €9,000 | The funds were spent within the framework of activity 1.3.1 | Budget of Montenegro |  |
| 1.3.3 | Amend the Law on Local Self-Government | Law on Local Self-Government amendments regulating the following are adopted: - harmonisation with the Law on Civil Servants and State Employees - improvement of administrative oversight over the work of public services - elimination of challenges in implementing the current Law - inter-municipal cooperation - use of electronic services of trust of LSGU performed by the state administration authority in charge of electronic administration affairs and electronic business operations - other amendments according to the screening results | MPA MF UOM LSGUs | Q1 2023 | Q3 2024 | The draft law is in the phase of coordination with the Secretariat for Legislation, and its adoption is expected in Q1 2025 | Q1 2025 | €3,000 | €1,000 | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 1.3.4 | Promote the mechanism of inter-municipal cooperation | Two workshops on the importance of inter-municipal cooperation are held and attended by all LSGUs | MPA UoM LSGUs | Q1 2023 | Q4 2023 | The Union of Municipalities of Montenegro continuously promotes the mechanism of inter-municipal cooperation through workshops, meetings with LGUs, round tables, etc. |  | €13,000 | Budget funds were not spent | Budget of Montenegro |  |
| 1.3.5 | Carry out analysis of challenges associated with the collection of local public revenues and fiscal capacity of LSGUs | Analysis with action plan for improving the collection of local public revenues is carried out | MPA UoM LSGUs SIGMA | Q2 2022 | Q4 2023 | This activity is included in the Screening of the Local Self-Government System |  | €13,000 | Funds spent within activity 1.3.1. | Budget of Montenegro Donor funds - Direct SIGMA assistance |  |
| 1.3.6 | Strengthen oversight of LSGU financial operations by giving opinions on the budget and periodic reports on the financial situation of LSGUs which will include concrete recommendations | - Outstanding debt of local self-governments is reduced in absolute amounts - Number of issued opinions - Number of controls of budget inspectorate | MF | Q3 2023 | Q4 2024 | The Ministry of Finance gave 20 opinions on the submitted Proposals Decisions on Amendments to Decisions on Municipal Budgets for 2024 and 24 opinions on the Proposal Decisions on Municipal Budgets for 2025 (the Municipality of Kotor did not submit the Proposal Decision on the Budget for 2025 for opinion). - One control of the Budget Inspectorate was carried out |  | €15,000 | No funds were spent | Budget of Montenegro |  |
| 1.3.7 | Increase the share of own revenue in the current revenue of LSGUs | - Number of training events to strengthen the capacity of LSGs to collect own revenues - Normative framework for collection of own revenues is improved | MF LSGUs UoM | Q4 2022 | Q4 2023 | Three trainings were organised under the title “Subsidiary application of the Law on Administrative Procedure in the area of determination and collection of local public revenues”. Two round tables were organised on the topic of real estate taxes The Law on Amendments to the Law on Financing of Local Self-Governments was adopted by the Parliament on January 19, 2024 |  | €5,000 | €2,500 | Budget of Montenegro |  |
| 1.3.8 | Strengthen the capacity of LSGU Representative of Property and Legal Interests | - At least 20 persons completed training - Role of the LSGU Representative of Property and Legal Interests is promoted by means of training addressing amended decision on internal organisation and method of operation of local self-government bodies, workshops etc. | HRA MPA UOM LSGUs | Q1 2023 | Q4 2024 |  | Q2 2026 | €18,000 |  | Budget of Montenegro | The activity was redefined through AP 2025-2026. |

STRATEGIC GOAL II CITIZENS AND BUSINESSES USE HIGH-QUALITY SERVICES OF THE PUBLIC ADMINISTRATION

| Operational goal 2.1 Higher efficiency of service delivery and introduction of service delivery quality management |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| Number of institutions with introduced quality management system | 0 | 1 | 1 | 11 |  | 5 | 15 |
| Citizens’ satisfaction with public services (Balkan barometer) | 2.9 | 3 | 2.8 | 4 |  | 3.5 | 3.7 |
| Percentage of administrative acts cancelled by the Administrative Court | 20.33% | 28% | N/A | N/A |  | 20% | 18% |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1.1 | Defining Roadmap for introducing service delivery quality management system | Roadmap defined at the Council for Public Administration Reform | MPA | Q1 2022 | Q2 2024 | The Roadmap of quality management in the public administration of Montenegro with a promotion plan for the period 2024-2026 was adopted by the Government on July 11, 2024 |  | €27,000 | €19,220 | Budget of Montenegro | The Roadmap was developed with the support of ReSPA through an on-demand tool |
| 2.1.2 | Development of methodology for introduction of quality management in the public administration system | Methodology for introduction of quality management in the public administration system developed and promoted | MPA ReSPA | Q3 2022 | Q2 2023 |  |  | €10,000 |  | Budget of Montenegro Donor funds - direct assistance from SIGMA | The development of the Methodology was discountinued |
| 2.1.3 | Implementation of quality management mechanism CAF and CAF performance assessment | CAF model implemented in three institutions/organisational units of the administration Report on external CAF evaluation in institutions/organisational units of the public administration | MPA ReSPA | Q3 2022 | Q4 2024 | CAF implemented in 3 institutions - MPA, Institute of Metrology and Municipality of Zeta, CAF quality management mechanism and made an improvement plan. |  | €75,000 | €11,200 | Budget of Montenegro Donor funds - direct assistance from SIGMA | Project implemented with the support of ReSPA |
| 2.1.4 | Establishing Public Administration Quality Management Network | - Institutions with the highest frequency of service provision to citizens and businesses in Montenegro identified - Focal points for establishing for Public Administration Quality Management Network identified - Minimum three Network meetings held | MPA Public administration authorities | Q2 2023 | Q4 2024 | A registry of institutions that use some of the quality management standards has been created and contact persons have been identified | Q1 2025 | €18,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 2.1.5 | Raising awareness on quality management system (CAF as one of the methods) and its relevance for public administration | - Experience and best practice exchanged between public administration employees aiming at raising service quality and service users satisfaction (via training, study visits, round tables, regional initiatives) - Web page development designated to quality management - Promotion activities on social media and videos, presentation of good practice at two round tables implemented | MPA Chamber of Commerce ReSPA | Q3 2022 | Q4 2024 | - Organised conference on the topic: “Quality Management in Montenegro - Doing the Right Thing.” - Created a page dedicated to the CAF method within the MPA portal - Created and published a video on CAF Quality Management |  | €53,000 | €5,716 | Budget of Montenegro |  |
| 2.1.6 | Work processes mapping with a view to optimise operations and introduction of management system at the level of public administration | Analysis for improving work processes and services with specific recommendations for improving internal organisation developed in minimum four pilot institutions (MPA, Sports and Youth Administration, Agency for Personal Data Protection and Free Access to Information, Social Welfare Centre Podgorica, Employment Agency) - Improvement and digitalisation of internal procedures (including streamlining) - Reorganisation and optimal work processes implemented in line with the Analysis | MPA MF APDPFAI Social Welfare Centre Podgorica Employment Agency Sports Administration LSGUs (Nikšić, Pljevlja) | Q2 2022 | Q2 2023 | CAF - 3 institutions (MPA, Institute of Metrology and Municipality of Zeta); ISO 9001 - 6 institutions (Ministry of Maritime Affairs, Directorate of Maritime Security and Port Management, Agency for the Prevention of Corruption, Ministry of Transport, Health Insurance Fund, Institute for Medicines and Medical Devices); BFC SEE - 2 institutions (Municipality of Bijelo Polje, Municipality of Bar) |  | €370,000 | €120,000 | Budget of Montenegro | The activity will be acknowledged through AP 2025-2026 |
| 2.1.7 | Improving reporting on administrative decisions quality | Methodology improved with adjudication on the merits in the II instance, data exchange as official duty and authorised official, parties present their position on the results of the proceedings and ping pong effect, repeated proceedings, detailed statistics on deciding of the Administrative Court with emphasis on the number and content of final decisions on its own merits in respect to specific administrative matter, and the number of decisions when administrative matters have been returned for repeated proceedings | MPA - Directorate for Efficient Good Governance Implementation SIGMA | Q3 2022 | Q1 2023 | The report on handling administrative matters for 2022 contains a new methodological approach |  | €6,000 | No funds were spent | Budget of Montenegro Donor funds - direct assistance from SIGMA |  |
| 2.1.8 | Creation of Catalogue of services in pilot institutions | Catalogue of services and administrative procedures pilot project in five institutions with cost estimate and possibility of digitalisation of specific services | MPA - Directorate for Efficient Good Governance Implementation | Q1 2022 | Q4 2024 | MPA developed a Guide to administrative procedures Drafted 10 Guides to administrative procedures. Guides under the jurisdiction of the Ministry of Public Administration and the Ministry of Sports have been published |  | €16,000 | No funds were spent | Budget of Montenegro |  |
| 2.1.9 | Creation of Catalogue of all services at the central and local level | Off-line and On-line Services Catalogue with analysis of their condition/quality with the concept of “human centered design” with an overview of administrative procedures and recommedations for further aligning of bylaws wth the Law on Administrative Procedure developed | MPA Public administration authorities SIGMA | Q1 2023 | Q4 2024 | The Catalogue developed |  | €372,000 | €300,000 | Budget of Montenegro Donor funds - direct assistance from SIGMA | In the first phase, services under the jurisdiction of 10 ministries were listed, while procedures were initiated with some. If the need for Phase II is recognised, services from the competence of other state administration bodies will also be listed. |
| 2.1.10 | MPA change management capacities improvement | Minimum 20 MPA civil servants attended specialised trainings related to work processes management, quality of delivered services and change of culture modeled after countries with the best practice | MPA | Q1 2023 | Q4 2023 | More than 30 employees underwent training in strategic planning, quality management, communication and presentation, improvement of service delivery and others |  | €16,000 | €25,000 | Budget of Montenegro |  |

| Operational objective 2.2 Full interoperability of information systems and increased number of electronic services with high level of sophistication |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| Number of digitalised services in a single portal in areas defined in line with EU methodology “eGovernment Benchmark” | 0 (2020) | 0 | 0 | 32 |  | 10 digitised services on a single portal | 20 digitised services on a single portal |
| Percentage of electronically submitted requests compared to the total number of submitted requests by users for pilot service use [1] | 0 | 85.3% | 86.14% | 86.14% |  | 15% per pilot service | 45% per pilot service |
| Number of electronic exchanges from registries in metaregistry | 8 (2021) | 12 | 16 | 16 |  | 30 | 50 |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.2.1 | “Montenegro Digital” project implementation | - Project adopted by the Government | MPA | Q1 2022 | Q3 2024 | The Montenegro Digital project has shifted its focus following the execution of the Agreement established with the EU for participation in the Digital Europe programme. The 59th session of the Government, held on November 28, 2024, adopted the Information on the activities related to the Digital Europe (DIGITAL) Project, which concluded this activity. |  | €1,900,000 |  | Budget of Montenegro |  |
| 2.2.2 | Designing new single public administration ePortal | - New public administration portal designed based on once-only principle in regards to integration of separated systems as a single point for all services of public administration: electronic payments, electronic authentication and electronic identification of users (availability of services delivered by LSGUs) - eGovernment portal improved to be accessible to people with disabilities | MPA– Directorate for Digitalisation and eServices | Q2 2022 | Q4 2024 | The new eGovernment Portal has been implemented. It is expected to go into production in March 2025 |  | €655,000 | €232,650 | Budget of Montenegro Donor funds EU/UNDP project “E-services and digital infrastructure as a response measure to COVID-19” |  |
| 2.2.3 | Development of new eServices in a single public administration portal in key life events | - 10 new eServices developed in line with eGovernment Benchmark minimum level of sophistication 3*/4* - Promotion activities- short videos on use of services, video instructions, information campaigns | MPA Public administration authorities | Q1 2022 | Q4 2024 | It is expected that 32 services will be installed on the eGovernment Portal, including services related to NGOs, the Ministry of Culture and Media and the Directorate for Diaspora. A promotional video was published on the MPA YouTube channel. | Q4 2026 | €337,000 | €275,305 | Budget of Montenegro Donor funds EU/UNDP project “E-services and digital infrastructure as a response measure to COVID-19” |  |
| 2.2.4 | Analysing method for keeping and managing state administration authorities and local self-government units registries | Analysis on the method for keeping and managing state administration authorities and local self-government units registries adopted with proposal of measures for improvement | MIA MPA MF | Q1 2023 | Q4 2023 | Analysis - Information on electronic data exchange between registries adopted on December 21, 2023 |  | €7,000 |  |  | Budget of Montenegro |
| 2.2.5 | Setting up electronic exchange of data between registries | - Development of new data exchange web services - Minimum 30 public administration civil servants attended training for setting up electronic data exchange between registries and SISEDE use | MPA MIA MJHMR Tax Administration UoM LSGUs Cadastre | Q1 2022 | Q4 2023 | Electronic data exchanges between 16 pairs of registries are currently active Interoperability Academy organised Workshops for ICT practitioners organised |  | €378,000 | €50,800 | Budget of Montenegro Donor funds EU/UNDP project “E-services and digital infrastructure as response measures to covid-19” |  |
| 2.2.6 | Establishing Certification Authority (CA) for state administration authorities and local self-government authorities needs and provision of qualified trust electronic services (certificates for: qualified electronic signature, qualified electronic seal and service of qualified time stamp) | - Certification Authority (CA) established with the status of qualified provider of trust electronic services - Number of issued certificates for state administration authorities needs for: qualified electronic signature and qualified electronic seal - Number of state administration authorities using qualified time stamp service - Number of local self-government authorities and administration authorities using qualified time stamp service | MPA LSGUs | Q1 2022 | Q4 2024 | The certification body (GovME CA) has been successfully established |  | €49,000 | €1,198,793 | Budget of Montenegro | The production solution is in use. The complete documentation has been prepared and the procedure for registering MPA in the Registry of Qualified Trust Service Providers will be completed soon |
| 2.2.7 | Connecting LSGUs to SISEDE aiming at data exchange | Technical requirements and safety standards for LSGUs access to this system aiming at data exchange established | MPA LSGUs | Q1 2022 | Q4 2024 | The capital city is connected to SISEDE and consumes CRS data (registry of the Ministry of Internal Affairs). Connection of other LGUs is underway |  | €270,000 | €14,949 | Budget of Montenegro |  |
| 2.2.8 | IT system upgrade with a view of data collection for statistical purpose | Increased use of CAPI, CAWI and introduction of CATI method for data collection | MONTSTAT | Q1 2023 | Q4 2024 | Increased application of the CAPI and CAWI method (in 2024, the CAPI method was introduced for one statistical survey and the CAWI method for one statistical survey) |  | €590,000 | €200,450 | Budget of Montenegro |  |
| 2.2.9 | Establishing efficient information systems (IS) and electronic services auditing within state administration authorities | - Guidelines for IS and electronic services auditing in state administration authorities developed - Two workshops for IT sector employees implemented aiming at training on key standards in managing IS | MPA MF | Q3 2022 | Q4 2024 |  | Q2 2026 | €27,000 |  | Budget of Montenegro | The activity will be acknowledged through the new AP 2025-2026 |
| 2.2.10 | Risk identification system quality raising in the process of IS and electronic services management | - Framework for risk identification in the process of IS management and use by state administration authorities analysed aiming at creating guidelines for raising IS quality level -Two workshops implemented for leaders on the role of IS auditing in raising the quality of risk management and controls in the area of IS and electronic services | MPA MF | Q2 2022 | Q4 2024 | - Analysis in progress - Held 3 workshops for over 50 participants, on the topic “IT controls and audit of the information system” for internal auditors in the public sector. | Q2 2026 | €38,000 | €7,500 | Budget of Montenegro | The activity will be acknowledged through the new AP 2025-2026 |
| 2.2.11 | Conducting analysis of needs and existing tools for IS auditing support with reference to use of CAAT software | Analysis on support tools for IS auditing conducted | MPA MF | Q2 2023 | Q4 2024 | Presented best practice on IS audit support tools from the Bosnia and Herzegovina public sector. The possibility of developing the same or similar application for internal audit purposes in Montenegro will be further considered. |  | €8,000 |  | Budget of Montenegro | The activity was recognised through the Public Finance Management Programme 2022-2026 |

STRATEGIC GOAL III PROFESSIONAL PUBLIC ADMINISTRATION

| Operational objective 3.1 Effective Efficient HR planning system based on identified needs, depoliticisation and improving human resources recruitment procedure and further digitalisation of civil service system |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| Percentage of authorities which developed their HR plan with improved quality through CPR Percentage of local self-government authorities and services at the local level which developed their HR plans through CPR in line with LCSSE and in line with LLSG | 28.5% of state authorities (2021) 0% of local self-government authorities and services (2021) | 82% of state authorities 0% | 92% of HR plans of state authorities were adopted for 2023 0% | 70% of state authorities 30% of local self-government authorities and services |  | 70% of state authorities 30% of local government bodies and services | 100% of state authorities 100% of local government bodies and services |
| Percentage of public institutions with adopted HR plan | 0 | 0 | 0 | 0 |  | Baseline established | 100% of public institutions |
| Percentage of HR plans adopted by state authorities and local self-government authorities | 63% of HR plans of state auhtorities 37% of HR plans of local government bodies | 82% of HR plans of state authorities 63% of HR plans of local government bodies | 92% of HR plans of state authorities were adopted for 2023 | 86% of state authorities |  | 100% of HR plans of state authorities and local government bodies | 100% of HR plans of state authorities and local government bodies |
| Average number of candidates per advertisement | Internal notice 1.1 Public notice 4.8 | Internal notice 2.1 Public notice 6.9 | Internal notice 1.92 Public notice 11.51 | Internal notice 0.54 Public notice 4.37 |  | Internal notice 1.6 Public notice 5 | Internal notice 1.8 Public notice 5.5 |
| Average number of candidates per competition | 2.14 | 2.46 | 3.14 | 1.68 |  | 4 candidates | 6 candidates |
| Number of HR functions where records are kept through HRIS alone | 0 | 3 | 3 | N/A |  | 3 records | 5 records |
| Percentage of local self-governments with developed HRIS | 0 | 0 | 0 | 0 |  | 30% | 100% |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1.1 | Conducting analysis of civil service system within public administration | - Analysis of civil service system conducted with reference to further model of developing civil service system, scope and further recommendations for improving civil service system - Action Plan developed based on conducted analysis | MPA – Directorate for Normative Affairs SIGMA | Q3 2022 | Q2 2023 |  |  | €14,000 |  | Budget of Montenegro Donor funds - direct assistance from SIGMA | Analysis discontinued |
| 3.1.2 | Drafting amendments to the Law on Civil Servants and State Employees | With the focus on strengthening internal labour market, mobility, amendments to assessing capacities and competences of civil servants, amendments to assessment procedure, internal labour market | MPA | Q2 2023 | Q4 2024 | The Government has approved the Bill |  | €7,000 | Budget funds not spent | Budget of Montenegro |  |
| 3.1.3 | Adopting of Competency Framework | Competency Framework for all categories of civil servants and applying the Competency Framework within the recruitment and assessment procedures – developed and adopted | MPA HRA | Q1 2022 | Q4 2023 |  | Q3 2025 | €9,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 3.1.4 | Innovation of Guidelines for HR Plan Development | HR Plan Development Guidelines amended in regards to alignment of HR plan development steps with the Law on Budget, previous analysis of employment needs, financial estimate for new employment with mid-term budget estimate, mandatory items and form for requests for budget funds allocation, termination of employment in the event that it includes severance pay, with information on employment outside of HR plan and other | MPA HRA UoM MF | Q1 2022 | Q3 2022 | Guidelines amended |  | €17,000 | No funds were spent | Budget of Montenegro |  |
| 3.1.5 | Organising trainings for civil servants in charge of innovated HR plan development | Minimum 90 civil servants trained | HRA | Q3 2022 | Q4 2024 | A total of 106 civil servants were trained |  | €9,000 | €4,500 | Budget of Montenegro |  |
| 3.1.6 | Establishing working group of MF-MPA-HRA for the purpose of preparing connection between HR plans and Budget draft | - Identified focal points from relevant institutions with the purpose of preparing -Improved coordination between identified institutions in regards to HR plan and Budget development coordination | MPA MF HRA | Q2 2022 | Q4 2022 | The activity was implemented |  | €3,000 | No funds were spent | Budget of Montenegro |  |
| 3.1.7 | HR plan connection to the Budget | - HR plans connected to Budget preparation, by means of improving HR Plans Development Guidelines, and development quality control and HR plans adoption and results monitoring - Analysis of quality of previous HR plans | MPA MF HRA | Q3 2022 | Q4 2024 | The guidelines for the development of the HR plan were upgraded. HR planning is connected with budget planning | Q3 2026 | €2,000 | No funds were spent | Budget of Montenegro |  |
| 3.1.8 | Improving Inspectorial Oversight of HRIS data | - Regular supervision plan publicly available -Inspectorial Oversight of HRIS conducted | AIA HRA | Q3 2022 | Q4 2023 | - Publicly announced plan - As per the findings from the 2023 report, nearly complete up-to-dateness was attained, with 110 out of 111 state authorities meeting the criteria. The MIA was the sole entity that did not attain current standards in the HRIS. The HRA provides the AIA with monthly updates regarding the current status of the HRIS. Supervision of the HRIS is conducted regularly. |  | €4,000 | No funds were spent | Budget of Montenegro |  |
| 3.1.9 | Improving applied candidates selection procedure | Decree on Assessment of Knowledge, Skills and Competences improved Developed system for e-application of candidates for HRA positions (with electronic delivery note) | MPA HRA | Q1 2022 | Q4 2024 | - Decree drafted - The technical concept of the e-application system has been developed, the tender procedure has been started | Q3 2025 | €60,000 | €30,000 | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 3.1.10 | Implementing promotion activities aiming at encouraging employment within public administration | - Developed videos on candidate selection process - Established HRA communication via social media – FB, Instagram and YouTube channel | HRA | Q3 2022 | Q4 2024 | - Video clips created - Communication established through FB, Instagram and Youtube channels |  | €46,000 | €17,000 | Budget of Montenegro |  |
| 3.1.11 | Establishing ILIAS platform for online learning with training programmes | - ILIAS platform for online training established at HRA - Minimum three training programmes developed at online platform for training | HRA | Q1 2022 | Q4 2024 | ILIAS Platform established - 3 training programmes published on ILIAS |  | €195,000 | €150,000 | Budget of Montenegro |  |
| 3.1.12 | Establishing internal mobility of civil servants via digital platform “Take Advantage of the Opportunities” | Developed module on ILIAS platform with available profiles of all civil servants and the list of key projects to be implemented by the Government for the purpose of making a link between necessary and available civil servants skills | HRA MPA | Q1 2023 | Q3 2023 |  | Q3 2026 | €54,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 3.1.13 | Establishing efficient functioning of Human Resources Information System | - Developed business processes analysis with recommendations on further HRIS components development - HRIS upgraded with the following modules: - HR plan - Training process from applying to evaluation - Annual leave recording process from applying to implementation - Training planning process for all state authorities and local self-government authorities – connected to the budget HRIS improved with forms on legal employment status (decision on appointing form, decision on employment form, decision on job assignment form, decision on termination of employment form, annual leave decision form and the like) | HRA | Q3 2022 | Q2 2024 | - Developed business process analysis with recommendations on further development of HRIS components - HRIS has been upgraded with the following modules: o HR plan o Training process from applying to assessment o Recording of annual leave o The training planning process for all state and LSG authorities - linked to the budget - HRIS improved with Decisions on legal employment status (decision on job assignment form, decision on establishment of employment form, decision on deployment form, decision on termination of employment form, decision on annual leave form, etc.) |  | €152,000 | €50,000 | Budget of Montenegro |  |
| 3.1.14 | Improving civil servants capacities for innovated HRIS use | - Instruction on HRIS Use improved in view of new modules – Three presentations organised on HRIS importance for heads of authorities and higher managerial staff - Three trainings organised for minimum 20 focal points for HR management | HRA | Q2 2024 | Q4 2024 | Improved Instruction. Held 5 trainings for managing the innovative Central Personnel Records for a total of 34 participants. |  | €25,000 | €7,500 | Budget of Montenegro |  |
| 3.1.15 | HRIS software upgrade related to HRIS local level development | - Analysis on the State of Play in HR Management within HR units on local level developed - Tender procedure development/project prepared and tendering - Local level HRIS system upgrade with HRIS functions at the central level | HRA MPA LSGUs UoM | Q2 2022 | Q2 2024 | - Prepared Analysis on the state of play in human resource management within HR units at the local level - Project prepared and tender announced - Development of the HRIS System at the local level in progress |  | €62,000 | €50,000 | Budget of Montenegro |  |
| 3.1.16 | Local level civil servants knowledge on HRIS use improvement | - Instruction on entering data into HRIS, development of HR plans, monitoring and reporting implemented – Three trainings organised for minimum 60 local level civil servants | HRA MPA LSGUs UoM | Q2 2024 | Q4 2024 | The activity has been implemented. Three trainings were organised for officials at the local level. |  | €13,000 | No funds were spent | Budget of Montenegro |  |

| Operational objective 3.2 Public administration attractive employer – efficient system of assessment, promotion and rewarding based on merits and continuous development |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| Percentage of assessed civil servants in state authorities | 63.38% (2019) | 46.6% [1] | 29%[2] | 54.09% |  | 100% | 100% |
| Percentage of civil servants promoted or rewarded based on their performance assessment | 0 | 0.01%[3] | N/A | N/A |  | 10% | 15% |
| Percentage of state authorities, state administration authorities and local self-government units with strategic training planning | Absence of strategic planning of training within state authorities, public administration authorities and local self-government units | 29% of state authorities strategically plan trainings, 16% of local self-government units strategically plan trainings | 29.5% of state authorities strategically plan trainings, 68% of local self-government units strategically plan trainings | 63% of state authorities strategically plan trainings; 32% of local governments |  | 50% | 100% |
| Percentage of new civil servants who were trained during their first year of work at initial positions of civil servant posts | Training programme for new employees developed | 2 training cycles implemented | 4.2% | 10.7% |  | 50% | 80% |
| Percentage of institutions measuring satisfaction of state level civil servants and local level civil servants | 0% | 0% | A total of 40 authorities participated in the survey conducted at the central level, with no activities carried out at the local level. | Satisfaction measurement performed in all local self-governments (the measurement was not performed at the central level) |  | 50% of public administration authorities, 20% LGUs | 70% of public administration authorities, 40% of LGUs |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.2.1 | Improving the quality of Internal Organisation Acts | -Amended criteria for systematisation acts development aiming at improving their quality using clear and precise job descriptions and description of competences necessary for good performance (mandatory development of analysis of existing jobs, job description of civil servant posts and requirements for duties concerned) and monitoring and evaluation of employees performance - Commission for Opinion Provison on Systematisation Acts comprised of HRA, MPA, MF representatives established | MPA HRA SIGMA | Q3 2022 | Q4 2024 | Activities commenced on the development of the catalogue, an analysis of the job descriptions based on current regulations was conducted, and two workshops took place with representatives from state authorities. | Q3 2026 | €17,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 3.2.2 | Improving employees performance assessment system | - Manual amended regarding employees performance assessment Employees in state authorities assessed using HRIS in pilot authorities | HRA LSGUs NGO | Q2 2022 | Q4 2024 | A new Manual for assessement, work monitoring and professional development has been prepared. Held training in pilot authorities for the implementation of e-assessment |  | €15,000 | €4,500 | Budget of Montenegro |  |
| 3.2.3 | Connecting assessment system with further professional development and training | - Performance based assessment system is connected to necessary trainings for further employees development - Employees attend professional development trainings on the basis of identified weaknesses within annual assessment process | HRA | Q1 2023 | Q3 2024 | Assessment system based on work performance linked with necessary trainings for further development of employees; Employees attended professional development trainings and improvement based on identified weaknesses within annual assessment process |  | €23,000 | €7,400 | Budget of Montenegro |  |
| 3.2.4 | Improving of rewarding system | System improved based on performance results(related to activity 3.3.2 – Law on Salaries in the Public Sector and Law on amendments to the Law on Civil Servants and State Employees amended in respect to employees performance measuring and defining efficient mechanism between employees performance results and rewarding) | MF MPA HRA | Q3 2022 | Q4 2024 |  |  | €18,000 | €5,167 | Budget of Montenegro | This activity has been discontinued |
| 3.2.5 | Training implementation in line with authorities needs | - Guidelines for development of training needs analysis revised - Five trainings for employees competent for training needs analysis implementation at the central and the local level realised | HRA MPA UMM | Q3 2022 | Q1 2023 | - Revised guidelines for the preparation of the Training Needs Analysis - Realised five trainings for employees responsible for conducting training needs analysis at the central and local level |  | €127,000 | €7,300 | Budget of Montenegro |  |
| 3.2.6 | Improving of professional development and training system | Decree on Professional Development and Training amended in regards to programme type, training effect analysis, training cycle management | MPA HRA | Q2 2022 | Q3 2023 |  | Q4 2026 | €7,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 3.2.7 | Set up/revise new civil servants training programmes | - New civil servants training programme set up/revised - Two cycles of new civil servants training programmes realised | HRA | Q3 2022 | Q4 2024 | - Set up training programme for newly employed civil servants - A total of 3 cycles were realised, attended by 78 participants. |  | €62,000 | €7,500 | Budget of Montenegro |  |
| 3.2.8 | Improving platform for e-trainings – establishing Digital Academy | -Guidelines for e-trainings developed at HRA -E-trainings platform improved - Minimum 20 trainings developed in line with guidelines for e-trainings | HRA | Q3 2022 | Q4 2023 | The Digital Academy has been established |  | €72,000 | €66,000 | Budget of Montenegro |  |
| 3.2.9 | Existing units/focal points for human resources analysis | - Developed analysis with recommendations for further improvement of work of units /focal points for human resources - Minimum 50 HR civil servants successfully finished training for acquiring knowledge and skills for HR management | HRA MPA | Q2 2022 | Q4 2024 | - In 2022, two trainings were organised on the topic: “Management of human resources to ensure proper business structure and compliance with particular IPA obligations”, with 22 participants; and a training programme for managers with 29 participants. - In 2023, two trainings were conducted on the topic: Leadership/management of organisational units, attended by 55 participants | Q4 2026 | €66,000 | €4,500 | Budget of Montenegro | The proposal for the upcoming AP 2026 has led to a modification of this activity, focusing on the development of Methodology and Analysis regarding the operation of human resources units |
| 3.2.10 | Network for Human Resources Management at the central level agenda development | - Analysis related to application solution for Network activities information exchange developed - E-platform for the Network established | HRA HR management units | Q2 2022 | Q4 2024 |  |  | €39,000 |  | Budget of Montenegro | This activity has been discontinued |
| 3.2.11 | Promoting the work of the Network for Human Resources Management at the central level | - Minimum three Networks for Human Resources Management meetings - Development and distribution of Network activities promotion material | HRA HR management units | Q2 2023 | Q3 2023 |  |  | €9,000 |  |  |  |
| 3.2.12 | Implementing specialised trainings for HRA employees | Minimum 20 employees at HRA and MPA attended standardised trainings of HR management institute in the country with the best HR management practice | HRA | Q2 2022 | Q4 2023 |  |  | €15,000 |  | Budget of Montenegro | This activity has been discontinued |
| 3.2.13 | Organising gender equality trainings for public administration employees | 200 participants attended gender equality trainings | HRA | Q2 2022 | Q4 2023 | A total of 272 participants underwent training on gender equality on the following topics: “Gender Equality”, “Resolution 1325 - Women, Peace and Security”, “Gender-Based Hate Speech”, “Gender Responsible Communication in Public Administration”, “Gender Equality Training for Communication Trainers”. |  | €45,000 | €12,500 | Budget of Montenegro |  |
| 3.2.14 | Organising training on inclusive public administration based on human rights principles | Two trainings on inclusive public administration based on human rights principles organised for: civil servants, managerial staff, Government Commissions members (Commission for Economic Affairs (CEA) and Commission for Political System (CPS)), HR Commission members and HRA, integrity managers, PR civil servants | HRA | Q1 2023 | Q3 2024 | Organised two trainings on the topics: The Right to Trial Within a Reasonable Time in Administrative Proceedings, (European Convention on Human Rights - Article 6) for 12 participants and Prohibition of Discrimination with 16 participants. |  | €12,000 | €3,000 | Budget of Montenegro |  |
| 3.2.15 | Leader competences development programme preparation | - Leader competences training developed including principles of diversity, equality, inclusiveness and accessibility - 30 leaders attended leader competences training - Expert group for encouraging 21st century leadership within public administration aiming at improving organisational culture and motivating managerial styles in the public administration established | HRA MPA GSG Prime Minister Office | Q1 2023 | Q4 2024 | Training programme for managers developed; Trainings for over 30 managers ongoing. |  | €43,000 | €75,000 | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 3.2.16 | Mentorship modules for public administration leadership development | - Mentorship modules for public administration leadership with focus on integrating principles of equality and human rights respect developed - 100 public administration employees received mentoring through modules | HRA MPA GSG Prime Minister Office | Q3 2023 | Q4 2024 |  |  | €23,000 |  | Budget of Montenegro |  |
| 3.2.17 | Promotion of public administration based on principles of diversity, equality and non-discriminatory policy | - Organised round table with the topic of public administration based on principles of diversity, equality and anti-discrimination in the process of recruitment and work within public administration authorities at leadership level - Videos for promotion of public administration based on principles of diversity and equality created | MPA | Q2 2022 | Q4 2024 | Participation in 3 events on the topic of inclusivity and gender equality Organised 1 panel discussion on the topic of public administration Created a training programme for gender equality in HRA - In cooperation with UNDP Montenegro, a video clip was created with the aim of empowering women in public administration |  | €56,000 | €37,000 | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 3.2.18 | Public administration employees digital skills improvement | - Digital skills training programme designed - Training for minimum 80 civil servants implemented | HRA MPA | Q2 2022 | Q2 2024 | - Training programme in preparation - In 2022, an advanced computer course was implemented in 3 groups with 31 participants. | Q4 2026 | €49,500 | €4,500 | Budget of Montenegro |  |
| 3.2.19 | Public administration employees digital skills improvement – within financial services | -Training programme for public administration financial services employees designed -20% of public administration financial services employees trained | HRA MPA | Q2 2022 | Q2 2024 |  |  | €49,500 |  | Budget of Montenegro | This activity has been discontinued |
| 3.2.20 | Public administration employees digital skills improvement – within legal services | -Training programme for public administration legal services employees designed -20% of public administration legal services employees trained | HRA MPA | Q2 2022 | Q2 2024 |  |  | €49,500 |  | Budget of Montenegro | This activity has been discontinued |
| 3.2.21 | Implementing promotion campaign on relevance of improving public administration employees digital skills | - Promotion campaign on importance of improving public administration employees digital skills developed - Number of promotion activities | MPA | Q1 2023 | Q4 2024 | Conducted promotional campaigns on the benefits of digitisation and the use of ICT through social networks Created educational (tutorials) and promotional material |  | €49,500 | €7,500 | Budget of Montenegro |  |
| 3.2.22 | Improving of skill gaps in respect to digital skills for future IT engineers positions within public administration | - Accredited digital skills programme needed for IT engineer positions within public administration - Minumum 120 persons trained on digital skills | University of Montenegro Employment Agency MPA NGO | Q3 2023 | Q4 2024 | In 2024, the University of Montenegro completed the accreditation of the Master’s study programme Information Security within the Institute for Interdisciplinary and Multidisciplinary Studies. |  | €307,000 |  | Budget of Montenegro |  |
| 3.2.23 | Improving capacities on e-accessibility concept | - 200 public administration employees trained on eAccessibility concept (document development) - 50 public administration website editors and 50 public administration website administrators trained on eAccessibility standards application in the process of public administration authorities websites planning and development - 5 MPA employees trained/certified in the area of eAccessibility standards for portal GOV.ME (WCAG 2.1) administrators. | HRA MPA LSGUs | Q2 2022 | Q4 2023 | Trainings were not organised due to technical, organisational challenges and lack of employees | Q2 2026 | €98,000 |  | Budget of Montenegro | The activity will be acknowledged through the new AP 2025-2026 |
| 3.2.24 | Administrators for applicative section of Single Information System for Electronic Data Exchange (SISEDE) capacities strengthening | 40 administrators of SISEDE information system trained | HRA MPA | Q1 2022 | Q4 2023 |  | Q1 2026 | €12,000 |  | Budget of Montenegro | This activity has been discontinued |
| 3.2.25 | Content administrators at portal data.gov.me training implementation | 66 administrators of data.gov.me information system trained | HRA MPA | Q1 2022 | Q4 2023 |  | Q4 2026 | €16,000 |  | Budget of Montenegro | The activity will be acknowledged through the new AP 2025-2026 |
| 3.2.26 | Promotion of data preparation in open data format | - Number of trainings held for public administration and local self-government units with the purpose of improving their skills and understanding when preparing data in open data format - Number of workshops held on the topic of open data for diverse stakeholders | MPA HRA CEM | Q2 2022 | Q4 2023 | 4 trainings on the topic of “Free Access to Information” were organised, with 119 participants at the state; and 2 trainings with 48 participants, at the local level. |  | €47,000 | €8,000 | Budget of Montenegro |  |
| 3.2.27 | Raising awareness on eServices provision relevance | - Number of implemented promotion events/workshops about public administration eServices provision relevance - Number of trained administrators and moderators of eGovernment portal | MPA HRA | Q3 2022 | Q4 2024 | - More than 10 promotional events were held on the complete importance of digital transformation. At these events, all systems managed by MPA were presented, all with the aim of creating electronic services and using shared systems. - 10 trained moderators |  | €24,000 | €17,000 | Budget of Montenegro |  |
| 3.2.28 | Raising capacities of civil servants at MPA on ICT project management | 10 employees trained on ICT project management | MPA | Q1 2022 | Q4 2023 | 20 employees of the Ministry of Public Administration were trained; The training lasted 6 months and consisted of five modules |  | €19,000 | €51,008 | Budget of Montenegro |  |
| 3.2.29 | Training implementation in ISO standards and GDPR (for certificates for implementators and internal audits) | - 20 public administration employees trained/certified for one of ISO standards - 20 public administration employees trained for GDPR | MPA | Q1 2022 | Q4 2023 |  | Q4 2026 | €25,000 |  | Budget of Montenegro | The activity will be acknowledged through the new AP 2025-2026 |
| 3.2.30 | Improvement of system for measuring public administration employees satisfaction | - Methodology for public administration employees satisfaction measuring improved - Standardised guidelines for public administration employees satisfaction measuring developed | HRA MPA | Q3 2022 | Q3 2024 | Methodology for public administration employees satisfaction measuring has been prepared - Based on the methodology, a satisfaction survey was carried out in Q3 2023. The guidelines are specified within the Methodology - Information on the results of survey was adopted by the Government 01/2024 |  | €25,500 |  | Budget of Montenegro |  |
| 3.2.31 | Implementing training for focal points within HR management units on employees satisfaction measuring procedures | - Number of HR management focal points trained on employees satisfaction measuring procedure -Promotion activities on importance of measuring employees satisfaction | HRA MPA | Q3 2022 | Q3 2024 | - 40 persons trained from public administration bodies. Conducted Satisfaction Survey in June 2023.G305 - Organised workshops for members of the Human Resources Network |  | €25,500 |  | Budget of Montenegro |  |

| Operational objective 3.3 Optimal administration |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| Number of institutions with amended organisational and functional structure based on functional analyses recommendations | 0 | 0 | 0 | 0 |  | The value will be established after functional analyses | The value will be established after functional analyses |
| Share of the total number of employees at the central and the local level in the total number of employees in Montenegro | 26% | 23% | 21.7 %​ | 21.1% |  | 23.70% | 22.3% |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.3.1 | Records/registry development for all employees at the central level financed from the budget of Montenegro | Records of employees at the central level developed at MF | MF LSGUs | Q1 2022 | Q3 2022 | Created records of employees at the central level in the Ministry of Finance |  | No funds needed. |  | Budget of Montenegro |  |
| 3.3.2 | Improvements to the normative framework regulating public sector salary system | - Law on Salaries amended in respect to employees performance measuring and defining efficient mechanism between employees performance results and rewarding; establishing mandatory single records keeping on the number of employees financed from the budget, creation of legal basis for employment termination by mutual consent and redundant labour with severance pay and establishing mechanism for limiting employment of persons who received severance pay with establishing of adequate mechanism for limiting re-recruitment within public administration during defined period of time, after receiving severance pay Relevant bylaws amendment | MF MPA MED LSGUs | Q1 2022 | Q4 2024 | Drafting of the Law amending the Law on Salaries of Employees in the Public Sector is in progress |  | €7,000 |  | Budget of Montenegro |  |
| 3.3.3 | Labour Law amendments | Labour Law amended in respect to establishing HR planning (HR plans) in institutions financed from the budget | MED MPA MF | Q2 2022 | Q3 2024 | The work of the Working Group on drafting the Draft Law is ongoing | Q2 2026 | €3,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 3.3.4 | Establishing efficient mechanism for concluding temporary service contracts and temporary employment contracts | - Increased Inspectorial Oversight of concluding temporary service contracts and temporary employment contracts - Personal Income Tax Law amended in respect to temporary service contracts tax rate increase - Promotion of concept on recruitment from the list of those who passed capacities assessment up to six months, in line with LCSSE | MF LSGUs | Q1 2022 | Q4 2024 | The Department of Administrative Inspectorate conducted inspections in all LGUs in 2023 | Q2 2025 | €17,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 3.3.5 | Public administration functional analysis development in stages | Public administration functional analysis with stages developed with recommendations for improvements in education and health sector (internal work processes, public administration efficiency and accountability, HR policy, number of employees and the like) | MPA MF LSGUs World Bank | Q3 2022 | Q4 2024 |  |  | €505,000 | €157,000 | Budget of Montenegro |  |
| 3.3.6 | Coordination of implementation of public administration optimisation recommendations (including development of functional analyses) | - Teams established applying sectoral approach aiming at monitoring of recommended optimisation measures implementation and developed functional analyses - Recommendations implementation in respect to developed functional analyses (according to AP time frame) - Coordination teams reporting on developed functional analyses implemented recommendations | MF MPA All ministries All PA authorities Public institutions | Q2 2023 | Q3 2024 | The activity is conditioned by the realisation of the previous activity 3.3.5 |  | €407,000 |  | Budget of Montenegro |  |
| 3.3.7 | Development of cost-benefit analysis on introducing common services for key administration functions aiming at work processes optimisation | - Analyses with recommendations on introducing common functions developed (legal service, accounting, HR management, procurement, real-estate management and the like) and merging regional units of authorities merged at the central level based on the Decree on Public Administration Organisation - Action Plan with defined further activities developed based on analysis recommendations (*connected to activity 1.1.12) | MF MPA MED MCI SIGMA | Q3 2022 | Q4 2023 |  |  | €108,000 |  | Budget of Montenegro | This activity has been discontinued |
| 3.3.8 | Creation of mechanism for controlling medical certificates for temporary inability to work (sick leave) | - Amended normative framework on health care adopted - Analytical material on the number of sick leaves and financial implications developed - Temporary inability to work monitoring mechanism created | MH MF MPA | Q3 2022 | Q4 2024 | National Commission for the control of abuses of temporary incapacity for work |  | €15,000 | €7,600 | Budget of Montenegro |  |

STRATEGIC OBJECTIVE IV TRANSPARENT AND OPEN PUBLIC ADMINISTRATION

| Operational objective 4.1 Improvement of the functioning of the system of legal protection in the FAI area and strengthening of the capacities of the Personal Data Protection and Free Access to Information Agency |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| Share of decisions of the Agency annulled by the Administrative Court, in relation to the total number of judgements in administrative disputes in relation to the decisions of the Agency | 42.17% | 17.10% | 5.67% | 1.43% |  | - 10 compared to the baseline value | -15 compared to the baseline value |
| Share of Administrative Court decisions in administrative disputes instituted because of the failure of the Agency to issue decision | 82.28% | 10% | 29.97% | 87% |  | 55% | 40% |
| Share of authorities which register requests for access to information in the information system (in relation to the total number of authorities) | 85.90% | -1365 | 1475 | 1475 |  | + 10 compared to the baseline value | + 20 compared to the baseline value |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1.1 | Improvement of the Free Access to Information Law | - FAI Law innovated in accordance with international and European standards - Amendments to the Law adopted | MPA – Legislative Affairs Directorate APDPFAI | Q1 2022 | Q4 2024 | New LFAI adopted |  | €3,000 |  | Budget of Montenegro |  |
| 4.1.2 | Improvement of the appeal and other procedures as well as of the formal organizational setup and practice of the Agency | - Analysis of the appeal procedure and other procedures conducted by the Agency developed | APDPFAI | Q1 2022 | Q4 2024 | Analysis of the appeal procedure done |  | €5,000 | €4,200 | Budget of Montenegro Donor funds |  |
| 4.1.3 | Digitization and improvement of work on the cases and record keeping | - Needs analysis conducted and ToR developed (with the option of establishing links with the information system, with the Administrative Court and the Supreme Court) - Electronic document management system introduced in the Agency | APDPFAI MPA | Q1 2022 | Q2 2024 |  | Q4 2026 | €60,000 |  | Budget of Montenegro | The activity will be acknowledged through the new AP 2025-2026 |
| 4.1.4 | Improvement of the functioning of the Agency information system and data publishing | - Analysis developed of the functioning of the information system from Article 41/2 of FAI Law - Categorisation revised, data input plan developed and the plan of basic statistical indicators (rulebook, plan) - Database on the authorities published in the open format - Appeals data entered (appeal linked to previously entered request) | APDPFAI MPA | Q4 2022 | Q4 2024 | Analysis is underway. - The conditions for linking the appeal procedure with the part of the IT System related to the appeal procedure have not been met due to the lack of funds | Q3 2026 | €87,000 |  | Budget of Montenegro | The activity will be acknowledged through the new AP 2025-2026 |
| 4.1.5 | Establishment of the FAI Council | - Legal framework for the establishment of the Council prepared - Two Council sessions held - Working parties established | APDPFAI MPA State authorities NGOs Media Academic Institutions | Q1 2022 | Q4 2022 |  | Q4 2026 | €3,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 4.1.6 | Strengthening the capacities of the APDPFAI | - Increase in the number of the employees of the APDPFAI at the annual level - At least six training sessions conducted for the employees of the APDPFAI | APDPFAI | Q2 2022 | Q4 2024 | - 8 people employed - Conducted special training by the Council of Europe in November 2024 |  | €40,000 | €40,000 | Budget of Montenegro |  |
| 4.1.7 | Trainings of the employees of the Agency aimed at strengthening the capacity for the implementation of FAI Law | - Programme of training and support created according to different needs and areas (sanctions, enforcement, restrictions, etc.) - 5 workshops implemented, 1 round table discussion, 1 study visit to the institution with best practice in certain issues for 5 APDPFAI employees | HRMA APDPFAI MPA MNE Courts SIGMA | Q1 2022 | Q4 2024 | Organised a round table on how to overcome existing challenges in the field of access to public information, with the support of SIGMA | Q4 2026 | €79,000 | €3,500 | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 4.1.8 | Providing continuous support to beneficiaries | - Improved information via the website and social networks, including the review and analysis of the website and other ways of communication (FAQ), phone line to be used by the beneficiaries, e-mail address - Open-door day organised for beneficiaries | APDPFAI FAI Council | Q1 2022 | Q4 2024 | The awareness of citizens via the website has been improved; Prepared a Manual for proactive publication of data on the websites of those obliged to apply the Law and a questionnaire for self-assessment of the compliance of authorities in fulfilling the obligations prescribed by the LFAI |  | €26,000 | €7,200 | Budget of Montenegro |  |
| 4.1.9 | Preparation and implementation of the Agency communication plan | - Development of the APDPFAI communication strategy - Strategy implementation report | APDPFAI | Q1 2022 | Q2 2024 | Funds are not provided and the activity was discontniued |  | €15,000 |  | Budget of Montenegro |  |
| 4.1.10 | Improvement of the methodology for the annual report of the Agency which is submitted to the Parliament | - Reporting methodology for the Parliament developed - Report published on the website and on networks | APDPFAI FAI Council | Q1 2022 | Q1 2023 | The activity is discontniued, the form of reporting is prescribed by law |  | €17,000 |  | Budget of Montenegro |  |

| Operational objective 4.2 Improvement of the application of the LFAI by those obliged to apply the Law and strengthening of the capacities of the users of the Law with a view to ensuring adequate exercise of the access to information right |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| Share of upheld appeals against administrative silence in relation to the total number of appeals | 23.15% (2020) | 23.5% | 29.5% | 35.34% |  | 15% | 10% |
| Share of decisions of the authorities annulled by the Agency in relation to the total number of appeals | 53.19% (2020) | 38% | 26.36% | 15.49% |  | 45% | 35% |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.2.1 | Providing support to chosen authorities with a view to improving the application of the LFAI | - Analysis developed and support plan prepared with recommendations for improvement for key identified authorities having most access to information requests and appeals (at least 10 authorities) - Number of requests reduced by 30%, quantity of information on the website increased by 30% | APDPFAI FAI Council | Q4 2021 | Q4 2024 | Identified institutions, training for identified key authorities having most access to information requests and appeals was held in December 2023, a workshop was organised with school secretaries and principals (schools were identified as authorities that had an increased number of requests) and training was held for FAI managers |  | €13,000 | €6,700 | Budget of Montenegro | Due to the large number of activities and challenges, other trainings will be organised in the following period, on a one-on-one basis. |
| 4.2.2 | Development of guidelines for the application of the provisions of the LFAI | - Guidelines for proactive publishing developed (by categories, as stated in the wording of the LFAI article, individually or as a whole) for the application of exclusions and restrictions related to free access to information, for conducting the harm test or public interest test, for certain LFAI related issues and the procedure | APDPFAI MPA NGOs FAI Council | Q1 2022 | Q4 2023 | Guidelines prepared |  | €26,000 | €7,000 | Budget of Montenegro |  |
| 4.2.3 | Development of browser of the decisions of the Agency and courts, with browsing option | - Needs analysis and the proposal of searchable base structure developed, including the proposals for linking judicial bases with the Agency eDMS - Applicative solution ordered and implemented with (at least) included option of browsing by the type of authority, restriction, key words and decision outcome | APDPFAI MPA Administrative Court / Supreme Court | Q1 2022 | Q2 2023 |  | Q3 2026 | €32,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 4.2.4 | Preparation of manuals, publications and training materials | - Manual for information officers in the authorities developed and published - Award established for the most proactive authority and manner of award presentation | APDPFAI MPA Ministries NGOs Academic community FAI Council | Q1 2022 | Q4 2023 | The draft of the Manual made after verification will be available on the Agency’s website |  | €36,000 | €6,200 | Budget of Montenegro |  |
| 4.2.5 | Continuous trainings ensured for authorised officers, managerial staff and other civil servants in the authorities | - Training Plan developed containing target groups (authorised persons, information officers, other persons, managerial staff), contents by category, contents by type, as well as trade secret, data marked by a degree of confidentiality, protection of personal data and privacy) - At least 200 persons underwent training | APDPFAI FAI Council HRA MF NGOs Academic community | Q1 2022 | Q4 2024 | - The training plan developed as part of the General Training Programme In 2024, 120 participants attended workshops covering this topic. When combined with the earlier timeframe and the count of participants, the overall total for this subject reaches 306. |  | €27,000 | €21,000 | Budget of Montenegro |  |
| 4.2.6 | Planning and implementation of continuous training and raising of awareness of the beneficiaries | - Strategic Plan developed for the identification of targeted beneficiaries and partnership - Advertising material developed (national TV and Radio) | APDPFAI FAI Council NGOs Media | Q2 2022 | Q4 2023 |  |  | €42,000 |  | Budget of Montenegro | The implementation of this activity has been discontinued |
| 4.2.7 | Training for lecturers for the application of the LFAI | - Training of trainers plan developed - Training of trainers conducted, with at least 15 trainers attending | HRA APDPFAI FAI Council NGOs Media Academic community | Q2 2023 | Q4 2024 | 4 APDPFAI employees were trained according to a shortened programme In 2024, two cycles of the Training of Trainers programme (TOT) were implemented, attended by 27 participants |  | €25,000 | €17,000 | Budget | The activity will be acknowledged in AP 2025-2026 |
| 4.2.8 | Development of internal FAI management / working parties for the improvement of transparency | - Guidelines developed for the establishment of the working parties of the LFAI at the level of the authorities - Establishment of the LFAI Working Party at the level of the authorities – at least 50 authorities in the first year, 100 in the second etc. | APDPFAI FAI Council Authorities | Q1 2022 | Q3 2022 | The activity is related to the formation of the FAI Council, the implementation of which is foreseen in the new AP 2025-2026 |  | €2,000 |  | Budget of Montenegro |  |
| 4.2.9 | Improvement of quality in the area of free access to information (questionnaire on the quality of access to information for the purpose of assessment and improvement of observance of the LFAI) | - Quality management model in the area of FAI developed with the purpose of application in the authorities, containing the following: - Self-assessment and action plan - Training of the employees | APDPFAI MPA FAI Council Authorities | Q1 2023 | Q4 2023 |  | Q4 2026 | €13,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 4.2.10 | Support to authorised persons in the authorities through the establishment of a network of authorised persons | - Special group of civil servants for information organised as a support to the Council (4.3.) - Communication channels secured (social network group, mailing list, online forum) | APDPFAI MPA Authorities | Q2 2022 | Q1 2023 | Organised information exchange meetings of authorised officials from the ministries |  | €2,000 |  | Budget of Montenegro |  |
| 4.2.11 | Establishment of high-quality fiscal transparency for the authorities | - Budget transparency strengthening plan prepared in accordance with international and European standards - Pilot plan prepared in at least 20 authorities of various groups | APDPFAI MF MPA FAI Council Authorities NGOs Academic community | Q1 2022 | Q4 2023 |  | Q4 2026 | €4,000 |  | Budget of Montenegro | The implementation of this activity has been discontinued |

| Operational objective 4.3 Improvement of information reuse and increasing the availability of open data |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| Number of datasets on the Open Data Portal www.data.gov.me | 146 (2021) | 197 | 0 | 456 |  | 500 | 800 |
| Number of institutions publishing the data on the Open Data Portal | 1.5% institutions obliged to apply the LFAI | 1.5% | 0 | 2.18% |  | 10% of institutions subject to FAI | 15% of institutions subject to FAI |
| Number of published high-value datasets with APIs on the Open Data Portal | 0 | 0 | 0 | N/A |  | At least 10 | At least 20 |
| Share of authorities which publish proactively the information in line with the LFAI | Baseline value will be determined on the basis of the Report of the operation of the Agency in March 2021 | The baseline value will be determined in 2023 for all ministries, GSG, CC Podgorica, municipalities of Nikišić and Herceg Novi | 47 inspections of 47 subjects of application | 85 inspectorates |  | 65% of ministries and other (selected) administrative authorities 65% of local governments | 80% of ministries and other (selected) administrative authorities 80% of local governments |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.3.1. | Development of the Draft amendment to the LFAI in the part related to information reuse and open data | Analysis of alignment of the existing provisions of the LFAI with European standards and Open data Directive with recommendations for improvement | MPA – Legislative Affairs Directorate Open Data Council | Q3 2023 | Q2 2024 |  |  | €12,000 | €3,200 | Budget of Montenegro |  |
| 4.3.2 | Improvement of www.data.gov.me portal | - Increased number of total datasets (50%) as well as of dynamic datasets (50%) - Analysis of the need for improving the functionality of the Portal | MPA MONSTAT Union of Municipalities of Montenegro Local self-government units Authorities obliged to apply the LFAI Open Data Council | Q1 2022 | Q4 2024 | The new Open Data Portal is in operation at www.data.gov.me |  | €67,000 | €110,000 | Budget of Montenegro |  |
| 4.3.3 | Identification and review of already published datasets | Existing sets updated – at least 75% of datasets on the Portal - Pilot project in ministries, chosen authorities and chosen local self-governments for the publishing of data in open format (at least 30 authorities) | MPA Authorities obliged to apply the LFAI | Q2 2022 | Q4 2024 |  |  | €37,000 | €21,000 | Budget of Montenegro |  |
| 4.3.4 | Identification of high value open datasets- pilot initiatives for key areas like public finance, geolocation, healthcare, transport | - Completed analysis of high value datasets developed, with recommendations - Increased number of high value open datasets (at least 10) | MPA MF MED MH MCI Open Data Council | Q3 2022 | Q4 2023 |  | Q4 2026 | €17,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 4.3.5 | Organisation of campaign with a view to raising awareness of the public and of public administration on the importance of open data and their value | - At least 2 promotional events organised - At least 6 training events organised for civil servants tasked with entering datasets onto the data.gov.me Portal - At least 2 Hackatons on the occasion of Open Data Days (March every year) | MPA HRMA NGOs Association of Montenegrin Managers Academic community CCM Authorities obliged to apply the LFAI Open data Council | Q3 2022 | Q4 2024 |  | Q4 2025 | €62,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 4.3.6 | Improving the availability of gender equality data | - Development of Manual for the application of GAP III European standards for publishing gender equality data - Rasing the awareness of public administration bodies of the publishing of gender equality data on the Open Data Portal | MPA – Innovation Directorate All public administration bodies | Q2 2023 | Q4 2024 |  | Q4 2026 | €15,000 |  | Budget of Montenegro Donor funds | The activity will be acknowledged through the new AP 2025-2026 |

STRATEGIC OBJECTIVE V POLICY PLANNING WITH AND FOR CITIZENS

| Operational objective 5.1 Strengthening the data-based planning system that leads to sustainable policies and achievement of Government priorities |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| Percentage of new strategic documents fully aligned with the methodological criteria | 69% (2020) | 50% | 76.33 %​​ | 66.66% |  | 75% | 80% |
| Percentage of reports on implementation of strategic documents that are fully aligned with the methodology | 52% (2020) | 38% | 51.06 % | 58.82% |  | 65% | 70% |
| Percentage of ministries with Annual Work Programmes that contain clear objectives and indicators | 18% (2019) | 0% | 0% | 0% |  | 80% | 100% |
| Percentage of ministries with annual performance reports that present the result as per the set objectives and indicators | 0% | 0% | 0% | 0% |  | 80% | 100% |
| Percentage of strategic documents followed up by evaluation | The baseline value will be determined after the analysis (2022) | 31% | 60% | 62% |  | 40% | 60% |
| Percentage of policy consultations conducted in line with the legal framework and SIGMA principles compared to the number of Government acts subject to public consultation | 0 | 23.1%[8] | 32.86% | N/A |  | 100% | 100% |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1.1 | Development of a supplemented methodology for medium-term planning of the work of the Government and the ministries | -- Official promotion of the methodology held - Presentation of the methodology held (at least once in the line ministries) | GSG SIGMA | Q1 2022 | Q3 2024 | A draft Methodology was developed. The preliminary document was presented to the Ministry of Finance and MEA for feedback; however, the ongoing political instability and the restructuring of public administration hindered effective coordination on this matter, resulting in delays in finalising the Methodology. | Q3 2025 | €15,000 |  | Donor funds, project „Strengthening the capacities of the Montenegrin authorities for the EU accession process II”, UNDP; MFA of the Kingdom of Norway | The continuation of the development of the Methodology is ensured through the EU4PFM project, the implementation of which began in late 2024, and this activity will be recognised through the new AP 2025-2026. |
| 5.1.2 | Delivery of training on the development of medium-term work programmes of the ministries and development for the 2023-2025 cycle | - Number of training events on developing MTWP for the civil servants responsible for these activities Developed 2023-2025 MTWP in all ministries | GSG MPA SIGMA | Q2 2022 | Q4 2024 | It is necessary to implement activity 5.1.1 beforehand | Q4 2025 | €6,850 |  | Donor funds, EU/SIGMA support | The activity will be acknowledged in AP 2025-2026 |
| 5.1.3 | Revision of the Training Programme for Strategic Planning in terms of the topics covered and pool of participants | Revised contents of the Training Programme for Strategic Planning to cover gender mainstreaming and environmental impact assessment, with the pool of participants expanded to the civil servants working in other state institutions and local governments | GSG HRA MJHMR MESPU LSGUs | Q1 2022 | Q1 2022 | The strategic planning education programme revised. The incorporation of gender equality considerations and a strategic evaluation of environmental impacts has enhanced the programme. |  | €5,200 | €1,870 | Donor funds-OSCE |  |
| 5.1.4 | Organisation of training as per the revised Programme | - Number of delivered Programme cycles - Number of trained participants (central and local levels) who completed the Programme | GSG HRA | Q1 2022 | Q1 2023 | In total, the fifth cycle of the programme was implemented. Since the beginning of implementation, the Programme has been attended by 23 civil servants and 112 civil servants. The education programme is part of the HRA training agenda |  | €15,000 | €11,800 | Human Resources Administration |  |
| 5.1.5 | Development of the analysis on the mechanisms for cooperation with researchers and producers of official statistics | Developed analysis and identified mechanisms for establishing systemic cooperation between researchers and state administration | GSG | Q1 2022 | Q1 2022 | Analysis done |  | €3,600 | €7,250 | Donor funds, project “Strengthening the capacities of the Montenegrin authorities for the EU accession process II”, UNDP; MFA of the Kingdom of Norway |  |
| 5.1.6 | Piloting of selected mechanisms for cooperation with researchers for joint policy design and use of data for policy making | Number of strategic documents that integrated the findings of scientific research | GSG | Q1 2022 | Q2 2022 | Piloted 3 strategic documents |  | €5,940 | €53,700 | Donor funds, project “Strengthening the capacities of the Montenegrin authorities for the EU accession process II”, UNDP; MFA of the Kingdom of Norway | Propose the same principle of cooperation for other strategic documents |
| 5.1.7 | Development of guidelines for integrating research findings and official statistics in the next policy planning cycle | Developed guidelines for using research findings in policy design | GSG in cooperation with MONSTAT | Q1 2022 | Q2 2022 | Guidelines developed |  | €1,620 | €9,540 | Donor funds, project “Strengthening capacities for faster accession of Montenegro to the European Union II”, UNDP; MFA of the Kingdom of Norway | Refer departments to the Guidelines when planning the creation of new strategic documents and use them as one of the textbooks for the Strategic Planning Education Programme |
| 5.1.8 | Development of an analysis on the implementation of strategic document evaluation | Developed analysis with information on the implementation of evaluations of strategic documents and recommendations for improvement | GSG | Q1 2022 | Q1 2022 | Based on the analysis, prepared Manual for evaluation of strategic documents |  | €2,420 | €2,250 | Donor funds, project “Strengthening the capacities of the Montenegrin authorities for the EU accession process II”, UNDP; MFA of the Kingdom of Norway |  |
| 5.1.9 | Development of a Manual on evaluation and incorporation of evaluation and reporting findings in the new policy planning cycle | Developed Manual | GSG | Q1 2022 | Q3 2022 | A methodological guide was created for the evaluation of strategic documents in accordance with the OECD-DAC criteria. The manual on evaluation of strategic documents is publicly available. |  | €7,000 | €6,210 | Donor funds, project “Strengthening the capacities of the Montenegrin authorities for the EU accession process II”, UNDP; MFA of the Kingdom of Norway, support | Familiarise officials with the manual and use it as one of the textbooks for the Strategic Planning Education Programme. |
| 5.1.10 | Development of digital contents (video material, short reports) on the policy planning process | Developed digital contents available at www.javnepolitike.me | GSG | Q1 2022 | Q4 2023 | Short animations on the topic of strategic planning were made |  | €6,150 | €3,000 | Donor funds, project “Strengthening the capacities of the Montenegrin authorities for the EU accession process II”, UNDP; MFA of the Kingdom of Norway |  |
| 5.1.11 | Development of a list of standard costs in drafting strategies | Developed list of standard costs | GSG MF | Q2 2022 | Q3 2022 | The implementation approach was defined between GSG and MF. Due to unstable political conditions, as well as due to the process of reorganisation of the public administration, there was no effective coordination on this issue and the work was prolonged. | Q4 2026 | €2,400 |  | Donor funds, project “Strengthening the capacities of the Montenegrin authorities for the EU accession process II”, UNDP; MFA of the Kingdom of Norway | It is planned that the activity will be implemented through the EU4PFM project. The activity will be acknowledged through the new AP 2025-2026 25-2026.ovi AP 2025-2026.26.ste. |
| 5.1.12 | Defining the list of national performance indicators per sector of policies, to be regularly produced and monitored | - Defined list of national performance indicators, linked with IPA - Number of performance indicators being regularly produced and monitored - Number of performance indicators aligned with IPA indicators | GSG MF EAO MONSTAT | Q2 2022 | Q4 2024 | A list of national sustainable development indicators that are monitored at the national level has been set. An overview of the indicators is available at: Indicators for Sustainable Development Goals (sdgmontenegro.me) |  | €1,000 | €4,300 | Budget of Montenegro |  |
| 5.1.13 | Development of a methodology for integrated strategic planning | Developed methodology for integrated strategic planning which links the policy planning process with the budget planning process | GSG MFSW MPA EAO SIGMA | Q2 2022 | Q4 2024 | A draft methodology was prepared, the key aspect of which is related to the alignment of the strategic planning process with the budget process. | Q3 2025 | €12,500 | €12,500 | Donor funds, EU support | The activity will be integrated into activity 5.1.1- Development of the Methodology for medium-term planning of the work of the Government and ministries within the new AP 2025-2026 |
| 5.1.14 | Upgrade of the methodology for policy planning, drafting and monitoring of implementation of strategic documents related to gender mainstreaming | Methodology upgraded in terms of the impact of strategic documents on gender equality | GSG | Q3 2022 | Q3 2023 | Methodology improved. The application of the innovative Methodology and opinion forms began in Q2 2023 |  | €7,500 | €8,452 | Donor funds, OSCE support |  |
| 5.1.15 | Development of an analysis of the IT system for strategic planning (MESPH), monitoring and reporting (ISPI), programme-based and medium-term budget | Developed analysis of the existing IT systems with options for connecting them | GSG MPA MFSW | Q1 2023 | Q4 2023 | In July 2023, the Information on the establishment of a coordination system of strategic partners was adopted, and in September 2023, ISPI was revitalised, after a cyber attack. The potential for integration with IT systems utilised for programme budgeting has been established. In the upcoming period, it is essential to define precise technical specifications for their connection, as a prerequisite for their effective integration. | Q3 2026 | €5,400 | €3,718 | Donor funds, EU support | The MESPH portal is under the jurisdiction of the MEA, and from the aspect of strategic planning, it has no further importance at the moment. Work on the improvement of ISPI will continue in the coming period and activities on more complete technical specification for linking with programme budget software will be planned in the new AP 2025-2026 |
| 5.1.16 | Development of an analysis of the legislative framework on strategic planning | Developed analysis of the possibilities for improvement of the regulatory framework on strategic planning | GSG | Q1 2023 | Q4 2024 | A comprehensive analysis of the strategic planning framework in Montenegro for the year 2024 was conducted, providing an overview of the current status of the strategic planning system and its practical implementation. The analysis took into account the implementation of the current regulatory structure for strategic planning, while noting the obstacles that require attention. |  | €4,600 | €4,600 | Donor funds, EU support |  |
| 5.1.17 | Delivery of training for the civil servants involved in drafting legislation and strategies on the standards related to stakeholder consultations in the course of development of laws and strategies | At least 80 civil servants trained | HRA MPA | Q3 2022 | Q2 2024 | The trainings were not organised due to technical and organisational deficiencies and the lack of staff. | Q4 2026 | €17,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 5.1.18 | Upgrade of the report on the implementation of the Decree on the election of NGO representatives and conduct of public consultatitions in the process of drafting laws and strategies | - Revised structure of the report, with upgraded statistics and additional information on the satisfaction of the working group members, annual evaluation of the conducted public consultation processes - Number of working bodies involving LSGU representatives | MPA GSG | Q2 2022 | Q3 2022 | Report on the implementation of the Decree on the election of representatives of non-governmental organisations to the working bodies of public administration bodies and the implementation of public consultations in the procee of drafting laws and strategies improved, for 2022 and 2023 |  | €5,000 |  | Budget of Montenegro | In the next report, clearly highlight the satisfaction of the participants in the working groups, as well as the number of working bodies in which representatives of LGUs are included |
| 5.1.19 | Efficient use of e-platforms for public participation in policy design | - Developed analysis of the reasons behind poor utilisation of the e-petition and e-participation portals, with relevant recommendations - Overcoming of the already identified challenges on the basis of user experience and implementation of the recommendations generated by the analysis (e-petition validation deadline, access from tablets and mobile phones etc.) - Promoted good practices of public participation in the policy design process, with particular focus on the consultations during the initial stages of document development - The e-petition and e-participation portals promoted | MPA | Q3 2022 | Q3 2024 |  | April 2026 | €87,000 |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |

| Operational objective 5.2 Enhanced institutional coordination for stronger policy impacts |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| % of ministries that set up the strategic planning units | 30% (2021) | 22.2% [1] | 26.3%[2] | 24% |  | 70% | 100% |
| % of ministries that have civil servants who are members of the Strategic Planning Network | 50% (2021) | 87.50% | 89.50% | 100% |  | 70% | 100% |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.2.1 | Development of the Briefing Note on the need for setting up the strategic planning units merged with IPA programming | The Briefing Note adopted by the Government, with recommendations and conclusions concerning further activities | GSG EIO | Q1 2022 | Q1 2022 | Briefing Note on the work of the Sector for Strategic Planning in 2022, adopted on February 24, 2023, and Briefing Note on the establishment of a strategic partner coordination system adopted on August 3, 2023. |  |  |  | Budget of Montenegro |  |
| 5.2.2 | Amendment to the ministries’ Rulebooks on job systematisation (classification) to identify the units for strategic planning and IPA programming | Number of ministries with Rulebooks on job systematisation that include merger of the strategic planning unit and IPA unit | Ministries, with GSG as a coordinator | Q1 2022 | Q4 2024 | By January 2025, six ministries set up their organisational units. The recent restructuring of the public administration has led to a notable rise in the number of ministries, which currently stands at 25. This alteration raises concerns regarding the financial viability of the suggested solution. During discussions with SIGMA and in the evaluation of the strategic planning framework, a different approach was proposed. This involves identifying essential policy coordination roles that would complement the existing positions within the ministries. | Q1 2026 |  |  | Budget of Montenegro | It is necessary to redefine the proposed model in accordance with the findings of the Strategic Planning and Communication System Analysis with SIGMA and propose appropriate activities for the new AP 2025-2026 |
| 5.2.3 | Establishment of strategic planning units merged with IPA programming | Number of ministries with strategic planning units set up and merged with IPA units | Ministries, with GSG as a coordinator | Q1 2022 | Q4 2024 | Strategic planning units have been established in 6 ministries so far | Q1 2026 |  |  | Budget of Montenegro | The activity will be transferred to the next AP and will be redefined in accordance with the comment for activity 5.2.2. |
| 5.2.4 | Development of a Briefing Note on the formalisation of the Strategic Planning Network | The Briefing Note adopted by the Government, with recommendations and conclusions concerning further activities | GSG | Q2 2022 | Q2 2022 | It is necessary to implement activity 5.2.3 previously - officers employed in strategic planning units should be members of the Network | Q3 2026 | €1,600 |  | Budget of Montenegro, Donor funds, project „Strengthening the capacities of the Montenegrin authorities for the EU accession process II”, UNDP, Ministry of Foreign Affairs of the Kingdom of Norway | The activity will be linked with activity 5.2.5 and accordingly included in the new AP 2025-2026 |
| 5.2.5 | Formalisation of the Strategic Planning Network | Number of civil servants included in the Network/Number of ministries that have two representatives in the Network | GSG | Q2 2022 | Q3 2022 | It is necessary to implement activity 5.2.3 previously - officers employed in strategic planning units should be members of the Network | Q3 2026 | No funds needed |  | Budget of Montenegro | The activity will be linked with activity 5.2.4 and accordingly included in the new AP 2025-2026 |
| 5.2.6 | Develop the agenda and work plan of the Strategic Planning Network for the period 2022-2024 | Network Agenda for 2022-2024 designed and adopted | GSG Network (line ministries) | Q2 2022 | Q4 2022 | The current status has been outlined, highlighting recognised challenges alongside the advantages of formalisation, as detailed in Briefing Note on the formalisation of the Network’s operation. Furthermore, the criteria for selecting the members of the Network were established, along with the Network’s positioning concerning the line ministries and GSG. |  | €5,000 | €7,700 | Donor funds, project „Strengthening the capacities of the Montenegrin authorities for the EU accession process II”, UNDP |  |
| 5.2.7 | Develop guidelines for ministries on the coordination mechanisms ad internal policy planning procedures | Developed guidelines that explain the mechanisms and procedures for policy design and coordination in the ministries | GSG Network | Q1 2023 | Q1 2024 | It is essential to carry out actions aimed at establishing the policy coordination role within the ministries, while also clarifying the specifics of this role to appropriately outline the content of the guidelines. In the upcoming phase of policy planning, the role of policy coordination will be established, serving as a crucial function across all ministries. | Q3 2025 | €4,700 |  | Donor funds, EU support | The activity will be acknowledged in AP 2025-2026 |
| 5.2.8 | Develop guidelines for aligning national policy planning with IPA programming | Developed guidelines | GSG EIO MFSW | Q2 2023 | Q4 2023 | The guidelines were prepared in May 2022 |  | €3,800 | €3,800 | Donor funds, EU support |  |
| 5.2.9 | Develop an analysis of the relations between national-level and local-level strategic documents | Developed analysis on the relations between the national-level and strategic-level documents, with recommendations for improvement | GSG UOM LSGUs | Q1 2023 | Q4 2023 | The initiative was halted, as it is essential to initially document the local support requirements and subsequently outline the strategy and focus for addressing the identified needs. |  | €4,600 |  | Donor funds, EU support |  |

| Operational objective 5.3 Expand the scope of RIA and strengthen the capacities for its implementation |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | Baseline value | Value for 2022 | Value for 2023 | Value for 2024 | Trend | Target value by 2024 | Target value by 2026 |
| Percentage of laws with RIAs that implement the Standard Cost Model | 18% (2020) | 18.5% | 18.75% | 27.04% |  | 20% | 30% |
| Percentage of high-quality RIAs against the total number of RIAs delivered to the MFSW for its opinion | 68.72% (2020) | 82.49% | 83.15% | 89.86% |  | 77% | 88% |

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.3.1 | Revision of the Guidance on development of RIA Reports and RIA Manual | Revised Guidance section on the budgetary impact on LSGUs and gender equality, revised RIA Manual | MF | Q2 2022 | Q4 2024 | The draft Manual for Regulatory Impact Assessment (RIA) and the Regulatory Impact Analysis Report for the preparation of comprehensive RIA was presented to the representatives of the RIA network and prepared in October 2024. After that, the text was improved in accordance with the suggestions of representatives of the RIA network and the business community. | Q2 2025 | No funds needed |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 5.3.2 | Delivery of training on the implementation of the techniques used to estimate costs of regulations and consideration of long-term fiscal impact of regulations | 140 civil servants trained | HRA MF | Q1 2022 | Q4 2023 | Trainings were attended by 300 officials on the following topics: Introduction to the Regulatory Impact Assessment, Economic Analysis, Fiscal Analysis and Practical Work |  | €12,500 | €13,000 | Budget of Montenegro |  |
| 5.3.3 | Upgrade of the annual reports on the quality of preparation of RIA, by ensuring involvement of external evaluators in the quality assessment exercise | 2 upgraded annual reports on the state of play concerning RIA | MF | Q4 2022 | Q4 2024 | The report for 2023 was adopted on April 25, 2024. The report for 2024 will be prepared in April 2025 |  | €2,400 | No funds were spent | Budget of Montenegro |  |
| 5.3.4 | Make all RIAs publicly available on the consolidated new e-government portal | Number of RIAs on the new e-government portal | MPA MF | Q3 2022 | Q4 2023 | All RIAs since 2012 have been published on the MF website: https://www.gov.me/mif/analiza-efekata-propisa-ria |  | €3,000 | No funds were spent. | Budget of Montenegro |  |
| 5.3.5 | Upgrade of the template for the MF opinion on RIA | Adopted upgraded template for the mandatory opinion and feedback on the quality of RIA | MF | Q1 2022 | Q4 2024 | In cooperation with SIGMA, a draft manual was prepared and the improved opinion form will be part of this manual. | Q4 2025 | No funds needed |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |
| 5.3.6 | Establish cooperation with the Parliament to ensure better RIA implementation | Number of consultations and trainings held | MF | Q1 2022 | Q4 2024 | Cooperation with the Parliament has been established, and during 2025, trainings will be organised for representatives of the Parliament | Q4 2025 | No funds needed |  | Budget of Montenegro | The activity will be acknowledged in AP 2025-2026 |

STRATEGY IMPLEMENTATION, MONITORING AND REPORTING ACTIVITIES

|  | Activity | Outcome indicator | Competent institutions | Start | End | Indicator implementation status | New deadline | Funds planned | Funds realised | Source of funding | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Increase the capacity of employees of the Directorate for Strategic Planning, International Cooperation and IPA funds | - At least 4 employees have completed accredited strategic management training - At least 4 employees have completed specialised training | HRMA Specialised training providers | Q2 2022 | Q2 2024 | - 4 employees received strategic planning training - 6 employees underwent specialised CEF training |  | €49,000 | €53,000 | Budget of Montenegro |  |
| 2 | Improved coordination of the identified implementing institutions and MPA | - Four two-day monitoring and reporting workshops are organised for the contact persons of the institutions identified in the Strategy - Study visit of MPA to a country with the best strategic monitoring system is organised | MPA Relevant institutions listed in the Strategy | Q3 2022 | Q4 2024 | - At least one two-day workshop was organised annually - MPA organised 4 study visits |  | €86,000 | €71,000 | Budget of Montenegro |  |
| 3 | Development of additional mechanisms for better monitoring and reporting on the results of the Strategy 2022-2026 | - Analysis of the best regional practice concerning the monitoring system for the Strategy implementation is developed - Tender dossier is developed for developing an IT system for monitoring purposes - Creation of IT solutions for monitoring the strategy implementation | MPA | Q1 2022 | Q4 2024 | - The analysis preparation is in progress through the technical support project - Activities related to the IT system are under the competence of GSG |  | €105,000 |  | Budget of Montenegro |  |
| 4 | Promotion of the AURUM, achieved results and activities | Plan for implementing the AURUM communications strategy is adopted, covering 2022 – 2024 | MPA | Q2 2022 | Q4 2024 | - The communication plan for the AURUM is being developed - Prepared bilingual abbreviated version of the AURUM |  | €120,000 | €1,942 | Budget of Montenegro |  |

The Public Administration Reform Strategy 2022-2026, along with its initial three-year Action Plan covering 2022-2024, was officially adopted in December 2021. This strategy was developed through a comprehensive and inclusive process, involving extensive consultations among all pertinent institutions. The Strategy’s structure adhered to the logic of the reform areas outlined in the document Principles of Public Administration. Additionally, the wider strategic framework of relevant EU policies and UN agenda was considered, influencing the definition of goals and activities while ensuring alignment with national overarching documents.

The indicator is formulated as "Amount collected by means of enforcement procedure in labour cases handled by the Protector of Property and Legal Interests". However, according to the current reporting structure of the Protector, it is possible to report only on the total amount of forcibly collected funds. Currently, it is impossible to single out a category of labour disputes.

drop in value compared to 2020 improvement compared to 2020 value same trend compared to 2020 data unavailable or not tracked

4 Information from the Protector of Property and Legal Interests of Montenegro for the reporting period from October 1, 2023 until December 31, 2023

Information from the Protector of Property and Legal Interests of Montenegro, for the reporting period from October 1, 2024 until December 31, 2024

Annual work report of the Administrative Court for 2024

Percentage of Ministries that delegated financial management and internal control powers to senior management in accordance with the Regulation in 2022

Information on the percentage of realisation of indicators was difficult to determine due to frequent organisational changes and turnover of employees in managerial positions. Source: Consolidated report on management and internal controls in the public sector of Montenegro for the year 2023

Not all ministries submitted data.

Ministries and local self-government

The data collection process is underway

Public debt of all local self-government units as of December 31, 2023 (€107.78 million) compared to the total receipts at the level of all local self-government units for 2023 (€486.26 million).

CAF - 3 institutions (MPA, Institute of Metrology and Municipality of Zeta); ISO 9001 - 6 institutions (Ministry of Maritime Affairs, Directorate of Maritime Security and Port Management, Agency for Prevention of Corruption, Ministry of Transport, Health Insurance Fund, Institute for Medicines and Medical Devices); BFC SEE - 2 institutions (Bijelo Polje Municipality, Bar Municipality, Tivat Municipality, Podgorica Municipality, Danilovgrad Municipality, Žabljak Municipality)

https://www.rcc.int/balkanbarometer/results/2/public

https://www.rcc.int/balkanbarometer/results/2/public

eJob, eStudent, eNGO and eProfessional exam

eStudent pilot service

eStudent pilot service

eStudent pilot service

In accordance with the Law on Civil Servants and State Employees and the Law on Local Self-Government

Through the Law on Local Self-Government, establish the connection of MPA with the IT system, in order to monitor this indicator

Data was submitted by 19 municipalities. Of that number, 12 municipalities adopted HR plans within the legal deadline, 4 municipalities were on temporary funding, but adopted HR plans within a month of the adoption of the Budget, two municipalities adopted HR plans in delay, one municipality did not adopt a HR plan for 2022 at all. Six municipalities did not submit data

Work Report of the Human Resources Administration for 2022 (www.gov.me)

Internal notices 2.1, - public notices - 6.9, public competitions for senior management personnel - 2.46, public competitions for senior management bodies - 3.86

The list of HR functions planned to be fully digitised by 2026 is: HR Plan, Training, Assessment, Salary Calculation, Annual Vacation.

Training Record, HR plan and Salary Calculation

According to data from the Central Personnel Records, out of a total of 10,247 employees, for the year 2022, 4,774 were assessed, which represents 46.59% of those assessed.

For the year 2023, out of a total of 10,245 employees, 2,958 employees were assessed, which represents 29% of those assessed.

20 decisions on advancement. The total with grade A is 3,304, so this percentage is a little lower

During 2023, 622 employees were employed, of which 26 attended the training programme for new employees

The total number of respondents who responded to the survey is 1,157, which represents 37.3% of the total number of employees in 40 bodies that were included in the Survey on the satisfaction of employees in the public administration in Montenegro in accordance with the Methodology for researching employee satisfaction in the public administration in Montenegro

In 2024, the satisfaction of employees in local self-government units was measured. From the total number of employees, the percentage of valid answers is 28.8%.

Data taken for December 2024 from Monstat and the Ministry of Finance (a total of 257,390 employees; at the central and local levels, a total of 54,376 employees)

The total number of decided appeals is 3,743, of which 882 appeals were upheld due to the administrative silence.

The total number of decided cases is 6,717, of which 2,374 were upheld due to the administrative silence.

Total number of decided appeals is 3,743, 1,425 decisions of the first instance authorities were annulled.

Total number of decided cases is 6,717, 1,041 decisions of authorities were annulled by the Agency.

The latest value, currently the portal is not operational.

Entities subject to the LFAI– total of 1327 (year 2020)

20 institutions.

36 institutions out of a total of 1,649.

Due to frequent reorganisations, it is not possible to show the value of the indicator in %.

Due to frequent reorganisations, it is not possible to show the value of the indicator in %.

The value achieved in 2024 was calculated on the basis of the total opinions issued by the Sector for Strategic Planning and Policy Coordination of the Government (General Secretariat of the Government) in 2024 on the annual and final reports on the implementation of strategic documents, in accordance with the new forms for the assessment of strategic documents, effective from March 2023.

The recalculated value of the performance indicator achieved in 2023 based on the revised passport of the indicator.

The value achieved in 2024 calculated on the basis of the total opinions issued by the Sector for Strategic Planning and Policy Coordination of the Government (General Secretariat of the Government) in 2024 only on proposals for strategies and programs, in accordance with the new forms for the assessment of strategic documents, effective from March 2023.

That received a positive opinion from the GSG

The recalculated value of the performance indicator achieved in 2023 based on the revised passport of the indicator.

The value achieved in 2024 was calculated on the basis of the opinions issued by the Sector for Strategic Planning and Policy Coordination of the Government (General Secretariat of the Government) in 2024 on the annual and final reports on the implementation of strategic documents, according to the new forms for the assessment of strategic documents , effective from March 2023.

The process of adopting the new Medium-Term Planning Methodology of the Government and ministries is ongoing. Its adoption will enable the creation of medium-term plans based on clear criteria.

The revised Medium-Term Planning Methodology will be adopted by the end of May 2024, which defines new criteria for the preparation of annual programmes, after which training for relevant ministries will be implemented.

Statistics of the Sector for Strategic Planning and Coordination of Government Policies, General Secretariat of the Government, based on the total of opinions issued in 2023 on current strategies and programmes

Report on the implementation of the Regulation concerning the election of representatives from non-governmental organisations in the working bodies of public administration and the conduct of public consultations for the preparation of laws and strategies for 2023, published in December 2024.

The report will be prepared by the end of 2025 for the previous year.

During 2022, the public administration was reorganised and the number of ministries was increased compared to 2021 from 12 to 18 ministries

That received a positive opinion from the GSG