# SPECIAL CONDITIONS

# CONTENTS

IMPORTANT! These conditions amplify and supplement, if necessary, the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, those General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the Articles of the General Conditions.

Article 2	Language of the Contract

2.1	The language used shall be English.

Article 4	Communications

4.1	Any written communication relating to this Contract between the Contracting Authority and/or the Project Manager, on the one hand, and the Contractor on the other must state the Contract title and identification number, and must be sent by post, e-mail or by hand.

For the Contracting Authority:

Contact name: 	Radomir Šćepanović
Address: 		Ministry of Interior - Directorate for Protection and Rescue

Jovana Tomaševića bb (zgrada “Limenka”)

81000 Podgorica, Montenegro

E-mail: 		inerep.mne@gmail.com

For the Contractor:

<Contact name
Address
E-mail>

Article 9	General Obligations

9.9	The Contractor shall take the necessary measures to ensure the visibility of the European Union co financing. These activities must comply with the rules lay down in the Interreg Brand Design Manual published on the  website https://interreg-hr-ba-me.eu/wp-content/uploads/2024/06/Interreg-brand-Design-Manual.pdf

Article 10	Origin

## 10.1	All supplies under this contract may originate from any country.

Article 11	Performance guarantee

11.1	The amount of the Performance Guarantee shall be  5 % of the total Contract price, including any amounts stipulated in addenda to the Contract.

Article 12	Liabilities and Insurance

12.1a)	No liability / insurance measures are required.

12.1b)	No liability / insurance measures are required.

12.2. Insurance

No liability / insurance measures are required.

Article 13	Programme of implementation of tasks

13.2	Timetable for submission and approval of the programme of implementation of the tasks, with dates and deadlines:

| Action | Deadline |
| --- | --- |
| Supply, delivery, unloading (where applicable), installation (where applicable), commissioning | 120 calendar days from the contract signature date |
| Issuance of the Provisional Acceptance Certificate by Contracting Authority | 30 calendar days from the notification of successfully implemented tasks issued by the Contractor |
| TOTAL IMPLEMENTATION PERIOD | 150 calendar days |

Article 18	Commencement order

18.1	The implementation of the tasks is to commence on the date of the contract signature date by the last party.

Article 19	Period of implementation of the tasks

19.1	The period of implementation of tasks starting from the contract signature date by the last party until the date of issuance of the Provisional Acceptance Certificate shall be 150 calendar days.

The implementation period will include delivery period of 120 calendar days for all lots and 30 days for the Contracting Authority to issue the certificate of provisional acceptance.

Article 25	Inspection and testing

25.2	The inspection and testing prior to the provisional acceptance will take place at the locations where the equipment is delivered, installed and put into operation. The inspection and testing of all equipment will start and be completed within a implementation period, but prior to issuing certificate of provisional acceptance. During the testing period the Contracting Authority will inform the Contractor about the possible problems related to devices. The Contactor has obligation to respond to those requirements and to help to resolve the problem. In case of the malfunctioning of the supplied goods the Contractor must resolve the situation within 15 calendar days either by repair of the good or by replacement of the good supplied.

Article 26	General principles for payments

26.1	Payments shall be made in euros.

Payments shall be authorised and made by the Ministry of Interior of Montenegro, Directorate for Protection and Rescue.

All amounts are to be quoted excluding VAT. The program exempts the Ministry of Interior of Montenegro, Directorate for Protection and Rescue, from paying VAT, because the total value of the project from which the equipment is procured exceeds 5,000,000,00 EUR. Upon awarding the Contract, the Ministry of Interior of Montenegro, as the Contracting Authority will hand over the VAT exemption certificate to the selected supplier.

26.5	In order to obtain payments, the Contractor must forward to the authority referred to in paragraph 26.1 above:

a) 	After the contract signature, the Contracting Authority will, based on the advanced invoice and the pre-financing guarantee, pay to the Contractor 40% pre-financing

b)	For the 60 % final payment, the invoice(s) in duplicate together with the request for provisional acceptance of the supplies.

Article 28	Delayed payments

28.2	By derogation from Article 28.2 of the General Conditions, once the deadline laid down in Article 26.3 has expired, the Contractor shall, upon demand, be entitled to late-payment interest at the rate and for the period mentioned in the General Conditions. The demand must be submitted within two months of receiving late payment.

Article 29	Delivery

29.3	The packaging shall become the property of the recipient subject to environmental considerations.

29.5/6/7	The documents which have to accompany the delivery include:

a)	A detailed packing list identifying the contents of each package;

b)	Usual transport document;

c)	Technical documentation/operating instructions and certificates, as specified in the technical specifications (Annex II);

Article 31	Provisional acceptance

The Certificate of Provisional Acceptance must be issued using the template in Annex C11.

Article 32	Warranty obligations

32.6 	The commercial warranty shall remain valid for minimum 24 months, starting from the date of issuance of Final Acceptance Certificate (after the end of 1-year standard warranty).	32.7	The warranty must remain valid for 12 months after provisional acceptance.

Article 40	Settlement of disputes

40.4	Any disputes arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of courts in Podgorica, Montenegro, in accordance with the national legislation of the state of the Contracting Authority

- * * *