Montenegro

Ministry of Agriculture, Forestry and Water Management

Montenegro Forest for Shared Prosperity (P507869)

DRAFT

ENVIRONMENTAL and SOCIAL

COMMITMENT PLAN (ESCP)

Appraisal

November 13, 2025

ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN

- The Ministry of Finance of Montenegro (the Borrower) will implement the Montenegro Forest for Shared Prosperity Project (the Project), with the involvement of the Ministry of Agriculture, Forestry and Water Management of Montenegro, as set out in the Loan Agreement. The International Bank for Reconstruction and Development/International Development Association (the Bank) has agreed to provide financing for the Project, as set out in Agreement.

- The Borrower shall ensure that the Project is carried out in accordance with the Environmental and Social Standards (ESSs) and this Environmental and Social Commitment Plan (ESCP), in a manner acceptable to the Bank. The ESCP is a part of the Agreement. Unless otherwise defined in this ESCP, capitalized terms used in this ESCP have the meanings ascribed to them in the Agreement.

- Without limitation to the foregoing, this ESCP sets out material measures and actions that the Borrower shall carry out or cause to be carried out, including, as applicable, their respective timeframes; institutional, staffing, training, monitoring and reporting arrangements; and grievance management. The ESCP also sets out the environmental and social (E&S) documents that shall be prepared or updated, consulted, disclosed and implemented under the Project, consistent with the ESSs, in form and substance acceptable to the Bank. Said E&S documents may be revised from time to time with prior written agreement by the Bank. As provided for under the referred Agreement, the Borrower shall ensure that there are sufficient funds available to cover the costs of implementing the ESCP.

- As agreed by the Bank and the Borrower, this ESCP will be revised from time to time, if necessary, to reflect adaptive management of Project changes or unforeseen circumstances or in response to Project performance. In such circumstances, the Bank and the Borrower agree to update the ESCP to reflect these changes through an exchange of letters signed between the Bank and the Borrower’s Representative specified in the Agreement. The Borrower shall promptly disclose the updated ESCP.

- The subsection on “Indicators for Implementation Readiness” below identifies the actions and measures to be monitored to assess Project readiness to begin implementation in accordance with this ESCP. Nevertheless, all actions and measures in this ESCP shall be implemented as set out in the “Timeframe” column below irrespective of whether they are listed in the referred subsection.

| MATERIAL MEASURES AND ACTIONS |  | TIMEFRAME | RESPONSIBLE ENTITY |
| --- | --- | --- | --- |
| IMPLEMENTATION ARRANGEMENTS AND CAPACITY SUPPORT |  |  |  |
| A | ORGANIZATIONAL STRUCTURE a. Establish and maintain a Project Implementation Unit (PIU) with qualified staff and resources to support management of environmental, social, health and safety (E&S) risks and impacts of the Project including one environmental specialist and one social specialist.. | Establish a PIU and hire or appoint one environmental specialist and one social specialist no later than three months after the Effective Date of the Project, and thereafter maintain the PIU and these positions throughout Project implementation. | Ministry of Agriculture, Forestry and Water Management of Montenegro |
| B | CAPACITY BUILDING PLAN/MEASURES Prepare and implement the following capacity building measures: Training for PIU staff, on ESF and specific aspects of environmental and social assessment, e.g. E&S screening, E&S risks, stakeholder engagement, etc.. | 30 days after PIUs are established and E&S specialists appointed. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| MONITORING AND REPORTING |  |  |  |
| C | REGULAR REPORTING Prepare and submit to the Bank regular monitoring reports on the environmental, social, health and safety (E&S) performance of the Project. The reports shall include: Status of preparation and implementation of E&S documents required under the ESCP. Summary of stakeholder engagement activities carried out as per the Stakeholder Engagement Plan. Complaints submitted to the grievance mechanism, the grievance log, and progress made in resolving them. E&S performance of contractors and subcontractors as reported through monthly contractors’ and supervision firms’ reports. Number and status of resolution of incidents and accidents reported under action E below. | Submit bi-annual reports to the World Bank during implementation of the Activities, commencing after the Effective Date. Submit each report to the World Bank no later than 30 days after the end of each reporting period. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| D | CONTRACTORS’ MONTHLY REPORTS Require contractors and supervising firms to provide monthly monitoring reports on E&S performance in accordance with the metrics specified in the respective bidding documents and contracts and submit such reports to the Bank. | Submit the monthly reports to the Bank as annexes to the reports to be submitted under action C above. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| E | INCIDENTS AND ACCIDENTS Notify the Bank of any incident or accident relating to the project which has, or is likely to have, a significant adverse effect on the environment, the affected communities, the public or workers, including those resulting in death or significant injury to workers or the public; acts of violence, discrimination or protest; unforeseen impacts to cultural heritage or biodiversity resources; pollution of the environment; dam failure; forced or child labor; displacement without due process (forced eviction); allegations of sexual exploitation or abuse (SEA), or sexual harassment (SH); or disease outbreaks. Provide available details of the incident or accident to the Bank upon request. Arrange for an appropriate review of the incident or accident to establish its immediate, underlying and root causes. Prepare, agree with the Bank, and implement a Corrective Action Plan that sets out the measures and actions to be taken to address the incident or accident and prevent its recurrence. | Notify the Bank no later than 48 hours after learning of the incident or accident. Provide available details upon request. Provide review report and Corrective Action Plan to the Bank no later than 10 days following the submission of the initial notice, unless a different timeframe is agreed to in writing by the Bank. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| ESS 1: ASSESSMENT AND MANAGEMENT OF ENVIRONMENTAL AND SOCIAL RISKS AND IMPACTS |  |  |  |
| 1.1 | ENVIRONMENTAL AND SOCIAL ASSESSMENTS AND/OR PLANS 1. Prepare and implement the subproject site-specific Environmental and Social Management Plan (ESMP), for the Project consistent with the relevant ESSs and as set out in the Environmental and Social management Framework (ESMF), Stakeholder Engagement Plan (SEP), and Resettlement Policy Framework (RPF) -when land acquisition is required-. The proposed subprojects described in the exclusion list set out in the ESMF shall be ineligible to receive financing under the Project and identified during the screening to be conducted on an individual basis for each subproject activity. 2. Prepare and implement an Environmental and Social Management Framework (ESMF) for the Project, consistent with the relevant ESSs. | 1. Conduct screening, prepare the ESMP, prior to carrying out any site-specific investment activities and civil works and incorporate the ESMP, SEP, RPF (when land acquisition is required) as part of the respective bidding documents for the respective subproject prior to carrying out any site-specific investment activities and civil works that requires the preparation of such ESMP. Once finalized, implement the respective ESMP, SEP, and (when applicable) RPF, throughout Project implementation. 2. Prepare the ESMF prior to Appraisal and thereafter implement the ESMF throughout Project implementation. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| 1.2 | MANAGEMENT OF CONTRACTORS Incorporate the relevant aspects of the ESCP, including, inter alia, the ESMF, ESMP, the Labor Management Procedures, and code of conduct, into the E&S specifications of the procurement documents and contracts with contractors and supervising firms. Thereafter ensure that the contractors and supervising firms comply and that they require their subcontractors to comply with the E&S specifications of their respective contracts. Provide copies of the relevant contracts with contractors/subcontractors and supervision firms to the Bank. | As part of the preparation of procurement documents and respective contracts. Supervise contractors throughout Project implementation. Copies of relevant contracts provided to the Bank upon request. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| 1.3 | TECHNICAL ASSISTANCE Carry out the consultancies, studies (including feasibility studies, if applicable), capacity building, training, and any other technical assistance activities under the Project in accordance with terms of reference acceptable to the Bank, that are consistent with the ESSs. Thereafter prepare and finalize the outputs of such activities in compliance with the terms of reference. | Throughout Project implementation. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| 1.5 | ASSOCIATED FACILITIES Ensure that the activities in each identified Associated Facility are carried out in accordance with the applicable requirements of this ESCP and the ESSs, including, inter alia,, the ESMF, ESIA, ESMP, LMP, management of contractors, RPF, and SEP, as applies. | Prepare the ESIA or ESMP, for AF prior to carrying out any site-specific investment activities and civil works and incorporate the ESMP, SEP, RPF (when land acquisition is required) as part of the respective bidding documents for the respective subproject prior to carrying out any site-specific investment activities and civil works that requires the preparation of such ESMP. Once finalized, implement the respective ESMP , SEP, and (when applicable) RAP, throughout Project implementation. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| ESS 2: LABOR AND WORKING CONDITIONS |  |  |  |
| 2.1 | LABOR MANAGEMENT PROCEDURES Prepare and implement the Labor Management Procedures (LMP) for the including, inter alia, provisions on working conditions, management of workers relationships, OHS (including personal protective equipment, and emergency preparedness and response), code of conduct (including relating to SEA and SH), forced labor, child labor, grievance arrangements for Project workers, and applicable requirements for contractors, subcontractors, and supervising firms. | Adopt the LMP prior to appointment and/or hiring of Project workers and thereafter implement the LMP throughout Project implementation. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| 2.2 | OCCUPATIONAL HEALTH AND SAFETY MANAGEMENT PLAN Prepare and implement an OHS Management Plan to assess and manage the OHS risks and impacts of the Project. AND Require contractors and subcontractors to prepare and implement OHS Management Measures or Plan in accordance with ESIA and ESMP. | Prepare the OHS Management Plan prior to commencement of works, and thereafter implement the plan throughout Project implementation. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| 2.3 | GRIEVANCE MECHANISM FOR PROJECT WORKERS Establish and operate a grievance mechanism for Project workers, as described in the LMP and consistent with ESS2. | Establish grievance mechanism prior to engaging Project workers and thereafter maintain and operate it throughout Project implementation. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| ESS 3: RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT |  |  |  |
| 3.1 | WASTE MANAGEMENT PLAN Where relevant, prepare and implement a Waste Management Plan (WMP), as part of the ESMP prepared for the Project, to manage hazardous and non-hazardous wastes, consistent with ESS3. | Same timeline as ESMP preparation and implementation under 1.1. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| 3.2 | RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT Incorporate resource efficiency and pollution prevention and management measures in the ESMP to be prepared under action 1.1. above, where and if relevant in line with the provisions of the ESMF. | Same timeline as ESMP preparation and implementation under 1.1. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| ESS 4: COMMUNITY HEALTH AND SAFETY |  |  |  |
| 4.1 | TRAFFIC AND ROAD SAFETY Incorporate measures to manage traffic and road safety risks as required in the ESMP to be prepared under action 1.1 above. | Same timeframe as for the preparation and implementation of the ESMP. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| 4.2 | COMMUNITY HEALTH AND SAFETY Assess and manage specific risks and impacts to the community arising from sub-projects’ activities and include mitigation measures in the ESMPs to be prepared in accordance with the ESMF. | Same timeframe as for the preparation and implementation of the ESMPs. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| 4.3 | SEA AND SH RISKS Implement SEA/SH prevention and mitigation measures as required in the ESMPs and LMP, including codes of conduct, training, SEA/SH referral mechanisms. Under Part 1, cause the contractors to incorporate such measures in their respective ESMPs under action 1.1 above. | Implement SEA/SH prevention and mitigation measures prior to mobilization of project workers and thereafter implement such measures throughout Project implementation. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| ESS 5: LAND ACQUISITION, RESTRICTIONS ON LAND USE AND INVOLUNTARY RESETTLEMENT |  |  |  |
| 5.1 | RESETTLEMENT FRAMEWORK 1. Adopt and implement the Resettlement Policy Framework for the Project activities with potential impacts associated with land acquisition and restrictions on land use, involuntary resettlement, and livelihood losses, consistent with ESS5. | 1. Adopt the RPF prior to beginning of implementing the road network part of the project and thereafter implement the RPF throughout Project implementation. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| ESS 6: BIODIVERSITY CONSERVATION AND SUSTAINABLE MANAGEMENT OF LIVING NATURAL RESOURCES |  |  |  |
| 6.1 | BIODIVERSITY RISKS AND IMPACTS Where relevant, and identified through the processes laid out in the ESMF, prepare and implement a Biodiversity Management Plan (BMP) as part of the ESMP, in accordance with the guidelines of the Project ESMF, and consistent with ESS6. | Same timeline as ESMP preparation and implementation under 1.1. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| ESS 7: INDIGENOUS PEOPLES/SUB-SAHARAN AFRICAN HISTORICALLY UNDERSERVED TRADITIONAL LOCAL COMMUNITIES |  |  |  |
| ESS 8: CULTURAL HERITAGE |  |  |  |
| 8.1 | CHANCE FINDS Describe and implement the chance finds procedures in ESIA/ESMP of the sub-projects. | Same timeframe as for the preparation and implementation of the ESMPs. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| ESS 9: FINANCIAL INTERMEDIARIES |  |  |  |
| ESS 10: STAKEHOLDER ENGAGEMENT AND INFORMATION DISCLOSURE |  |  |  |
| 10.1 | STAKEHOLDER ENGAGEMENT PLAN Adopt, update, and implement the SEP for the Project, consistent with ESS10, which shall include measures to, inter alia, provide stakeholders with timely, relevant, understandable, and accessible information, and consult with them in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination, and intimidation. | Adopt the SEP no later than one month following the Effective Date and thereafter implement the SEP throughout Project implementation. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| 10.2 | PROJECT GRIEVANCE MECHANISM Establish, publicize, maintain, and operate an accessible grievance mechanism, to receive and facilitate resolution of concerns and grievances in relation to the Project, promptly and effectively, in a transparent manner that is culturally appropriate and readily accessible to all Project-affected parties, at no cost and without retribution, including concerns and grievances filed anonymously, in a manner consistent with ESS10. The grievance mechanism shall be equipped to receive, register, and facilitate the resolution of SEA/SH complaints, including through the referral of survivors to relevant gender-based violence service providers, all in a safe, confidential, and survivor-centered manner. | Establish the grievance mechanism no later than one month following effectiveness, and thereafter maintain and operate the mechanism throughout Project implementation. | Ministry of Agriculture, Forestry and Water Management of Montenegro PIU |
| INDICATORS FOR IMPLEMENTATION READINESS [This subsection lists the ESCP actions (by their numbering in the first column of the ESCP) that are identified as relevant to monitor project readiness from an E&S standpoint. These may include actions related to: i) establishment of E&S risk management units in the Project Implementation Entities, ii) recruitment and training of E&S staff within Project Implementation Entities, iii) Memorandums of Understanding or other written agreements/arrangements between Project Implementation Entities and other concerned agencies to ensure proper coordination of E&S risk management activities; iv) E&S effectiveness or disbursement conditions, if deemed warranted, v) ES assessments and plans to be prepared by the Borrower at the onset of implementation; vi) other project-specific requirements related to E&S readiness for implementation]. |  |  |  |
| The following actions are indicators for implementation readiness: 1. Establishment of the Project Implementation Unit (PIU) with adequate E&S personnel (A above) 2. Recruitment and training of E&S staff within PMT (B above) 3. E&S assessments and plans to be prepared by the Borrower, through PMT prior to tendering of the works (1.1 above) |  |  |  |