ACTION PLAN 2025-2026

| Strategic goal | Reduce fraud and other irregularities affecting the EU's financial interests in Montenegro by 2028 by strengthening the AFCOS system, the coordination role of the Directorate for the Protection of EU Financial Interests/AFCOS, improving cooperation among all stakeholders, implementing preventive measures and maintaining capacity for detecting irregularities, thus ensuring the protection of EU and Montenegrin taxpayers' money, as well as the efficient and effective use of EU resources. |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Success indicator | Irregularity detection rate |  |  |  |  |  |  | Initial value in 2024: 1.53% | Target value in 2026: <1.53% |  |  | Target value in 2028: <1.53% |
| Operational goal 1 | Improving the legal framework with aim of establishing a fully functional AFCOS system |  |  |  |  |  |  |  |  |  |  |  |
| Success indicator 1.1 | Operational and fully functional AFCOS system established |  |  |  |  |  |  | Initial value in 2024: 30% | Target value in 2026: 60% |  |  | Target value in 2028: 100% |
| Measures related to the operational objective 1 | Activity | Performance indicator | Responsible institution |  | Start date |  |  | End date | Estimated costs |  |  | Source of funding |
| 1.1. Adoption of amendments to the Law on Budget and Fiscal Responsibility | Adopt amendments to the Law on Budget and Fiscal Responsibility | Amendments to the Law on Budget and Fiscal Responsibility adopted | Ministry of Finance |  | I Q 2025 |  |  | IV 2026 | 3.500,00EUR |  |  | Twinning light project "Further enhancing the functioning of Montenegrin AFCOS system with the aim of efficient protection of the EU financial interests" |
| 1.2. Adoption of by-laws for the functioning of the system for the protection of the EU's financial interests in Montenegro | Adopt the Regulation on the institutional framework for the functioning of the system for the fight against fraud and irregularities (AFCOS system) | Regulation on the institutional framework for the functioning of the system for the fight against fraud and irregularities (AFCOS system) adopted | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | I Q 2025 |  |  | IV 2026 | 3.500,00EUR |  |  | Twinning light project "Further enhancing the functioning of Montenegrin AFCOS system with the aim of efficient protection of the EU financial interests" |
|  | Adopt the Regulation on the method of implementing EU support through the Reform and Growth Instrument | Regulation on the method of implementing EU support through the Reform and Growth Instrument adopted | Ministry of Finance |  | III Q 2025 |  |  | IV 2026 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance |
|  | Adopt the Decision on the establishment of a Working Body for the implementation of activities in the field of protection of the EU's financial interests in Montenegro | Decision on the establishment of a Working Body for the implementation of activities in the field of protection of the EU's financial interests in Montenegro adopted | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | I Q 2025 |  |  | IVQ2025 | 3.500,00EUR |  |  | Twinning light project "Further enhancing the functioning of Montenegrin AFCOS system with the aim of efficient protection of the EU financial interests" |
| 1.3. Further alignment of national legislation with EU legislation/PIF Directive | Adopt amendments to the Criminal Code in line with the PIF Directive | Criminal Code amended in the part of alignment with the PIF Directive | Directorate for Criminal and Civil Legislation/ Ministry of Justice |  | I Q 2026 |  |  | IVQ 2026 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Justice |
| 1.4. Further alignment of national legislation with EU legislation/Regulation 883/2013 and Regulation 2185/1996 | Amend legal acts defining the area concerning alignment with Regulations 883/2013 and 2185/1996 | Legal acts defining the area concerning alignment with Regulations 883/2013 and 2185/1996 amended | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | I Q 2026 |  |  | IVQ 2026 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance |
| 1.5. Harmonization of national legislation with EU legislation/Directive 2019/1937 on the protection of persons reporting violations of European Union law (Whistleblower Directive) | Adoption of a separate Law on Whistleblower Protection | Law on Whistleblower Protection adopted | Ministry of Justice/Agency for prevention of corruption |  | IV Q 2025 |  |  | IV Q 2026 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Justice/Agency for prevention of corruption |
| Operational goal 2 | Strengthening the coordination role of the AFCOS office and improving cooperation between institutions involved in the protection of the EU's financial interests |  |  |  |  |  |  |  |  |  |  |  |
| Success indicator 2.1 | Index of satisfaction with cooperation between institutions involved in the protection of the EU's financial interests. |  |  |  |  |  |  | Initial value in 2024: 7 points on a scale to 10 | Target value in 2026: At least 7.5 points on a scale to 10 |  |  | Target value in 2028: At least 7.5 points on a scale to 10 |
| Success indicator 2.2 | Attendance rate at meetings of the Working Body for the implementation of activities in the field of protection of the EU's financial interests in Montenegro |  |  |  |  |  |  | Initial value in 2024: 30% | Target value in 2026: 70% |  |  | Target value in 2028: 90% |
| Success indicator 2.3 | Number of meetings initiated by the Irregularity reporting structure and AFCOS network institutions. |  |  |  |  |  |  | Initial value in 2024: 0 | Target value in 2026: 2 |  |  | Target value in 2028: 4 |
| Measures related to the operational objective 2 | Activity | Performance indicator | Responsible institution |  | Start date |  |  | End date | Estimated costs |  |  | Source of funding |
| 2.1. Organise an annual experience exchange event in the field of protection of EU financial interests | Organise an annual experience exchange event between the Irregularity Reporting Structure and the AFCOS network | 2 experience exchange events in the field of protection of EU financial interests organised | Directorate for the Protection of EU Financial Interests /Ministry of Finance Struktura za izvještavanje o AFCOS mreža |  | IQ 2025 |  |  | IVQ 2026 | Neophodno je isplanirati u budžetu iznos od 200,00 EUR |  |  | Ministry of Finance |
| 2.2. Development of an online documentation platform for more efficient information exchange | Develop an online documentation platform for information exchange between the AFCOS office, the Irregularity Reporting Structure and the AFCOS network. | 1 online documentation platform developed | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | IQ 2026 |  |  | IVQ 2026 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance |
| 2.3. Organizing trainings with the participation of experts from OLAF and EU Member States | Organize trainings with the participation of experts from OLAF and EU Member States for representatives of the Irregularity Reporting Structure and the AFCOS Network. | 2 trainings with the participation of experts from OLAF and EU Member States for representatives of the Irregularity Reporting Structure and the AFCOS Network. | Directorate for the Protection of EU Financial Interests/AFCOS |  | IQ 2025 |  |  | IVQ 2026 | It is necessary to plan the amount of EUR 3,500.00 in the budget. |  |  | Ministry of Finance |
| Operational goal 3 | Further strengthening the prevention of irregularities and fraud through appropriate risk assessments and the introduction of effective and proportionate measures against irregularities and fraud, including establishing a systematic approach to education and awareness-raising |  |  |  |  |  |  |  |  |  |  |  |
| Success indicator 3.1 | Effective and proportionate anti-fraud measures implemented |  |  |  |  | Initial value in 2024: 70% |  |  |  | Target value in 2026: 100% of the activities from the Action Plan for 2025-2026 were implemented within the deadline | Target value in 2028: 100% of the activities from the Action Plan for 2025-2026 were implemented within the deadline |  |
| Success indicator 3.2 | Number of trained officials from institutions and bodies working on the protection of the EU's financial interests |  |  |  |  | Initial value in 2024: 55 |  |  |  | Target value in 2026: 55 (u 2025-2026) evenly distributed between men and women | Target value in 2028: 55 (u 2027-2028) evenly distributed between men and women |  |
| Measures related to the operational objective 3 | Activity | Performance indicator | Responsible institution |  | Start date |  |  | End date | Estimated costs |  |  | Source of funding |
| 3.1. Establishing a sustainable training system for institutions involved in the protection of the EU's financial interests | Conduct a new training needs analysis for representatives of the Irregularities Reporting Structure and the AFCOS network. | Training needs analysis conducted | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | IQ 2025 |  |  | IIIQ 2025 | 6.000,00 EUR |  |  | PFM/CEF |
|  | Develop a training program and plan (catalog) for the period 2025-2028 in accordance with the results of the training needs analysis. | Training program and plan (catalog) for the period 2025-2028 developed | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | IQ 2025 |  |  | IIIQ 2025 | 6.000,00EUR |  |  | PFM/CEF |
|  | Conduct training in cooperation with the Agency for Prevention of Corruption | Training for persons responsible for receiving and acting on reports conducted | Directorate for the Protection of EU Financial Interests /Ministry of Finance and Agencija za sprečavanje korupcije (ASK) |  | IIQ2026 |  |  | IIIQ2026 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Agency for Prevention of Corruption |
| 3.2. Maintaining the operational system for managing the risk of irregularities and fraud. | Conducting irregularities and fraud risk analysis in accordance with the methodology for managing risks in the area of ​​irregularities and fraud in the management and use of EU funds. | Fraud risk analysis for 2025-2026. conducted | Directorate for the Protection of EU Financial Interests /Ministry of Finance Irregularity Reporting Structure AFCOS Network |  | IIIQ 2026 |  |  | IVQ 2026 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance |
| 3.3. Ensuring adequate visibility and transparency regarding EU funds and raising awareness of the importance of the process for protecting EU and national financial interests | Develop a comprehensive communication strategy | Communication strategy for the period 2026-2028 adopted | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | IIQ 2025 |  |  | IVQ 2026 | 21.000,00 EUR |  |  | Twinning light project "Further enhancing the functioning of Montenegrin AFCOS system with the aim of efficient protection of the EU financial interests" |
| 3.4. Monitoring the latest developments in anti-fraud measures and exchange of best practices. | Regular participation in annual conferences organised by OLAF | 2 annual conferences organised by OLAF attended | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | IIIQ 2025 |  |  | IVQ 2026 | 8.800EUR |  |  | OLAF |
|  | Organize at least one seminar on the importance of reporting irregularities and on different types of fraud and irregularities for the Project Implementation Unit | One seminar in the period 2025-2026 organized | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | IIIQ 2025 |  |  | IVQ 2026 | It is necessary to plan an amount of EUR 2,000.00 in the budget. |  |  | Ministry of Finance |
| 3.5. Inclusion of the Directorate for the Protection of the Financial Interests of the EU / AFCOS in the IPA Monitoring Committee as an observer. | Adopt changes in the composition of the Monitoring Committee | Changes in the composition of the Monitoring Committee approved | Directorate for the Management of EU Pre-Accession Assistance Structures NIPAK |  | IIIQ 2025 |  |  | IVQ 2025 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance Ministry of European Affairs |
| Operational goal 4 | Maintaining capacity to detect irregularities while improving the quality of reporting on irregularities and improving the recognition of red flags and signs of fraud. |  |  |  |  |  |  |  |  |  |  |  |
| Success indicator 4.1 | Percentage of irregularities reported via IMS within the set deadline (within 45 days of the PACA date). |  |  |  |  |  |  | Initial value in 2024: 4% | Target value in 2026: 50% |  |  | Target value in 2028: 90% |
| Success indicator 4.2 | Percentage of irregularities reported as suspected fraud |  |  |  |  |  |  | Initial value in 2024: 5% | Target value in 2026: 6% |  |  | Target value in: 8% |
| Success indicator 4.3 | Number of irregularity reports returned by the Directorate for the Protection of the Financial Interests of the EU/AFCOS to the Implementing Agencies for processing. |  |  |  |  |  |  | Initial value in 2024: 60 | Target value in 2026: 40 |  |  | Target value in 2028: 20 |
| Measures related to the operational objective 4 | Activity | Performance indicator | Responsible institution |  | Start date |  |  | End date | Estimated costs |  |  | Source of funding |
| 4.1 Improvement of the Guidelines on Irregularity Management | Review of the Guidelines on Irregularity Management and their adaptation to the requirements of the IPA III regulation | Guidelines on Irregularity Management updated and approved | Directorate for the Protection of EU Financial Interests Directorate for the Management of EU Pre-Accession Assistance Structures |  | IIIQ 2025 |  |  | IVQ 2025 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance |
|  | Incorporation of the procedures from the updated Guidelines on Irregularity Management into Chapter "Irregularities" of Manual of Procedures | Chapter "Irregularities" in the Manual of Procedures updated | Directorate for the Management of EU Pre-Accession Assistance Structures |  | IQ 2026 |  |  | IIQ 2026 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance |
| 4.2 Improving the indirect management and control system for the implementation of projects from IPA funds | Create a single electronic database of projects financed from EU support, i.e. an internet platform for EU funds in Montenegro and provide access to it in order to consolidate all necessary information for end users of EU support and future potential applicants | Internet platform for EU funds in Montenegro | Directorate for the Management of EU Pre-Accession Assistance Structures |  | IVQ 2025 |  |  | IVQ 2026 | Funds will be provided either from EU donations or from planned funds in the budget of the Ministry of Finance - budget line for the Directorate for Management of EU Pre-Accession Assistance Structures for the development of a single database. |  |  | Ministry of Finance |
|  | Prescribe a precise procedure for lines of communication between all competent IPA bodies for checking the connection between persons conducting on-site checks and persons subject to checks in order to avoid potential conflicts of interest. Additionally, ensure that a Declaration of Impartiality is signed by all persons involved in the process. | The procedure for communication between IPA structures for checking the connection between persons conducting on-site checks and persons subject to checks is defined and the signing of a Declaration of Impartiality is ensured | Directorate for the Management of EU Pre-Accession Assistance Structures |  | IIIQ 2025 |  |  | IVQ 2026 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance |
| Operational goal 5 | Improving cooperation between investigative bodies, AFCOS and OLAF |  |  |  |  |  |  |  |  |  |  |  |
| Success indicator 5.1 | All OLAF requests have been properly processed and completed. |  |  |  |  |  |  | Initial value in 2024: 100% | Target value in 2026: 100% |  |  | Target value in 2028: 100% |
| Measures related to the operational objective 5 | Activity | Performance indicator | Responsible institution | Start date |  |  |  | End date | Estimated costs |  |  | Source of funding |
| 5.1 Improving cooperation by clearly defining mechanisms and responsibilities for cooperation with OLAF and the Directorate for the Protection of the Financial Interests of the EU/AFCOS | Development of procedures/regulations that clearly define the activities and competences of the institutions of the AFCOS system during inspection visits by OLAF investigators to economic operators in Montenegro | Procedures/regulations that clearly define the activities and competences of the institutions of the AFCOS system during inspection visits by OLAF investigators to economic operators in Montenegro developed. | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | IQ 2026 |  |  | IVQ 2026 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance |
| Operational goal 6 | Improving capacity to ensure efficient and effective recovery of improperly spent funds |  |  |  |  |  |  |  |  |  |  |  |
| Success indicator 6.1 | Recovery rate of improperly spent funds |  |  |  |  |  |  | Initial value in 2024: 43% | Target value in 2026: 60% |  |  | Target value in 2028: 75% |
| Measures related to the operational objective 6 | Activity | Performance indicator | Responsible institution |  | Start date |  |  | End date | Estimated costs |  |  | Source of funding |
| 6.1 Analysis of the causes of low recovery rates and subsequent corrective actions | Conduct an analysis of the causes of low recovery rates from previously implemented projects | Analysis of the causes of low recovery rates conducted | Directorate for the Management of EU Pre-Accession Assistance Structures |  | IIIQ 2026 |  |  | IVQ 2026 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance |
| COMMUNICATING REFORM ACTIVITIES |  |  |  |  |  |  |  |  |  |  |  |  |
| Measures | Activity | Performance indicator | Responsible institution |  | Start date |  | End date |  | Estimated costs |  |  | Source of funding |
| 1. Adoption of the Communication Strategy | Promoting the importance of the Strategy and the achieved goals, through activities foreseen by this strategy | Raising awareness of the importance of realizing the Strategy's goals | Ministry of European Affairs/Ministry of Finance |  | I Q 2025 |  | IV Q 2028 |  | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of European Affairs |
| 2. Organizing seminars to promote the Strategic Document | Organize seminars to promote the Strategy and Action Plan and address topics of importance for the successful implementation of defined goals | Raising awareness of the importance of implementing the Strategy's goals | Ministry of Finance |  | I Q 2025 |  | IV Q 2028 |  | Predviđeni troškovi kroz aktivnosti navedene ovim Akcionim planom (2000,00EUR) |  |  | Ministry of Finance |
| 3. Improving visibility through increased cooperation with the PR department in accordance with internal rules of communication with the public | Promotion through social networks | Raising awareness of the importance of realizing the goals of the Strategy | Ministry of Finance |  | I Q 2025 |  | IV Q 2026 |  | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance |
| 4. Develop a communication strategy for the protection of the EU's financial interests | Adopt a communication strategy for the protection of the EU's financial interests | Communication strategy for the period 2026-2028 adopted | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | II Q 2025 |  | IV Q 2026 |  | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance |
| Cross-section of the situation after 2 years |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Performance indicator | Responsible institution |  | Start date |  |  | End date | Estimated costs |  |  | Source of funding |
| Development of the Action Plan for the period 2027-2028 |  | Action Plan 2027-2028 developed | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | IIIQ 2026 |  |  | IVQ 2026 | This activity will be implemented by the responsible institution within the existing budget. |  |  | Ministry of Finance |
| Evaluation of the Strategy at the end of the validity period |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Performance indicator | Responsible institution |  | Start date |  |  | End date | Estimated costs |  |  | Source of funding |
| Evaluation of the Strategy 2025-2028 |  | Evaluation report prepared and sent to the Government of Montenegro for adoption | Directorate for the Protection of EU Financial Interests /Ministry of Finance |  | IV Q 2028 |  |  | II Q 2029 | It is necessary to plan in the budget an amount of EUR 60,000.00 for the engagement of an external evaluator. |  |  | Twinnig light project |