ENVIRONMENTAL AND SOCIAL MANAGEMENT FRAMEWORK

for

Montenegro Forest for Shared Prosperity Project

MONTENEGRO

OCTOBER 25, 2025

Table of Contents

List of Tables	4

List of Figures	5

Abbreviations and Acronyms	6

Executive Summary	7

1.	Introduction	12

1.1 Background Information	12

1.2 Purpose of the Environmental and Social Management Framework (ESMF)	12

1.3 Rationale for an Environmental and Social Management Framework	13

1.4 Aim and Objectives of the Environmental and Social Management Framework	13

1.5 Study Approach and Methodology	14

2.	Project Description	15

2.1 Project Overview	15

2.2 Rationale for Project implementation	16

2.2.1 Rationale for Implementing the Montenegro FSPP	16

2.3 Project Development Objectives	16

2.4 Project Components	16

2.5 Implementation and Timeframe	24

2.5.1	Description of proposed project components	25

2.6 Institutional and Implementation Arrangements	25

3. Environmental and Social Policies, Regulations, and Laws	27

3.1Project Categorization under the World Bank ESF	27

3.2 Summary of Environmental and Social Risks and Impacts:	27

3.3 Relevant World Bank Group Guidelines	29

3.4 	National Environmental Legal Framework	29

3.5 	Relevant Labour and Regulatory Framework	32

3.5.1 Other Relevant Social and Labor Legislation in Montenegro	34

3.5.2 Grievance Management (Complaints and Appeals Mechanism)	35

3.6 Gaps between World Bank ESF and National Legislation	35

3.7 World Bank Environmental and Social Framework	37

3.8 Institutional Framework	47

4. Environmental and Social Baseline	53

4.1 General overview of Montenegro 	53

4.1.1. Geography	54

4.1.2.Forest coverage	54

4.2. Environmental Baseline and Relevant Potential Issues	61

4.2.1. Air Emissions and Air Quality	62

4.2.2 Water Quality	63

4.2.3 Waste Management	64

4.2.4 Noise	65

4.2.5. Nature Protection	65

4.2.6. Climate Change	75

4.3 Socio-economic Environment	76

4.3.1. Demography/Population	76

4.3.2. Economy	79

4.3.3. Labor market and employment	85

4.3.4. Social policy	88

4.3.5. Healthcare policy	90

4.3. 6. Poverty	90

5. Analysis of Alternatives	92

5.1 Do-Nothing / ‘Without Project’ Option	92

5.2 Technological Option	92

5.3 Circular Economy vs wastes Option	93

5.4 Market-based mechanisms:	93

6.Potential Environmental and Social Risk Impacts and Standard Mitigation Measures	94

6.1 Project Activities with Potential Environmental and Social Risks and Impacts	94

6.1.1 Potential Positive Impacts	94

6.1.2. Overview of Environmental Risks and Mitigation Measures in Planning and design phase, Implementation phase and Operational phase	102

6.1.3 Special Assistance for Vulnerable PAPs	109

6.2 Special Assistance for Vulnerable PAPs	110

7. PROJECT IMPLEMENTATION SET-UP	111

8.Environmental and Social Monitoring	111

8.1Environmental and Social Management Procedures and Implementation Arrangements	114

8.2 Proposed Training and Capacity Building	115

8.2.1 Capacity Assessment	115

8.3 Estimated Budget	118

9.Stakeholder Engagement, Disclosure, and Consultations	119

APPENDICES	122

Appendix 1: National ESIA Procedure	122

Appendix 3. Environmental and Social Screening Form	126

Appendix 4: ESIA Report Template	135

Appendix 5. Environmental and Social Code of Practices (ESCOP)	139

Appendix 6. Environmental and Social Management Plan (ESMP) Template	148

Appendix 7: Indicative Outline- Forest and Biodiversity Management Plan (BMP)	150

Appendix 10: Screening Form for Land Acquisition and Resettlement	154

Appendix 12: ESF Implementation Reporting Template	155

Appendix 13: Waste Management Plan	157

Appendix 14: Chance Find Procedures	164

Appendix 15: Sample Incident Form	167

Appendix 16: Occupational Health and Safety (OHS) Procedures	169

Appendix 17: World Bank general EHS guidelines	170

Appendix 18: Attendance log	172

Appendix 19: Sample Contractor ESMP (C-ESMP)	176

# List of Tables

Table 1Proposed project characteristics	24

Table 2 Relevant legal framework applicable to the proposed project	27

Table 3 List of Environmental and related Laws-Montenegro	29

Table 4 Labor legislation and safety at work are regulated by the following regulations	30

Table 5 Gap Analysis	34

Table 6 Relevant World Bank Environmental and Social Standards that apply to FSPP	36

Table 7 Forest coverage	53

Table 8 Air Quality Zones	59

Table 9 Number of populations by municipalities	73

Table 10 Population by Gender and Age	75

Table 11Structure of wood processing and Furniture industries in Montenegro,2022	78

Table 12 Gross domestic product	79

Table 13Gross Value added, indices of nominal growth and structure of GDP	80

Table 14 Projected growth rates in Montenegro	82

Table 15Persons in employment by sectors of activity and sex, Montenegro,2023	83

Table 16 Overview of the social protection in Montenegro	85

Table 17 Environmental risks and mitigation measures	92

Table 18: Potential Social Risks/Impacts and Standard Mitigation Measures	94

Table 19: Cross-Cutting E&S Risk Management and Mitigation Tools	96

Table 20 Environmental Risks and Measures-Planning phase	99

Table 21: Environmental Risks and Mitigation Measures — Implementation and operational phase	101

Table 22: Summary of Environmental and Social Standards (ESS) Risks and Mitigation Measures (FSPP)	103

Table 23: Potential Environmental and Social Risks and Impacts and Mitigation Measures during the design, construction and operations phases	105

Table 24Monitoring and Evaluation Framework for ESMF	108

Table 25: Proposed training and Capacity Building Approach	112

Table 26.ESMF Implementation Budget	114

# List of Figures

Figure 1Montenegro Forest	15

Figure 2Map of Montenegro	50

Figure 3National Forest inventory of the Montenegro	57

Figure 4 Existing Protected Area	63

Figure 5 Graphical representation of the projection of protected area	67

Figure 6 Areas with International Status	69

Figure 7 Biodiversity rich Area	71

Figure 8 Montenegro Wood product Exports by Value 2014-2023	79

# Abbreviations and Acronyms

| ABP | Animal By-Product (facility) |
| --- | --- |
| BMP | Biodiversity Management Plan |
| BoQ | Bill of Quantities |
| CESMP | Contractor Environmental and Social Management Plan |
| CHS | Community Health and Safety |
| E&S | Environmental and Social |
| EA | Environmental Assessment |
| EHS | Environment, Health and Safety |
| EIA | Environmental Impact Assessment |
| ESMP | Environmental and Social Management Plan |
| ESMF | Environmental and Social Management Framework |
| ESMP Checklist | Simplified Environmental and Social Management Plan Checklist |
| ESCP | Environmental and Social Commitment Plan |
| ESIA | Environmental and Social Impact Assessment |
| ESS | Environmental and Social Standard (World Bank) |
| EU | European Union |
| FP | Fishing Port |
| FSPP | Montenegro Forest for Shared Prosperity Project |
| GIS | Geographic Information System |
| GIIP | Good International Industry Practice |
| GRM | Grievance Redress Mechanism |
| HVAC | Heating, Ventilation and Air Conditioning |
| IPM | Integrated Pest Management |
| LMP | Labor Management Procedures |
| MoA | Ministry of Agriculture, Forestry and Water Management (or relevant authority) |
| OHS | Occupational Health and Safety |
| PARO | Paying Agency Regional Office |
| PPE | Personal Protective Equipment |
| PMT | Project Management Team |
| RAP | Resettlement Action Plan |
| RPF | Resettlement Policy Framework |
| SEP | Stakeholder Engagement Plan |
| SEA/SH | Sexual Exploitation and Abuse / Sexual Harassment |
| WB | World Bank |
| WMP | Waste Management Plan |

# Executive Summary

The Government of Montenegro through the Ministry of Agriculture, Forestry and Water Management of Montenegro (MNE) will implement a $20 million Montenegro Forest for Shared Prosperity Project (FSPP) to ensure the long-term sustainability of the country’s forest resources and align fully with the EU forestry policy, as a future EU member state, with the financial support of the World Bank (WB). The Ministry of Agriculture, Forestry and Water Management will use the allocation of funds from the World Bank loan (18 million euros) to finance the establishment of institutions necessary for the implementation of the new Forestry Law, as well as to improve the productivity of the wood industry.

The Project Development Objective (PDO) is to improve the sustainable management of forest resources and to enhance the competitiveness of the forest industry in targeted project areas in Montenegro.

ESMF document is the environmental and social due diligence instrument made to ensure that the proposed Project is implemented in accordance with the World Bank operational guidelines, ESS standards and local legislation related to environmental protection, It is also the instrument prepared to manage E&S risks where project details and specifics are not known as well as a practical tool to be used during design, implementation, and monitoring of the Project activities.

The ESMF presents methodologies for developing and implementing environmental and social risk management instruments for project activities/sub-projects, including how to conduct environmental and social screening of activities/sub-projects (Appendix 1), identify and assess potential environmental and social risks and impacts and proffer mitigation measures for the identified environmental and social impacts/risks. It covers a broad description of the project, existing policy and legal frameworks in Montenegro, relevant World Bank Environmental and Social Standards (ESSs), baseline social and biophysical information and conditions of the project environment, broad environmental and social risks and impacts, their accompanying management and mitigation measures, the implementation arrangements and capacity building programs.

The ESMF also defines the implementation and institutional responsibilities of various stakeholders involved in the project implementation. The Framework analyzes environmental policies and legal regime of the MNE and ESS standards of the WB; presents the institutional and capacity assessment related to environmental management; and describes the principles, objectives and approach to be followed at a later stage while designing site-specific sub-projects and environmental mitigation measures.

The project is structured around four key components: Component 1: Strengthening Sector Governance, Enhancing Information Services, and Upgrading Institutional Capacity, which aims to strengthen governance and modernize systems for better decision-making and effective forest management; Component 2: Supporting Sustainable Forest Management & Enhancing Climate Resilience, focused on advancing SFM and improving climate adaptation and mitigation strategies; Component 3: Improving Forestry Sector Competitiveness, which seeks to boost the economic potential of the sector through sustainable practices and market development; and Component 4: Project Management, Monitoring, and Communication dedicated to ensuring effective oversight, management and stakeholder engagement.

| Component | Description | Estimated US$ |
| --- | --- | --- |
| Component 1 | Strengthening Sector Governance and System Modernization | 5 million |
| Subcomponent 1.1 | Strengthening Policy Framework and Institutional Capacity |  |
| Subcomponent 1.2 | Modernizing Forest Resources measurement and Traceability | 3.5M |
| Subcomponent 1.3 | Supporting the Operationalization of the State-Owned Enterprise (SOE) | 1.0M. |
| Component 2 | Advancing Sustainable Forest Management and Climate Resilience against wildfires | 7.5 million |
| Subcomponent 2.1 | Advancing Adoption of SFM Practices | 2.5M |
| Subcomponent 2.2: | Promoting Forest Fire Resilience | $2.0M |
| Component 3 | Improving Forestry Sector Competitiveness |  |
| Subcomponent 3.1 | SmartWood Capacity Program (SmartWood |  |
| Subcomponent 3.2 | Grant Scheme Support for Advancing Wood Industry SMEs | 2M |
| Subcomponent 3.3 | Advancing Certification, Grading, and Standardization in Montenegro’s Wood Processing Industry | 0.5M |
| Component 4: | Project Management, Monitoring, and Communication (estimated US$2 million | 2 million |

Environmental and Social Baseline Conditions

Montenegro, a small mountainous country in Southeast Europe, borders Croatia, Bosnia and Herzegovina, Serbia, Kosovo, Albania, and the Adriatic Sea. Its varied landscape includes 827,536 ha of forests as of 2019, with deciduous species making up 71%, coniferous 18%, and mixed forests 11%. The National Inventory lists 68 tree species, highlighting Montenegro’s rich but unevenly distributed forest diversity. While forest areas have expanded due to reduced agriculture and rural depopulation, quality and biodiversity remain concerns, with wood productivity below habitat potential in many regions.

According to the official results of the 2023 Population Census, Montenegro's total population reached 623,633—an increase of 2.1% compared to the 2011 Census, as reported by the Statistical Office of Montenegro (MONSTAT). Preliminary 2023 census data by municipalities indicate a marked decrease in population within northern municipalities, while coastal areas and Podgorica experienced population growth. Specifically, compared to 2011, the municipality of Andrijevica saw a decline of 22%, Mojkovac by 21%, Pljevlja by 20%, Kolašin by 19%, and Bijelo Polje by 14%. In Berane, the reduction was 12%. Beyond the northern region, notable decreases were also observed in Nikšić (8%) and Cetinje (13%). Conversely, the highest population increase since the 2011 Census occurred in Budva (39%), followed by Podgorica (14%), Tivat (10%), Bar (10%), and Ulcinj (7%). These figures reflect significant migration from the northern municipalities toward Podgorica and the coastal regions. Most municipalities experiencing substantial depopulation were previously centers of a developed wood industry. Notably, these areas are currently home to the highest levels of timber resource exploitation.

Potential Risks and Impacts and Proposed Mitigation Measures

The ESMF has been prepared to identify the potential environmental and social risks and impacts of proposed project activities and propose suitable mitigation measures to manage these risks and impacts. At the time of project preparation, the specific sites that the project would be implemented are not known in sufficient details. Based on the nature and scope of project activities primarily under component 2 (construction of reservoirs, forest management systems, sensitivity of environmental and social factors and the capacity of PIU, the Project’s Environmental and Social (E&S) risk rating is Moderate.

Positive Impact Positive Environmental and Social Impacts

The Montenegro Forests for Shared Prosperity Project (FSPP) project is expected to bring significant benefits Montenegro. The project seeks to improve the sustainability, competitiveness, and climate resilience of Montenegro's forestry sector through institutional reform, resource monitoring, sustainable management, and support for the wood industry. The initiative is designed to deliver long-term environmental and socio-economic gains, including healthier ecosystems, climate mitigation, water regulation and soil health, greater carbon storage, reduced fire risk, and stronger forest governance. Additionally, forested strips lower noise levels and offer ecological benefits such as CO₂ absorption, dust filtration, and habitats for biodiversity, supporting integrated urban environmental quality. Sustainable Forest Management (SFM) and climate resilience strategies are identified as important factors in environmental protection and social development, especially regarding climate adaptation and mitigation.

The project will have a significant impact on local communities, especially in rural areas. It is expected:

- Creating new jobs, especially in forestry and wood processing, which will contribute to reducing unemployment and increasing living standards;

- Improving education and vocational training, through programs for training personnel in the forestry and wood industry sector;

- Supporting local communities, through the inclusion of the population in decision-making on the use of forest resources and the implementation of sustainable development projects.

- enhanced capacity for forest management systems, and the prevention, management and control of wildfires.

- Strengthen regulatory and policy framework for improved forest management

- Institution of Controlled timber logging and forest regeneration initiatives

The introduction of these measures will create a stable business environment that will encourage sustainable development and economic empowerment of the population.

Potential Adverse Environmental and Social Risks and Impacts/Mitigation measures

The environment risk rating is Moderate given the breadth of activities in the country, the local context and the capacity of the institutions to manage E&S risks associated with the project activities. The project involves SFM, however, poorly planned and implemented SFM can cause unsustainable logging, soil erosion, biodiversity loss, and ecosystem damage. Land clearing for forest protection can lead to sediment runoff from exposed forest floor and topsoil, bringing about poor soil quality. Instituting fire protection areas, such as fire breaks and barriers, and maintaining buffer zones may bring about forest fragmentation, with impact on wildlife. Provision of milling and furniture manufacturing support to SMEs could increase demand for and undue pressure on forests products leading to forest degradation. The situation can be exacerbated if the country eventually becomes a prime supplier of forest products. Climate change adds risks like wildfires, pests, and unpredictable weather, which SFM aims to address.

On the social front, insufficient stakeholder consultation risks conflict and confusion. Limiting forest access can especially harm women and indigenous communities, while cultural resistance and poor benefit-sharing may hinder SFM goals. There is potential for conflict with private forest owners over felling licenses and state control over their property. Although the institution of forest management plans is designed to enhance sustainability, these property owners will explore opportunities to undermine the scheme if control becomes unbearable and licenses are exorbitant.

To ensure that the mitigation measures are implemented and monitored, environmental and social risk management instruments such as Environmental and Social Screening Reports (The PIU will screen all project activities/sub projects for their environmental and social risks and impacts for environmental and social risk categorization). This will enable the PIU to prepare the appropriate environmental and social risk management instruments for approval by the World Bank and the respective national authorities prior to the commencement of a sub project/activity.

Where applicable, site-specific instruments such as Environmental and Social Impact Assessments (ESIAs), and site specific Environmental and Social Management Plans (ESMPs), Biodiversity Management Plan (BMPs), and Resettlement Plans (RPs) will be prepared by the Project Implementation Units for approval by the Bank. Subsequently, the PIU will be required to disclose, implement and report on implementation progress of the approved ESIAs/ESMPs/ BMPs/RPs. The PIU will ensure that the Codes of Conducts and Environmental and Social Clauses are inserted into contract documents and reporting mechanisms. Contractors will be required to adopt Contractor ESMPs (C-ESMPs) with Codes of Conduct and SEA/SH-sensitive supervision

Institutional Arrangements for ESMF Implementation

A Project Implementation Unit (PIU) will be established within the Ministry of Agriculture, Forestry and Water Management to facilitate the execution of all project activities. The PIU will consist of a Project Manager responsible for coordination and oversight of activities and monitoring and evaluation (M&E), an Administrative Assistant tasked with logistical, procurement, and financial support, a Social Specialist to ensure activities adhere to ESF documents and stakeholder engagement strategies, and an Environmental Specialist charged with integrating environmental risk measures and ensuring compliance with relevant standards and regulations. A Grant Manager will oversee the design, allocation, and monitoring of grant mechanisms under Component 3, as well as coordinate related activities. Additionally, the PIU will include part-time Communications and Monitoring & Evaluation Specialists to assist with project visibility, stakeholder engagement, knowledge dissemination, and results tracking during the implementation period.

Capacity Building and Training for ESMF

Training programs to build capacity for the implementation of mitigation and management measures outlined in the ESMF and the cost associated with capacity building programs is approximately, two hundred and ten thousand United States Dollars (US$ 210,000). These include training programs in grievance mechanisms (GM), SEA/SH and Occupational Health and Safety, Environmental and Social Risk Management Procedures, E&S monitoring and reporting, Incident and accident reporting and the World Bank Environmental and Social Framework as outlined in the ESCP.

Stakeholder Engagement, Disclosure, and Grievance Redress

A separate Stakeholder Engagement Plan (SEP) has been prepared for the Project, based on the World Bank’s Environmental and Social Standard 10 (ESS 10) on Stakeholder Engagement. The SEP can be found on the Ministry of Agriculture, Forestry and Water Management’s website and WB external website. The World Bank ESF / ESS require continuous engagements with stakeholders during the preparatory and implementation stages of all projects.  After incorporating stakeholders’ views in all environmental reports for projects, they are made available to project affected groups, local NGOs, and the public at large. The ESMF was prepared in conjunction with the PIU within the Ministry of Agriculture, Forestry and Water Management, other government agencies, community-based organizations, NGOs, and other relevant stakeholders. Stakeholder consultations have been undertaken in the preparation of this project as well as the ESMF.  Upon approval of the draft final ESMF report by the proponent and World Bank, the report will be disclosed and made available to the public, including all stakeholder parties. The Ministry of Agriculture, Forestry and Water Management will disclose the ESMF on their website, and the link shared with the Bank.

Estimated Budget

It is estimated that a total amount of one million three hundred and twenty-three thousand thirty-two United States Dollars (US$ 468,000), excluding costs related to RAP implementation will be required to implement activities identified in the ESMF throughout the project. However, details on the budget will be included in the prepared ESIAs/ESMPs and RPs. These estimates only serve as a potential guideline for the preparation of site-specific ESMPs which will have costed expenditures required to implement the ESMP. The details are summarized in Table 15 of the ESMF.  These figures are indicative and the PIU of FSPP will prepare subsequent funds as more clarity is obtained on project activities.

# Introduction

# 1.1 Background Information

Montenegro is a country rich in forests, covering more than 60% of its territory. This natural resource plays a key role in biodiversity conservation, environmental protection and economic development, especially in rural areas. However, the forestry sector faces numerous challenges, including climate change, which is leading to the degradation of forest ecosystems. On the other hand, forests are economically exploited in an irrational manner, and the wood industry is insufficiently modernized.

In this context, the FSPP represents a strategic response to these challenges. Its aim is to improve sustainable management of forest resources, increase resilience to climate change and stimulate the development of the wood industry. The project is aligned with national strategic documents, including the Forest and Forestry Development Strategy (2025–2030) and the Wood Processing and Furniture Production Development Programme (2025–2028), making it a key step towards modernizing the sector and strengthening its competitiveness.

## 1.2 Purpose of the Environmental and Social Management Framework (ESMF)

This Environmental and Social Management Framework (ESMF) is the guiding document for environmental and social risk assessment and management under the FSP Project. It has been prepared in full compliance with the World Bank’s Environmental and Social Framework (ESF) as per the guidance of Environmental and Social Standard 1 (ESS1): Assessment and Management of Environmental and Social Risks and Impacts (ESS1). This ESMF provides guidance for project agencies in screening, assessing, and managing environmental and social risks during project design and implementation, including preparing site-specific ESMPs, addressing labor requirements, and mitigating asset and livelihood impacts as per the World Bank ESF. The Ministry of Agriculture, Forestry and Water Management will be the lead agency.

The ESMF ensures that environmental and social risks associated with the eventually investments are identified, assessed, and proposes suitable mitigation measures to manage these risks and impact, in a structured and transparent manner, aligned with both Montenegrin legislation and the World Bank ESF.

This ESMF will be updated as necessary in the event of any material changes to the project description, scope of activities, or environmental and social risk profile during the project cycle, subject to World Bank review and clearance.

The ESMF also complements and should be read together with other key safeguard instruments including the Stakeholder Engagement Plan (SEP), and The Labor Management Procedures (LMP).

The ESMF is a living document and will be updated, as necessary, throughout Project implementation to reflect evolving project conditions, legal developments, lessons learned, and updated World Bank guidance

## 1.3 Rationale for an Environmental and Social Management Framework

The Project’s Environmental and Social (E&S) risk rating is Moderate. The Project aims to improve the environmental and sustainable management of the forestry sector in Montenegro. The Project will prepare E&S framework instruments, such as to manage and mitigate subproject specific risks and impacts. For coherence and simplicity, only the ESMF and SEP will be prepared as standalone instruments. Site specific risk management plans will be prepared prior to the start of any Project-related physical works. Site-specific activities will be screened to determine their individual risk levels and the risk management instrument determined accordingly.

The rationale for preparing the framework stems from the fact that the locations and designs of all subprojects will be determined during project implementation. As a result, detailed site investigations will be conducted to identify specific project activities and designs at selected sites, ensuring a thorough understanding of the environmental and social impacts. The ESMF will offer essential background information on environmental and social considerations, provide a checklist of potential issues to be addressed, and guide the integration of these considerations into project design. This approach supports socially sustainable implementation, including environmental and social screening of subprojects and guidance for preparing targeted assessments and plans. Site-specific risk management plans will be finalized prior to the start of any Project-related physical works

## 1.4 Aim and Objectives of the Environmental and Social Management Framework

This ESMF has been developed to support environmental and social due diligence for activities funded by the World Bank in FSPP in Montenegro. The ESMF serves as a practical resource during project formulation, design, implementation, and monitoring. It offers guidance regarding environmental management for the proposed project, covering works and studies such as environmental and social screening, assessments, and management plans. Additionally, it outlines steps, processes, procedures, and mechanisms designed to ensure appropriate consideration and integration of environmental and social factors throughout the project cycle, and describes relevant principles, objectives, and approaches to avoid, minimize, or mitigate impacts.

Specifically, the ESMF seeks to:

- assess potential environmental and social risks and impacts of the proposed project and propose mitigation measures;

- establish procedures for environmental and social screening, review, approval, and implementation of activities;

- specify roles and responsibilities and define reporting procedures for managing and monitoring environmental and social issues;

- identify staffing requirements and detail training and capacity-building needs for implementing the ESMF;

- address mechanisms for public consultation and disclosure of project documents, as well as grievance redress;

- establish budgetary requirements for ESMF implementation.

This ESMF is intended to be read alongside other project plans, such as the i) Labor Management Procedures (LMP), which incorporate gender, SEA/SH, and GBV risk assessments and prevention plans, ii) the Resettlement Framework (RF) addresses impacts related to asset and livelihood loss from land acquisition or involuntary relocation and provides guidance for preparing Resettlement Action Plans (RAP) or Abbreviated Resettlement Plans (ARAP),iii) the Stakeholder Engagement Plan (SEP) identifies key stakeholders and ensures inclusive consultation, including a grievance redress mechanism (GRM) to assist with complaints and support participation in decision-making iv)the Environmental and Social Commitment Plan (ESCP) details required actions to comply with environmental and social standards, including implementation of the ESMF, RF, and SEP.

## 1.5 Study Approach and Methodology

This ESMF aligns with the World Bank Environmental and Social Framework (ESF) and Montenegro national and local laws. Key steps included reviewing project details, documents, including the PAD and relevant national policies, and regulatory requirements, conducting field visits and scoping, consulting stakeholders from relevant sector institutions, incorporating stakeholder feedback into the ESMF, and obtaining approval for disclosure. The Ministry of Agriculture, Forestry and Water Management will lead the project, providing strategic direction, coordination, and oversight to ensure alignment with national forestry policies and priorities. Within the Ministry, the Directorate for Forest Management will play a central operational and technical role, guiding regulatory frameworks, coordinating field activities, and liaising with key institutions. These include a newly established State-Owned Enterprise focused on forest management operations (Components 1 and 2), the Forest Administration responsible for on-the-ground management and compliance, the Ministry of Interior for forest fire prevention and response (Component 2), and the Institute for Multi-Disciplinary Studies for workforce development and innovation in the wood processing industry (Component 3).

A dedicated Project Implementation Unit (PIU) will be set up within the Ministry, comprising a Project Manager, Administrative Assistant, Social Specialist, Environmental Specialist, Grant Manager, and part-time Communications and M&E Specialists. The PIU will ensure effective execution, coordination, monitoring, and reporting of project activities, with specialized roles to address social inclusion, environmental compliance, grant management, and stakeholder engagement.

Oversight and inter-institutional coordination will be provided by a Project Steering Committee (PSC), chaired by the Minister. The PSC will review and approve work plans and budgets, resolve inter-agency issues, monitor progress, and ensure coherence with national policies, fostering participatory and transparent governance.

Fiduciary functions, including procurement and financial management, will be handled by the centralized fiduciary/Technical Support Unit (TSU) at the Ministry of Finance. The TSU, experienced in World Bank procedures, will ensure compliance, consistency, and efficiency in fiduciary management, support the PIU in contract management and financial reporting, and maintain transparency and financial controls throughout the project.

# 2.	Project Description

## 2.1 Project Overview

Montenegro boasts significant forest resources, comprising almost 60% of the country's territory, with forests and woodland covering 69.7% of the total area. These forests represent a key element in the ecological balance, given the rich biodiversity, protection of soil from erosion, climate regulation and preservation of clean water sources.

Figure 1Montenegro Forest

There are as many as 68 tree species in the forests of Montenegro, dominated by beech, oak, spruce, fir and various types of pine.

Forest management in Montenegro faces numerous challenges, such as inadequate protection from climate change, the occurrence of forest fires, inadequate management and the need to modernize the wood industry. Although the law prohibiting clear-cutting is observed, selective logging is applied, which allows for the preservation of the structure and quality of forests.

Soils in the forest areas of Montenegro are diverse and include about 30 types and subtypes of soil. Among them, brown soils dominate in the northeastern part, rendzina in the central and western parts, and alluvial and diluvial soils in coastal and water areas.

In recent decades, the number of fires in Montenegro has varied, but on average it has been 91 fires per year, with an average burned area of ​​500 hectares. The main causes of fires are the deliberate burning of meadows and pastures and the irresponsible behavior of hikers.

Non-timber forest products, such as herbs, fruits, mushrooms, resins and other forest components, also represent a significant resource. In the last five years, 27 companies have been granted the right to commercially exploit these products, indicating a growing non-timber forest products sector in the country.

The ownership structure of forests in Montenegro is divided almost evenly between state and private forests, with a tendency to increase the number of private forests due to problems with the cadaster and restitution.

Considering all these aspects, forestry in Montenegro plays a key role in preserving the ecological balance, providing economic benefits and conserving natural resources, but also faces challenges in terms of protection, sustainable management and adaptation to climate change.

## 2.2 Rationale for Project implementation

This ESMF is intended to be read alongside other project plans, such as the i) Labor Management Procedures (LMP), which incorporate gender, SEA/SH, and GBV risk assessments and prevention plans, ii) the Resettlement Framework (RF) addresses impacts related to asset and livelihood loss from land acquisition or involuntary relocation and provides guidance for preparing Resettlement Action Plans (RAP) or Abbreviated Resettlement Plans (ARAP),iii) the Stakeholder Engagement Plan (SEP) identifies key stakeholders and ensures inclusive consultation, including a grievance redress mechanism (GRM) to assist with complaints and support participation in decision-making iv)the Environmental and Social Commitment Plan (ESCP) details required actions to comply with environmental and social standards, including implementation of the ESMF, RF, and SEP.

### 2.2.1 Rationale for Implementing the Montenegro FSPP

Montenegro’s forests are a vital ecological and economic resource, covering over 60% of the country’s territory and playing a vital role in biodiversity conservation, climate regulation, water protection, and rural livelihoods. However, the sector faces challenges including: i)Outdated forest governance due to Inefficient concession models and weak oversight have led to unsustainable logging and poor forest regeneration ii)Climate vulnerability due to  Increasing risks from wildfires, droughts, and pests threaten forest ecosystems and rural communities) iii) low productivity in the wood industry as SMEs lack access to modern technologies, certification, and competitive markets iv) Northern municipalities, once wood industry hubs, face economic decline and migration vii) Social inclusion gaps due to underrepresented  of women  and vulnerable groups and in forest-related decision-making and benefit-sharing, and viii) as a future EU member, Montenegro must meet EU forestry, biodiversity, and climate standards.

The FSPP shall address these issues through institutional reform, sustainable forest management, climate resilience, and support for wood industry competitiveness. It promotes inclusive development, job creation, and environmental sustainability, aligning with Montenegro’s national strategies and EU accession goals.

## 2.3 Project Development Objectives

The Project Development Objective (PDO) is to improve the sustainable management of forest resources and to enhance the competitiveness of the forest industry in targeted project areas in Montenegro

## 2.4 Project Components

The project is organized into four main components, which include:

Component 1: Strengthening Sector Governance and System Modernization (estimated US$5 million, or 25 percent of total cost)

Subcomponent 1.1: Strengthening Policy Framework and Institutional Capacity. This subcomponent will provide technical assistance to support the development of policies and regulations that address barriers to creating a dynamic, market-driven, and productive forest sector. It will also facilitate the effective implementation of the new Forest Law by establishing operational mechanisms, assisting in the preparation of essential by-laws and regulations, and enhancing both institutional capacity and frameworks. Technical assistance will be provided across the following areas:

- Supporting the formulation of policies, regulations, and operational guidelines to boost sector competitiveness, with particular emphasis on EUDR compliance;

- Reviewing and updating institutional and policy frameworks for forest fire management modernization of wildfire prevention, detection, and alert systems. This includes  the development of emergency response plans for the SOE,   as well as strengthening the capacity to implement these strategies through targeted training and capacity development;

- Supporting the development of performance and compliance standards for public sector contractors by implementing certification and audit mechanisms to promote sustainable timber sourcing;

- Conducting market studies and enhancing market information on timber production and sales, improving access to foreign investment, and facilitating entry into the European Union single market;

- Developing protocols and procedures for reinforcing law enforcement and regulatory oversight to combat illegal logging, through measures such as expanding legal access to timber and fuelwood, improving supervision and documentation of authorized removals, thereby increasing the frequency and effectiveness of forest inspections.

Subcomponent 1.2: Modernizing Forest Resources measurement and Traceability ($3.5M). This subcomponent will focus on improving systems that measure forest resources and forest carbon, as well as those that establish a chain of custody for forest products. Improving the supply of information will help forest management decisions, in turn ensuring a more predictable, transparent, and legal timber supply. Activities envisioned under this subcomponent are:

- Update the Forest Management Information System (FMIS), including the integration of Geographic Information System (GIS) data sets. This enhancement will be based on the Terms of Reference (TOR) developed with financial support from the European Union.

- Updating the design of the National Forest Inventory (NFI) to improve the assessment of the quantity and quality of current forest resources and carbon stocks, enabling more effective updates to forest management plans (FMPs).

- Upgrading the existing timber valuation system by enhancing the Decision Support System (DSS), which will provide more accurate estimates of the volume, number, and diameter class breakdown of log assortments that can be harvested from standing timber lots.

- Supporting the establishment of an Electronic Timber Tracking System (ETTS) to improve traceability and transparency throughout the timber supply chain by developing the system, providing complementary technical assistance and procuring necessary equipment to make it operational.

- Updating the measuring, reporting, and verification (MRV) system to better track forest sector emissions and carbon sequestration, supporting compliance with national and international reporting requirements.

- Expanding the collection, analysis, and reporting of official forestry statistics. This will be implemented in partnership with MONSTAT, focusing on two main areas: (a) automating the data collection, analysis, and publication processes, and (b) building MONSTAT’s capacity through knowledge exchange programs and the procurement of essential materials.

- Establishing a comprehensive, one-stop, web-based portal to provide access to data from the FMIS, including NFI results, DSS outputs, ETTS, MRV, and statistical reports, ensuring transparency and ease of access for stakeholders.

Subcomponent 1.3: Supporting the Operationalization of the State-Owned Enterprise (SOE) ($1.0M). To ensure robust governance and efficient operation of the SOE envisioned by the new Forest Law, this subcomponent will support the development of comprehensive governance and management systems, as well as operational mechanisms, to effectively guide the functions and responsibilities of the new SOE. Two primary activities are planned under this subcomponent:

- Supporting the preparation and implementation of a comprehensive business plan, corporate charter, and financing strategy for the SOE to ensure its effective operation from inception through to commercial viability. Given the initial delays in establishment, this support will follow a phased approach—beginning with the development of necessary legal frameworks, followed by the support to establishing the organizational structures and associated financial planning. This will be followed by the rollout of forest operations and recruitment of staff, ultimately leading to the SOE's direct management of wood sales.

- Facilitating the development of competitive, transparent, and equitable forest product sales mechanisms. This activity includes support to the development of methodologies that will inform the Government decisions and procedures that govern timber sales, with a strong emphasis on open and competitive bidding processes. Additionally, the integration of an online timber commodity auction system will be prioritized to enhance market efficiency and transparency.

Component 2: Advancing Sustainable Forest Management and Climate Resilience against wildfires (estimated US$7.5 million, or 37.5  percent of total project cost)

The main objectives under this component include advancing the use of SFM principles in Montenegro's forests—both public and private—and enhancing practices for mitigating and managing climate change exacerbated forest fires risks. By doing so, the component aims to ensure a reliable and sustainable supply of raw materials to wood processing firms, while maintaining carbon stocks at targeted levels.

Subcomponent 2.1: Advancing Adoption of SFM Practices ($2.5M). This subcomponent aims to enhance overall forest maintenance practices, strengthen forest climate resilience, and promote biodiversity in selected areas. The activities emphasize the mandatory adoption of SFM practices by public forests and encourages the uptake of these practices in private forests through targeted technical and financial assistance. In addition, the subcomponent will advance the development and implementation of forest management certification standards—such as FSC and PEFC—which are currently absent in Montenegro. The interventions under this sub-component will include:

- Supporting practical forest management activities regeneration felling, selective thinning, intermediate silviculture (such as systematic thinning), modernizing seedlings and human-assisted natural forest regeneration from seeds or coppice, as appropriate and in alignment with approved forest management plans. These activities will be implemented in targeted areas with the objective of enhancing forest maintenance practices, increasing forest resilience, and promoting biodiversity.

- Increasing awareness among private forest owners and improving harvesting plans for selected privately owned forests, particularly where a Forest Management Plan (FMP) is required for holdings exceeding 5 hectares, to ensure compliance with SFM principles under the new Law on Forests. Ongoing support will be provided to private forest owners to help them prepare management plans, apply for felling licenses, and carry out harvesting and silvicultural interventions in a more sustainable manner. This technical assistance will be delivered primarily through a strengthened forest extension service, which will help the Forest Administration enhance.

- Providing technical and financial assistance to advance and implement FSC and PEFC certification schemes. Key activities will include conducting baseline assessments to identify gaps in current forest management practices, facilitating audits by accredited certification bodies, and supporting forest enterprises throughout the certification process to ensure alignment with international standards.

Subcomponent 2.2: Promoting Forest Fire Resilience ($2.0M). This subcomponent will support investments aimed at enhancing the climate resilience of Montenegro’s forests and reducing the risk of wildfire through fire prevention measures, enhancement of local detection system, community participation, support for repressive measures (fire suppression) and support for restoration of selected forest land degraded by wildfire. The expected outcomes will include improved fire protection areas and buffer zones, improved silvicultural and enhanced fuel load management practices, and the adoption of new technologies and practices. The interventions under this subcomponent will include wildfire prevention, preparedness, response and recovery activities:

- Improving fire prevention measures such as (a) Increasing awareness and preparedness of  communities to better manage the landscape to reduce the risk of ignition sources and improving local detection and response, (b) Maintaining fire protection areas (through clearing land from forest vegetation), cultivating mineralized strips on the boundary between agricultural and forests, creating buffer zones with forest fire resistant species (such as cultivation of broadleaved and mixed stands) between forest areas, silvicultural interventions, fuel load management interventions (such as thinning, grazing, controlled burning etc.); (c)Supporting the development of fire protection infrastructure including support for the construction of new and maintenance of existing firebreaks and barriers, construction of water reservoirs in high-risk areas, modernization of warehouses and storage facilities for firefighting equipment already in place, improving firebreaks and boundary lines (addressing the edges of roads and transition points of electrical communication lines).

- Strengthening preparedness activities at the local level through (a) Development and updating of local Integrated Forest Fire Management Plans and preparation of detailed plans for forest management units, including incorporating  data on climate change(i.e. changing precipitation patterns, frequency of forest fires), areas, forest types, degree of vulnerability, and potential fire types; (b) Preparation and digitalization of fire protection maps showing roads, water reservoirs, telecommunication and power lines, observation points, tourist zones, and equipment warehouses, (c). Technical assistance aimed at strengthening the local detection system including through developing recommendations for enhanced  forest fire danger rating and the local forest fire detection systems through network of fire towers, local community spotters, remote sensing (drones), (d)  Supporting Resource Inventory and Maintenance  through procurement of equipment for direct and indirect firefighting, procurement of new vehicles and specialized firefighting equipment, and upgrading and increasing the location of vehicles and machinery.

- Strengthening the operational readiness and system responses and fire suppression that includes (a) Modernizing surveillance and detection approaches to reduce the detection time for forest fires through maintenance of unmanned watchtowers, (b) Enhancing communications and dispatching systems to reduce first response time through creation and maintenance of databases on available personnel and technical resources, replacement of old equipment and the establishment of a Digital Radio Communication System, establishment and marking of permanent water supply points and development of capacities to implement these interventions; (c)  Improving the response system for forest fires at the local level including training of Forest Administration and SOE staff and community firefighting teams, provision of suitable hand tools (e.g., rakes, mattocks, beaters, leaf blowers, knapsack sprayers, etc. and protective clothing, as well provision of key equipment for mobile firefighting teams)Supporting rehabilitation and restoration of existing burned areas including support for the preparation of rehabilitation plans (mandatory under the new Forest Law) and implementation of activities for the restoration of forest areas affected by fires, and support for the improvement of existing monitoring and analysis of fire causes with the aim of improving future and reducing fire risks. This activity will also include restoration of selected forest land degraded by wildfire using appropriate techniques to increase resilience to climate change and other stressors (e.g. pests), as well as to increase biodiversity and ecosystem services post-fire (e.g., flood protection, soil erosion, etc.).

- v.	Supporting the rehabilitation/construction of the forest road network to improve access for forest fire management, operational forestry activities, and recreational use. The activity will focus on selected municipalities, prioritizing the rehabilitation of existing forest roads to optimize resources and maximize impact. Proven construction and renovation rates will be leveraged to ensure that the project remains on schedule and delivers measurable results within the planned timeframe. The selection of target municipalities will be guided by a combination of factors: the current value of forest accessibility, the physical condition of existing roads, and the wildfire index rating for each area.

Component 3: Improving Forestry Sector Competitiveness (estimated US$, or xxx percent of total cost)

The objective of this component is to strengthen the competitiveness and sustainability of Montenegro’s forest industry by building the productive, technological, and human capacities of enterprises, promoting certification and standardization, and supporting modernization and innovation across the sector. The component will pursue three complementary lines of action. First, it seeks to enhance the skills base and workforce quality through targeted training, professional education, and practical learning programs to address key labor market and skills gaps in the sector . Second, it will improve the competitiveness of small businesses in the wood processing  industry in Montenegro through a competitive grant scheme that will enable firms to finance the modernization of production, technology adoption, and upgrade product quality. Third, it aims to promote the adoption of certification and quality assurance systems, enabling firms to meet domestic and international market requirements and improve their export readiness. Collectively, these interventions are expected to expand the scale of operations, improve firm competencies, increase product diversification, and boost workforce capacity—ultimately leading to the creation of better and higher-paying jobs. The activities are closely interconnected; for example, small, and medium-sized enterprises (SMEs) awarded through the grant scheme will commit to capacity development and extension services. This approach will enable firms to diversify their products, enhance operational efficiency, improve productivity, and adopt novel and innovative practices. By meeting required industry standards and quality benchmarks, participating SMEs will be better positioned to compete in regional and EU markets, thereby increasing the economic contribution to the national economy.

Subcomponent 3.1: SmartWood Capacity Program (SmartWood). This sub-component will focus on supporting establishment and operationalization of SmartWood Capacity Program (SmartWood) that will be dedicated to advancing workforce, innovation, and sustainability in Montenegro’s wood processing industry but also in the forestry sector in general. It will serve as the central mechanism for delivering technical assistance, training, and advisory services to enterprises, particularly those supported under the grant scheme described in Subcomponent 3.2, and for fostering long-term collaboration between academia, industry, and government. SmartWood  will be housed at the Institute of Interdisciplinary and Multidisciplinary at the University of Montenegro ensuring close integration of research, education, and industry practices. SmartWood will aim at enhancing the capabilities of the labor force, improve quality of products, and promote innovation and sustainability of forest industry in Montenegro. The reach of the SmartWood program is intended to go beyond the grant recipients under component 3.2 and ensure access to skills and knowledge at scale. The interventions under this sub-component include:

- Capacity and Workforce Development: SMARTWOOD will design and deliver comprehensive training programs tailored to the needs of the wood processing and forestry sectors. Training modules will cover key areas such as modern production techniques, digital transformation, sustainable resource use, certification and quality management, and innovation practices. Special focus will be placed on upskilling workers and managers from SMEs participating in the Grant Scheme under Subcomponent 3.2, ensuring that investments in equipment and processes are complemented by improved human capital. SMARTWOOD will foster partnerships with educational institutions and vocational schools to align curricula with industry needs and promote lifelong learning. In addition, the project will support the establishment of a Forestry Program at the University of Montenegro—a four-year bachelor’s program designed to address the sector’s long-term skills gap. Project assistance will finance the preparation of teaching materials, procurement of limited essential laboratory and field equipment, and the development of applied learning modules to ensure practical and industry-relevant instruction.

- Development and Delivery of Advisory and Extension Services that will provide ongoing advisory and extension services to Wood Industry companies, including hands-on technical support and guidance in adopting new technologies and processes. The activities will include developing and delivering advisory services and offering practical assistance to businesses in achieving certification and compliance (as stated under sub-component 3.3). The activities will also facilitate the dissemination of best practices and innovations through on-site demonstrations, technical bulletins, and expert consultations.

- Technical and Applied Research-Based Support that will advance innovation and sustainability in the sector through applied and technical research. The activities will include technical support to wood industry SMEs to develop new products and improve production processes and include assistance to adopt and scale up research-driven solutions that enhance resource efficiency, reduce environmental impacts, and support the transition to sustainable business models.

- Market Intelligence and Business Insights to identify emerging trends, export opportunities, and evolving consumer preferences. It will disseminate relevant market intelligence and organize industry dialogues to help companies anticipate changes, adapt to market dynamics, and strengthen their export strategies;

- Improving the Enabling Environment for Industry Competencies through developing analysis on the regulatory landscape to identify bottlenecks and barriers hindering workforce and industry development of the wood processing sector. Prepare policy notes and recommendations (for relevant government agencies) aimed at streamlining procedures, enhancing transparency, and promoting an enabling environment for skills development and innovation.

Subcomponent 3.2: Grant Scheme Support for Advancing Wood Industry SMEs ($2M). This sub-component is designed to strengthen the capacity and capabilities of wood industry SMEs—including sawmills, panel producers, and furniture manufacturers—so they can effectively secure and utilize commercial financing in the long run. The initiative integrates a targeted grant program with comprehensive technical assistance, establishing a sustainable pathway for SMEs to enhance their business and technological capabilities, thus improving their overall performance and competitiveness. Although funding for firms in Montenegro is now more accessible than in previous years, banks remain hesitant to lend to the sector due to past supply chain challenges, limited financial literacy, insufficient collateral, and weak business planning. Many companies also lack the capacity to access not only commercial bank funding but also concessionary finance. The interventions under this sub-component will include:

- Establishing a Competitive Grant Scheme: A competitive grant scheme will be developed specifically to address the unique needs of wood industry SMEs. This scheme will offer direct financial support to encourage investment in key areas such as the modernization of production facilities and equipment, adoption of green and sustainable technologies, product development and diversification, market access and export readiness, certification, standardization, and more. The grants aim to stimulate innovation and enhance the overall competitiveness of participating SMEs.

- Technical Assistance (TA): Complementing the grant scheme, technical assistance will be provided to strengthen the managerial, financial, and operational capacities of SMEs. The TA program will include: (a) Financial Literacy and Business Planning—training in preparing robust business plans, financial statements, and loan applications to boost bankability; (b) Mentorship and Advisory Services—personalized coaching from industry experts and financial advisors to address specific business challenges and improve access to commercial loans; and (c) Market Linkages and Networking—facilitated connections with financial institutions, buyers, and export platforms to help broaden market access and (d) Digital transformation – introducing change in which the companies go about their internal processes, deal with documentation and interact with their partners and clients.

- Technical assistance will be delivered primarily through SmartWood Capacity Program, as described under sub-component 3.1. A comprehensive Grant Manual will be developed to clearly outline the processes, eligibility criteria, technical criteria in line with Government priorities relevant to the forestry sector and requirements for accessing grant support, ensuring transparency and accountability throughout the program including all relevant State-aid regulations. By integrating both the grant scheme and technical assistance, the manual will provide detailed guidance on the application process, optimize use of available resources for capacity building, promote the adoption of best practices and advanced technologies, and support the seamless integration of the grant scheme with the technical assistance provided under sub-component 3.1 and with certification and standardization efforts (sub-component 3.3). The scheme will be implemented by the Project Implementation Unit (PIU), staffed with personnel possessing adequate technical, fiduciary, and monitoring expertise. Transparent selection and evaluation mechanisms will be applied to ensure accountability and equitable access.

Subcomponent 3.3: Advancing Certification, Grading, and Standardization in Montenegro’s Wood Processing Industry ($0.5M).This sub-component will support the delivery of technical assistance needed for the  implementation and uptake of certification, grading, and standardization of the wood processing industry products, processes and services, which is fundamental to strengthening the competitiveness and credibility of Montenegro’s wood processing industry as the global markets including the EU single market has increasingly demand traceable, high-quality, and sustainably sourced wood products.  A key focus of this activity and priority in terms of beneficiaries initiative is the is the prioritization of SMEs selected for support under the Grant Scheme (Sub-Component 3.2). These SMEs will receive tailored technical guidance and capacity-building assistance through the SmartWood Capacity Program (Sub-Component 3.1), equipping them to meet rigorous certification and grading requirements. This targeted approach ensures that the most promising and growth-oriented enterprises are empowered to achieve compliance with international standards, thereby maximizing the impact of the program. The implementation of the certification and standardization program will be carried out in close partnership with the Institute for Standardization of Montenegro (ISME). The interventions under this component include:

- Supporting selected SMEs, through technical assistance and advisory, to meet rigorous certification and grading requirements through tailored technical guidance and capacity-building assistance

- Supporting the establishment of certifiable chains of custody (CoC) for wood products, in accordance with Forest Stewardship Council (FSC) or Programme for the Endorsement of Forest Certification (PEFC) standards, through targeted pilot testing.

- Building local capacity by training and accrediting CoC and other certification assessors, thereby strengthening Montenegro’s ability to maintain and expand certified supply chains.

Component 4: Project Management, Monitoring, and Communication (estimated US$2 million, or 10 percent of total cost)

This component will finance the operating costs of the Project Implementation Unit to carry out the oversight and management functions of the project. This includes activities such as project management and coordination, environmental and social risk management, monitoring and evaluation, stakeholder engagement and communication as well as documentation of lessons learned from project implementation and stakeholders’ efforts to scale-up good practices.  All fiduciary functions will be carried out by a Technical Support Unit (TSU) housed at the MoF, as is the case with all World Bank-financed investment projects in Montenegro. Expenses incurred by the TSU will be financed out of the loan on a pro rata basis with other World Bank-financed projects in Montenegro.

## 2.5 Implementation and Timeframe

The implementation of the Montenegro Forest for Shared Prosperity Project is planned in several phases, in order to ensure efficiency and gradual implementation of key activities.

- Preparatory phase (2025): This phase includes an analysis of the situation in the forestry and wood industry sector, identification of priority activities, development of management plans and preparation of the regulatory framework. Consultations with relevant institutions and local communities are also planned to ensure inclusiveness and compliance with national and international policies.

- First phase (2025–2028): During this period, the implementation of specific measures in the forestry and wood industry begins. The focus will be on improving forest management methods, implementing afforestation programs, and strengthening the monitoring and protection system of forests. In parallel, work will be done on modernizing the capacities of the wood industry, including the introduction of modern technologies and increasing energy efficiency. Also, special attention will be paid to education and professional training of personnel.

- Phase 2 (2028–2032): This phase involves expanding activities to additional areas and strengthening the acquired capacities. Special focus will be on increasing wood processing capacities, developing markets for high value-added products and strengthening the sector's export potential. Also, the achieved results in the field of forest protection and biodiversity will be evaluated, with the aim of further adjusting management strategies and plans.

- Evaluation and adjustment (2032+): After the completion of the key implementation phases, a detailed assessment of the project's results and impacts is planned. This phase will enable the definition of long-term development directions for the forestry and wood industry sector, with continuous monitoring of new challenges and adjustment of strategies.

The project will be financed through a combination of national funds, international donations and investments, including support from the World Bank, EU funds and the private sector.

### 2.5.1	Description of proposed project components

Table 1Proposed project characteristics

| Section | Description |
| --- | --- |
| Forest area under pilots for improved forest maintenance practices (Hectare (Ha)) | regeneration felling, selective thinning, intermediate silviculture (such as systematic thinning), and human-assisted natural forest regeneration from seeds or coppice, as appropriate and in alignment with approved forest management plans |
| Advancing Sustainable Forest Management and Fire Resilience (Forest area under enhanced wildfire prevention (Hectare (Ha) | Includes reducing ignition sources, buffer zones, fire prevention infrastructure |
| Forest area with improved harvesting plans (Hectare(Ha)) |  |
| Tools to support forest resource measurement and traceability implemented or updated (Number) | Update to Forest Management Information System (FMIS) including GIS integration Revision of National Forest Inventory (NFI) Upgrade to existing timber valuation system incl enhancing the Decision Support System (DSS) Introduction of Electronic Timber Tracking System (ETTS) MRV and forestry statistics updated |
| SmartWood Capacity Programs | Training individuals in modern forestry and wood processing techniques |
| Support to SMEs |  |

Source: Project FSPP

## 2.6 Institutional and Implementation Arrangements

A dedicated Project Implementation Unit (PIU) will be established within the Ministry of Agriculture, Forestry and Water Management to ensure effective and timely execution of all Project activities. The PIU will be composed of a Project Manager, who will provide overall coordination and oversight of activities’ implementation and coordinate monitoring and evaluation (M&E) activities, an Administrative Assistant, responsible for logistical, procurement, and financial support functions, a Social Specialist, ensuring that activities are designed and implemented in an inclusive and socially sustainable manner, while being aligned with ESF documents and stakeholder engagement strategies prepared under the Project; an Environmental Specialist, tasked with integrating environmental risk measures into the Project activities and ensuring compliance with environmental standards and regulations; and a Grant Manager, who will oversee the design, allocation, and monitoring of grant mechanisms aimed at stimulating innovation, value addition, and competitiveness within the wood industry under Component 3. The Grant manager will also coordinate other activities under Component 3. Lastly, the PIU will also include a part-time Communications Specialist & Monitoring and Evaluation (M&E) Specialist to support effective project visibility, stakeholder engagement, knowledge dissemination, and results tracking throughout the implementation period.

# 3. Environmental and Social Policies, Regulations, and Laws

This section summarizes the regulatory framework relevant/applicable to the FSPP implementation. The section will compare national regulatory and legal frameworks with the requirements of the World Bank Environment and Social Framework (ESF), identify gaps between these two pieces of instruments, and how propose measures by which these gaps will be addressed.

## 3.1Project Categorization under the World Bank ESF

Under the World Bank ESF, the World Bank classifies projects into four (4) categories: High, Substantial, Moderate and Low Risk largely based on the scale of the project, level of impact, environmental and social sensitivities and risks associated with the project, in country socio-political conditions as well as the capacity of the borrower to manage the associated impacts and risks.

Based on the nature and scope of project activities primarily under component 2 (construction of forest Management system, forest management and the capacity of the PIU in Montenegro to manage the environmental risks of project activities consistent with the ESSs, the risk rating is assessed to be Moderate at this stage. At this point, no permanent or irreversible environmental risks or repercussions are predicted.

## 3.2 Summary of Environmental and Social Risks and Impacts:

Key environmental concerns identified at this stage include: i)climate change risks ii) hazardous materials and wastes from construction activities  may pose risks to soil, water ecosystems iii)OHS related risk as result of workers involved in forest operations and infrastructure developments including risks from machinery, exposure to chemicals and fire hazards iv)Community Health and Safety including increases vehicle traffic, noise and dust from activities. Additional activities such as the establishment of fire zones and forest management may restrict access to forest resources affecting local communities. Other risks include the risk of Sexual Exploitation, Abuse, and Sexual Harassment (SEA/SH) social exclusion. However, these concerns will be addressed by preparing E&S instruments including ESIAs, ESMPs,BMP,,SEA/SH plan, Capacity building and awareness measures and  other measures that will minimize possible risks. Additional social risks include potential labor influx during small-scale works, which may increase community exposure to SEA/SH risks. These will be mitigated through mandatory Codes of Conduct for all workers, SEA/SH training, strict worker–community interaction protocols, and a confidential survivor-centered GRM channel.

Stakeholder engagement will focus on inclusive participation and information disclosure using appropriate language and media. A Stakeholder Engagement Plan (SEP) has been prepared, proportional to the project's nature, scale, risks, and impacts. The SEP will be disclosed before project appraisal, ensuring consultations are timely, relevant, understandable, and accessible. A documented record of stakeholder engagement at different stages of the project cycle will be maintained and publicly disclosed. A project-wide GRM will address concerns, including a confidential channel for SEA/SH issues. Local actors and liaison officers may be designated to coordinate the SEP implementation.

When there is adequate information about the Project locations, scope of investment and the corresponding risks, the Project E&S risks will be reassessed based on the scope of Project activities and determine if it needs revision to upgrade the E&S risk rating and additional E&S instruments as needed.

## 3.3 Relevant World Bank Group Guidelines

The guidelines relevant to the project, and that will be summarized here are:

- The World Bank Environment and Social Framework (ESF), 2017

- World Bank Group Environmental, Health and Safety Guideline (EHSG), 2007 (General Guidelines)

- ESF Guidance notes for Borrowers

- ESF Good Practice for assessing and Managing the Risks of Adverse Impacts on Communities from Project-Related Labor Influx

- Good Practice Note Addressing Sexual Exploitation and Abuse and Sexual Harassment in the

- Good Practice Note for Non-discrimination and Disability

- Good Practice Note: Non-Discrimination Sexual Orientation and Gender Identity (SOGI)

- Good Practice Note for Gender

- Good Practice Note: Assessing and Managing the Risks and Impacts of the Use of Security Personnel

- Interim Guidance Notes: Managing the Risks of Projects Involving Protected Areas, 2025

The principal guiding instrument is the World Bank ESF, which sets out the World Bank’s commitment to sustainable development, through a Bank Policy and a set of Environmental and Social Standards that are

designed to support Borrowers’ projects, with the aim of ending extreme poverty and promoting shared prosperity. The Environmental, Health and Safety Guideline (EHSG), also apply to the Project. The EHS Guidelines are technical reference documents with general and industry specific examples of Good International Industry Practice.

## 3.4 	National Environmental Legal Framework

The relevant environmental laws and regulations to guide the project the project cycle is presented in Table 5 and these include

Table 2 Relevant legal framework applicable to the proposed project

| No. | Legal and Regulatory Framework |
| --- | --- |
|  | EU environmental legislation has been transposed into national legislation since 2006 for all environmental sectors (water, air, waste, noise, climate change, industrial emissions, chemicals, and nature and biodiversity) for which emission standards and limits have been established (air, water, soil). The transposition of waste management legislation is in accordance with EU requirements, but it is partially implemented in practice. For various segments of the environment (including human health), strategic environmental impact assessments of plans and programs, as well as environmental impact assessments of projects, are conducted. According to the nature protection law, prior to the development of strategic documents and plans, the preparatory work holder is obliged to obtain a decision from the competent authority regarding the conditions and guidelines for nature protection. |
|  | The Environmental law ("Official Gazette of Montenegro", No. 52/16, 03/19, 84/24), regulates the principles of environmental protection and sustainable development, instruments and measures for environmental protection, and other matters of environmental importance. Article 10 of this law stipulates the obligation for both domestic and foreign legal and natural persons to ensure the rational use of natural resources, incorporate environmental protection costs within investment and production costs, comply with regulations, and implement environmental protection measures in accordance with this law and other regulations. Chapter III of the Law establishes the Protection of Environmental Segments – land, water, sea, and coastal areas, air, nature, forests), which must be protected from pollution individually and within other environmental segments, considering their interrelations and interdependencies |
|  | The Law on Nature Protection (“Official Gazette of Montenegro”, Nos. 54/16, 18/19) regulates the preservation and sustainable use of natural values by ensuring the protection of biodiversity, geological and soil diversity, and by harmonizing human activities with nature conservation principles. It also requires that strategic plans, programs, and projects include nature protection guidelines, and introduces an Assessment of Acceptability for ecological network areas (in line with the Natura 2000 process) to prevent significant adverse impacts on conservation objectives and ecological integrity. |
|  | The Law on Strategic Environmental Impact Assessment (“Official Gazette of Montenegro”, Nos. 80/05, 73/10, 40/11, 59/11, 52/16) ensures that environmental and social considerations are integrated into plans, programs, and strategies before their adoption. Aligned with the EU SEA Directive (2001/42/EC) and the UNECE Kyiv Protocol (2003), the Law makes SEA mandatory for sectors such as agriculture, forestry, energy, transport, tourism, and spatial planning to prevent negative environmental impacts at the strategic level. |
|  | The Law on Environmental Impact Assessment (“Official Gazette of Montenegro”, No. 75/18) regulates the procedure for assessing projects that may have significant environmental impacts, including the preparation and evaluation of EIA reports, public participation, and decision-making based on identified impacts and consultation results. |
|  | The Regulation on Projects for which Environmental Impact Assessment is Carried Out (“Official Gazette of Montenegro”, Nos. 20/07, 47/13, 53/14, 37/18) defines projects for which an EIA is mandatory or may be required, while the accompanying Regulations on the Content of Documentation from 2019 further specify the documentation needed for determining the scope, content, and necessity of the EIA, as well as the structure of the EIA report. Complementing these, the Law on Liability for Damage to the Environment (“Official Gazette of Montenegro”, No. 27/14) establishes procedures and responsibilities for operators in preventing, mitigating, and remedying environmental damage, thereby ensuring accountability and environmental protection. |
|  | The Law on Forest Reproductive Material, originally adopted in 2007 and amended in 2015 to fully align with the EU Directive on the Marketing of Forest Reproductive Material (EC/1999/105), regulates the collection, production, and trade of forest tree reproductive material. The establishment of a state-owned forestry enterprise enables the full implementation of this law, as the company will be responsible for developing implementation projects to organize the supply of native reproductive material needed for forest regeneration through reforestation. This is particularly important for Montenegro’s integration into EU seed and planting material marketing schemes within the EU single market. |
|  | The Law on Forests, adopted in August 2024 and amended in 2025, marks a significant shift by abandoning the concession model for forest resource use. It introduces measures aligned with Montenegro’s Sustainable Development Strategy until 2030 and the EU Forest Strategy. One of the primary objectives of the law is to create conditions for establishing a state-owned forestry company that will sustainably manage forests in public interest, in accordance with forestry planning documents. This approach envisions a state-managed forestry system, where an administrative body is responsible for strategic and operational planning, while a forestry enterprise executes these plans using revenue generated from forest resource use. The funds generated by the soon to be established state-owned forestry company will be invested in forest cultivation, protection, and infrastructure, contributing to the implementation of the Forestry Development Strategy and ensuring sustainable forest management. This model aligns with practices in most EU and regional countries. A cornerstone of the Law on Forests is the establishment of a state-owned company dedicated to forest management. This entity is envisioned to be tasked with conducting forest management activities that serve the public interest, ensuring that these activities are sustainable and adhere to comprehensive planning documents. By dividing the responsibilities between public administration and commercial operations in the forestry sector and centralizing forest management, Montenegro aims to improve governance, streamline decision-making processes, and ensure consistent application of sustainable practices across all forested areas |

Table 3 List of Environmental and related Laws-Montenegro

| No. | Law / Regulation | Official Gazette (OG) |
| --- | --- | --- |
| 1 | Law on Excise Taxes | 65/01, 12/02, 76/05, 76/08, 50/09, 78/10, 40/11, 61/11, 28/12, 38/13, 45/14, 08/15, 01/17 |
| 2 | Law on Inspection Supervision | 39/03, 76/09, 57/11, 18/14, 11/15, 52/16 |
| 3 | Law on Integrated Prevention and Control of Environmental Pollution | 80/05, 54/09, 40/11 |
| 4 | Law on Strategic Environmental Assessment | 80/05, 73/10, 40/11, 59/11, 52/16 |
| 5 | Law on Criminal Liability of Legal Entities | 2/07, 30/12 |
| 6 | Law on Protection and Rescue | 13/07, 05/08, 86/09, 32/11, 54/16, 146/21 |
| 7 | Law on Water | 27/07, 73/10, 32/11, 47/11, 48/15, 52/16, 84/18 |
| 8 | Law on Transport of Dangerous Materials | 05/08, 33/14, 13/17 |
| 9 | Law on Genetically Modified Organisms | 22/08, 40/11 |
| 10 | Law on Explosive Substances | 49/08, 31/14, 31/17 |
| 11 | Law on Spatial Planning and Construction of Structures | 51/08, 40/10, 34/11, 47/11, 35/13, 39/13, 33/14 |
| 12 | Law on Hunting and Game | 52/08, 40/11, 48/15 |
| 13 | Law on Mining | 65/08, 74/10, 40/11 |
| 14 | Law on Concessions | 08/09, 73/19, 125/23 |
| 15 | Law on Ionizing Radiation Protection and Radiation Safety | 56/09, 58/09, 40/11, 55/16 |
| 16 | Law on National Parks | 56/09, 28/14 |
| 17 | Law on Flammable Liquids and Gases | 20/10, 48/15 |
| 18 | Law on Air Protection | 25/10, 40/11, 01/15, 43/15 |
| 19 | Law on Forests | 74/10, 40/11, 47/15 |
| 20 | Law on Protection of the Sea from Pollution by Vessels | 20/11 |
| 21 | Law on Regional Development | 20/11, 26/11, 20/15, 47/19 |
| 22 | Law on Protection from Noise | 28/11, 28/12, 01/14, 02/18 |
| 23 | Law on Waste Management | 64/11, 39/16 |
| 24 | Law on Free Access to Information | 44/12, 30/17 |
| 25 | Law on Spatial Development and Construction of Facilities | 35/13 |
| 26 | Law on Construction Products | 18/14, 51/17 |
| 27 | Law on Liability for Damage to the Environment | 27/14, 55/16 |
| 28 | Law on Administrative Procedure | 56/14, 20/15, 40/16, 37/17 |
| 29 | Law on Efficient Use of Energy | 57/14, 3/15 |
| 30 | Law on Food Safety | 57/15 |
| 31 | Law on Environment | 52/16, 03/19, 84/24 |
| 32 | Law on Nature Protection | 54/16, 18/19 |
| 33 | Law on Communal Activities | 55/16, 02/18, 66/19 |
| 34 | Law on Municipal Wastewater Management | 02/17 |
| 35 | Law on Chemicals | 51/17 |
| 36 | Law on Spatial Planning and Construction of Structures | 64/17, 44/18, 63/18, 11/19, 82/20 |
| 37 | Law on Provision of Healthy Water for Human Use | 80/17 |
| 38 | Law on Environmental Impact Assessment | 75/18 |
| 39 | Law on Industrial Emissions | 17/19, 03/23 |
| 40 | Law on Protection from Negative Effects of Climate Change | 73/19 |
| 41 | Law on Marine Environment Protection | 73/19 |
| 42 | Law on Public-Private Partnerships | 73/19 |
| 43 | Law on Public Procurement | 79/19, 03/23 |

Data sources: https://epa.org.me/ & https://www.gov.me/

## 3.5 	Relevant Labour and Regulatory Framework

Table 4 Labor legislation and safety at work are regulated by the following regulations

|  | Montenegro |
| --- | --- |
| Labor Law | Regulates the rights and obligations of employees under employment contracts, the manner and procedure of their realization, the promotion of employment and the facilitation of flexibility in the labour market, conclusion of employment contract, working hours, salary, work contract termination, right and obligations under employment contracts and collective bargaining. The Law, inter alia, treats working hours, breaks and leave, general protection of workers, salaries, allowances and other receipts. |
| Law on Safety and Health at Work | Regulates measures to encourage improvements of occupational safety and health, measures related to working conditions and measures related to special protection of workers, rights, obligations and responsibilities of organization, employer and worker, records, inspection surveillance and penalty provisions. |

The key provisions of the Labor Law in Montenegro are the following ones:

- Employment contracts can be concluded as open ended or fix-term, part-time, for temporary and occasional work, for performing work under special conditions as well as for work outside of employer’s premises (home office).

- The Law prohibits discrimination in terms of employment requirements and selection of candidates, education, training and professional development, promotion and employment contract termination. Pregnancy and maternity leave cannot be a reason not to hire a woman or because of pregnancy, childbirth or breastfeeding offer her the employment contract with unfavorable conditions.

- The Law prohibits mobbing, harassment and sexual harassment at work and in connection with work.

- The Law prescribes the minimum employment age of 18 for concluding an employment contract, with exception of allowing persons between 15 and 18, with the consent of their legal custodians and based on a medical certificate issued by health facility, and provided that the given job does not endanger the minor’s health, moral and education.

- Employers are required to register workers for pension and disability, health and unemployment insurance. After registration provide the worker with a copy of the registration within 5 days from the day issued by the competent authority.

- Workers are entitled to a salary and salary compensation during absence from work, as well as to working conditions which ensure safety and protection of their life and health at work. The annual holiday entitlement cannot be replaced by monetary compensation.

- Full time work is, as a rule, 40 hours a week. Overtime work is allowed in Montenegro in the duration of maximum 10 hours a week.

- Workers are entitled to an increased salary for overtime, night work and work during holidays.

- The Law defines in detail breaks from work to which workers are entitled (breaks during working hours, daily, weekly and annual leave).

- The Law envisages that a worker who believes that the employer violated any of his/her employment related rights can request from the employer to provide him/her with such right. The employer is obliged to respond to such request within 15 days. The Law envisages a mechanism of amicable dispute resolution (by the Agency for the Amicable Labor Dispute Resolution) as well as lodging court suits.

Key provisions of the legislation on occupational health and safety (OHS) in Montenegro are the following ones:

- Employers are obliged to ensure protective measures by preventing, eliminating and controlling work related risks and organizing training for workers,

- Employers are required to implement safety measures and select work and production methods that will ensure improved or higher levels of OHS,

- While assigning an employee to a position with special working conditions or with increased risk, the employer is required to take into account the employees’ abilities, which may affect their protection and health.

- Employers are obliged to provide employees with training for safe work at the time of employing a new employee, assigning him/her to another position, introducing new technology, introducing new or replacing work equipment, making changes in work processes and re-assigning him/her to work after absence of more than one year.

- Workers must be provided with a working environment, assets for work and personal protection equipment that do not endanger the safety or health of workers and other persons,

- Workers must use personal protection equipment and comply with other instructions related to safety at work.

## 3.5.1 Other Relevant Social and Labor Legislation in Montenegro

Law on Prohibition of Discrimination (Official Gazette of Montenegro, No. 46/2010, 40/2011, 18/2014, and 42/2017), prohibits direct and indirect discrimination based on gender, ethnicity, religion, disability, age, sexual orientation, and other personal characteristics.

Law on Expropriation (Official Gazette of Montenegro, No. 53/2025 (amendments and supplements)) regulates the procedure for expropriation or restriction of property rights in the public interest, including compensation and protection of ownership rights.

Law on Social and Child Protection (Official Gazette of Montenegro, Nos. 27/2013, 1/2015, 42/2015, 47/2015, 56/2016, 66/2016, 1/2017, 31/2017, 42/2017, 50/2017, 59/2021, 145/2021, 3/2023, 48/2024, 33/2025), regulates the system of social and child protection, forms of social assistance, and rights of vulnerable groups including children, persons with disabilities, and the elderly.

Law on Labor Inspection (Official Gazette of Montenegro, No. 69/2003), establishes the competencies and powers of labor inspectors, inspection procedures, and penalties for violations of labour laws.

Law on Prohibition of Harassment at Work (Mobility / Mobbing) (Official Gazette of Montenegro, No. 30/2012 and 16/2021) prohibits workplace harassment and defines mechanisms for protection of employees from psychological abuse, harassment, or other forms of intimidation at work.

Law on Gender Equality (Official Gazette of Montenegro, No. 76/2021), regulates policies on gender equality, equal access to opportunities, and measures for promoting the equal participation of women and men in all areas of social life.

Constitution of Montenegro (Official Gazette of Montenegro, Nos. 1/2007 and 38/2013)- the highest legal act guaranteeing fundamental human rights and freedoms, including the right to life, health, work, property, and equality before the law.

## 3.5.2 Grievance Management (Complaints and Appeals Mechanism)

Grievance management refers to the systematic process for receiving, reviewing, and resolving complaints or grievances raised by employees, citizens, or other stakeholders. Its purpose is to ensure timely, transparent, and fair resolution of issues arising during project implementation or organizational activities, thus preventing conflicts and fostering trust and accountability.

In Montenegro, there is no single law specifically regulating grievance mechanisms, but the legal basis is provided through several acts, including:

- Labor Law (Official Gazette of Montenegro, Nos. 74/2019, 8/2021, 59/2021, 68/2021, and 145/2021)

- Law on Prohibition of Harassment at Work (Official Gazette of Montenegro, Nos. 30/2012 and 16/2021)

- Law on Labor Inspection (Official Gazette of Montenegro, No. 69/2003)

- Law on Administrative Procedure (Official Gazette of Montenegro, Nos. 56/2014, 20/2015, 40/2016, 37/2017, and 12/2021)

- Law on Local Self-Government (Official Gazette of Montenegro, Nos. 2/2018, 34/2019, 38/2020, 50/2021, and 92/2023)

These acts jointly form the legal framework for establishing and implementing grievance redress mechanisms within public institutions, enterprises, and projects, ensuring the protection of rights for employees, communities, and other affected parties.

Community health and safety may also be affected by workers coming from outside the area. To reduce SEA/SH risks, workers will sign Codes of Conduct, receive SEA/SH awareness training, and be required to follow strict rules of conduct when interacting with communities. All incidents will be addressed through a confidential, survivor-centered GRM.

## 3.6 Gaps between World Bank ESF and National Legislation

The following table summarizes the compliance status between Montenegro’s national framework and the World Bank’s Environmental and Social Standards (ESS).

Table: Gap Analyses of ESS and National Legislation compliance

Table 5 Gap Analysis

| ESS | National Framework | Compliance Analysis (Gaps) |
| --- | --- | --- |
| ESS1: Assessment and Management of Environmental and Social Risks and Impacts | - Law on Environment - Law on EIA - Law on Nature Protection - Law on Occupational Health & Safety | EIA legislation covers environmental assessment. Social risk assessments, cumulative impacts, and adaptive management are not required. Gaps addressed through Project ESMF, site-specific ESIAs, ESMPs, and ESCP. |
| ESS2: Labor and Working Conditions | - Labor Law - Law on OHS | Core labor rights and OHS covered; no legal requirement for gender-balanced OHS committees, retaliation protection, or grievance mechanisms. CRFASD LMP addresses this. |
| ESS3: Resource Efficiency & Pollution Prevention | - Law on Environment - Law on Air Protection - Law on Waste Management - Law on Water - Law on Energy Efficiency | Aligns with EU directives; lacks GHG accounting and climate mitigation requirements. Enforcement gaps exist. CRFASD ESMF and ESMPs apply GIIP and EHSG. |
| ESS4: Community Health & Safety | - Law on Environment - Law on OHS | Community health & safety not fully covered; engagement and CHS plans not mandated. |
| ESS5: Land Acquisition & Involuntary Resettlement | - Law on Expropriation | Compensation exists; broader livelihood restoration, negotiated settlements, and transaction cost coverage missing. RPF developed to ensure ESS5 compliance. |
| ESS6: Biodiversity Conservation | - Law on Nature Protection - Law on EIA | Biodiversity protection aligned with EU Natura 2000; BMP and ESS6 mitigation hierarchy not fully applied. |
| ESS7: Indigenous Peoples | Not applicable | No Indigenous Peoples in Montenegro. |
| ESS8: Cultural Heritage | - Law on Protection of Cultural Heritage | Strong legal framework; chance find procedures not always required. |
| ESS9: Financial Intermediaries | Not applicable | Not relevant to CRFASD. |
| ESS10: Stakeholder Engagement & Information Disclosure | - Law on Environment - Law on Free Access to Information - Law on Personal Data Protection | Public consultation required; formal SEP and engagement with vulnerable groups not mandated. |

There are some gaps between existing laws of the country and WB ESSs. Gaps between Government of Montenegro laws including policies related to environmental and social risk management and suggested gap filing measures are given in Table 5.

A comprehensive review of Montenegro’s legal and institutional frameworks was conducted during the preparation of this Environmental and Social Management Framework (ESMF). The review concluded that Montenegro’s environmental regulations generally align with the World Bank Environmental and Social Framework (ESF), particularly because of the country’s ongoing harmonization with EU directives. However, some important differences and gaps remain. These relate mainly to social risk assessment, advanced labor protections, biodiversity management planning, and formalized, proactive stakeholder engagement—all of which are addressed through the ESF and the CRFASD’s environmental and social instruments.

## 3.7 World Bank Environmental and Social Framework

The World Bank ESF helps borrowers develop and manage environmentally and socially sustainable projects by following 10 Environmental and Social Standards (ESSs). These standards ensure projects are sustainable, inclusive, transparent, and meet international best practices. The Bank and the Government have agreed on risk management responsibilities in an Environmental and Social Commitment Plan (ESCP), included in the project's legal agreement.

Table 6 Relevant World Bank Environmental and Social Standards that apply to FSPP

| Environmental and Social Standard (ESS) | Key Requirements | Status | Remarks/Comments |
| --- | --- | --- | --- |
| Environmental and Social Standard 1 (ESS1): Assessment and Management of Environmental and Impacts and Risks | ESS1 provides structured processes or procedures for project categorization, assessing and evaluating project environmental and social risks and impacts, as well as management of same (mitigation hierarchy). This standard also sets out Borrower’s requirements, including the preparation of various instruments such as Environmental and Social Management Frameworks, Environmental and Social Impact Assessment, Environmental and Social Management Plans and Environmental and Social Commitment Plans as well as information disclosure. The standard also lays out project environmental and social monitoring and reporting requirements. ESS1 establishes the applicability of the other ESSs. It establishes the basis for categorizing projects based on the borrower’s capacity to manage and monitor environmental and social risks/impacts as well as the implementation of mitigation measures, socio-political context, scale of the undertaken as well as spatial extent and significance of anticipated impacts and Risks | Relevant | ESS1 is relevant to the project as the planned activities, have the potential to generate a range of environmental and social (E&S) risks and impacts. These include Component 2 activities that may include clearing of forests to prevent spread of forest fires, while focusing on a sustainable supply of raw materials to the forest industry. These activities, if not aligned with sound forestry and environmental practices pose the risk of noise, biodiversity impacts, invasive species, management of forest waste & harvesting of forest products and generation of organic wastes.... ESS1 provides an overarching framework for identifying, assessing, managing, and monitoring these risks in a structured and consistent manner throughout the project cycle. It also ensures that appropriate instruments are developed to mitigate potential adverse impacts while maximizing project benefits. To address these requirements, the borrower has prepared an Environmental and Social Management Framework (ESMF) to guide the screening of activities and the preparation of site-specific instruments. The ESMF includes a gender, SEA/SH, and GBV risk assessment and prevention plan, as well as Labor Management Procedures (LMP). In addition, the project has prepared a Stakeholder Engagement Plan (SEP) to guide systematic stakeholder engagement. The Borrower has prepared Environmental and Social Commitment Plans (ESCP). The ESCP sets out the specific measures and actions to be implemented, along with monitoring and reporting responsibilities, ensuring alignment with the ESSs. Before appraisal, the ESMFs, SEPs and ESCPs will be finalized and publicly disclosed. Based on screening outcomes, site-specific instruments such as Environmental and Social Impact Assessments (ESIAs), Environmental and Social Management Plans (ESMPs), Biodiversity Management Plans (BMPs), and Resettlement Plans (RPs) may be prepared, consulted upon, and disclosed before implementation of relevant activities. For activities. |
| Environmental and Social Standard 2 (ESS2): Labor and Working Conditions | It is to ensure a safe, healthy and conducive working environment for workers and ensure that the environment is free of forced and child labor as well as other forms of intimidation, discrimination and harassment. ESS2 also ensures that workers have channels for grievance resolution, freedom of association and access to collective bargaining rights as prescribed by national law. The standard also seeks to protect vulnerable workers. The Labor and Working Conditions requirements will cover all project workers in this project: direct, community and contract workers as well as primary supply workers. | Relevant | ESS2 is relevant to the project as it addresses labor and working conditions, which are critical in the context of the project. Project activities may involve a range of workers, including direct workers, and contracted workers, whose rights, safety, and wellbeing must be safeguarded. ESS2 ensures that labor risks are effectively managed through fair treatment, nondiscrimination, protection of vulnerable groups, and the promotion of safe and healthy working conditions. Before project appraisal, the borrower has prepared Labor Management Procedures (LMP) as part of the Environmental and Social Management Framework (ESMF). The LMP covers working conditions, grievance redress mechanisms for all categories of workers, and the roles and responsibilities of the implementing agencies. It outlines key provisions on nondiscrimination and equal opportunity, occupational health and safety (OHS), and the requirement for all workers to sign a Code of Conduct (CoC). The CoC specifies behavioral standards, including prohibitions against sexual exploitation, abuse, and harassment (SEA/SH). To reinforce compliance, all workers will receive SEA/SH training and awareness sessions. Contracts with contractors, subcontractors, and supervising entities will be aligned with national labor laws and ESS2 requirements, ensuring fair terms of employment. The LMP also requires Occupational Health and Safety Plans consistent with national regulations and the World Bank Group’s Environmental, Health, and Safety (EHS) General and Industry specific Guidelines. These plans will include incident reporting protocols, compliance monitoring, emergency preparedness and response measures, and provisions for ongoing training. In addition, contracts will integrate environmental and social mitigation measures and include provisions prioritizing the use of local labor, where appropriate. The CoCs will clearly define prohibited actions, associated penalties, procedures for reporting violations, and mechanisms for complaints handling, thereby ensuring accountability and a safe working environment. For forest and fire management safe equipment management, environmental safeguards to prevent unintended damage, emergency preparedness measures, and comprehensive crew training will be considered. Through these measures, ESS2 requirements will be fully integrated into project implementation, promoting safe, fair, and equitable labor practices across all participating countries and entities. |
| Environmental and Social Standard 3 (ESS3): Resource Efficiency and Pollution Prevention and Management | ESS 3 promotes sustainable resource utilization, avoiding and/or minimizing project pollution, generation of hazardous and non-hazardous waste and project-related emissions. This standard enjoins the Borrower to ensure efficient use of energy, water and other raw materials as well as manage air pollution, hazardous and non-hazardous waste, chemicals and hazardous materials (including pesticides) in both degraded and non-degraded areas in line with Good International Industry Practice (GIIP). | Relevant | ESS3 is relevant to the project as it addresses resource efficiency and pollution prevention, which are concerns given the scope of its activities. Project activities may require the use of natural resources. Without careful planning, the use of these resources could strain local supplies, increase costs, and contribute to environmental degradation. ESS3 ensures that resource use is efficient and that pollution resulting from project activities is avoided or minimized. The project will generate both solid and liquid waste. These are expected to include excavated soils, debris, wood. If not properly managed, these wastes could create risks to soil, water, and air quality, and public health and safety. To address these issues, site-specific Environmental and Social Management Plans (ESMPs) will assess resource use and management scenarios in detail and prescribe appropriate mitigation measures. These measures will include efficient sourcing and use of raw materials, energy optimization, waste segregation and recycling, safe disposal of hazardous materials, and pollution control measures consistent with national regulations and the World Bank Group’s Environmental, Health, and Safety (EHS) Guidelines. Through these actions, the project will minimize resource consumption, reduce pollution, and promote sustainable construction practices. ESS3 requirements will be fully integrated into project design and implementation, ensuring that environmental sustainability is maintained across all activities. |
| Environmental and Social Standard 4 (ESS4): Community Health and Safety | Environmental and Social Standard 4 (ESS4) is titled “Community Health and Safety”. The objective of this standard is to anticipate, avoid and/or mitigate adverse project impacts on beneficiary communities as well as safeguard project-affected communities from traffic and road safety risks, diseases and hazardous materials associated with project implementation and operation. | Relevant | ESS4 is relevant to the project as it addresses community health and safety, which may be affected by project activities. Key concerns include increased vehicle flow and associated road safety risks, as well as noise, dust, and vibrations from vehicular transport. There is also potential for exposure to hazardous materials during handling, transportation, and storage. Improper storage of chemicals or poor disposal of waste could pose health and safety risks to communities. To address these issues, site specific Environmental and Social Management Plans (ESMPs) will identify and prescribe mitigation measures, including traffic management plans, safe storage and handling chemicals, protocols for waste management, and measures to control noise, dust, and vibration. These instruments will also include health and safety safeguards for both workers and communities, incident reporting protocols, and emergency preparedness measures. In addition, the ESMF and SEP incorporate grievance mechanisms (GMs) to enable communities to raise concerns and have them addressed transparently and promptly. A gender assessment and a Sexual Exploitation, Abuse, and Harassment (SEA/SH) Prevention Plan will further evaluate potential health and safety risks, including those linked to labor influx, and put in place measures to mitigate them. The Labor Management Procedures (LMP), as part of the ESMF, establish safeguards to protect project workers and ensure safe working conditions. If security risks are identified, a Security Management Plan (SMP) may also be prepared. The SMP will define roles, responsibilities, and monitoring arrangements for managing potential security hazards in line with good international practice. Through these measures, ESS4 requirements will be fully integrated into project design and implementation, ensuring that communities are protected from health, safety, and security risks throughout the project life cycle. |
| Environmental and Social Standard (ESS5)- Land Acquisition, Restrictions on Land Use and Involuntary Resettlement | ESS 5 acknowledges that project-related land acquisition and land-use limitations can negatively affect communities and individuals. Physical displacement (relocation, loss of residential land, or loss of shelter) or economic displacement (loss of land, assets, or access to assets leading to loss of revenue sources or other means of subsistence) may result from project-related land acquisition or limits on land usage. | Relevant | ESS5 is relevant to the project as certain activities may require land acquisition and could disrupt livelihoods. The exact locations and detailed designs have not yet been finalized, which makes it difficult at this stage to estimate the number of potentially affected individuals. The World Bank task team will actively engage with the client on issues related to land acquisition, economic displacement, and compensation in order to assess and address these needs. Where required, these aspects may warrant inclusion in the project components to ensure compliance with ESS5 principles. To provide a framework for managing these potential impacts, Resettlement Policy Framework (RPF) |
| Environmental and Social Standard- (ESS6) - Biodiversity Conservation and Sustainable Management of Living Natural Resources |  | Relevant | ESS6 is relevant to the project as it is designed around forest ecosystems. These environments may host critical biodiversity that provides essential ecosystem services and supports local livelihoods. To minimize risk of disturbance, the Environmental and Social Management Plan (ESMP) has to assess potential ecological impacts from project activities. The ESMF will also include screening procedures to identify subprojects that may interact with natural habitats or biodiversity. Where risks are identified, site-specific instruments such as Environmental and Social Management Plans (ESMPs), and Biodiversity Management Plans (BMPs) will be prepared to prescribe detailed avoidance, minimization, and restoration measures. |
| Environmental and Social Standard (ESS8) - Cultural Heritage | It defines cultural heritage elements to include tangible assets such as shrines, artifacts and intangible assets such as taboos. ESS 8 lays out the Bank’s requirements for development within or close to culturally sensitive zones. This standard also discusses the requirements that should be met prior to the development of projects that are likely to have adverse risks and impacts on cultural heritage sites and resources. The critical requirements include meaningful consultation with affected persons, experts and other interested parties, confidentially/disclosure as well as movement and commercial use of cultural (heritage) resources. The Bank’s Environmental and Social Standard on Cultural Heritage seeks to protect cultural heritage resources from adverse project impacts and establish them as an integral part of sustainable development. | Relevant | This standard is considered relevant with a precautionary approach. Currently, it is not possible to ascertain the existence of culturally significant sites related to the project. It is possible that both identified and unidentified physical and cultural treasures may be discovered. While the likelihood is not deemed substantial in the project context, the ESMF will outline the likelihood of Cultural heritage in the project area and offer recommendations on unexpected discoveries. The ESMP will encompass the evaluation of all cultural heritage elements, such as archaeological artefacts and spiritual sites within the project vicinity. If any sites are discovered, they will be deliberately avoided. If avoidance is not feasible, the Environmental and Social Management Plan (ESMP) will determine the necessary steps to mitigate the consequences of these sites. |
| Environmental and Social Standard (ESS10) - Stakeholder Engagement and Information Disclosure | ESS10 establishes a systematic approach to stakeholder engagement while ensuring that appropriate information on project risks and impacts is provided to stakeholders in a timely, comprehensive, accessible, and appropriate manner. The standard also ensures inclusive and effective engagement of project-affected parties throughout the project cycle and provides avenues for assessing stakeholder interest and incorporating their views into project design and monitoring of projects. | Relevant | ESS10 is relevant to the project as meaningful stakeholder engagement is critical for identifying, assessing, and managing the environmental and social risks associated with the project. ESS10 ensures that engagement processes are inclusive, culturally appropriate, and responsive to the needs of different groups, particularly vulnerable and marginalized populations, thereby supporting both project sustainability and success. To meet these requirements, the Ministry has developed a Stakeholder Engagement Plan (SEP) tailored to the project’s scope and risks prior to project appraisal. The SEP has been consulted upon and will be publicly disclosed prior to appraisal. They identify and engage key national institutions. In addition, other critical stakeholders include mobile carriers, end-users, civil society organizations advocating vulnerable groups, and associations representing persons with disabilities. Stakeholder engagement will be conducted through open consultations using a variety of formats and locations to ensure accessibility and inclusivity. The SEPs also establish country-level grievance mechanisms (GMs), to receive and address complaints in a timely, transparent, and fair manner. These mechanisms will help strengthen accountability, build trust, and foster inclusive decision-making throughout the project’s life cycle. The SEPs, and the GMs, will play a central role in ensuring that the project meaningfully engages affected and interested stakeholders, manages expectations, mitigates risks, and ultimately maximizes the long-term social and environmental benefits of the project. |

## 3.8 Institutional Framework

This section of the report provides institutional assessment of Montenegro’s forestry sector, focusing on the organizational structures, mandates, and staffing gaps of the key institutions responsible for sustainable forest management and the development of the wood industry. The primary objective of this assessment is to identify institutional gaps, analyze the effectiveness of current structures, and provide recommendations to strengthen the governance and operational capacity of Montenegro's forestry institutions in line with EU requirements.

The Review on institutional mandates introduces the key institutions involved in forest governance in Montenegro, such as the Ministry of Agriculture, Forestry and Water Management (MAFW), the Forest Administration, and the soon to be established State-Owned Enterprise (SOE) for Forest Management that is envisioned to be established by the new Law on Forest (and hasn’t been as of February 2025). This section outlines the roles and responsibilities of each institution, highlighting areas where mandates may overlap or where institutional fragmentation may hinder effective implementation of policies related to forest management and the wood industry.

Following this, the Organizational structure section offers an examination of the internal structures and functions of the primary institutions involved in forestry management. This includes an analysis of institutional hierarchies, decision-making processes, staff capacities, and resource allocation. The assessment also evaluates the current functional efficiency of these institutions in relation to their mandates and explores how well they coordinate with one another to meet the goals of sustainable forest management.

Through this institutional assessment, the report provides insights into the current state of Montenegro’s forestry governance structures, identifying key challenges and offering practical recommendations for addressing the institutional and regulatory gaps that hinder the sector’s development. The findings and recommendations outlined in this section will guide future reforms, helping to build more effective and resilient institutions that are equipped to manage Montenegro’s forest resources in a sustainable and climate-resilient manner.The following government institutions associated with the FSPP project are described on the potential environmental and social issues. The role of each institution, with respect to the implementation and monitoring of the ESMF, is summarized in table

Table 7. Project Institutional framework

| Institution | Role and Responsibilities |
| --- | --- |
| Ministry of Agriculture, Forestry, and Water Management (MAFWM) | The Ministry of Agriculture, Forestry, and Water Management (MAFWM) holds key responsibilities in two areas. In terms of regulatory oversight, the Ministry focuses on policy development, monitoring implementation, and ensuring the enforcement of laws, while ensuring compliance with EU legislation and national regulations. In strategic planning, the Ministry is responsible for developing forest management strategies, with a particular emphasis on the sustainable management of private forests, aiming to ensure long-term protection and conservation of forest resources. The Ministry of Agriculture, Forestry, and Water Management (MAFWM), according to the Regulation on the Organization and Method of Operation of State Administration ("Official Gazette of Montenegro", No. 049/22 of May 6, 2022, No. 052/22 of May 13, 2022, No. 056/22 of May 27, 2022, No. 082/22 of July 29, 2022, No. 110/22 of October 5, 2022, No. 139/22 of December 16, 2022), has the following mandate regarding forestry: developmental policy in the field of forestry; systemic solutions for the management of forests and forest land and their protection; preservation, economic use, and improvement of forests; monitoring the planning of forest management; wood processing industry and wood product manufacturing; developmental policy in the field of hunting; systemic solutions for the management and regulation of game and hunting; ensuring the use of hunting grounds and the preparation of hunting development programs. The tasks mentioned are carried out by the Directorate for Forestry, Hunting, and Timber Industry as an organizational unit of the Ministry. To fulfill its responsibilities and carry out related tasks, nine individuals are employed in the Directorate for Forestry, Hunting, and the Wood Industry within the Ministry. In addition to the staff in the directorate, the Department for International Cooperation within the Ministry assists the Directorate in handling international forestry cooperation, preparing forestry-related regulations, and aligning domestic regulations with the European Union's legal framework. Additionally, the Department for Economic Analysis conducts economic assessments for the forestry and wood industry sectors, monitors trends in the trade of wood and wood products, and proposes economic measures to be implemented in these sectors. Furthermore, the Ministry as a whole is responsible for administrative supervision over the activities of the Forestry and Hunting Management Administration. |
| Directorate for Forestry, Hunting, and Wood Industry, Ministry of Agriculture, Forestry and Water Management | The Directorate for Forestry, Hunting, and Wood Industry is responsible for tasks related to proposing policies, preparing draft laws, and other strategic documents that regulate forestry, hunting, and the wood industry. It proposes the professional foundations for drafting laws and regulations in these areas, implements development policies in forestry, hunting, and the wood industry, and harmonizes national legislation with EU regulations in forestry, hunting, plant protection in forests, and the wood industry. It prepares regulations governing forest and forest land management, wildlife management, and hunting areas, as well as regulations related to the wood industry. The Directorate participates in administrative and professional supervision and enforces laws and other regulations in forestry, hunting, the wood industry, and plant protection in forests. Additionally, it manages information systems in forestry, hunting, and the wood industry, oversees monitoring processes, and coordinates the Monitoring Directorate’s work with other directorates and the Department for Forest and Wildlife Management. It also plans and conducts cooperation with international organizations, donors, other institutions, and NGOs relevant to forestry, hunting, and the wood industry. The Directorate proposes the annual budget and procurement plan and ensures compliance and effectiveness in managing the Department for Forest and Wildlife Management. |
| Department for Forestry | The Department for Forestry proposes economic policy measures for forestry, prepares or coordinates the preparation of strategic documents relevant to forestry, and monitors their implementation. It oversees concession contracts for the use of forests and contracts for timber sales in standing condition. The Directorate follows EU legislation and international standards on forestry and related products and proposes alignment measures. It initiates the adoption of laws and other regulations in forestry and drafts their texts. The Department monitors modern methods and achievements in forestry and collaborates with the EU, international organizations, agencies, and companies providing support to Montenegro in forestry. It also plans to support programs for forest cultivation and rural diversification, including forestry and forest products. |
| Department for the Wood Industry | The Department for the Wood Industry proposes measures to improve the organization of companies in the wood industry, provides professional foundations for drafting laws, strategies, and regulations, and suggests improvements in the business environment. It encourages the introduction of higher levels of wood processing, maintains a registry of wood industry companies, and promotes the organizational connection of businesses and entrepreneurs. The Department supports the establishment of clusters in the wood industry, enhances product tracking systems, and identifies measures to increase competitiveness and export stimulation. It provides support for programs and projects that enhance value addition in wood processing and offers advisory assistance to companies in adopting standards and product certifications. The current number of employees (January 2025) at the Ministry of Agriculture, Forestry, and Water Management in the Department for Forestry, Hunting, and Wood Industry is 8. The forestry-related staff includes: 2 forestry magistrates, 1 master engineer in wood technologies, 3 graduate forestry engineers, 1 graduate forestry engineer specializing in wood processing, 1 manager, and 1 legal professional (the ministry's general service - one person responsible for forestry). |
| Forestry and Hunting Management Administration (FHMA) | The main responsibility areas of the Forestry and Hunting Management Administration (FHMA) include planning, monitoring, and supervising sustainable forest use to ensure the effective management and utilization of forest resources. Additionally, FHMA is responsible for developing and managing a forest information system to support forestry operations, data storage, and the exchange of relevant forestry data. Another crucial function is inspection and compliance, which involves conducting inspections in both the forestry and hunting sectors to ensure adherence to regulations, sustainable practices, and legal requirements. While FHMA holds key supervisory roles, it faces significant capacity gaps, particularly in areas such as forest inventory, enforcement, and technical expertise. The organizational structure of FHMA is designed with a decentralized approach, featuring a Directorate that oversees multiple sectors and services. The Directorate is divided into specialized departments: Forestry and Hunting Management, Forest Planning, Forest Cultivation and Protection, Forest Utilization and Non-Timber Forest Products, Nature Protection and Special-Purpose Hunting Management, and Forestry Information Systems. Supporting services include the General Affairs Service, Finance, Accounting, and Procurement Service. The FHMA also operates through regional units in Pljevlja, Rožaje, Berane, Andrijevica, Petnjica, Plužine, Žabljak, Šavnik, Kolašin, Bijelo Polje, Mojkovac, Nikšić, Danilovgrad, Podgorica, Gusinje, and Kotor (with further subdivisions in Bar, Budva, Herceg Novi-Tivat, and Cetinje). This structure ensures a decentralized and streamlined approach to managing forestry and hunting resources across different regions. The Forestry and Hunting Management Administration of Montenegro employs a total of 370 individuals across various job positions. This includes 70 forestry engineers, 26 employees with higher education (VSS), and 4 with college education (VŠ). Additionally, there are 56 forestry technicians, 171 forest guards, and 40 employees with secondary education. Only 3 employees have primary education. This diverse workforce ensures the effective management of forestry and hunting resources across Montenegro. The Central administration is composed of the Director, various sectors, and specialized departments. It employs a total of 20 individuals in different roles. Among them, there are 9 forestry engineers, 6 employees with higher education (VSS), 1 employee with college education (VŠ), and 4 individuals with secondary education. Notably, there are no forestry technicians, forest guards, or employees with primary education within this part of the organization. The General affairs and Finance, accounting, and procurement services department consists of 32 employees. The team includes 8 employees with higher education (VSS), 2 with college education (VŠ), and 20 individuals holding secondary education. Additionally, there are 2 employees with primary education. There are no forestry engineers, forestry technicians, or forest guards in this department. This structure ensures a broad range of administrative and financial support across the organization |
| State-Owned Enterprise for Forest Management (SOE) | The State-Owned Enterprise (SOE) for Forest Management is responsible for managing forests, forest lands, trees outside forests, and barren lands under state ownership. Its activities include afforestation and reforestation, establishing new forests and restoring degraded areas, as well as forest cultivation through thinning, regeneration, and conversion to maintain healthy forests. The SOE also oversees forest protection and rehabilitation, implementing measures for forest health, pest control, and ecosystem restoration. Timber harvesting and utilization involves logging, processing, transportation, and export of wood assortments, while non-timber forest product utilization ensures the sustainable collection and commercialization of non-wood forest resources. Additionally, the SOE oversees forest infrastructure, constructing and maintaining forest roads and other facilities to support sustainable forest management. It also facilitates trade and the sale of forest products, ensuring a stable market supply for both wood and non-wood resources. Finally, the SOE plays a key role in maintaining and enhancing forest functions, ensuring that forests continue to provide environmental, social, and economic benefits. As the executive body responsible for implementing forest management plans, the SOE balances commercial operations with sustainability objectives. Article 97 of the transitional provisions of the Law on Forests (2024) stipulates that the SOE must be established within 90 days from August 13, making the deadline for its establishment November 13. According to the adopted Law on Forests (2024), State Forest Enterprise will be charged for forest management tasks, which concern the following: the establishment of new forests, afforestation and tending of new cultures, implementation of the protection of forests from biotic and abiotic factors, as well as diagnostic and prognostic activities, protection of forests from fire, marking of trees for felling, preparation of operational projects, marking of wood assortments, production of wood assortments and other forest products, collection, production and trade in non-timber forest products, production and trade in reproductive material of forest trees and construction, maintenance and restoration of forest roads in accordance with this Law and other tasks in accordance with the statute. Thus, in the final division of forest management responsibilities, the Ministry retains its role in developing forest policy. The Forestry and Hunting Management Administration (FHMA) is responsible for forest management planning, monitoring, and inspection control, while the soon to be established State-Owned Enterprise (SOE) will serve as the executive body that implements management plans on the ground. According to the law, soon to be established SOE will be responsible for commercial forest operations (harvesting, road infrastructure), but it is still in its formative stages. Significant staffing needs exist, particularly for forestry engineers and technical staff. The SOE will manage commercial operations: timber harvesting, forest infrastructure (such as roads), and the sale of wood products. It will also handle public forestry functions: afforestation, forest health monitoring, and fire prevention activities. In this model, the soon to be established SOE will operate commercially while adhering to sustainability standards, under the supervision and regulation of the FHMA. This ensures that all forest management activities align with national environmental and sustainability objectives |
| Department for Monitoring in Forestry and Hunting | This department monitors activities related to forest and forest land management, including wildlife management, through national and forest-level inventories, forest management programs, forest and wildlife cadastres. It oversees the preparation of planning documents and forest management plans, monitors afforestation, forest cultivation, and protection activities, and ensures the production of reproductive material for forest trees. The Department oversees game management activities and the use of hunting areas, addresses irregularities, and provides recommendations for their resolution. It develops GIS and databases for tasks in its remit and prepares reports and other documents for policy and strategy formulation. |
| Department for Hunting | The Department for Hunting proposes management measures for hunting areas, coordinates the preparation of the Hunting Development Program, and recommends improvements for hunting. It monitors EU legislation and international standards on hunting and related products and proposes alignment measures. The Department drafts the texts of laws and regulations governing hunting and monitors modern methods and professional achievements in the field. It reviews hunting management plans, coordinates with the unit responsible for rural development, and plans support programs for game management, wildlife protection, and rural diversification. It implements planned activities defined by the Ministry’s work program and oversees the tender process for leasing hunting areas, ensuring contract compliance. |

# 4. Environmental and Social Baseline

This chapter presents the descriptions of the biophysical and socio-economic environment across the Montenegro. The physical and biological factors considered included climate, topography and geology, soils, hydrology, flora and fauna and socio-economic factors among others.

4.1 General overview of Montenegro

Figure 2Map of Montenegro

Figure 2. Map of Montenegro

4.1. Basic information about the country

Official name: Montenegro

Abbreviation: MNE

Capital: Podgorica

Other major cities or towns in the project area:

Pljevlja, Bijelo Polje, Pluzine, Berane, Mojkovac

Area: 13,812 km2

Geographical position: MNE borders Croatia, BiH, Serbia, Kosovo, Albania and the Adriatic Sea

Population: 622,277

Official name: Montenegro

Abbreviation: MNE

Capital: Podgorica

Languages: Official language: Montenegrin Other languages used: Serbian, Bosnian, Albanian, Croatian

Government structure: MNE is an independent parliamentary republic. The Government is the executive branch, and the Parliament is the legislative body.

Main industries: Steelmaking, aluminum, agricultural, consumer goods, tourism

Nominal GDP: 6.847,12million Eur (2023)

Nominal GDP per capita: 8,846 (2018)

GDP growth: 6% (2023)

EU status: MNE has an EU candidate status. Accession negotiations with the EU are ongoing.

Forest cover in MNE:  Forests cover 59,9% of the total national territory of Montenegro.

### 4.1.1. Geography

Montenegro (Montenegrin: Crna Gora, meaning "Black Mountain") is a small, mountainous country in Southeast Europe. It shares land borders with Croatia, Bosnia and Herzegovina, Serbia, Kosovo, and Albania, and its coastline along the Adriatic Sea separates it from Italy. The country’s land border stretches for 614 km, while its sea border measures 293.5 km. Despite its modest size of 13,812 km², Montenegro features a highly varied terrain, with 50 peaks rising above 2,000 meters. The physical landscape is dominated by mountains, a result of its location on the Balkan Peninsula and proximity to the Adriatic Sea.

Montenegro is home to some of Europe’s most rugged terrain, with prominent mountain ranges such as Durmitor, Orjen, and Lovćen. The country’s highest point is Bobotov Kuk in the Durmitor range, reaching 2,522 meters. Along the Adriatic coast, the Bay of Kotor—a submerged river canyon approximately 28 km (17 miles) long—stands out as a major geographical feature, flanked by the Lovćen and Orjen mountains.

Major rivers in Montenegro include the Tara and Lim. On the border with Albania lies Lake Skadar, the largest lake in Montenegro and Southern Europe, covering an area between 370 and 530 km² with an average depth of 5 meters. The country’s lowest point is at sea level along the Adriatic coast.

### 4.1.2.Forest coverage

According to the data from the Directorate for Statistics (MONSTAT), available on the website, the area of forests and forest land in Montenegro in 2019 was 827,536 ha, of which 711,681 ha was under forest, and forest land occupied an area of 115,855 ha. Deciduous forests make up 71%, coniferous 18%, while mixed forests account for 11% of the total forest area. In relation to sustainability indicators, the observed degree of mixture can be considered insufficient and unfavorable in relation to bio-ecological stability. By the degree of forestation, Montenegro is at the very top of Europe, taking 4th place.

Out of the total area of Montenegro, taking into account the statistical data stated in the National Forest and Forest Land Management Policy (2008), a total of 45% of the territory (621,609 ha) is under forest. Forest land, which by international definition includes thickets, scrubland, maquis, and garrigue, totals 9% (123,000 ha), which together makes up 54% (743,609 ha) of the total territory of Montenegro.

A different insight into the forestation of Montenegro can be seen in the reports of FRA (Forest Resources Assessments) and FAO (Food and Agriculture Organization of the United Nations) for certain periods, obtained by analyzing data in the interval 1990-2010. According to this source, forests occupy 39.3%, forest land 12.7%, and together they cover 52% of the area of Montenegro. According to data derived from LANDSAT images, forests cover 50.8% (705,605 ha), forest land 7.4% (102,712 ha), and together they make up 58.1% of the territory of Montenegro. The differences are evident when it comes to the data from the Real Estate Administration – UZN, as well as the data published in the statistical yearbooks of the Statistical Office of Montenegro, according to which the areas under forests amount to 621.00 ha. The observed differences (depending on the source) represent a major problem in relation to the objectivity of the forestation assessment as such and in relation to the optimums conditioned by the multifunctional use of forests.

In the Strategy with the plan for the development of forests and forestry, 2014-2023, it is stated that the area under forests has increased in recent decades. Certain areas of former barren land have become overgrown with forest, due to the abandonment of traditional agriculture and the depopulation of villages, part of the pastures and agricultural areas have become overgrown with forest due to spontaneous natural processes (reforestation). These are mostly maquis, scrubland, low and coppice forests that have a very important protective role. This is also evidenced by the statistical data of the National Forest Inventory. Since the NFI has been recognized as a tool for providing reliable data on forests for the purpose of providing an information base (IB) for the preparation of strategic plans, this source will be used in the following text to assess the state of forests.

According to the results of the National Forest Inventory (NFI), Montenegro is characterized by a high degree of forestation of 59.5% (826,782 ha). Forest land occupies 9.9% (137,480 ha). Together, forests and forest land make up 69.4% of the territory of Montenegro. By the degree of forestation, Montenegro is at the top of Europe. In all forests, about 12% of forests and 8% of forest land are inaccessible due to natural obstacles, and these areas, with an area of about 110,000 ha, are left to spontaneous natural processes. Taking into account the number of inhabitants, a degree of forestation of 1.3 ha/inhabitant is obtained.

In relation to the number of inhabitants, the forestation in Serbia is 0.3 ha per inhabitant, in Austria it is 1.01 ha, Bosnia and Herzegovina 1.38 ha, Bulgaria 1.31 ha, Croatia 1.25 ha, the Czech Republic 0.75 ha, Finland 5.91 ha, Germany 0.92 ha, Norway 6.93 ha, Romania 1.02 ha, Slovenia 1.01 ha, Switzerland 0.54 ha, and in Russia 11.11 ha (Banković et al. 2009).

The National Inventory registered 68 tree species (57 deciduous and 11 coniferous), which indicates the great diversity of Montenegrin forests. The intensity of biodiversity is reduced by the uneven participation of individual species in the forest fund. Although the percentage of areas under forest is satisfactory, due to the mediocre quality of the forest, there is a need for their improvement. The wood volume and volume increment, as the basic indicators of productivity, are below the production potential of the habitat on most of the forested area, which is especially true for newly forested areas.

The NFI data also indicate that there has been a change in the area of forests in relation to ownership and that the share of private forests has increased. Of the total area under forest, 52.3% is in state ownership, while 47.7% is in private ownership. When it comes to forest land, 58.0% is in private ownership and 42.0% is in state ownership. It should be noted that the restitution process is not yet fully completed, as is the arrangement of cadastral data of Montenegro (so far on 80% of the area) by the Real Estate Administration, so the assessment of ownership on exemplary areas during the NFI was determined based on the available data at that moment.

The quality of forests is strongly related to ownership. Private forests are concentrated in the karst and coastal regions, and for the most part they are of coppice origin, young, poorly or unmanaged, or degraded. In Serbia, 47.0% are in state ownership, and 53.0% are in private ownership. The ratio of state and private forests in some European countries is as follows: Austria 17.5%:82.5%, Bosnia and Herzegovina 78.4%:21.6%, Croatia 75.5%:24.5%, Czech Republic 84.1%:15.9%, France 26.2%:73.8%, Romania 94.6%:5.4%, Slovenia 30.0%:70.0%, Finland 28.9%:71.1% (Banković et all., 2009). In Europe, private forest ownership covers 52%, state 46%, and 2% is undefined (TBFRA; 2020).

State-owned forests have a significantly more favorable structure compared to private forests, which is best reflected by the amount of wood volume per unit area, which is significantly smaller in private forests. State forests have average volumes of 228 m³/ha and account for 72.7% of the total volume. In private forests, the volume is 89 m³/ha, and they account for 27.3% of the total volume. Private forests are also characterized by fragmented ownership. According to a study by the Dutch Development Agency (SNV), 57% of forests, private properties, are in the size category up to 5 ha, 27% in the category from 6 ha to 20 ha, and 13% in the category from 21 ha to 50 ha in size. The latter and the conditionally smaller part of the second category (6-20 ha), at least by area, form a secure basis for the permanence of yield (according to the classical understanding of permanence related to area). Only two-thirds of forest owners use their forest (for felling), of which slightly more than half of the wood volume (53%) is for their own needs (mostly firewood).

The National Forest Inventory found that the total standing volume of wood in Montenegrin forests is 122 million m³, with an average volume of 160 m³/ha. Most Montenegrin forests (78.7%) are mountain forests, located at an altitude of 800-1800 m, on slopes with a 60-350% inclination (87.2%). Average volumes greater than 200 m³/ha occur between 1200 and 2000 m above sea level, while in lower regions they are significantly smaller. The average volume values are different by region and are similar in the eastern and northern regions (the volume is 243 m³ and 255 m³, respectively), in the central region the volume is 188 m³, and an expected modest production effect is found in the coastal region 73 m³ and in the karst region 42 m³. The obtained values of the volume increment are analogous. The average volume increment is 6.80 m³ in the northern region, 6.0 m³ in the eastern, 3.7 m³ in the central, 1.8 in the coastal and 1.1 m³ in the karst region. In accordance with the previous indicators, the ecological service (ecological services - ES) of forests is also expressed, from the pronounced production services - wood production as a net primary production in the eastern, northern and central regions to the protective regulatory functions on the karst and ecological social in the coastal area and social on the entire territory of Montenegro.

Table 7 Forest coverage

| Country | Total Area (thous. ha) | Forest Area (thous. ha) | Forest cover (%) | Average Volume (m³/ha) | Average Increment (m³/ha per year) |
| --- | --- | --- | --- | --- | --- |
| Austria | 8237 | 3886 | 47, 0 | 286 | 8, 16 |
| B&H | 5100 | 2273 | 44, 6 | 110 | 4, 73 |
| Bulgaria | 11055 | 3690 | 33, 4 | 130 | 3, 28 |
| Croatia | 5592 | 1783 | 31, 9 | 201 | 4, 22 |
| Czech Republic | 7728 | 2632 | 34, 1 | 260 | 7, 95 |
| Finland | 30452 | 21935 | 72, 0 | 89 | 3, 51 |
| France | 55010 | 15341 | 27, 9 | 191 | 6, 38 |
| Germany | 34927 | 10740 | 30, 7 | 268 | 8, 78 |
| Greece | 12890 | 3599 | 27, 9 | 45 | 1, 14 |
| Norway | 30683 | 8868 | 28.9 | 89 | 3.33 |
| Poland | 30442 | 9047 | 29, 7 | 213 | 5, 47 |
| Romania | 23034 | 6448 | 28, 0 | 213 | 5, 47 |
| Russian Fed. | 1668851 | 851392 | 50, 4 | 105 | 1, 41 |
| Slovakia | 4808 | 2177 | 45, 3 | 253 | 7, 23 |
| Slovenia | 2012 | 1107 | 55, 0 | 283 | 5, 92 |
| N. Macedonia | 2543 | 906 | 35. 6 | 70 | 2. 07 |
| Switzerland | 3955 | 1199 | 35. 6 | 70 | 2. 07 |

Source: Medarević, 2006

The average volume in European forests is 114 m³/ha (TBFRA; 2020). The density of stands is conditioned by the developmental stages, the intensity of previous management, and the quality of the habitat, and in state-owned forests the density is 746 trees/ha, and in private forests 881 trees/ha.

In relation to the silvicultural form:

High forests cover 51.1%, with an average wood volume of 253 m³/ha, and coppice forests have an average of 63 m³/ha and occupy 48.9% of the total area under forests. High forests, available for use, cover an area of 339,608 ha, with private ownership covering 104,520 ha. There are significant differences in the values of basic production indicators in relation to ownership in high forests; in state ownership, the volume (v) is 282 m³/ha and in private forests it is 177 m³/ha (or 63% in relation to state forests). There are also evident differences in the volume increment (iv); in state forests it is 6.5 m³/ha, and in private forests it is 4.3 m³/ha (or 66% in relation to state forests). Coppice forests have been recorded on an area of 335,781 ha, with private ownership being dominant, where they cover 236,088 ha. Coppice forests are characterized by significantly lower values of production indicators, and in state ownership the volume is 89 m³/ha and in private forests it is 48 m³/ha. These values are more pronounced in mature stand categories and range around 200 m³/ha. Analogous to the difference in volume, there are evident differences in the volume increment; in state forests it is 2.5 m³/ha and in private forests the volume increment is 1.3 m³/ha (52% in relation to state forests).

The forests of the southern forest area, which include forests on the coast and karst, have an unfavorable structure in terms of silvicultural form (73% are coppice forests, thickets, scrubland and maquis) and are mostly separated into the category of protective forests. They cover an area of about 305,000 ha, of which about 64,000 ha is uncultivated forest land. Different stages of degradation occupy 73% of the total area of these forests. Most European countries do not have a recorded category of coppice forests, and their participation in other countries is: Albania 93.9%, Bulgaria 10.0%, Croatia 12.8%, Serbia 64.7%, Hungary 29.0%, Italy 44.1%, Portugal 53.3%, the Netherlands 28.6%, Slovenia 13.3%, Moldova 19.0% and Russia 1.9% (Banković et al., 2009).

There is a large proportion of stands with poor closure and overgrowth as indicators of stability and productivity, namely 48.2% of stands have a closure of < 60% (at the critical limit). In stands of high origin, in state ownership, insufficient closure (below 60%) was recorded on an area of 36.7%, and in high forests in private ownership on 46.6%. The state of closure is even more unfavorable in the category of coppice forests, and in state ownership, insufficient closure (below 60%) was recorded on an area of 52.0%, and in coppice forests in private ownership on 59.6%.

The forests of Montenegro are dominated by the developmental phases of maturing stands, seedlings, young stands, and pole stands, which together occupy 60.5% of the area under forest. The stated condition has resulted in low current production effects (average volume and volume increment). The previous assessment highlights the need to apply measures to fill in or regenerate mature, partially thinned stands.

Montenegro is characterized by the dominance of deciduous tree species whose forests, according to NFI data, cover 76.2% of the area; the average volume for deciduous trees is only 136 m³/ha, in contrast to conifers, where it is 293 m³/ha. The share of conifers in the total volume is 40.2%. The average volume increment of the present coniferous tree species is 8.1 m³/ha and is significantly higher than that of deciduous trees, where it amounts to 2.9 m³/ha. Conifers with 46.6% participate in the total volume increment.

In the forest fund, by area, beech dominates with 42.9%, followed by spruce 20.0%, fir 12.5%, turkey oak 3.9%, Austrian pine 2.8%, durmast oak 2.0%, Bosnian pine 2.0%, common hornbeam 1.6%, black hornbeam 1.6%, white pine 1.4%, Macedonian pine 1.3%, ash 1.2%, manna ash 1.0%, birch 0.8%, aspen 0.7%, maple 0.6%, alder 0.5%, and other conifers with 0.3%. Other species (55) participate in the volume with 2.3%.Of the number of tree species registered by the NFI, according to a preliminary estimate, there are about 50 species from the list of relict, endemic, rare and endangered species (according to IUCN): Coniferous species: Aleppo pine, Bosnian pine, Macedonian pine, maritime pine, mountain pine; Deciduous species: Italian oak, prickly oak, Macedonian oak, mountain maple, white ash, narrow-leafed ash, European white elm, black hornbeam, common birch, European aspen, small-leaved lime, large-leaved lime, poplar, black alder, grey alder, white willow, sweet chestnut, European silver fir, white poplar, black poplar, wild pear, wild cherry, brittle willow, stinkwood, common hackberry, Norway maple, sycamore maple, field maple, Montpellier maple, European hackberry, bear's hazel, walnut, olive, wild service tree, mahaleb cherry, black hawthorn, holm oak, whitebeam, mountain whitebeam, rowan, wild apple.

In relation to the need and obligation to protect the forest fund as a whole, to protect biodiversity, and the attitude towards rare and endangered species, only 10 species from the existing inventory can be used for planned felling (if they are not covered by stricter protection regimes in protected areas), namely: beech, spruce, fir, hornbeam, turkey oak, black pine, sessile oak, white pine, manna ash, and ash. Other species can be used for the purpose of maintaining their health if they are dry, dry-topped, uprooted, broken, and diseased.

In the total volume, beech dominates with 34%, then fir with 32%, spruce 11%, turkey oak and durmast oak 5.5%, while other deciduous trees participate with 6.7%. If the composition of forests is taken into account, and especially in the mountain and subalpine areas a significant share of conifers, it is certain that the average volume of 160 m³/ha with an average current annual increment of 3.85 m³/ha is far below the potential possibilities of the habitat, and is a consequence of historical circumstances and often an irrational attitude towards this potential (method of use) in the earlier period.

The forest fund is covered by 38 stand affiliations. This clearly indicates the pronounced biodiversity of the present tree species, which are enriched at the stand level by the presence of shrub and herbaceous companions. In the area from Bar to Ulcinj in the coastal area, 160 species of trees and shrubs were found, of which about 45% are native species, while in the area of Boka Kotorska, 264 species of trees, shrubs and climbers were found.

Despite the pronounced biodiversity, mixed forests cover only 11% of the area, and the aforementioned makes it necessary to increase the participation of this category of forests in accordance with the natural potential, ceno-ecological affiliation and active adaptability in relation to climate change, which would gradually fulfill one of the principles of nature-based management (positive experience from Germany indicates a future commitment - at the stand level, at least 4 species when establishing new forests).

Biodiversity is also expressed in relation to dimensional frequency. In relation to the total thickness structure, the volume is distributed as follows: <10 cm - 2.8%, 11-30 cm 34.6%, 31-50 cm 37.3%, 51-70 cm 16.7%, 71-90 cm 6.1 cm and >90 cm 2.5 cm. In relation to the expected structure of the future yield, the previous state can be rated as moderately favorable because the volume of thin and medium-sized trees dominates the forest fund, with a total share of 71.9%. In support of the previous statement about the pronounced biodiversity, there is also a previous insight into the structure of stands in Montenegrin forests, where, as already pointed out, the inventory of thin and medium-thick trees dominates, with a significant share of the volume of large-sized trees.

In state-owned forests, the ratio of the volume of thin:medium-sized and large trees (10-30 cm:31-50:>50 cm) is 29.1%:42.7%:28.2% in high forests, and in coppice forests it is 10.8% (up to 10 cm):54.2%:19.8%:15.1%. This finding points to a potential assortment structure, and in connection with it, certain economic analyses and plans in the forestry sector and the potential for the use of wood volume. On the other hand, the former is especially important in selection forests, the sustainability of the structure of which implies the presence of the volume of large-sized trees >50 cm from 24-57% (Šuc, 2006). This is especially important for fir as the bearer of the selection structure, whose current volume distribution by thickness is 28.6%:42.5%:28.9%. A similar structural characteristic is found in spruce, while in beech the participation of the volume of large trees is significantly smaller (17.4%). A long-term management measure would undoubtedly be related to maintaining the previous structural relations by thickness in the selection forests of fir, beech and spruce, bearing in mind the importance of such a distribution for the permanence of the forest and biodiversity both at the stand level and at the landscape level.

In relation to the structural characteristics, fragmented uneven-aged stands are expressed, with even-aged stands covering 33.8%, two-storied 47.2% and multi-storied, in which there is a significant presence of selection forests, 19.0%. One of the principles and imperatives of nature-based management is actively promoted and maintained uneven-aged stands in small areas, depending on the forest management system. In relation to the degree of closure expressed in relative indicators, a potential threat to bio-ecological stability can be stated, because a closure below the critical limit (up to 50%) is found on 29.1% of the forested area, and on 48.2% the closure is 60%. The specific problem can be solved by assisting the overgrowth of thinned parts, partly by artificial filling in.

In the EU Biodiversity Strategy for 2030, it is emphasized that most of the terrestrial biological diversity is in forested areas. The same Strategy emphasizes that from 2011 to 2020, almost a third of forests in the EU were classified as poorly preserved (31%), and more than half of the forests as very poorly preserved (54%). In December 2022, in Montreal (Canada), the EU signed an ambitious global agreement on biodiversity. One of the global goals is to start or complete the restoration of at least 30% of degraded ecosystems by 2030 (the entire area by 2050). Now we must begin to restore nature as quickly as possible, for our own benefit and to meet our global obligations.

In relation to the developmental phases, as an indicator of the previous attitude towards the forest (use of forests) and at the same time an indicator of the type and extent of future measures and activities on forest tending and use, we find the following structure: young stands 4.8%, thickets 20.7%, pole stands 15.9%, middle-aged stands (15-29 cm) 19.1%, maturing stands 16.6%, mature stands 1.6%, thinned mature - well regenerated 1.8%, thinned mature poorly regenerated 5.5%, selection stands and group selection stands and other stands with a three-storied or multi-storied structure 14.0%.

Graph 1:

Figure 3 National Forest inventory of the Montenegro

Source: National Forest Inventory of the Montenegro

Natural regeneration of stands can be assessed as favorable, and seedlings (h < 1.30 m) were recorded on 76,607 ha, and with h over 1.30 m on 102,879 ha. This clearly indicates the possibility of the continuity of natural regeneration as one of the prerequisites for nature-based management.

In Montenegrin forests, the relief and inclination are very pronounced; on a slope of >250, we find 27.9% of the stands, which, in addition to their productive role, also have an anti-erosion protective role. At the same time, such conditions limit the management system (favoring small-area management) and the possibility of using wood for commercial purposes. The land under the forest is dominantlyrendzina (50.7%) and brown soil (42.7%). According to FAO data (2020), 6% of the territory of Montenegro is degraded.

Montenegro is at the intersection of three climate zones: Mediterranean, continental, and mountain. The altitude amplitude is between 100 and 2523 m above sea level, which has conditioned a very pronounced ecological series and diversity of habitats by altitude and a dissected relief by width. The area of uncultivated forest land, which covers almost 10% of the total area of forests and forest land, indicates the extensiveness and uneconomical nature of the previous use (with all caution and the need for a planned relationship to the social demands of the rural population - ecological services (ES) and a significant production potential in relation to an active attitude towards adaptability to climate change. To recall at this point, we emphasize the previously highlighted importance of increasing the area of forests at the global level (the plan is +3% by 2030) to reduce the negative effects of climate change and thereby control the increase in temperature within the limits of +1.5°C (according to the RCP 8.5 scenario).

The percentage of participation of even-aged forests should be taken with a suspicion, given the percentage of participation of coppice forests which are almost exclusively even-aged.

## 4.2. Environmental Baseline and Relevant Potential Issues

Environmental issues in Montenegro stem from inadequate management of various aspects of the environment. In urban areas such as Podgorica, Bijelo Polje, Pljevlja, and Nikšić, excessive air pollution is present during the autumn and winter months. Waste management remains insufficient, with a significant number of illegal landfills. Water management is also problematic, particularly concerning the pollution of surface waters due to the lack of wastewater treatment facilities for industrial and urban wastewater, which is often discharged partially treated or untreated. Additionally, there is no unified pollutant register covering the entire territory of Montenegro.

Protected areas face challenges due to the absence of management structures. Climate change and extreme weather events represent additional concerns, along with continuous pressure to expand construction areas at the expense of green spaces, especially in coastal and central urban regions, including the capital.

Forests are directly linked to many of these challenges. Covering almost 70% of the national territory, they are a critical buffer against environmental degradation. Poorly managed or degraded forest areas contribute to soil erosion, increased runoff, and sedimentation of water bodies, exacerbating water management problems. Illegal dumping often occurs in forested and peri-urban areas, adding pressure to an already weak waste management system. At the same time, forests offer significant potential to mitigate these pressures: healthy forest ecosystems improve air quality by filtering pollutants, regulate water regimes by protecting springs and reducing erosion, and preserve biodiversity that underpins the functioning of protected areas. Their role is especially relevant in the context of climate change, as forests sequester carbon, reduce the risk of landslides and floods, and help maintain ecological stability in mountainous terrain.

### 4.2.1. Air Emissions and Air Quality

The Regulation on Air Quality Monitoring Methods and Conditions ("Official Gazette of Montenegro," No. 021/11) prescribes the methods for monitoring air quality and data collection, including reference measurement techniques, data quality criteria, assurance, and validation. In accordance with the Regulation on the Establishment of a Network of Air Quality Monitoring Stations ("Official Gazette of Montenegro," No. 044/10 of 30.07.2010, 013/11 of 04.03.2011, 064/18 of 04.10.2018), an optimal territorial coverage for air quality data collection has been established.

The designated monitoring stations are representative in terms of station type and their compatibility with other macro- and micro-locations within the same air quality zone. The Environmental Protection Agency continuously publishes real-time air quality data on its website, along with validated monthly air quality reports prepared by the Center for Ecotoxicological Research, which conducts air quality monitoring.

Air quality assessments are conducted in accordance with the Regulation on the Determination of Pollutants, Limit Values, and Other Air Quality Standards ("Official Gazette of Montenegro," No. 045/08, 025/12). All data from automatic stationary monitoring stations are publicly available on the website of the Environmental Protection Agency (www.epa.org.me).

According to the Regulation on the Establishment of a Network of Air Quality Monitoring Stations, Montenegro's territory is divided into three zones (northern, central, and southern – Table 1). These zones are defined based on a preliminary air quality assessment, considering pollutant concentration thresholds determined from available data and data modeling. The air quality zone boundaries align with the external administrative boundaries of the municipalities within each zone.

Table 8 Air Quality Zones

| Air Quality Zone | Municipalities within the zone |
| --- | --- |
| Northern Air Quality Zone | Andrijevica, Berane, Bijelo Polje, Gusinje, Pljevlja, Kolašin, Mojkovac, Petnjica, Plav, Plužine, Rožaje, Šavnik i Žabljak |
| Central Air Quality Zone | Podgorica, Nikšić, Danilovgrad i Cetinje |
| Southern Air Quality Zone | Bar, Budva, Kotor, Tivat, Ulcinj i Herceg Novi |

Sources:

During 2023, air quality improvement was recorded in the Northern and Central zones compared to 2021 and 2022. In the Southern zone, air quality remained very good throughout the monitoring period, with occasional and rare exceedances of the average daily concentration of PM10 particles. High air pollution in the Northern and Central zones is observed from October to April, primarily due to suspended particles (PM10 and PM2.5), mainly from the combustion of solid fuels (wood and coal) used for heating. Frequent temperature inversions prevent emissions dispersion, causing pollutants from fossil fuel combustion, traffic emissions, and similar sources to accumulate near the ground, leading to high pollutant concentrations.

The highest concentrations of these particles, exceeding prescribed health protection levels, were recorded in Pljevlja and Bijelo Polje, as well as significant levels in Podgorica and Nikšić. The Northern zone recorded the highest number of days exceeding the PM10 daily limit in Pljevlja (89 days), while in the Central zone, the highest exceedances were recorded at the Podgorica3 roundabout station in Zabjelo (65 days). Pollution from benzo(a)pyrene, a byproduct of fossil fuel combustion (heating, industry, and traffic), was evident in urban areas, particularly in Pljevlja, Nikšić, Podgorica, and Bijelo Polje, where measurements confirmed elevated concentrations during the heating season. The highest concentration of this pollutant in 2023 was recorded in Pljevlja.

The air quality improvement concerning PM particles is attributed to measures improving energy efficiency, particularly in Pljevlja, where many individual boiler rooms switched from coal to pellet fuel. Meteorological conditions in 2023 also contributed to reduced demand for solid fuel heating, cumulatively improving air quality. To sustain this trend, it is essential to intensify planned measures and complete the planned heating system infrastructure in Pljevlja, which would significantly reduce urban emissions.

Forests play an important role in air quality. Acting as natural filters, they capture particulate matter and absorb atmospheric pollutants, while at the same time functioning as carbon sinks by sequestering CO₂ and releasing oxygen. Dense forests in mountainous areas help to stabilize local microclimates and reduce the spread of pollutants from lower-lying urban and industrial zones. Forest belts in peri-urban areas provide additional protection against traffic-related emissions and noise, contributing to healthier living conditions. However, the predominance of coppice and degraded stands reduces the full potential of forests to provide these ecosystem services, pointing to the need for active management and restoration.

## 4.2.2 Water Quality

Surface Water Quality – In 2023, the surface water quality monitoring network included 20 watercourses with 27 locations, four natural lakes with seven locations, one artificial lake with one location, and five mixed water bodies with five locations. Based on analyses of general physico-chemical parameters, priority and specific pollutants, phytoplankton, phytobenthos, macrophytes, and macrozoobenthos:

- Of 27 examined river locations, only four (14.8%) were classified as having good status (Ibar-above Rožaje; Vrbnica-below the camp; Tara-below Mojkovac; Tara-Šćepan Polje).

- Twelve locations (44.4%) had moderate status.

- Nine locations (33.3%) had poor status.

- Two locations (7.4%) had very poor status (Bojana, Fraskanjel; Crmnica, above Bojana estuary).

For four natural lakes, none met satisfactory overall water quality standards:

- Five locations (71.4%) had moderate status.

- One location (14.3%) had moderately poor status.

- One location (14.3%) had very poor status (Skadar Lake - Kamenik).

The artificial lake (Piva Lake - Plužine) had a moderately poor water quality status. Among five mixed water bodies (river estuaries), two had good status (40.0%), while three had moderate status (60.0%).

Groundwater Quality – Of 32 monitored locations (23 new boreholes, three dug wells, and six aquifers/springs), good status was recorded at 19 locations, while 13 had poor status. Nitrate levels ranged from 8.50–50.09 mg NO₃⁻/l, with one well (Vranj) exceeding the 50 mg NO₃⁻/l threshold. Increased phosphate levels were recorded at Vranj and Drešaj wells, along with elevated K and Na concentrations, indicating the influence of synthetic fertilizers. Pollution sources affecting groundwater quality include wastewater from settlements and industries, agricultural runoff, improper solid and liquid waste disposal, deforestation, and human and animal activities.

Drinking Water Quality – In 2023, a total of 28,095 drinking water samples were tested from municipal water supplies and public facilities, including 14,280 microbiological and 13,815 physicochemical analyses. Of all tested samples, 9.03% were non-compliant with drinking water standards.

Forests are an essential factor for water quality protection in Montenegro. With more than 27% of forest stands located on slopes steeper than 25°, forests reduce erosion and sediment transport into rivers and lakes, thereby preserving surface water quality. They also act as natural regulators of hydrological cycles, supporting groundwater recharge and stabilizing flow regimes in rivers. Healthy forest ecosystems protect springs and aquifers from contamination, particularly in karst regions that are vulnerable to pollution. Conversely, deforestation or poor forest management accelerates erosion, increases nutrient runoff (nitrates and phosphates), and reduces the capacity of soils to filter pollutants, directly impacting both groundwater and surface waters. Sustainable management and restoration of degraded forests are therefore directly linked to maintaining and improving the country’s water quality.

### 4.2.3 Waste Management

As a candidate for EU membership, Montenegro is obligated to establish a modern and integrated waste management system, which is one of the priorities in the EU accession process. This entails harmonization with EU waste management legislation, promoting waste prevention and reduction, source separation, the development of recycling processes, and the transition to a circular economy. Proper waste management, including waste minimization, particularly of non-recyclable waste, collection and recycling, increased reuse, energy recovery, and proper disposal of residual waste, is an integral part of sustainable development, ensuring minimal environmental risk.

The principles in line with EU directives include the "polluter pays" principle, where the waste owner bears the costs of waste management measures and remediation of any environmental damage caused; the proximity principle, ensuring that waste treatment occurs as close as possible to its place of origin; the establishment of a waste information system; an increase in the population covered by municipal waste collection systems; the establishment of standards and capacities for waste treatment; waste reduction, reuse, and recycling; and raising societal awareness of waste management issues.
(In Sweden, less than 1% of untreated waste ends up in landfills, with over 35 facilities generating electricity from waste).

Montenegro’s planned development requires waste management through more efficient resource use and waste reduction.

Forests and forestry are indirectly linked to waste management through the potential use of wood residues, biomass, and logging by-products as renewable energy sources, which can reduce the pressure on landfills and contribute to the circular economy. Illegal waste disposal often occurs in forested and peri-urban areas, undermining both ecosystem services and landscape values. Sustainable forest management can provide cleaner streams of raw material for energy recovery, composting, and recycling, while simultaneously protecting forest ecosystems from pollution. Raising awareness on proper disposal and valorization of forest biomass strengthens both the waste management system and environmental protection overall.

### 4.2.4 Noise

Environmental noise monitoring in Montenegro was conducted in accordance with the 2023 Environmental Noise Monitoring Program. The program covered 15 measurement sites across 14 municipalities, including Podgorica, Nikšić, Žabljak, Petrovac, Budva, Kotor, Ulcinj, Kolašin, Mojkovac, Bijelo Polje, Berane, Bar, Tivat, and Pljevlja. At each location, multi-day measurements were taken from September 2023 to January 2024.

During Noise Measurement Cycle I (2023), daytime, evening, and nighttime noise levels exceeded regulatory limits.

Forests and green belts represent an effective and sustainable form of noise protection. Dense tree belts along highways and railway corridors absorb and diffuse sound waves, reducing noise propagation into residential and recreational areas. In addition to lowering noise levels, forested strips simultaneously provide ecological benefits such as CO₂ absorption, dust filtration, and biodiversity habitats, making them a multifunctional solution. Integrating forested areas into urban planning can therefore serve both as a natural noise barrier and as a contributor to broader environmental quality improvements.

### 4.2.5. Nature Protection

Currently, 76 areas have formal protection status, which are registered in the Central Register of Protected Areas, including 3 strict nature reserves with an area of 420 hectares (0.03% of the territory), 1 special nature reserve with an area of 150 hectares (0.01% of the territory), 5 national parks with an area of 100,427 hectares (7.271% of the territory), 9 nature parks (including three in the sea) with an area of 79,583.1 hectares (5.76% of the territory), 56 natural monuments with an area of 4,493.54 hectares (0.32% of the territory), and 2 areas of exceptional natural value with an area of 196.0 hectares (0.014% of the territory). Therefore, the total area under formal protection is 13.77% of the territory, of which 13.22% is on land and 0.33% is in the sea.

Figure 4 Existing Protected Area

(Source: https://cloud.gdi.net/smartPortal/zppCG)

Proposed and Planned Protected Areas

In order to further increase the quality and extent of protection to achieve at least 30% of the land territory, efforts should continue to establish new protected areas, which have been identified within the framework of the GEF - UNEP MEPPU project "Promoting Protected Area Management through Integrated Marine and Coastal Ecosystem Protection in Montenegro’s Coastal Area." Some of these areas are currently in the process of establishment.

Projected Protected Areas

Nature Parks:

- Sinjajevina – A Protection Study (2016) was conducted, proposing a protected area of 63,863.63 ha covering the territory of 4 municipalities (Mojkovac 15,687.17 ha; Kolašin 18,006.24 ha; Žabljak 16,069.93 ha; Šavnik 14,100.34 ha).

- Mountain Massif of Rumija – tentative boundaries for EMERALD (12,237 ha), IBA (2,300 ha), IPA (2,000 ha), and KBA (9,266 ha) areas. Territory of the Bar municipality.

- Ljubišnja – tentative boundaries for EMERALD (4,332 ha), IPA (2,831 ha). Territory of the Pljevlja municipality.

- Turjak with Hajla – tentative boundaries for EMERALD (2,266 ha), IBA (2,000 ha), IPA (1,551 ha). Territory of the Rožaje municipality.

Strict Nature Reserves:

- Zeletin: Location Goveđak and surrounding areas (approximately 300 ha). Territory of the Andrijevica municipality.

- Tuležine: Old-growth forest of black pine, spruce, and fir (approximately 470 ha). Territory of the Pljevlja municipality.

Nature Parks:

- Vrmac – Protection Study of the "Vrmac" hill (2021), proposing a protected area of 2,361 ha (territories of the municipalities of Kotor and Tivat).

- Prekornica – A Protection Study (2020), proposing a protected area of 13,800 ha. Territory of the Danilovgrad municipality.

- Ćehotina Valley – A Protection Study was conducted and a Draft Decision on the declaration of the protected area "Upper course of the Ćehotina River" in the Pljevlja municipality (1,326.87 ha). The protective belt area is 2,782.71 ha. The Bijelo Polje municipality has initiated the process of protecting the Ćehotina River (2023) in the section passing through its territory (from Stožer to Kovren). Protection is also needed for the lower course of the Ćehotina River, from Pljevlja to the border with Bosnia and Herzegovina.

- Mrtvica – A Protection Study proposed a protected area of 7,500 ha. Territory of the Kolašin municipality.

- Štedim – tentative area of 380 ha. Territory of the Rožaje municipality.

- Zeletin – tentative area of approximately 7,000 ha. Territory of the municipalities of Andrijevica and Plav.

- Parts of Kučke Prokletije (1. Žijovo - Šila Velja - Treskavac; 2. Prijun - Vila - Prasica - Beškeća - Krisitor; 3. Surdup - Kariman - Torač) – Possible inclusion of these three mountain ranges in the "Komovi" Nature Park or designation as a separate wider landscape unit. Tentative area 5,100 ha; Territory of the Capital City of Podgorica.

- Lukavica – A wider landscape unit that includes Borovnik, Mali and Veliki Žurim, Ilijin vrh, Stožac, Trebiješ, Kapetanovo, and Manito-Brnjičko Lake (approximately 380 ha). Territory of the municipalities of Nikšić and Kolašin.

Natural Monuments:

- Kapetanovo Lake with Brnjik – Territory of the Kolašin municipality.

- Canyon of the Stožernica River.

- King Nikola's Forbidden Forest in Morakovo – Territory of the Nikšić municipality.

- Platije – Tentative area 2,200 ha. Territory of the municipalities of Podgorica and Kolašin.

- Canyon of the Male River – Tentative area 3,600 ha. Territory of the Podgorica municipality.

- Canyon of Mrtvica – Area of 2,903 ha within the boundaries of the same-named EMERALD area. Territory of the Kolašin municipality.

- Canyon of Ibrištica – Tentative area 349 ha. Territory of the Kolašin municipality.

- Canyon of the Piperska River – Tentative area 620 ha. Territory of the Podgorica municipality.

- Bogutovski Creek (right tributary of Morača, canyon section) – Tentative area 21 ha. Territory of the Kolašin municipality.

- Bjelopoljska Bistrica (right tributary of Lima, outside the boundaries of Đalovića Gorge) – Tentative area 170 ha. Territory of the Bijelo Polje municipality.

- Tifranska Gorge – Tentative area 200 ha. Territory of the Berane municipality.

- Morin Bay – Tentative area 300 ha. Territory of the Kotor municipality.

- Plav Lake – Within the boundaries of the IBA area (300 ha). Territory of the Plav municipality.

- Čakor (from the spring area of Bjeluha to the border with Kosovo) – Tentative area 1,100 ha. Territory of the Plav municipality.

- Torna (Bablji Zub) – Tentative area 345 ha. Territory of the Kolašin municipality.

- Jerinja Glava – Tentative area 750 ha. Territory of the Andrijevica municipality.

- Bjeloshevske Marshes (from the school in Donji Morakovo to the waterfall, bridge on Gračanica) – Tentative area 38 ha. Territory of the Nikšić municipality.

- Budoške Marshes – Tentative area 370 ha. Territory of the Nikšić municipality.

- Semolj – Tentative area 65 ha. Territory of the Kolašin municipality.

- Canyons of the Upper Popče and Radmanska Rivers – Tentative area 1,300 ha. Territory of the Petnjica municipality.

- Large and Small Pošćensko Lake – Tentative area 13 ha. Territory of the Šavnik municipality.

Areas of Exceptional Features:

- Visitor (optionally also Zeletin) – Within the boundaries of the EMERALD area (13,680 ha) (along with Visitor in the IPA area boundaries (1,779 ha). Territory of the municipalities of Plav and Andrijevica.

- Beech Forests on Obzovica – Tentative area 115 ha. Territory of the Cetinje municipality.

- Luštica – Tentative area 3,500 ha. Territory of the Herceg Novi municipality.

- Morača River Basin: Protection as an integrated protected area (hydrological basin) or (optionally) as individual canyons/canyon valleys. Tentative area 82,000 ha. Territories of the municipalities of Podgorica and Kolašin.

In the Sea and Coastal Areas

- Sopot and Dražin Vrt: Locations in the Bay of Kotor designated as natural monuments.

- Šasko Lake, Bojana River, Knete, Ada Bojana: New or newly proposed protected areas, where the spatial extent in the Protection Study can be defined within the boundaries of:

  - (a) EMERALD Area ME000000C (7,397 ha),

  - (b) IBA Areas: Ada Bojana (494 ha), Bojana Delta (7,500 ha), Šasko Lake (315-380 ha), and Paratuk Island (0.2 ha), or

  - (c) KBA Areas: 1. Šasko Lake (448 ha), 2. Bojana Delta (12,561 ha). Territory of the Ulcinj municipality.

- Kotor-Risan Bay: A new protected area, the spatial extent of which in the Protection Study can be defined within the boundaries of:

  - (a) EMERALD Area ME000000Q (Kotor-Risan Bay, 2,778 ha),

  - (b) IPA Area: Kotor-Risan Bay (2,778 ha),

  - (c) KBA Area: Kotor-Risan Bay (2,781 ha), or

  - (d) UNESCO Area: Kotor-Risan Bay (14,600 ha). Territories of the municipalities of Herceg Novi, Kotor, and Tivat.

- Areas of significant marine habitats representing potential marine protected natural assets have been identified at the following locations:

  - Luštica (from Mamula to Cape Mačka),

  - Zone from Cape Volujica to Dobri Voda,

  - Zone from Valdanos Bay to Velika Bay,

  - and Seka Đjeran with the southern part of the area in front of Velika Beach to the mouth.

Figure 5 Graphical representation of the projection of protected area

Within the protected areas, protection regimes have been defined as Levels I, II, and III.

Ecologically Significant Areas:

Areas with International Status

According to the Action Plan for meeting the final criteria in Chapter 27 - Environment and Climate Change, it is necessary to ensure the protection of recognized significant areas from the perspective of biodiversity value.

UNESCO World Natural and Cultural Heritage

The Bay of Kotor-Risan (15,000 ha) and Durmitor with the Tara Canyon (33,895 ha) are listed as World Natural and Cultural Heritage Sites under the UNESCO Convention concerning the protection of World Natural and Cultural Heritage, recognizing them as areas of outstanding universal value. Management of these areas must explicitly be based on the recognized values and focus on risk assessment.

The Tara River Basin (182,899 ha) is protected as a UNESCO Biosphere Reserve. It is necessary to establish management that ensures the sustainable use of natural resources and biodiversity conservation. In addition, the procedure for inscribing the beech forests of Biogradska Gora on the UNESCO list was initiated in 2019.

Ramsar Areas

The Skadar Lake (20,000 ha), Tivat Saltworks (150 ha), and Ulcinj Salina (1,477 ha) are listed on the World Wetland Sites list under the Ramsar Convention. Management of these areas involves preserving the ecological character and basic functions and values for future generations. Additionally, the Ramsar Convention obligates signatories to promote wise use of all wetlands within their territory.

Emerald Areas

Emerald Areas, identified in accordance with the Bern Convention on the Conservation of European Wildlife and Natural Habitats, form the basis for the future ecological network of Natura 2000 sites. Montenegro has established a list of 32 candidate areas for the Emerald ecological network (also defined as areas of special interest for protection at the European level - ASCIs). These areas cover 240,077.1 ha, or 17% of the territory. Some of these Emerald habitats are already part of existing protected areas or those planned for protection at this time. However, due to changes in the Bern Convention and new findings, a revision of the identified boundaries is necessary.

The Bern Convention requires signatory countries to devise and implement adequate protection mechanisms for these areas. Therefore, any approval of projects that do not align with maintaining the favorable status of species and habitats in these areas could trigger compliance issues with the Bern Convention (e.g., the "Porto Skadar Lake" project), which may result in recommendations that, through negotiations with the European Commission in the context of Montenegro's EU accession, become binding.

A special guideline for Emerald areas covering forest habitats highlights the inclusion of strict protection measures and restrictions related to forest use, as well as cooperation with experts to preserve forest habitats and biodiversity.

Key Biodiversity Areas (KBA)

KBAs represent the most important areas for species and their habitats at the global level. In Montenegro, 18 KBAs have been identified.

Important Plant Areas (IPA)

The goal of defining IPAs is to preserve a network of areas that contain the most representative habitats of international significance, as well as internationally and nationally significant plant species, thereby achieving one of the objectives of the Convention on Biological Diversity. To date, 27 such areas have been identified in Montenegro, covering a total area of 708,606 ha.

Important Bird Areas (IBA)

IBA areas are important for bird conservation. They provide refuge for significant populations of one or more globally or regionally threatened bird species, endemic birds, or certain highly representative bird groups. IBAs are selected based on international criteria and standards (BirdLife International). In these areas, it is essential to reduce the effects of habitat loss and degradation on birds and other biodiversity. Montenegro has identified 20 IBA areas.

Special Protection Areas (SPA)

These areas are designated to protect one or more bird species listed in Annex I of the EU Birds Directive, and as such, they are part of the process of establishing the Natura 2000 network, with IBA areas being the starting point for their identification. A total of 33 such areas have been recognized, covering 53.5% of the territory.

According to the "Action Plan for Meeting the Final Criteria in Chapter 27 - Environment and Climate Change," it is necessary to ensure the protection of these areas in terms of their biodiversity value.

Figure 6 Areas with International Status

Natural Units of High Biodiversity Value – Indicative Ecological Network

For the purposes of the development of the Spatial Plan of Montenegro, as part of the GEF-MEPPU project "Integrating Biodiversity into Sectoral Policies and Practices and Strengthening Protection of Critical Biodiversity Hotspots in Montenegro," a detailed expert analysis was conducted on the available spatial data regarding the distribution of nationally and internationally significant species and habitats in Montenegro. This was done with the participation of the expert and scientific community from the nature protection sector. International and national criteria were used, with a focus on Natura 2000 habitats and species. The analysis particularly highlighted sites containing rare habitats for Montenegro that have been recognized as priorities for protection according to the EU Habitats Directive.

By overlaying these spatial data, natural units (outside national parks) with high biodiversity value were identified, based on the overall number of significant species and habitats present, of which three units stand out:

Areas of Exceptional Biodiversity Richness Under Strong Anthropogenic Pressure

These areas are dominated by Natura 2000 habitats of excellent and good representativity and have recorded populations of many nationally/internationally significant species.

Areas with High Biodiversity Value Under Strong Anthropogenic Pressure

These areas are under strong anthropogenic pressure due to ongoing or planned land-use changes. As a result, there may be a significant reduction or permanent loss of these species or habitats from the territory of Montenegro. Therefore, it is necessary to establish conditions for the protection of these areas, which includes the prohibition of infrastructure projects and land-use changes. These areas represent an indicative 3.34% of the territory, and some of them are already recognized in the projections of protected areas or are within areas with international status. During this planning period, the preparation of biodiversity baseline studies with proposed conservation measures should be initiated for these areas, regardless of whether they are included in the protection projections.

Areas Rich in Biodiversity

In these areas, Natura 2000 habitats of excellent and good representativity dominate, and populations of nationally/internationally significant species have been recorded. However, these areas are not subject to inherent anthropogenic pressures. In these areas, it is necessary to prevent land-use changes and the construction of large infrastructure projects, while promoting revitalization and sustainable land-use practices, such as extensive agriculture and eco-tourism. Interventions in the space should be limited to existing built-up areas, with the possibility of reconstruction and expansion of existing buildings according to land-use purposes. Special emphasis should be placed on the promotion of traditional pastoralism, which maintains mountain pastures and the associated biodiversity, as well as measures such as the removal of invasive species. These areas represent an indicative 21.69% of the territory, and some of them are also recognized in the projections of protected areas or are within areas with international status. Areas not currently included in the protection projections should be considered part of the future ecological network and treated as such. In this case, the preparation of biodiversity baseline studies with proposed conservation measures should also be required.

This category also includes individual objects that are important from a biodiversity perspective, such as caves, springs, and marshes. In relation to these objects, spatial planning should avoid changes in the buffer zone within a 200-meter radius around the location until more precise protection measures are determined through the development of baseline studies. These areas are dominated by Natura 2000 habitats of good representativity or have been recognized for the presence of significant species. Additionally, these areas represent potential corridors that enable connectivity between other areas, thus ensuring the functioning of ecosystems and the provision of their services. They represent an indicative 39.72% of the territory of Montenegro. Connectivity between areas via corridors is essential because it prevents the isolation of species populations, allows for the recovery of habitats under pressure, and enhances the overall resilience of ecosystems, including climate change. Therefore, it is important to maintain the integrity of the landscape in these areas and avoid space degradation. Infrastructure planning should take this into account and avoid fragmentation and loss of connectivity that these areas provide. Parts of these units should also be considered as part of the future ecological network. It is important to note that, with continued research, it is expected that even within these areas, sites with exceptionally rich biodiversity may be identified and could become subject to formal protection in the future.

Figure 7 Biodiversity rich Area

Figure 4 – Areas of High Biodiversity Value Identified Based on Existing Data on the Distribution of Nationally and Internationally Significant Species and Habitats

The area covered by the aforementioned spatial units can be considered an indicative part of the ecological network and should be treated as such in future plans. The establishment of the ecological network is an obligation of Montenegro concerning the closure of Chapter 27 in the EU integration process and will be implemented in accordance with the realization of the project "Establishing Natura 2000 in Montenegro."

### 4.2.6. Climate Change

National Greenhouse Gas Inventory 1990-2021

The National Greenhouse Gas Inventories for the period 1990-2021 were updated as part of the National Emission Report (NIR of Montenegro), which was submitted to the UNFCCC Convention in July 2023. The 2006 IPCC international methodology was used for the inventory update, along with a specially created Excel tool for calculating GHG emissions and air pollutants.

The updated inventories, i.e., the sources and sinks of GHG emissions (carbon dioxide (CO2), methane (CH4), nitrous oxide (N2O), synthetic gases (fluorinated carbon compounds – HFCs, PFCs, and sulfur hexafluoride - SF6), are presented graphically and in tables for each of the four main sectors: Energy, Industrial Processes and Product Use, Agriculture, Land Use Change and Forestry, Waste.

Substances that Deplete the Ozone Layer and Alternative Substances

In 2023, the Environmental Protection Agency issued one permit for the import of an ozone-depleting substance (HCFC 22) in a total amount of 480 kg. From the alternative substances, the following were imported in the previous period: HFC-134a, HFC-32, HFC 404A, HFC 407C, 410A, HFC 507A, HFC-227ea, and SF6. In 2023, permits were issued for the import of HFCs (HFC 32, HFC-134a, HFC 404A, HFC 407C, 410A) in a total amount of 67,170 kg.

Air Temperature and Precipitation Analysis for 2023

Characteristic of the year 2023: air temperature above the climate norm; according to the distribution of percentiles, the air temperature falls into the categories of very warm and extremely warm; the amount of precipitation, according to the percentile distribution, falls into the categories of normal, rainy, and very rainy.

Forests are central to Montenegro’s climate change strategy. They cover nearly 70% of the country’s territory and act as long-term carbon sinks, with an estimated standing volume of around 122 million m³. By absorbing CO₂, forests directly reduce national greenhouse gas balances, making the Land Use,

Land-Use Change and Forestry (LULUCF) sector one of the few with a net positive effect in the inventory. At the same time, degraded coppice and shrub forests reduce the overall sequestration potential, underscoring the importance of restoration and sustainable management.

Forests also provide key adaptation functions: they stabilize soils and slopes, regulate water cycles, and mitigate the risks of floods, landslides, and droughts, which are expected to increase under climate change. One of the most pressing threats is the growing incidence of forest fires, amplified by higher summer temperatures and prolonged dry periods. Effective fire prevention and response systems, combined with silvicultural measures such as creating mixed and climate-resilient stands, are critical for reducing vulnerability.

Montenegro is aligned with the EU Biodiversity Strategy 2030, which requires the restoration of at least 30% of degraded ecosystems, including forests. Investments in reforestation, sustainable forest management, and the prevention of land degradation will therefore play a dual role: reducing greenhouse gas emissions and strengthening resilience to the impacts of climate change.

## 4.3 Socio-economic Environment

### 4.3.1. Demography/Population

According to official results of the 2023 Population Census, the total population of Montenegro was 623,633. According to data from the Statistical Office of Montenegro (MONSTAT), and it is 2.1% higher compared to the population recorded in the 2011 Population Census.

According to preliminary data from the 2023 Population Census by municipalities, a noticeable decrease in the number of inhabitants was recorded in the northern municipalities, while population growth was recorded in the coastal municipalities and Podgorica (Data provided in Table No. ?).

Accordingly, compared to the 2011 Population Census, the population in the municipality of Andrijevica has decreased by 22%, in Mojkovac by 21%, in Pljevlja by 20%, in Kolašin by 19%, in Bijelo Polje by 14%, while in Berane, the decline amounted to 12%.

Besides the northern cities, a significant population decline has also been recorded in the municipalities of Nikšić (8%) and Cetinje (13%).

The highest population growth compared to the 2011 Popualtion Census has been recorded in the municipality of Budva (as much as 39%), while the population of Podgorica has increased by 14%, Tivat by 10%, Bar by 10%, and Ulcinj by 7%.

These data clearly indicate a significant migration of the population from the northern municipalities to Podgorica and the coastal municipalities.

Most of the municipalities experiencing mass depopulation were once centers of a developed wood industry. Furthermore, the highest exploitation of timber resources is currently taking place in these municipalities.

Table 9 Number of populations by municipalities

| Municipality | Census 2011 | Census 2023 | Difference 2011/2023 |
| --- | --- | --- | --- |
| Total Montenegro | 620029 | 633158 | 13130 |
| Andrijevica | 5071 | 3978 | -1093 |
| Bar | 42048 | 46171 | 4123 |
| Berane | 28488 | 25162 | -3326 |
| Bijelo Polje | 46051 | 39710 | -6341 |
| Budva | 19218 | 26667 | 7449 |
| Cetinje | 16657 | 14465 | -2192 |
| Danilovgrad | 18472 | 18832 | 360 |
| Herceg Novi | 30864 | 31471 | 607 |
| Kolašin | 8380 | 6765 | -1615 |
| Kotor | 22601 | 21916 | -685 |
| Mojkovac | 8662 | 6824 | -1838 |
| Nikšić | 72443 | 66725 | -5718 |
| Plav | 9081 | 10378 | 1297 |
| Pljevlja | 30786 | 24542 | -6244 |
| Plužine | 3246 | 2232 | -1014 |
| Podgorica | 158327 | 180186 | 21859 |
| Rožaje | 22964 | 25247 | 2301 |
| Šavnik | 2070 | 1588 | -482 |
| Tivat | 14032 | 16340 | 2308 |
| Ulcinj | 19921 | 21395 | 1474 |
| Žabljak | 3569 | 3002 | -567 |
| Gusinje | 4027 | 4662 | 635 |
| Petnjica | 5482 | 5552 | 70 |
| Zeta | 16231 | 16206 | -25 |
| Tuzi | 11379 | 13142 | 1763 |

Sorce: MONSTAT

Out of the total population, 316,826 people, or 50.80%, are female, while 306,807 people, or 49.20%, are male. Women have an average age of 40.90 years, while men have an average age of 38.52 years. The average age of Montenegro's population is 39.73 years.

Looking at municipalities, the population of Plužine is the oldest on average, with 47.32 years, while Rožaje has the youngest population, with an average of 35.83 years.

Regarding age groups, children aged 0-5 years, representing the preschool age group, make up 6.85% of the total population. Those of primary school age (6-14 years) account for 11.18%, while those of secondary school age (15-18 years) make up 4.63% of the total population. The population aged 0-14 years represents 18.03% of the total population.

The working-age population (15-64 years) accounts for 65.13%, while those aged 65 and older make up 16.84%. The adult population constitutes 78.45% of the total population.

Table 10 Population by Gender and Age

| Age | Population |  |  | In % |  |
| --- | --- | --- | --- | --- | --- |
|  | total | male | female | male | female |
| Montenegro 0-4 | 623 633 35 368 | 306 807 | 316 826 17 131 | 49,20 | 50,80 48,44 |
|  |  | 18 237 |  | 51,56 |  |
| 5-9 | 38 269 | 19 830 | 18 439 | 51,82 | 48,18 |
| 10-14 | 38 807 | 20 204 | 18 603 | 52,06 | 47,94 |
| 15-19 | 35 250 | 18 432 | 16 818 | 52,29 | 47,71 |
| 20-24 25-29 30-34 | 34 699 38 809 42 465 | 17 949 | 16 750 19 195 21 333 | 51,73 | 48,27 49,46 50,24 |
|  |  | 19 614 |  | 50,54 |  |
|  |  | 21 132 |  | 49,76 |  |
| 35-39 | 46 328 | 23 096 | 23 232 | 49,85 | 50,15 |
| 40-44 | 45 511 | 22 545 | 22 966 | 49,54 | 50,46 |
| 45-49 50-54 55-59 | 42 709 40 099 39 965 | 20 859 | 21 850 20 428 20 302 | 48,84 | 51,16 50,94 50,80 |
|  |  | 19 671 |  | 49,06 |  |
|  |  | 19 663 |  | 49,20 |  |
| 60-64 | 40 346 | 19 551 | 20 795 | 48,46 | 51,54 |
| 65-69 70-74 75 and more | 37 231 30 120 37 657 | 17 833 | 19 398 16 639 22 947 | 47,90 | 52,10 55,24 60,94 |
|  |  | 13 481 |  | 44,76 |  |
|  |  | 14 710 |  | 39,06 |  |
| 0-5 6-14 15-18 | 42 745 69 699 28 861 | 22 068 | 20 677 33 496 13 753 | 51,63 | 48,37 48,06 47,65 |
|  |  | 36 203 |  | 51,94 |  |
|  |  | 15 108 |  | 52,35 |  |
| 0-17 | 134 420 | 69 772 | 64 648 | 51,91 | 48,09 |
| 18 and more | 489 213 | 237 035 | 252 178 | 48,45 | 51,55 |
| 0-14 15-64 65 and more | 112 444 406 181 105 008 | 58 271 | 54 173 203 669 58 984 | 51,82 | 48,18 50,14 56,17 |

Sorce: Monstat

Montenegro’s Northern Region contains a greater concentration of coniferous high forests with denser growing stock. Accordingly, these municipalities are home to the majority of forestry and wood-processing firms. The Central and Coastal Regions of the country contain more coppice forests, in part due to the natural reforestation of formerly agricultural land.

### 4.3.2. Economy

Montenegro’s small, open, and service-based economy is highly vulnerable to external shocks, and it relies on fiscal policy and structural reforms to maintain macroeconomic stability. Montenegro aspires to join the European Union (EU). Since starting accession negotiations in 2012, Montenegro has greatly aligned its legislation with the EU Acquis and made significant efforts to improve its living standards.

However, Montenegro’s growth strategy has so far been based largely on attracting a few large investment projects in transport, energy, or tourism. Construction booms fueled temporary growth spurts but were not accompanied by productivity growth and were followed by sharp downturns, leaving the economy even more vulnerable to shocks. If GDP per capita is to grow at pre-COVID average rates of 3%, incomes would not converge to average EU levels in the next 40 years.

Montenegro is one of the most densely forested countries in Europe, with nearly 60 percent of its area covered by forests and forest land.  49.4 percent (687,061 ha) of the land area is covered with forests; forest land makes up an additional 10.1 percent (140,723 ha), as of 2022, according to the Statistical Office of Montenegro (MONSTAT).  Deciduous forests accounted for 71 percent, coniferous forests for 18 percent, and mixed forests for 11 percent of the total forest area as of 2022; dominant species include beech, spruce, fir, and black pine.

The state owns just over half (52 percent) of forested land in Montenegro, while the remaining 48 percent is privately owned.  By timber volume, however, the state’s share is considerably larger: 84.5 million m3 (73 percent) of standing stock is in public forests; private forests contain just 31.7 million m3 (27 percent) of harvestable timber in accessible forests. The average volume per hectare for public forests is 228 m3, compared to 89 m3 in private forests.

For Montenegro’s forestry sector to become more competitive, investment and policy reform are needed at multiple points along the value chain. Upstream, the implementation of sustainable forest management (SFM) practices is critically needed: under the prior concession-based model for timber sales—abolished by recent updates to the Law on Forests—the quality of wood in broadleaf forests, primarily beech forests, declined considerably. This reduction in quality (and more recently, uncertainty of supply during the transition away from the concessionary system) has constrained the ability of wood processors and furniture makers to plan and invest for the future.

Steadier and more sustainable production from the forest sector is possible. EBRD estimates that SFM practices have the potential to increase Montenegro’s annual allowable cut to between 1.43 to 1.85 million m3.  (In 2023, total roundwood removals amounted to just over 1.05 million m3. ). For this, however, public and private forest owners will need to develop or update forest management plans.

Greater investment is also needed to increase value addition through wood processing and furniture manufacturing. Despite Montenegro’s long history of forestry, wood processing remains centered on the production of sawnwood (270,000 m3 production in 2023) and wood pellets (98,534 tonnes, requiring an estimated 180,000 m3 of wood inputs). Production of wood-based board and panels, as well as modern furniture and paper products is minimal. The country’s wood-processing industry, focused on exports is dominated by a few players: there are only three sawmills with an annual capacity greater than 30,000 m3 in Montenegro.

Small family-owned mills with capacities between 1,000 to 5,000 m3 are also active but have historically operated as consortia to gain access to raw materials via forest concessions. These firms are generally too small to compete effectively in international sawnwood markets, where scale is important. A certain level of scale is necessary for competitiveness in the majority of the major segments involved in wood processing, suggesting a need for either consolidation or specialization (or both). This is the case among Montenegrin firms across the sector, many of which have only one or two formal employees (Table 1).

Table 11Structure of wood processing and Furniture industries in Montenegro,2022

| Code | Activity | Number | Revenues (EUR ths) | Employees |
| --- | --- | --- | --- | --- |
| 1610 | Sawing and processing of wood | 234 | 85,351 | 1,526 |
| 1621 | Manufacture of veneer and wood panels | 1 | 0 | 2 |
| 1622 | Manufacture of parquet | 2 | 591 | 21 |
| 1623 | Manufacture of other builders' carpentry and joinery | 71 | 36,423 | 507 |
| 1624 | Manufacture of wooden packaging | 1 | 0 | 1 |
| 1629 | Manufacture of other products of wood, cork, straw & wickerwork | 30 | 6,370 | 109 |
|  | Subtotal – Wood Processing | 339 | 128,735 | 2,166 |
| 3101 | Manufacture of furniture for business and retail premises | 44 | 17,811 | 251 |
| 3102 | Manufacture of kitchen furniture | 20 | 1,909 | 54 |
| 3103 | Manufacture of mattresses | 3 | 1,004 | 16 |
| 3109 | Manufacture of other furniture | 82 | 19,017 | 338 |
|  | Subtotal – Furniture | 149 | 39,741 | 659 |

Source: Spatial Plan of Montenegro Until 2040

Despite the relatively low quality of its output, Montenegro’s wood processing industry is export-oriented due to the country’s small domestic market. Major destinations of the country’s US$30.5 million in wood-product exports in 2023 were North Macedonia (US$ 8.1 million, or 27 percent of total), Serbia (US$7.9 million; 26 percent) and Italy (US$ 6.3 million; 21 percent) (ITC, 2024). Since 2014, the country has maintained a consistently positive balance of trade in wood products, excluding furniture. Official statistics show that 2023 revenues from the country’s sawnwood exports of 155,370 m3 were US$30.3 million, or US$195/m3; those for wood pellets—71,998 mt equivalent to about 131,000 m3—were US$17.2 million, or US$131/m3. These relatively low values are suggestive of significant foregone revenues for Montenegro’s wood processing industry due to an inability to invest in more sophisticated production technology.

(US$ million)

Figure 8 Montenegro Wood product Exports by Value 2014-2023

Source: ITC (2024)

- Montenegro’s producers of wood products are also disadvantaged by their inability to access higher-value markets due to increasingly stringent regulations. The prevailing EU Timber Regulation (EUTR), which focuses on the legality of timber and timber products, requires traders to keep a record of their suppliers and customers to curb illegal harvests. At the end of 2025, it will be replaced by the EU Deforestation Regulation (EUDR), which requires detailed geolocation traceability to determine where a given commodity was produced or grown, and if that process was associated with deforestation. Accordingly, it places a greater onus on importers and distributors of wood products to conduct value-chain due diligence to ensure producer compliance with forest-product legality standards. This in turn is expected to push firms in producing jurisdictions towards the adoption of SFM, certification and other measures.

#### 4.3.2.1. Gross domestic product (GDP)

Gross domestic product (GDP) of Montenegro in 2023 was 6 964 milion EUR, while for 2022 it was 5 924 million EUR. Gross domestic product (GDP) per capita in 2023 was 10 998 EUR, while in 2022 it was 9 598 EUR.

Real growth rate of GDP for 2023 was 6.3%.

Table 12 Gross domestic product

|  | 2022 | 2023 |
| --- | --- | --- |
| 1. Gross domestic product at current prices, mill. EUR | 5 924 | 6 964 |
| 2. Population (in thous.) | 617.2 | 633.2 |
| 3. Gross domestic product per capita in EUR 3 = (1/2) | 9 598 | 10 998 |
| 4. Gross domestic product at constant prices (at prices of previous year), mill. EUR | 5 273 | 6 299 |
| 5. Real growth rate of GDP (%) (GDP at constant prices in current year / GDP at current prices in previous year) x 100 - 100 | 6.4 | 6.3 |
| 6. Nominal growth of GDP-a (%) (GDP at current prices in current year / GDP at current prices in previous year) x 100 - 100 | 19.6 | 17.5 |
| 7. Deflator (%) (GDP at current prices in current year / GDP at constant prices in current year) x 100 - 100 | 12.4 | 10.5 |

Source: MONSTAT

Table 13Gross Value added, indices of nominal growth and structure of GDP

| Classification of activities |  | Gross value added (in thous. EUR) |  | Index of nominal growth | GDP structure (%) |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 2022 | 2023 |  | 2022 | 2023 |
| A | Agriculture, forestry and fishing | 358 047 381 062 |  | 106.4 | 6.0 5.5 |  |
| B | Mining and quarrying | 63 730 73 469 |  | 115.3 | 1.1 1.1 |  |
| C | Manufacturing | 231 469 221 183 |  | 95.6 | 3.9 3.2 |  |
| D | Electricity, gas, steam and air conditioning supply | 158 975 262 011 |  | 164.8 | 2.7 3.8 |  |
| E | Water supply; sewerage, waste management and remediation activities | 83 669 88 376 |  | 105.6 | 1.4 1.3 |  |
| F | Construction | 230 224 223 789 |  | 97.2 | 3.9 3.2 |  |
| G | Wholesale and retail trade; repair of motor vehicles and motorcycles | 850 708 952 606 |  | 112.0 | 14.4 13.7 |  |
| H | Transportation and storage | 251 696 281 985 |  | 112.0 | 4.2 4.0 |  |
| I | Accommodation and food service activities | 457 351 642 095 |  | 140.4 | 7.7 9.2 |  |
| J | Information and communication | 259 410 312 540 |  | 120.5 | 4.4 4.5 |  |
| K | Financial and insurance activities | 234 234 291 055 |  | 124.3 | 4.0 4.2 |  |
| L | Real estate activities | 328 995 369 366 |  | 112.3 | 5.6 5.3 |  |
| M | Professional, scientific and technical activities | 200 142 226 724 |  | 113.3 | 3.4 3.3 |  |
| N | Administrative and support service activities | 102 300 118 051 |  | 115.4 | 1.7 1.7 |  |
| O | Public administration and defense; compulsory social security | 339 312 411 391 |  | 121.2 | 5.7 5.9 |  |
| P | Education | 241 904 293 799 |  | 121.5 | 4.1 4.2 |  |
| Q | Human health and social work activities | 233 298 264 549 |  | 113.4 | 3.9 3.8 |  |
| R | Arts, entertainment and recreation | 90 350 104 801 |  | 116.0 | 1.5 1.5 |  |
| S+T | Other service activities; Activities of households as employers | 54 077 65 038 |  | 120.3 | 0.9 0.9 |  |
| U | Activities of extraterritorial organizations and bodies | … … |  | … | … … |  |
| Total |  | 4 769 890 5 583 889 |  | 117.1 | 80.5 80.2 |  |
| Taxes on products less subsidies on products |  | 1 154 128 1 379 726 |  | 119.5 | 19.5 19.8 |  |
| GROSS DOMESTIC PRODUCT (current prices) |  | 5 924 018 6 963 615 |  | 117.5 | 100.0 100.0 |  |

Source: MONSTAT

Gross value added, indices of nominal growth and structure of GDP at current prices. The total gross value added of agriculture, forestry, and water management in 2023 amounted to approximately 387 million euros, which is 6.4% higher than in 2022 when it was 358 million euros. The share of this sector in the total GDP in 2023 was 5.5%, which is lower compared to 2022 when it was 6%.

Despite officially accounting for only 0.5 percent of national GDP, the forest sector plays a significant economic role in Montenegro’s Northern Region, providing up to 20 percent of local incomes in some areas.

Preliminary projections of the Central Bank of Montenegro indicate that the GDP rate should amount to 3.6% in 2024. According to the forecasts of the Ministry of Finance from January 2024, in the following three-year period (2024 - 2026), the Montenegrin economy will grow annually at an average real rate of 3.2% according to the baseline scenario, and 1.6% according to the lower-growth scenario (Table). According to the same forecasts, domestic demand will continue to be the driver of growth “through high personal consumption by households and the start of a new investment cycle, which will be stimulated by easing business barriers and regulatory reforms, as well as youth employment policies.”

Table 14 Projected growth rates in Montenegro

| Projected GDP growth rates in Montenegro, 2024 - 2026, in % |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Baseline scenario |  |  | Lower-growth scenario |  |  |
|  | 2024 | 2025 | 2026 | 2024 | 2025 | 2026 |
| Real GDP growth (Ministry of Finance), ERP | 3.8 | 3.0 | 2.9 | 1.4 | 1.8 | 1.7 |

Source: Central Bank of Montenegro

### 4.3.3. Labor market and employment

According to the Montenegrin Central Bank’s 2023 Annual Report, the average number of employed persons amounted to 244,484 in 2023, being 9.27% higher than in 2022. Employment growth was recorded in all sectors, with the highest being recorded in the information and communications sector (31.07%) and the real estate business (29.70%), and the lowest in the state administration sector and defense, compulsory social security (0.69%).

According to the records of the Employment Agency of Montenegro (EAM), the average number of registered unemployed persons amounted to 40.961 in 2023 which is 15.42% less than in the previous year. The largest number of unemployed people was recorded in January (44,786), and the lowest in September (37,649). Nevertheless, long-term unemployment is still present on the Montenegrin labor market, which is to a certain extent the result of the long-standing mismatch between the education system and the labor market, which leads to a mismatch between supply and demand. Observing the unemployment structure by the duration of looking for job, as per the EAM records, there were 18,306 persons or 45.83% of the total number of unemployed persons that were looking for employment for over three years.

According to the data of the EAM, the registered unemployment rate stood at 13.95% at the end of 2023 and it was 3.07 percentage points lower than in 2022. According to the Labor Force Survey, which MONSTAT publishes on a quarterly basis, the unemployment rate was 15.46% in Q1, 12.94% in Q2, 11.79% in Q3, and 12.17% in Q4.

MONSTAT data indicate that the average gross earnings amounted to 987 euros in the reporting year, while the average earnings without taxes and contributions stood at 792 euros, with both showing the year-on-year increase of 11.78% and 11.24%, respectively. This growth is partly the result of an additional increase in earnings of employees in the public sector in 2023, on top of the already significant increase in total earnings recorded in the previous year as a result of the implementation of the “Europe Now1” Program.

Table 15Persons in employment by sectors of activity and sex, Montenegro,2023

|  | in thousands |  |  | % |  |  | % Women |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Total | Men | Women | Total | Men | Women |  |
| Total | 278,3 | 152,3 | 126,0 | 100,0 | 100,0 | 100,0 | 45,3 |
| Agriculture, forestry and fishery | 12,4 | 7,8 | 4,6 | 4,5 | 5,1 | 3,7 | 37,2 |
| Industry | 51,3 | 40,7 | 10,6 | 18,4 | 26,8 | 8,4 | 20,6 |
| Mining | (1,8) | ((1,6)) | . | 0,6 | 1,1 | . | . |
| Manufacturing | 17,0 | 11,7 | 5,2 | 6,1 | 7,7 | 4,2 | 30,9 |
| Electricity. gas. steam and air conditioning | 3,1 | 2,4 | . | 1,1 | 1,6 | . | . |
| Water supply, wastewater management | 5,4 | 4,8 | . | 1,9 | 3,1 | . | . |
| Construction | 24,0 | 20,2 | 3,8 | 8,6 | 13,2 | 3,0 | 15,8 |
| Services | 214,6 | 103,8 | 110,8 | 77,1 | 68,1 | 88,0 | 51,6 |
| Wholesale. retail; certain repair | 52,9 | 20,8 | 32,1 | 19,0 | 13,6 | 25,5 | 60,7 |
| Transport storage and communication | 17,3 | 13,3 | 4,0 | 6,2 | 8,7 | 3,2 | 23,2 |
| Accommodation and food services | 27,8 | 15,0 | 12,8 | 10,0 | 9,8 | 10,2 | 46,1 |
| Information and communications | 8,9 | 5,4 | 3,5 | 3,2 | 3,6 | 2,8 | 39,2 |
| Financial and insurance activities | 4,0 | 2,1 | 1,9 | 1,4 | 1,4 | 1,5 | 46,9 |
| Real estate. leasing and business activities | 4,9 | 3,2 | 1,8 | 1,8 | 2,1 | 1,4 | 35,7 |
| Professional. scientific and technical activities | 15,9 | 8,7 | 7,2 | 5,7 | 5,7 | 5,7 | 45,2 |
| Administrative and support service activities | 9,8 | 5,8 | 4,0 | 3,5 | 3,8 | 3,1 | 40,6 |
| Public administ. and defence | 21,8 | 12,3 | 9,5 | 7,8 | 8,1 | 7,6 | 43,6 |
| Education | 17,5 | 4,8 | 12,7 | 6,3 | 3,2 | 10,0 | 72,4 |
| Health and social work | 15,4 | 5,0 | 10,4 | 5,5 | 3,3 | 8,2 | 67,3 |
| Arts, entertainment and recreation | 7,8 | 3,9 | 3,9 | 2,8 | 2,5 | 3,1 | 50,5 |
| Other social and personal services | 10,5 | 3,4 | 7,0 | 3,8 | 2,2 | 5,6 | 66,7 |

Source: MONSTAT

The forest management and logging industries employ approximately 3,200 people; half of these jobs are in the Northern Region (Figure 2). (Nationally, wood processing and furniture manufacturing account for 2,280 and 780 jobs, respectively. Transportation and related services are also significant sources of employment in the sector.) In addition to being one of the few available sources of employment for many northern communities—which face higher poverty rates than the more urbanized and economically developed Central and Coastal Regions—the region’s forests also support subsistence through local collection of medicinal plants, herbs, berries, nuts, mushrooms, and other non-timber forest products.

### 4.3.4. Social policy

According to the MONSTAT Report for 2022, the share of the total social protection expenditures in the Gross domestic product of Montenegro (GDP) in 2022 was 18.6%, which is decrease by 0.6 percentage points compared to 2021. Nominal growth of Gross domestic product of Montenegro (GDP) in current prices in 2022 was 19.6%, while the total social protection expenditures in 2022 increased by 16.3%. Data are presented in Table 2. In all social protection functions in Montenegro, excluding the function Sickness/Health care, the largest share of all social protection benefits was allocated to cash benefits. Data are presented in Table 3. The largest share of social protection benefits by function non-means tested in 2021 and 2022 refer to function Sickness/ Health care, function Disability and function Unemployment. Data are presented in Table 4. In 2022, 1106.56 million EUR was allocated for social protection receipts, which is an increase by 15.6 percentage compared to 2021.

Montenegro’s social protection system is relatively centralized, especially with respect to financing, planning and policy design. The Ministry of Labor and Social Welfare (MLSW) is responsible for policy design and implementation through the 13 Centers for Social Work (CSW), some of which are responsible through branch units for multiple of the 24 municipalities, and a network of public and non-public institutions providing social services.10 The Employment Agency of Montenegro (EAM) is an independent body under the supervision of the Ministry of Labour and Social Welfare which provides employment services and unemployment benefits to registered unemployed, while also designing and implementing active labor market policies (ALMPs). The independent Fund for Pension and Disability Insurance (PIO) administers pension payments and contributions, and individual information is collected regularly and efficiently by the Tax Administration for the benefit and use of all other involved agencies. The administration of social assistance, as well as the provision of social services, is the responsibility of CSWs. Apart from the state, municipalities can design, implement and finance their own programs and services such as the provision of free textbooks for children for extremely vulnerable families or homecare for elderly.

Table 16 Overview of the social protection in Montenegro

| Category | Benefits and programs |
| --- | --- |
| Cash transfers to support the poor, the vulnerable and persons with disabilities | - Material Support (MO) - Veterans and disability protection9 - Child allowance - Personal Disability Allowance - Care and Support Allowance - Guardian allowance for disability and care benefits - Old-age benefit for farmers - Transportation subsidy - Costs of nutrition in kindergarten - Benefit for a newborn child - Paternity benefit for registered unemployed - Mothers’ benefits - Funeral Costs and Electricity Subsidy - One-time cash assistance |
| Social services | - Support services such as day care, homecare, personal assistance, interpretation and translation into sign language etc. - Counselling therapy and social-education services - Accommodation services - Services for urgent interventions Other services |
| Pensions | Contributory pensions (state budget funds the deficit) - Old-age pension - Disability pension - Survivor’s pension |
| Employment and labor market programs | - Graduate Internship Program - Public Works - Adult learning and training - Training for work at the employer - Training for independent work - Stop the grey economy program - Unemployment Benefit Maternity / Paternity benefit |

Source: MONTENEGRO Social Protection Situational Analysis

### 4.3.5. Healthcare policy

The legal regulations in force for the healthcare sector provide to all citizens right to equal access to health services. Following the revision of the Law on Health Insurance in 2017, which entitled all residents to health benefits, almost 100% coverage of the population is now theoretically insured (WHO, 2022a). This does not include persons without regulated legal status.

De facto access in Montenegro remains unequable, especially in remote, rural and northern areas (WHO, 2021a). This is clearly visible in the high costs of medical transportation to higher-level institutions.

Until December 2021, healthcare protection was financed through health insurance contributions paid with salaries (primary) and through transfer of funds by the Government of Montenegro. As of January 2022, the state budget is the only public source of financing for healthcare. More specifically, the previous system of financing through contributions was abolished by amendments to the Law on Contributions to Compulsory Social Insurance, and the health system is financed entirely from the state budget.

In 2019, spending on healthcare in Montenegro was 8.33% of GDP. This is under the average of EU Member States (9.92%), but is similar to levels in other Western Balkan states such as Bosnia and Herzegovina (9.05%), North Macedonia (7.25%) and Serbia (8.67%) (WHO, 2022b). However, during 2020, at the midst of the COVID-19 pandemic, Montenegro substantially increased healthcare spending from 8.33% in 2019 to 11.4% of GDP during 2020. However, this happened in the context of a huge decline of the annual GDP growth rate from 4.1% to -15.33% from 2019 to 2020 (World Bank, online). This is contrary to developments in current health spending in other countries in the region and with the EU average, which remain stable or have increased slightly.

### 4.3. 6. Poverty

In accordance with the data published by the MONSTAT, at-risk-of-poverty rate in 2023 was 20.1%, which represents a share of persons whose equivalized disposable income is below at-risk-of-poverty threshold. These persons are not necessarily poor, they are just at higher risk to be, because their equivalized disposable income is below at-risk-of-poverty threshold. Comparing the basic at-risk-of-poverty rate and at-risk-of-poverty rate before including social transfers, in 2023, it shows that excluding social transfers from income affects the increase in the percentage of people who are at the risk of poverty, from basic 20.1% to 28.4%. If social transfers and pensions are excluded from income, then the at-risk-of-poverty rate is 40.9%.

At-risk-of-poverty or social exclusion rate (AROPE), as a percentage of people at risk of poverty and/or are severe materially and socially deprived and/or live in households with very low work intensity, in 2023 was 31.0%. Severe material and social deprivation rate, in 2023 was 12.3% and it shows the proportion of persons living in households that cannot afford at least seven out of thirteen material deprivation items.

At-risk-of-poverty threshold, set to 60% of the median of national equivalized disposable income, in 2023 at annual level was 3 367 euro for one-person household, while for household with two adult persons and two children under 14 years aged, was 7 070 euro. Relative at-risk-of-poverty gap represents a difference between the at-risk-of-poverty threshold and the median of equivalized income of the persons below the-risk-of-poverty threshold, and in 2023 was 28.0%.

According to the type of the household, in 2023 the highest at-risk-of-poverty rate was for persons in households consisted of one adult with at least one dependent child (44.7%), then persons in households consisted of two adults with three or more dependent children (36.5%).

According to age, in 2023, persons under 18 years old, were the most exposed to the risk of poverty (27.3%), as well as persons aged 18 to 24 (24.4%). The lowest at-risk-of-poverty rate was for persons aged 65 years and over (13.8%).

# 5. Analysis of Alternatives

Project options and alternatives are considered to establish the preferred or most environmentally sound, financially feasible and least impactful option for achieving project objectives. There are usually several options and alternatives to any project. The selection of an Option or Alternative is premised on several considerations, including the desirability/acceptability of the project, Government policy or inclinations on the project, as well as the socio-economic impacts of the project. Even within a selected option, there are usually several alternatives, including technology, location, etc. This section examines the options and alternatives that were considered for this project, and the basis on which the decision for the current option/alternative was selected.

The analysis of alternatives aims to:

- Identify and compare feasible options for fire protection intervention techniques, forest regeneration locations, silviculture tools and techniques and fuel load management interventions.

- Minimize adverse environmental and social impacts.

- Maximize technical, economic, and operational efficiency.

- Ensure compliance with national and international regulations and standards

Analysis of project alternatives could follow a multi-criteria framework approach that takes into consideration, economic criteria, such as capital costs, operational costs, revenue generation, and return on investment; environmental criteria, including impact on biodiversity, carbon sequestration, water quality, and soil health; Social criteria, such as job creation, community benefits, and stakeholder engagement; and regulatory, market volatility and technological risks criteria.

## 5.1 Do-Nothing / ‘Without Project’ Option

This option is usually considered when funds are unavailable to implement the project, or when there are unacceptably high adverse environmental and social impacts associated with the project, or when very high public opinion is against the project, or conditions of political instability. However, choosing not to conserve forests or prevent and manage wildfires could undermine the resilience of the Montenegro forest, ranked as having some the highest forest cover in Europe, but this is threatened by climate change. The gains made over the past decades could be reversed, leading to irreparable forest cover and biodiversity loss, environmental, economic, and social harm. Inaction is unacceptable because forests are essential for climate regulation, biodiversity, soil health, water quality, and supporting local communities and the global economy.

## 5.2 Technological Option

As poor SFM implementation can cause unsustainable logging, the project could consider modern technology like precision logging and automated processing to boost efficiency, cut waste, and enhance quality. While this will involve high initial capital investment and potential job loss, it will improve competitiveness, lower labor cost, and high output. Although the law prohibiting clear-cutting is observed in Montenegro, selective logging is applied, which allows for the preservation of the structure and quality of forests. The project could promote and strengthen selective logging. The formulation of protocols and procedures for reinforcing law enforcement and regulatory oversight to combat illegal logging, through measures such as expanding legal access to timber and fuelwood, improving supervision and documentation of authorized removals, thereby increasing the frequency and effectiveness of forest inspections will complement deployment of technology. The project will also explore regeneration felling, selective thinning, and intermediate silviculture at different stages of forest management. Regeneration felling at the final harvest method stage creates a new age class of trees, while intermediate silviculture methods like selective thinning, will be applied to established stands to improve the growth of remaining trees and the stand's overall health and composition prior to regeneration felling. The project will also consider Modernizing forest regeneration techniques, which can boost biodiversity and carbon sequestration. However, some modernization techniques could damage existing ecosystems or reduce genetic diversity . The success of these techniques depend on whether the participating communities have equitable access to land and participation in decision-making processes.

## 5.3 Circular Economy vs wastes Option

The project will transition the forest sector from prioritizing raw timber to a circular model that incorporates recycling, remanufacturing, and the production of engineered wood and bio-based materials with potentially higher value. The resulting reduced waste will competitively position the market through innovation, thereby contributing to sustainability goals. There is, however, the challenge of substantial capital investment in research and development, establishment of new markets and experimenting with new business models. Moreover, there is the problem of illegal waste disposal often seen in forested and peri-urban areas, undermining both ecosystem services and landscape values. Forest conservation is indirectly linked to waste management through the potential use of wood residues, biomass, and logging by-products as renewable energy sources, which can reduce the pressure on landfills and contribute to the circular economy. Sustainable forest management can provide cleaner streams of raw material for energy recovery, composting, and recycling, while simultaneously protecting forest ecosystems from pollution.

## 5.4 Market-based mechanisms:

The scheme will explore options for carbon credits, payment for ecosystem services, and certification schemes. This activity will also include restoration of selected forest land degraded by wildfire using appropriate techniques to increase resilience to climate change and other stressors (e.g. pests), as well as to increase biodiversity and ecosystem services post-fire. It could provide financial incentives for sustainable practices, diversify revenue streams beyond traditional timber sales, and meet growing consumer demand for certified products. There is, however, the issue of complexity in implementation, potential for market volatility, and potential lack of financial viability in certain areas compared to unsustainable practices. Municipalities could work with forestry authorities to align land use and construction with forest management plans. This involves including forest belts in urban planning, improving fire protection, and protecting ecosystem services that forests provide.

# 6.Potential Environmental and Social Risk Impacts and Standard Mitigation Measures

This chapter presents a summary of the potential positive and negative impacts and risks as well as mitigation measures for the planning/design and implementation phases, and the project components that have potential environmental and social issues.

## 6.1 Project Activities with Potential Environmental and Social Risks and Impacts

### 6.1.1 Potential Positive Impacts

The project is expected to bring several benefits to Montenegro including Increased economic benefits, sustainable climate resilience and forest management

The Montenegro Forests for Shared Prosperity Project (FSPP) aims to enhance the sustainable management, competitiveness, and climate resilience of the forestry sector in Montenegro. Through institutional strengthening, forest resource monitoring, sustainable forest management (SFM) practices, and targeted support to the wood industry, the Project is expected to generate substantial long-term environmental and socio-economic benefits. These include improved ecosystem health, increased carbon sequestration, reduced fire vulnerability, and strengthened institutional capacity to manage forests as a key national asset. However, the implementation of project activities involving physical interventions in natural or semi-natural environments may entail certain environmental and social (E&S) risks. The main environmental risks relate to localized soil disturbance, erosion, and vegetation clearance during small-scale forestry works and infrastructure improvements; waste generation, including e-waste and wood residues; air emissions and dust during construction or processing; and potential disturbance to biodiversity or water quality in sensitive forest areas. Social risks are considered secondary and manageable through appropriate engagement and occupational safety measures.

Overall, the Project’s environmental risk is classified as Moderate and the social risk as Moderate, reflecting the geographical spread of activities, the diverse implementing entities (MoAFW, new SOE, DBM, and local stakeholders), and the moderate institutional capacity for environmental management. All potential impacts are expected to be site-specific, temporary, and reversible, and can be mitigated through standard good practice measures defined in the Environmental and Social Management Framework (ESMF).

The ESMF establishes procedures for screening, assessing, and managing environmental and social risks in line with Montenegro’s legal framework and the World Bank’s Environmental and Social Framework (ESF), particularly ESS1 (Assessment and Management of Environmental and Social Risks and Impacts) and relevant complementary standards (ESS2–ESS10). It provides consistent guidance for environmental due diligence across all subprojects and ensures that appropriate mitigation, monitoring, and stakeholder engagement measures are integrated throughout the project cycle. This framework is designed to strengthen institutional accountability, promote environmentally responsible investments, and ensure the sustainable use and protection of Montenegro’s forest resources.

Table 17 Environmental risks and mitigation measures

| Component/Subcomponent | Phase | Environmental Risks/Impacts | Standard Mitigation Measures |
| --- | --- | --- | --- |
| Component 1: Strengthening Sector Governance and System Modernization |  |  |  |
| 1.1 Strengthening Policy Framework and Institutional Capacity | Preparation of policies and regulatory frameworks | No direct physical impacts expected. Indirect risk of inadequate integration of environmental safeguards into new legislation and policies. | Ensure environmental screening in policy formulation; integrate climate adaptation and biodiversity safeguards; align with ESS1, ESS3 and ESS6. |
| 1.2 Modernizing Forest Resources Measurement and Traceability | Development and deployment of FMIS, NFI, MRV, and ETTS systems | E-waste generation from outdated IT equipment; minor risk of soil/water contamination during installation of monitoring devices; increased energy demand for servers. | Adopt green procurement and energy-efficient IT systems; establish e-waste management procedures; ensure safe disposal or recycling through licensed operators. |
| 1.3 Supporting the Operationalization of the SOE | Preparation of business plan and establishment of operations | Potential increase in field activity leading to small-scale soil disturbance, vegetation clearing, and noise emissions during forest infrastructure setup. | Conduct environmental screening for operational sites; implement good forestry practices; apply erosion and dust control; minimize vegetation clearance. |
| Component 2: Supporting Sustainable Forest Management and Enhancing Climate Resilience |  |  |  |
| 2.1 Advancing Adoption of SFM Practices | Implementation of sustainable forest management measures | Temporary soil compaction, erosion, and disturbance to wildlife habitats from silvicultural operations; risk of non-native species introduction. Significant soil compaction and physical disturbance from regeneration felling. Over-exploitation, deforestation and land degradation from issuing licenses to private forest owners and operators | Use low-impact logging methods; restrict operations in breeding seasons; reforest with native species; monitor soil and water quality; enforce buffer zones near waterways. |
| 2.2 Promoting Forest Fire Resilience | Construction of firebreaks, installation of fire detection systems, post-fire restoration | Localized vegetation removal; soil disturbance during firebreak construction; risk of contamination from fuel or retardants; potential alteration of microhabitats. Biodiversity loss, invasive species, and air pollution through various fire protection measures. | Conduct site-specific EIAs; minimize ground disturbance; use biodegradable fire retardants; manage waste and fuel storage properly; apply ecosystem-based restoration post-fire. |
| Component 3: Improving Forestry Sector Competitiveness |  |  |  |
| 3.1 Establishing Wood Industry Upgrading Program | Grant and TA support for modernization of production facilities | Possible increase in emissions, dust, and wood waste from industrial upgrades; energy overuse; risk of unsafe waste disposal. | Include environmental criteria in grant eligibility; support adoption of cleaner technologies and energy-efficient machinery; promote circular economy and waste recycling. |
| 3.2 Establishing Wood Industry Center of Excellence (WICE) | Construction and operation of the Center | Land conversion on small scale; construction dust and noise; potential increase in energy use and solid waste during operation. air pollution from dust and combustion, waste generation from off-cuts and sawdust, and water contamination from log yards and chemical use by SMEs supported by the project. | Locate on already disturbed or urban land; enforce construction site management plan; adopt renewable energy solutions and waste segregation system. |
| 3.3 Facilitating Access to Finance | Implementation of financing schemes through DBM and PFIs | Indirect risk of financing environmentally non-compliant enterprises leading to deforestation, water/air pollution, or inefficient energy use. | Apply environmental eligibility screening; include environmental due diligence in loan assessment; monitor funded firms’ compliance with SFM and pollution control standards. |
| 4. Project Management, Monitoring, and Communication | Implementation of PIU functions, M&E and reporting | Minor indirect risk of poor environmental monitoring or oversight leading to non-compliance at subproject level. | Ensure effective M&E system for environmental safeguards; conduct periodic site audits; ensure timely reporting and corrective action plans. |

Table 18: Potential Social Risks/Impacts and Standard Mitigation Measures

| Subcomponent | Phase | Social Risks/Impacts | Standard Mitigation Measures |
| --- | --- | --- | --- |
| 1.1 Strengthening Policy Framework and Institutional Capacity | Preparation of policies and regulatory frameworks | Risk of limited stakeholder engagement in policy design and potential exclusion of vulnerable groups or local communities. | Ensure broad stakeholder consultations, including women, vulnerable groups, and local forest users; apply inclusive communication strategies; document feedback integration. |
| 1.2 Modernizing Forest Resources Measurement and Traceability | Development and deployment of FMIS, NFI, MRV, and ETTS systems | Potential exclusion of local users or field workers from capacity-building processes; digital literacy gaps among forest staff. | Provide training and outreach tailored to different user groups; ensure equitable access to new systems; apply transparent communication of data use and privacy protection. |
| 1.3 Supporting the Operationalization of the SOE | Preparation of business plan and establishment of operations | Workforce restructuring may affect employment security; uncertainty over new roles and responsibilities within the forestry sector. | Develop and implement a Labor Management Procedure (LMP); ensure fair employment practices; establish a grievance redress mechanism for workers. |
| 2.1 Advancing Adoption of SFM Practices | Implementation of sustainable forest management measures | Temporary restrictions on forest resource access may affect local livelihoods; potential inequitable participation in community forestry activities. Potential conflict from displacement of communities. Additional risks may arise from a limited labor influx of external workers involved in SFM operations, which may elevate exposure of local communities—particularly women and vulnerable groups—to SEA/SH risks. | Conduct social screening for each site; apply participatory forest management planning; provide compensation or livelihood restoration measures where access is restricted. Support for strengthening forestry regulations and communities. implement worker Codes of Conduct with explicit SEA/SH provisions; provide SEA/SH training for all workers; supervise worker–community interactions; and ensure availability of a confidential, survivor-centered SEA/SH reporting channel under the Project GRM. |
| 2.2 Promoting Forest Fire Resilience | Construction of firebreaks, installation of fire detection systems, post-fire restoration | Health and safety risks for workers and volunteers involved in firefighting and forest restoration; risk of exclusion of local communities from preparedness programs. Forest fire protection measures may interfere with traditional land management practices for which fire is used. Clearing of vegetation and creating buffer zones may impact ecosystems. Labor influx associated with fire protection and post-fire restoration works may increase SEA/SH risks within nearby communities, particularly in remote and sparsely populated areas. | Implement occupational health and safety (OHS) measures; ensure community awareness and training; include women and youth in resilience and restoration programs. Green firebreaks with low-cost and low-maintenance plants can reduce the ecological impacts of traditional firebreaks Implement sustainable silviculture ,biodiversity management plans. Require all workers engaged in fire-related activities to sign Codes of Conduct covering SEA/SH; conduct SEA/SH awareness training; enforce rules on worker conduct and interactions with communities; and ensure confidential SEA/SH-sensitive grievance reporting mechanisms. |
| 3.1 Establishing Wood Industry Upgrading Program | Grant and TA support for modernization of production facilities | Unequal access to grants and TA for small or informal enterprises; potential labor and OHS risks in SMEs. | Develop transparent grant selection criteria; provide targeted outreach to small enterprises; enforce OHS and labor compliance as grant eligibility conditions. |
| 3.2 Establishing Wood Industry Center of Excellence (WICE) | Construction and operation of the Center | Temporary disruption to nearby communities from construction noise or traffic; risk of unequal access to training opportunities. Gender and vulnerable group exclusion. Construction-related labor influx may introduce SEA/SH risks for nearby communities, particularly women and youth. | Apply community communication plan before and during construction; ensure inclusive access to training and research programs for women and youth. Enforce contractor Codes of Conduct; deliver mandatory SEA/SH training for all construction workers; apply strict supervision and protocols for worker–community interactions; and establish a confidential and survivor-centered mechanism for SEA/SH complaints through the Project GRM |
| 3.3 Facilitating Access to Finance | Implementation of financing schemes through DBM and PFIs | Possible exclusion of smallholders or women-led businesses; limited understanding of environmental and social standards among borrowers. | Integrate social inclusion criteria into credit lines; provide capacity building for PFIs and borrowers on E&S standards and grievance procedures. |
| 4. Project Management, Monitoring, and Communication | Implementation of PIU functions, M&E and reporting | Risk of inadequate stakeholder communication or low transparency in decision-making; weak grievance handling. | Ensure timely and accessible information sharing; maintain a functional GRM; monitor social performance through regular reporting and stakeholder feedback. |

Table 19: Cross-Cutting E&S Risk Management and Mitigation Tools

| Tool / Instrument | Application |
| --- | --- |
| Environmental and Social Management Framework (ESMF) | Provides overall guidance for identifying, screening, and managing environmental and social risks for all subprojects. Defines classification, mitigation, and compliance with the World Bank ESF and national law. Serves as a reference for preparing ESMPs, RPF, LMP, and SEP. |
| Environmental and Social Management Plans (ESMPs / ESMP Checklists) | Developed for site-specific works (e.g., forest roads, depots, nurseries). Include mitigation, monitoring, responsibilities, and cost estimates; checklists are used for low-risk activities. |
| Contractor Environmental and Social Management Plans (CESMPs) | Prepared by contractors prior to mobilization, detailing implementation of ESMP measures (dust, noise, waste, worker safety). Must be approved by the PMT before works start. |
| Stakeholder Engagement Plan (SEP) | Ensures inclusive, transparent stakeholder participation. Defines procedures for consultation, disclosure, feedback, and a functional, accessible Grievance Redress Mechanism (GRM). |
| Labor Management Procedures (LMP) | Establish fair and safe labor practices under ESS2. Cover working conditions, non-discrimination, prevention of child and forced labor, OHS, and a worker GRM. |
| Resettlement Policy Framework (RPF) | Applies when project activities involve minor land acquisition or temporary use of land. Provides principles and steps for site-specific Resettlement Action Plans (RAPs) to ensure compensation and livelihood restoration in line with ESS5. |
| Resettlement Action Plans (RAPs) | Prepared where land acquisition or restrictions on land use are confirmed. Identify affected persons, compensation measures, and grievance procedures in line with the RPF and ESS5. |
| Waste Management Plans (WMP) | Define handling, segregation, storage, transport, and disposal of hazardous and non-hazardous waste from construction and operation, particularly for nurseries, workshops, and maintenance facilities. |
| Occupational Health and Safety (OHS) / Health and Safety Management Plans | Specify health and safety procedures for workers and nearby communities. Include PPE requirements, emergency response, and incident reporting. Mandatory for all contractors and implementing agencies. |
| Traffic Management Plans | Prepared for construction or forest operations involving machinery and vehicles. Ensure safety of workers and local communities through routing, signage, scheduling, and speed control. |
| Chance Finds Procedures | Define steps to be taken if cultural heritage or artifacts are discovered during excavation or construction. Include stop-work protocols, notification of authorities, and documentation procedures per ESS8. |
| Emergency Preparedness and Response Plans | Provide protocols for managing accidental events (fires, fuel spills, landslides) that may impact worker or community safety. Include coordination with local emergency services and training for response teams. |
| Biodiversity Management Plans (BMPs) | Prepared when screening identifies potential impacts on sensitive habitats, ecosystems, or species. Include mitigation, restoration, and monitoring actions consistent with ESS6 and national biodiversity strategies. |
| Environmental and Social Commitment Plan (ESCP) | Binding agreement between the Government of Montenegro and the World Bank defining all environmental and social commitments, including preparation of instruments, staffing, reporting, and monitoring requirements throughout implementation. |

### 6.1.2. Overview of Environmental Risks and Mitigation Measures in Planning and design phase, Implementation phase and Operational phase

The Montenegro Forests for Shared Prosperity Project (FSPP) aims to strengthen forest governance, enhance forest management systems, improve fire prevention capacity, and support value-chain competitiveness, thereby contributing to the long-term sustainability and resilience of Montenegro’s forest landscapes. The Project is expected to bring significant environmental and climate co-benefits through improved forest resource management, ecosystem restoration, and institutional strengthening. However, certain environmental risks may arise during the planning, implementation, and operational phases of project-supported activities. The environmental risk of the Project is rated as Moderate primarily due to the dispersed nature of activities, the need for multi-agency coordination, and limited institutional capacity for environmental management at the local level. Nevertheless, all potential impacts are expected to be site-specific, temporary, and reversible, and can be mitigated through the application of standard environmental management practices.

Typical risks and impacts across phases include:

Planning and design phase: insufficient integration of environmental considerations into technical designs; inadequate environmental screening or site selection in erosion-prone, fire-sensitive, or biodiversity-rich areas.
Implementation phase: minor physical interventions such as rehabilitation or improvement of existing forest roads, depots, nurseries, or installation of fire detection systems and monitoring equipment may result in localized soil erosion or compaction, dust, noise, or emissions from machinery; improper waste or fuel management; or temporary disturbance of vegetation and habitats. No large-scale construction, land conversion, or irreversible impacts are expected.
Operational phase: inadequate maintenance of rehabilitated infrastructure may cause drainage or sedimentation issues; poor waste management, including e-waste from monitoring systems, could lead to contamination; and increased human access might disturb local wildlife if not properly managed.

These risks are managed through the Project’s Environmental and Social Management Framework (ESMF), which defines screening procedures, exclusion criteria, and requirements for site-specific Environmental and Social Management Plans (ESMPs) or simplified ESMP Checklists for lower-risk activities. Contractors will prepare Contractor ESMPs (CESMPs) prior to mobilization to operationalize mitigation measures such as erosion control, waste segregation, noise suppression, and spill prevention.

Additional instruments—including Waste Management Plans, Biodiversity Management Plans, Traffic and Occupational Health and Safety (OHS) Plans, and Emergency Preparedness Plans—will be applied as needed. Environmental monitoring will focus on soil stability, water quality, habitat conditions, and emissions, ensuring that corrective actions are taken promptly when required.

This framework ensures that all FSPP activities are implemented in compliance with Montenegro’s environmental legislation and the World Bank’s Environmental and Social Framework (ESF), particularly ESS1 (Assessment and Management of Environmental and Social Risks and Impacts), ESS3 (Resource Efficiency and Pollution Prevention), and ESS6 (Biodiversity Conservation and Sustainable Management of Living Natural Resources). This approach supports environmentally sound, climate-resilient, and socially responsible forest management practices across Montenegro.

Table 20 Environmental Risks and Measures-Planning phase

| E&S Aspect | Mitigation Measures |
| --- | --- |
| Site selection and environmental screening | Apply the screening procedure defined in the ESMF to identify environmental sensitivity (e.g., erosion-prone or biodiversity-rich areas). Exclude protected areas and high biodiversity value sites. Ensure alignment with national spatial planning instruments and environmental regulations. |
| Integration of environmental considerations into design | Incorporate environmental mitigation and sustainability criteria into all technical designs and feasibility studies. Integrate erosion control, drainage management, and waste minimization measures in site planning. Ensure that design documents reflect applicable ESS1, ESS3, and ESS6 requirements. |
| Water and soil conservation | Avoid locating project-supported activities on steep slopes or near water bodies without appropriate buffer zones. Design drainage systems to minimize erosion and sedimentation. Promote soil stabilization through native vegetation cover where appropriate. |
| Biodiversity and habitat protection | Conduct baseline assessment of habitats and species before selecting sites. Avoid disturbance of critical habitats and migration corridors. Include provisions in design for vegetation protection, native species planting, and ecological connectivity maintenance. |
| Resource efficiency and energy use | Integrate energy-efficient technologies and materials in equipment procurement and facility design. Promote the use of renewable energy sources (e.g., solar panels for monitoring systems). Ensure energy management considerations are reflected in the Technical Design Specifications. |
| Waste management and e-waste prevention | Design waste handling and storage areas in accordance with the Waste Management Law. Plan for proper collection, segregation, and disposal of non-hazardous and hazardous waste through licensed operators. Integrate provisions for the safe management of e-waste from IT and monitoring equipment. |
| Occupational and community health and safety (OHS) | Integrate occupational health and safety measures into the design of project activities. Ensure that designs account for safe access, emergency exits, and secure equipment layout. Plan awareness programs and safety procedures for field staff and contractors in line with ESS2 and national OHS regulations. |
| Fire prevention and climate resilience | Include fire prevention and management measures in planning and design, particularly in fire-prone areas. Ensure adequate spacing, access roads, and firebreaks are integrated into forest management and landscape planning. Incorporate climate adaptation and resilience considerations (e.g., drought-tolerant native species, water-saving technologies). |
| Stakeholder engagement and disclosure | Ensure early and meaningful stakeholder consultations are conducted during planning and design. Document stakeholder feedback and integrate relevant inputs into design documents. Ensure transparency and accessibility of environmental information through public disclosure mechanisms as outlined in the SEP. |
| Institutional responsibilities and monitoring arrangements | Define roles and responsibilities for environmental management in design documents. Ensure that environmental monitoring indicators and reporting lines are incorporated into the project’s Monitoring and Evaluation (M&E) system. Provide for environmental supervision and capacity-building measures within the PIU and implementing agencies. |

Table 21: Environmental Risks and Mitigation Measures — Implementation and operational phase

| Subcomponent / Activity | Risks and Impacts | Mitigation Measures |
| --- | --- | --- |
| Rehabilitation or improvement of forest roads, depots, and nurseries | Temporary increase in dust, noise, and emissions; minor soil erosion or compaction; improper disposal of construction waste; localized vegetation disturbance. | Apply ESMP or ESMP Checklist; ensure erosion and dust control; schedule works outside rainy periods; segregate and dispose waste properly through licensed operators; implement CESMPs with OHS and traffic management measures. |
| Installation of monitoring and fire detection systems (FMIS, MRV, ETTS) | Localized soil disturbance and minor vegetation clearing; potential generation of e-waste from packaging or replaced devices | Minimize vegetation clearing; ensure safe installation and cable routing; use recyclable materials; plan for e-waste collection and disposal through authorized facilities. |
| Post-fire rehabilitation and reforestation activities | Disturbance of soil and microhabitats; introduction of non-native or invasive species; risk of soil erosion during planting operations. | Use native species for reforestation; conduct activities outside heavy rainfall periods; stabilize soil with mulching or contour planting; prohibit invasive species; monitor vegetation recovery. |
| Construction and equipment setup for the Wood Industry Center of Excellence (WICE) | Dust and noise during construction; generation of construction waste; minor soil and water contamination from spills or improper storage of materials. | Prepare and implement CESMP; restrict works to daylight hours; ensure waste segregation; provide spill kits and secondary containment for fuels and lubricants; maintain machinery in good condition. |
| Operation of rehabilitated infrastructure (roads, depots, nurseries) | Inadequate maintenance causing erosion, sedimentation, or drainage blockage; accumulation of solid waste; fuel or oil leaks from machinery. | Implement routine maintenance and inspection schedule; clear drainage channels; manage and dispose of waste properly; ensure spill prevention and containment measures. |
| Use and maintenance of IT and monitoring systems (FMIS, MRV, ETTS) | Energy consumption and generation of electronic waste; risk of improper data storage or disposal of obsolete equipment. | Use energy-efficient devices; establish e-waste collection and recycling protocol; ensure environmentally sound disposal of obsolete hardware; maintain system security and data protection. |
| Operation of the WICE and SME facilities supported through grants | Potential increase in waste generation, air emissions, and energy consumption from upgraded production; improper handling of wood residues or chemicals (paints, adhesives). | Integrate environmental eligibility criteria into grants; promote cleaner production technologies; ensure waste segregation and recycling of wood residues; enforce OHS and pollution control standards. |
| Forest management and field operations under SOE and local units | Soil erosion and compaction; disturbance to wildlife; fire risk from field activities or equipment use; pollution from fuel storage or vehicle maintenance. | Implement Sustainable Forest Management (SFM) plans; avoid sensitive habitats; ensure fire prevention training and equipment; store fuels in contained areas; conduct regular environmental supervision. |
| Long-term monitoring, evaluation, and maintenance | Neglect of environmental monitoring leading to unmitigated impacts; poor recordkeeping or delayed corrective actions. | Ensure continuous environmental monitoring and reporting as defined in the ESMF; maintain oversight by PIU and environmental specialists; conduct periodic environmental audits and update mitigation measures as needed. |

Table 22: Summary of Environmental and Social Standards (ESS) Risks and Mitigation Measures (FSPP)

| ESS Standard | Key Risks | Proposed Mitigation |
| --- | --- | --- |
| ESS1 – Assessment and Management of Environmental and Social Risks and Impacts | Potential localized environmental impacts due to small-scale rehabilitation works, installation of monitoring systems, and post-fire restoration activities. Limited capacity for E&S risk management across multiple institutions. | Apply ESMF procedures for screening, classification, and risk management. Prepare site-specific ESMPs or ESMP Checklists. Strengthen PIU capacity with environmental and social specialists. Conduct regular monitoring and reporting. |
| ESS2 – Labor and Working Conditions | Occupational health and safety (OHS) risks for workers during field and maintenance activities; possible gaps in labor conditions for contracted workers. | Implement Labor Management Procedures (LMP). Ensure compliance with national labor laws and ESS2. Provide PPE, safety training, and maintain a worker Grievance Redress Mechanism (GRM). |
| ESS3 – Resource Efficiency and Pollution Prevention and Management | Pollution from machinery operation, waste generation (including e-waste), and emissions from vehicles or equipment. Inefficient resource use (energy, materials). | Adopt resource-efficient technologies; manage waste through licensed operators; establish e-waste recycling program; use energy-efficient devices and renewable energy where feasible. |
| ESS4 – Community Health and Safety | Noise, dust, and increased vehicle movement during small-scale works. Community health and safety may also be affected by workers coming from outside the area. To reduce SEA/SH risks, workers will sign Codes of Conduct, receive SEA/SH awareness training, and be required to follow strict rules of conduct when interacting with communities. All incidents will be addressed through a confidential, survivor-centered GRM. Risks from fire management operations and use of heavy machinery near communities. | Implement CESMP with traffic and community safety plans. Conduct community awareness sessions on fire prevention and project safety. Establish emergency response procedures. Ensure contractors maintain updated worker registers and enforce controlled access to work sites and nearby community areas. Appoint a community liaison focal point to monitor worker–community interactions and respond to concerns. Coordinate with local service providers and institutions to ensure survivor-centered SEA/SH response pathways are functional and accessible. |
| ESS5 – Land Acquisition, Restrictions on Land Use and Involuntary Resettlement | Possible temporary access restrictions to forest resources or small-scale land use for infrastructure upgrades. | Apply Resettlement Policy Framework (RPF) and prepare site-specific Resettlement Action Plans (RAPs) if required. Ensure livelihood restoration and stakeholder consultation. |
| ESS6 – Biodiversity Conservation and Sustainable Management of Living Natural Resources | Disturbance to habitats and species from field operations, forest road maintenance, or post-fire planting. Risk of introducing non-native species. | Conduct biodiversity screening before site selection. Use native species for restoration. Avoid critical habitats. Implement Biodiversity Management Plans (BMPs) and monitoring programs. |
| ESS8 – Cultural Heritage | Low likelihood of encountering cultural or historical artifacts during small works or excavation. | Implement Chance Finds Procedures (CFP) across all project sites. Train contractors on procedures and ensure prompt reporting to authorities if artifacts are discovered. |
| ESS10 – Stakeholder Engagement and Information Disclosure | Potential gaps in stakeholder participation and information flow, particularly for rural communities and small forest users. | Implement Stakeholder Engagement Plan (SEP). Ensure inclusive consultations, regular disclosure of information, and maintain functional project-level GRM. |

### 6.1.3 Special Assistance for Vulnerable PAPs

Disproportionately impacted groups who are mostly vulnerable due to their distinct livelihood strategies, ways of living and other socio-economic dynamics. For these individuals/groups, in addition to resettlement, compensation and livelihood restoration programs, additional mitigation mechanisms are required. i.e. assistance in resettlement and compensation payment procedure, assistance in moving properties and identifying the resettlement plot (as needed), assistance with access to project benefit, assistance during the post-resettlement period and health care if required, particularly during any moving and transition periods, for persons that may be affected by physical works within the forests. The Project will consider, but not limited to the following mechanisms.

- The continuous awareness creation efforts of the project will ensure constant information flow especially to vulnerable groups including poor women, elderly and persons with disabilities. Hold separate focused group discussions (FGDs) with women and other vulnerable groups identified by the E&S assessment.

- Promote transparent procedures and avoid discrimination in recruitment process, ensure terms of employment and working conditions to include protection for vulnerable workers (e.g. women and persons with disabilities).

- Contractors to adapt the Labor Management Procedures to ensure availability of clear recruitment protocols, written employment contracts with clear working conditions, protection of vulnerable workers, prohibit the use of forced and child labor, availability of Grievance Mechanism for workers complaints etc.

- Engage CBOs and NGOs who are active in the Project implementation areas to help provide outreach programs and tailored programs to vulnerable groups and individuals.

- A systematic and functional GRM should be adopted to address the concerns of aggrieved parties (PAPs, vulnerable groups including women, gender-sensitive issues, workplace concerns and community concerns).

Moreover, the project will work on suitable design and standards to address the needs of girls, women, boys, and people with disabilities (such as brails, radio broadcasts, using sign languages, etc.).

By enforcing gender sensitive infrastructure, FSPP will emphasize gender and social inclusion, and services for women, girls and disability conditions.

Table 23: Potential Environmental and Social Risks and Impacts and Mitigation Measures during the design, construction and operations phases

## 6.2 Special Assistance for Vulnerable PAPs

Disproportionately impacted groups who mostly vulnerable due to their distinct livelihood strategies, ways of living and other socio-economic dynamics. For these individuals/ groups, in addition to resettlement, compensation and livelihood restoration programs, additional mitigation mechanisms are required. i.e. assistance in the compensation payment procedure, assistance in moving properties and identifying the resettlement plot (as needed), assistance in building activities, assistance during the post-resettlement period and health care if required, particularlyduring the moving and transition periods. The Project will consider, but not limited to the following mechanisms.

- The continuous awareness creation efforts of the project will ensure constant information flow especially to vulnerable groups including poor women, elderly and persons with disabilities. Hold separate focused group discussions (FGDs) with women and other vulnerable groups identified by the E&S assessment.

- Promote transparent procedures and avoid discrimination in recruitment process, ensure terms of employment and working conditions to include protection for vulnerable workers (e.g. women and persons with disabilities).

- Contractors to adapt the Labor Management Procedures to ensure availability of clear recruitment protocols, written employment contracts with clear working conditions, protection of vulnerable workers, prohibit the use of forced and child labor, availability of Grievance Mechanism for workers complaints etc.

- Engage CBOs and NGOs who are active in the Project implementation areas to help provide outreach programs and tailored programs to vulnerable groups and individuals.

- A systematic and functional GRM should be adopted to address the concerns of aggrieved parties (PAPs, vulnerable groups including women, gender-sensitive issues, workplace concerns and community concerns).

Moreover, the project will work on suitable design and standards for the proposed forest  and fire management systems  will address the needs of girls, women, boys, and people with disabilities (such as brails, radio broadcasts, using sign languages, etc.).

By enforcing gender sensitive infrastructure, FSPP will emphasize gender and social inclusion, and services for women, girls and disability conditions.

# 7. PROJECT IMPLEMENTATION SET-UP

The Ministry of Agriculture, Forestry and Water Management will lead the Project as the main implementing agency. It will set strategic direction, coordinate with other institutions, and oversee implementation to align with national forestry policies. The Directorate for Forest Management will manage operational and technical aspects, planning and monitoring project activities, provide regulatory guidance, and organize field efforts. The Project Implementation Unit (PIU) and Directorate will collaborate with: (1) the new State-Owned Enterprise, focusing on forest management operations; (2) the Forest Administration, overseeing sustainable forest management and compliance; (3) the Ministry of Interior, supporting forest fire prevention and response; and (4) the Institute for Multi-Disciplinary Studies, developing workforce and innovation programs for Montenegro’s wood industry.

A Project Implementation Unit (PIU) will be set up within the Ministry of Agriculture, Forestry and Water Management to manage all Project activities efficiently and on schedule. The PIU team will include:

- a Project Manager overseeing coordination and M&E,

- an Administrative Assistant handling logistics, procurement, and finance,

- a Social Specialist ensuring inclusive, socially sustainable practices aligned with ESF documents,

- an Environmental Specialist integrating risk measures and compliance,

- a Grant Manager responsible for managing grants and activities under Component 3,

- and a part-time Communications & M&E Specialist supporting project communication, engagement, knowledge sharing, and results tracking.

Project implementation in Montenegro requires strong inter-institutional coordination, as responsibilities for environmental management are distributed among several ministries, agencies, and local governments. Effective cooperation between the Ministry of Tourism, Ecology, Sustainable Development and Northern Region Development, the Environmental Protection Agency, the Ministry of Agriculture, Forestry and Water Management, and local self-governments is essential for the success of environmental and infrastructure projects. A Project Steering Committee (PSC), led by the Minister of Agriculture, Forestry and Water Management, will oversee project coordination and implementation. The PSC will review and approve work plans and budgets, align project activities with national policies, resolve inter-agency issues, and monitor project progress. By involving various institutions and stakeholders, the PSC will promote accountability and transparent governance. Regular meetings will ensure strategic guidance and efficient, coordinated execution of all project components.

# 8.Environmental and Social Monitoring

The aim of monitoring is to determine whether interventions have been effective in dealing with the negative impacts, whether further interventions are needed, or whether monitoring is to be extended in some areas. Monitoring indicators will be very much dependent on specific project contexts. The PIU, designated Environmental and Social Specialists, will be responsible for overall monitoring and reporting on compliance with the ESMF ensuring that the subproject is screened, their environmental and social instruments are prepared, cleared and disclosed prior to approval. The PIU will also ensure that contractors executing the work are implementing the specific ESMP for the subprojects that require it and submit reports on ESMP implementation as required.

The PIU will keep records of complaints received, resolved, accidents, and other environmentally or socially related topics of relevance and importance for this project. This data will be reflected in biannual reports on safeguard compliance to be furnished to the Bank. The Bank will conduct periodic audits of the projects and access documented information.

As per the commitment specified in the ESCP, any project-related fatalities or serious injuries will be reported to the World Bank within 48 hours after learning of the incident and in accordance with ESCP obligations and World Bank procedures. All employers under this project are therefore required to maintain insurance for workers and third-party liability. The monitoring indicators with verified indicators and responsible institutions are as in Table xxxx

The actual impacts caused by project implementation should be closely monitored during the construction and operation of the project to examine the effectiveness of the mitigation measures. The goals of monitoring are to measure the success rate of the project, determine whether interventions have resulted in dealing with negative impacts, and whether further interventions are needed, or monitoring is to be extended in some areas. Table 20 describes the Monitoring and Evaluation Framework for the ESMF and the Environmental and Social monitoring and reporting requirements in table 12.

Table 24Monitoring and Evaluation Framework for ESMF

| S/N | PHASE | INSTITUTION RESPONSIBLE | PERFORMANCE INDICATORS | PERIOD TO BE CONDUCTED |
| --- | --- | --- | --- | --- |
| 1 | PREPARATION/ PRE-CONSTRUCTION PHASE | PIU /independent consultant Monitoring by government’s regulatory agencies | Number/% of Staff/ Consultants/ Contractors/ and forest officers who received training on ESMF, ESMP, environmental, and social accountability training, Number of Subprojects with environmental and social screening checklist filled, reviewed and approved ESMP, and other site-specific plans including ESIA, RP, etc prepared. Establishment and functionality of GRM. | Before commencement of any works and contractor mobilization to site |
| 2 | CONSTRUCTION PHASE | PIU/Contractor/ Independent Consultant | I Number/ % of Staff/ Consultants/ Contractors/ forest officers/ community representatives who received training on ESMP, environmental, social accountability training Grievance redress mechanism operational and effective (no. of grievances logged, revolved, pended, etc.) GRC established and operational. Contractor’s staff sensitized Gender base violence (GBV). # of Contractor staff who have signed CoC CESMP implemented Stakeholder consultations undertaken with project affected people. Standard operating procedures for best environmental practices established Waste management plan developed and implemented Emergency Response Plan prepared and implemented. | During works implementation |
| 3 | OPERATION AND MAINTENANCE PHASE | Contractor The implementing agencies involved in the Project | Are environmental and social monitoring mechanisms in place Is disaster and emergency mechanism in place? Training provided to E&S staff of IAs on ESMP Traffic management plan implemented # of cases of traffic accidents ESMP measures being implemented. No. of complaints recorded, resolved, pending, from communities | Operational and Maintenance phase to project closure |
| 4 | DECOMMISIONING PHASE | The implementing agencies involved in the Project Ministry of Agriculture, Forestry and Water Management/ Contractor | Decommissioning plan been conducted. Disaster and emergency mechanism in place Standard operating procedures for best environmental practices established. # of complaints registered, resolved, referred, etc. from communities. | During decommissioning of the project |

## 8.1Environmental and Social Management Procedures and Implementation Arrangements

The Environmental and Social Specialists of the PIU are responsible for conducting E&S monitoring of E&S implementation by construction contractors, including consultations and feedback from relevant stakeholders involved as per principles and requirements prescribed in the project’s ESMF including RF, LMP and SEP. Regular E&S monitoring and reporting requirements are summarized in Table 12.

Table 12: Environmental and Social Monitoring and Reporting Requirements

| No | Report Prepared by | Submitted to | Frequency of Reporting |
| --- | --- | --- | --- |
| 1 | Contractors | PIU | Once before construction commences and monthly thereafter |
| 2 | Supervision consultant | PIU | Monthly, as soon as possible, as required |
| 3 | Environmental and Social Officers | PIU | Monthly, as soon as possible, as required |
| 4 | PIU | WB | Quarterly reports, in line with the ESCP including: (i) Status of preparation and implementation of E&S documents required under the ESCP. (ii) Summary of stakeholder engagement activities carried out as per the Stakeholder Engagement Plan (iii) Complaints submitted to the grievance mechanism(s), the grievance log, and progress made in resolving them (iv)E&S performance of contractors and subcontractors as reported through [monthly] contractors’ and supervision firms’ reports. Number and status of resolution of incidents and accidents Bi-annually for M&E report |

In addition to the regular reporting schedule, in line with the ESCP, reporting arrangements are needed for serious incidents, causing death, injury, or other major problems. The PIU must notify the World Bank within 48 hours of learning about the incident, including the complete investigation form, complete Root Cause Analysis (proportionate to the severity of the incident), and undertake immediate mitigation measures as well as medium- and longer-term corrective actions to prevent the incident from reoccurring.

## 8.2 Proposed Training and Capacity Building

### 8.2.1 Capacity Assessment

The FSPP has the objective of improving the sustainable management of forest resources and enhancing the competitiveness of the forest industry in targeted project areas in Montenegro. The project is implemented by the Ministry of Agriculture, Forestry and Water Management with a dedicated Project Implementation Unit (PIU) responsible for overall project management, including procurement, financial management, monitoring and evaluation, and environmental and social (E&S) safeguards management. The PIU will adopt the procedures for E&S screening, stakeholder engagement, GRM, and compliance monitoring, in line with the ESMF. The PIU’s engagement in capacity building and adaptive management as outlined in the ESCP demonstrates a commitment to continuous improvement in ESF implementation.

Training will include gender aspects and proportionate capacity building plans (human resource, soft skills training, and logistics). The PIU and implementing partners shall establish an E&S risk management in accordance with the ESF.

Successful implementation of the Project will depend, among others, on the effective implementation of the environmental and social risk management measures outlined in this ESMF. Training and capacity building will be necessary for the key stakeholders in order to ensure effective implementation of the ESMF, LMP, RF, SEP, and other environmental and social documents. An initial training approach is outlined in the table below. To the extent possible, training on environmental and social risk management will be integrated into the project cycle and operational procedures. Table 14 presents the proposed training and capacity building approach with an estimated budget of two hundred ten thousand United States Dollars only US$210,000.

Table 25: Proposed training and Capacity Building Approach

| Training Required |  | Who to train | Responsible Party | Budget (US$) |
| --- | --- | --- | --- | --- |
| World Bank ESF and ESSs training |  | PIU | to be agreed with WB | 15,000 |
| Deep dive training on resettlement and ESF |  | PIU | to be agreed with WB | 15,000 |
| OHS Management |  | PIU | to be agreed with WB | 10,000 |
| Training themes within Wood Processing and Forestry sectors: - Project E&S Screening - GBV/SEA/SH awareness, monitoring, and reporting - OHS Management/ESMP Training for Contractors - Waste Management/Hazardous material management - Emergency Preparedness and Response - Security Risk and Awareness - Biodiversity Management - Chance finds procedures - Incident investigation and reporting - E&S monitoring and reporting - Grievance redress mechanism - Stakeholder engagement and project communications - Deep dive training on resettlement and ESF. - SEA/SH Sensitization, monitoring and reporting |  | PIU | PIU supported by consultants as necessary for one year | 30,000 |
|  | PIU /Contractors/sub-contractors |  | Refresher year 2 | 20,000 |
|  |  | Refresher year 3 |  | 10, 000 |
|  |  | Refresher year 4 |  | 10,000 |
|  |  | Refresher year 5 |  | 10,000 |
| Environmental, Social, resettlement and OHS audit (midterm of the project and end of the project) |  | PIU | PIU | 60,000 |
| Forest and fire management systems and O&M |  | PIU | PIU supported by consultants as necessary |  |
| Climate risks, coastal resilience and disaster preparedness |  | PIU | PIU supported by consultants as necessary |  |
| Total |  |  |  | 180,000 |

N.B. Project sources should be available to train E&S staff.  Budget will not include staff salaries for environmental Specialist, social specialist and GBV/SEA/SH specialist staff the operating cost of the GRM, consultation of stakeholders, and preparation and implementation of the GBV/SEA/SH Prevention and Response Action Plan.

## 8.3 Estimated Budget

The project will allocate budget for the preparation of instruments, such as ESIA, ESMP, RP and other site-specific instruments as required. The following table lists estimated cost items for the implementation for the ESMF, which have been included in the overall project budget.

Table 26.ESMF Implementation Budget

| No | Activity | Indicative Cost (US$) |
| --- | --- | --- |
| 1 | Disclosure outreach consultations for ESF | as defined in the SEP |
| 2 | Hiring 1 social + 1 Environmental safeguard specialists in the PIU (full time) per year | 120,000 |
| 3 | Capacity Building and Training Program (presented in table 14) | 210,000 |
| 4 | Environmental Screening and Preparation of ESIAs/, ESMPs, BMP, Environmental and Social Audits other site-specific plans and disclosure, if needed through external hire | 50,000 |
| 5 | Resettlement Plans (RPs), RAP implementation other site-specific plans and disclosure | undetermined |
| 6 | Preparation and implementation of the GBV/SEA/SH Prevention and Response Action Plan | 20,000 |
| 7 | Cost of obtaining clearances or permits | 5,000 |
| 8 | Operating cost of the GRM | as defined in the SEP |
| 9 | Consultation of stakeholders |  |
|  | Contingency (5%) | 63,000 |
|  | TOTAL | 468.000 |

# 9.Stakeholder Engagement, Disclosure, and Consultations

A separate Stakeholder Engagement Plan (SEP) has been prepared for the Project, based on the World Bank’s Environmental and Social Standard 10 (ESS 10) on Stakeholder Engagement. The SEP can be found on the Project I website and WB external website.

The timing and methods of engagement with stakeholders throughout the life cycle of projects will be described in SEP. Public consultation activities (including public consultation meetings) will be carried out as defined in SEP to be prepared. Records of meetings and consultations with stakeholders will be included in the draft and final ESA instruments.

This ESMF, with annexes on the RF and LMP as well as the SEP and the Environmental and Social Commitment Plan (ESCP) that have been prepared for this project, have been disclosed in draft form stakeholder consultations on the stated websites.

Stakeholder Consultation Undertaken During Project Preparation and E&S Instruments

Stakeholder consultations were undertaken under the FSPP. The subsections below capture summarized findings from this stakeholder engagement activity.

Stakeholder Consultation: Project Preparation phase

Stakeholder engagement workshop was held ## the PIU Ministry of Agriculture, PIU and the World Bank, gathering ## participants representing all relevant institutions. It had the following objectives: (i) Consult key people, the PIU as well as other key partners and stakeholders to inform about the preparation of the proposed program; (ii) Discuss the preliminary content of the FSPP, solicit stakeholder inputs and fill requisite gaps; (iii) Present the program preparation timeline.

Appraisal Meeting

As part of the Project preparation, the Task Team has conducted a pre-appraisal meeting for FSPP. The meeting involved the FSPP PIU and officials of the Ministry of Agriculture, Forestry and Water Management. It had the following objectives: to ensure key aspects of the project design are covered including discussions on the Environmental and Social aspects of the project and to go over the key documents, including PAD, and ESCP, components and activities relevant to Montenegro

Stakeholder Consultation during E&S Instruments Preparation

Stakeholder engagements during the E&S instruments preparation were held between #, 2025, co-led by the Ministry of Agriculture forestry and Water management and the World Bank and includes the relevant government institutions associated with the project. The consultations had the following objectives: (i) consult key relevant institutions, the agriculture forestry and Water management and existing PIU of the Project as well as other stakeholders to inform about the preparation of the proposed project; (ii) discuss the preliminary content of the FSPP, solicit stakeholder inputs and fill requisite gaps.

Disclosure

The World Bank ESF / ESS require continuous engagements with stakeholders during the preparatory and implementation stages of all projects.  After incorporating stakeholders’ views in all environmental reports for projects, they are made available to project affected groups, local NGOs, and the public at large. Public disclosure of ESIA documents or environmental reports is also a requirement of EIA procedures.

The ESMF was prepared in conjunction with the PIU within the Ministry of Agriculture, forestry and water management, development partners, and other relevant stakeholders. Stakeholder consultations have been undertaken in the preparation of this project as well as the ESMF.  Upon approval of the draft final ESMF report by the proponent and World Bank, the report will be disclosed and made available to the public, including all stakeholder parties.  The FSP PIU and its agencies will disclose the ESMF on their website, and the link shared with the Bank. EPA Montenegro requires the ESIA/ESMP to be prepared for specific project activities to be EPA requires the ESIA/ESMP to be prepared for specific project activities to be disclosed national levels for transparency and accountability, to inform decision on the EIA license.

# APPENDICES

## Appendix 1: National ESIA Procedure

Montenegro applies procedures for Environmental Impact Assessment (EIA) and Strategic Environmental Assessment (SEA) that are harmonized with EU directives. The legal basis is established in the Law on Environmental Impact Assessment, which defines the types of projects subject to EIA, the stages of the procedure (screening, scoping, reporting, public consultation, decision-making), and the responsibilities of the competent authorities.

Projects in sectors such as energy, industry, transport, water, and forestry are subject to these procedures to ensure compliance with sustainability principles. In practice, the EIA process requires the preparation of environmental studies that assess potential impacts on air, water, soil, biodiversity, landscape, and cultural heritage. Public participation and transparency are mandatory elements, and the Environmental Protection Agency, along with relevant ministries, supervises the process.

For projects that intersect with forest areas, special attention is required. This includes assessing impacts related to:

- Deforestation and land-use change, which may contribute to habitat loss, fragmentation, and reduced carbon sequestration capacity.

- Biodiversity impacts, as forests in Montenegro host a large number of endemic and relict species, many of which are sensitive to disturbance.

- Soil erosion and hydrology, since the removal of forest cover on steep slopes can significantly increase erosion rates, runoff, and risks of flooding.

- Forest fire risks, especially where infrastructure development increases human presence in sensitive forest zones.

Mitigation measures are an integral part of EIA for forest-related projects. These may include reforestation or afforestation to compensate for deforested areas, establishing protective forest belts along new infrastructure, restoring degraded habitats, and implementing monitoring systems to track impacts on forest ecosystems. In addition, alignment with the Law on Forests and forest management plans is required to ensure that project implementation does not undermine long-term sustainability objectives.

By integrating forestry considerations into the EIA process, Montenegro ensures compliance not only with EU directives but also with World Bank Environmental and Social Standard 6 (ESS6) on biodiversity conservation and the sustainable management of living natural resources.

8. Overview of World Bank Environmental and Social Standards

The World Bank Environmental and Social Framework (ESF) establishes ten Environmental and Social Standards (ESS1–ESS10), which define the requirements for borrowers to identify, assess, and manage environmental and social risks and impacts. Montenegro’s environmental legislation is largely aligned with the EU acquis and, therefore, with many of the World Bank’s requirements. However, gaps remain in terms of implementation, monitoring, enforcement, and cross-sectoral coordination.

A summary of alignment is presented here, while a detailed comparison of national legislation and World Bank standards should be included in an Annex. This approach ensures clarity and avoids overloading the main body of the text, in line with expert recommendations.

The ESS most relevant to Montenegro’s context include:

- ESS1: Assessment and Management of Environmental and Social Risks and Impacts – largely aligned through national EIA/SEA procedures, but gaps exist in cumulative impact assessment and post-project monitoring.

- ESS2: Labor and Working Conditions – partly covered by labor law and occupational safety regulations, though enforcement needs strengthening.

- ESS3: Resource Efficiency and Pollution Prevention and Management – aligned with EU directives, though practical enforcement of energy efficiency and waste minimization is limited.

- ESS4: Community Health and Safety – reflected in public health and safety laws, with gaps in risk communication and disaster preparedness.

- ESS5: Land Acquisition, Restrictions on Land Use and Involuntary Resettlement – partially aligned, but Montenegro has limited experience with large-scale resettlement.

- ESS6: Biodiversity Conservation and Sustainable Management of Living Natural Resources – highly relevant to Montenegro, given that forests cover nearly 70% of the territory and host exceptional biodiversity, including endemic and relict species. National laws on forests, national parks, and nature protection provide a strong legal basis, but gaps remain in effective enforcement, illegal logging control, habitat connectivity, and the restoration of degraded forest land. Bridging these gaps requires stronger forest governance, the establishment of a professional state-owned enterprise for forest management, and enhanced monitoring systems.

- ESS7: Indigenous Peoples/Sub-Saharan African Historically Underserved Traditional Local Communities – not directly applicable in Montenegro.

- ESS8: Cultural Heritage – aligned through the Law on Cultural Heritage, with overlaps in protected forest landscapes.

- ESS9: Financial Intermediaries – requires further institutional capacity.

- ESS10: Stakeholder Engagement and Information Disclosure – national procedures mandate public participation, but consistency and early engagement should be improved.

In summary, Montenegro’s framework is broadly consistent with the World Bank’s ESS. However, specific areas, particularly those related to ESS6, require targeted bridging measures: enhanced enforcement of forest and biodiversity protection laws, increased transparency and stakeholder involvement in forest use decisions, and accelerated implementation of restoration and climate adaptation measures.

VIII ENVIRONMENTAL DUE DILIGENCE PROCEDURE

Environmental due diligence procedures in Montenegro are designed to ensure that all activities comply with national environmental law, EU directives, and the World Bank Environmental and Social Standards (ESS). The process includes screening, scoping, impact assessment, public participation, mitigation planning, monitoring, and reporting. The Environmental Protection Agency is the competent authority, while project proponents are responsible for preparing environmental documentation and ensuring compliance.

For projects with potential impacts on forests and biodiversity, due diligence must include specific steps:

- Identification of possible deforestation, degradation, or conversion of forest land as a result of project activities.

- Assessment of impacts on habitats, particularly those hosting endemic and relict species, Natura 2000 sites, or old-growth forests of international significance.

- Analysis of ecosystem services provided by forests, including carbon sequestration, erosion control, and water regulation.

- Evaluation of risks from increased forest fire occurrence due to project-induced land-use changes or infrastructure development.

Mitigation and compensation measures must be clearly defined in environmental management plans. These include afforestation or reforestation of degraded areas, establishing protective forest belts along roads and infrastructure, and ensuring sustainable forest management practices in line with the Law on Forests and forest management plans. Due diligence should also ensure compliance with ESS6, which prohibits significant conversion or degradation of critical habitats, and requires sustainable management of living natural resources.

Monitoring obligations must be integrated into due diligence procedures. For forestry-related projects, this includes monitoring forest regeneration success, tracking biodiversity indicators, and evaluating the effectiveness of erosion and fire prevention measures. Transparent reporting and stakeholder engagement are essential to guarantee accountability and build public trust.

By incorporating forestry into environmental due diligence, Montenegro ensures that infrastructure and development projects do not undermine long-term sustainability goals but instead contribute to biodiversity conservation, climate resilience, and improved ecosystem services.

IX SIGNIFICANCE OF THE PROJECT FOR NATURE PROTECTION AND ENVIRONMENT

Investing in the quality of forest resources represents one of the most impactful interventions for Montenegro’s environmental protection and sustainable development. By strengthening the measurement, reporting and verification (MRV) system, updating the National Forest Information System, and assessing the potential for forest restoration and carbon storage, the project directly contributes to improved governance of natural resources, compliance with climate commitments, and better planning for sustainable forest management. Maintaining natural forests through pilot programs ensures biodiversity conservation, safeguards ecosystem services, and demonstrates innovative models of climate-smart forestry.

Subcomponent 2.2: Scaling-up Wildfire Risk Reduction and Response System has particular importance in the context of climate change adaptation. Wildfires are among the greatest threats to Montenegro’s forests and biodiversity, especially in the southern coastal and karst regions where droughts and high summer temperatures are intensifying. By investing in climate-resilient forests, the project will reduce wildfire risk, enhance institutional and community preparedness, and restore degraded landscapes.

Key environmental benefits of the project include:

- Establishing buffer zones with fire-resistant broadleaved and mixed forest stands, which enhance biodiversity and habitat connectivity.

- Implementing improved silvicultural practices and fuel load management (e.g., thinning, grazing, controlled burning) to strengthen forest resilience and reduce catastrophic fire risks.

- Introducing modernized early warning systems, detection technologies, and communication protocols to minimize response times.

- Strengthening the Forest Wildfire Rescue system, including professional brigades and trained volunteers, to reduce risks to ecosystems, communities, and infrastructure.

These interventions not only protect forests as carbon sinks and biodiversity hotspots but also safeguard water resources, soil stability, and rural livelihoods. By integrating ecological restoration with disaster risk management, the project becomes a cornerstone for Montenegro’s transition toward a climate-resilient, sustainable, and EU-aligned natural resource management system.

## Appendix 3. Environmental and Social Screening Form

| Project Name and Location: |  |
| --- | --- |
| Contact person for project (telephone/email): |  |
| Have you visited the site as part of the screening process? (Yes, No, Not Applicable) |  |
| If yes, Date of site visit |  |

- Description of Activity

| Brief description of activity and its main goal: |  |
| --- | --- |
| Duration of activity (start and end dates): |  |
| State the Region, municipality and community where the activity will be implemented: |  |
| Estimated Cost: |  |
| Include satellite image of location and/or technical drawings attached to this screening. |  |

- Site Characteristics [complete this section if applicable]

| No. | Site Characteristics |  |
| --- | --- | --- |
| 1 | Adjoining Land Uses or Land Cover |  |
| 2 | South |  |
| 3 | North |  |
| 4 | East |  |
| 5 | West |  |
| 6 | Proximity to a natural habitat e.g. wetland, river/stream, wetlands, forest reserves, protected areas etc. |  |
| 7 | Proximity a residence or any community resource or facility |  |
| 8 | Proximity to a road |  |
| 9 | Are there outstanding land disputes within the area? |  |
| 10 | What is the status of the land holding required by the project (customary, lease, community lands, etc.)? |  |

- Risks Identification

| If implemented, would the activity Potentially | Yes | No | If Yes, give a brief description | If Yes indicate frequency of occurrence |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Very Rarely | Rarely | Occasionally | Very Frequently |
| Air Quality and Noise |  |  |  |  |  |  |  |
| Cause air pollution? - generation of dust - generation of smoke - generate fumes? - generate emissions - Create objectionable odor affecting people? |  |  |  |  |  |  |  |
| Expose persons to excessive vibration and noise? |  |  |  |  |  |  |  |
| Biological Resources and Natural Resources |  |  |  |  |  |  |  |
| Occur in legally protected/nature reserve or Environmentally Sensitive Areas or a legally defined buffer zone; (forest reserves, national parks, Ramsar sites and wetlands, wildlife habitat areas, steep slopes, riparian areas, upland forests, vulnerable aquifers, biosphere reserves, World Heritage Sites, prime agricultural lands? |  |  |  |  |  |  |  |
| Be located within 100m from a protected/nature reserve or Environmentally Sensitive Areas? |  |  |  |  |  |  |  |
| Have effect on neighbouring protected/nature reserve or Environmentally Sensitive Areas (forest reserves, national parks, Ramsar sites and wetlands, wildlife habitat areas, steep slopes, riparian areas, upland forests, vulnerable aquifers and prime agricultural lands? |  |  |  |  |  |  |  |
| Have effect on flora (vegetation or plants)? |  |  |  |  |  |  |  |
| Have effect on fauna (animals, wildlife)? |  |  |  |  |  |  |  |
| Lead to the clearing of forestlands and woodlands? |  |  |  |  |  |  |  |
| Lead to road construction or rehabilitation, or otherwise facilitate access to fragile areas (natural woodlands, wetlands, erosion-prone areas)? |  |  |  |  |  |  |  |
| Cause disruption of wildlife migratory routes? |  |  |  |  |  |  |  |
| Harvest wetland plant materials or utilize sediments of bodies of water? |  |  |  |  |  |  |  |
| Involve the harvesting of timber resources? |  |  |  |  |  |  |  |
| Involve the harvesting of non-timber resources? |  |  |  |  |  |  |  |
| Lead to increased hunting or the collection of animals or plant materials? |  |  |  |  |  |  |  |
| Accelerate erosion by water or wind? |  |  |  |  |  |  |  |
| Involve removing renewable natural resources such as forest products? |  |  |  |  |  |  |  |
| Involve the extraction of non-renewable natural resources? |  |  |  |  |  |  |  |
| Affect dry season grazing areas and/or lead to restricted access to a common resource? |  |  |  |  |  |  |  |
| Water Quality and Hydrology |  |  |  |  |  |  |  |
| Occur within 100m distance from the nearest water body or drainage channel? |  |  |  |  |  |  |  |
| Involve water extraction or abstraction from rivers, lakes, groundwater |  |  |  |  |  |  |  |
| Have effect on potable water supplies to communities? |  |  |  |  |  |  |  |
| Potentially contaminate surface water and groundwater supplies? - by generating liquid waste? - by generating liquid with human or animal waste? - by generating liquid with pH outside 6-9 range? - by generating liquid with an oily substance? - by generating liquid with a chemical substance? - by generating liquid with odor/smell? |  |  |  |  |  |  |  |
| Lead to changes in the drainage pattern of the area, resulting in erosion or siltation? |  |  |  |  |  |  |  |
| Lead to increase in surface run-off, which could result in flooding on or off-site? |  |  |  |  |  |  |  |
| Increase runoff, which could exceed the capacity of existing stormwater drainage? |  |  |  |  |  |  |  |
| Increase potential for flooding? |  |  |  |  |  |  |  |
| Potentially pollute or contaminate surface water? |  |  |  |  |  |  |  |
| Potentially pollute or contaminate groundwater resources? |  |  |  |  |  |  |  |
| Affect existing stream flow, reduce seasonal availability of water resources? |  |  |  |  |  |  |  |
| Hazardous Waste and Materials - Will the activity |  |  |  |  |  |  |  |
| Lead to the generation of hazardous waste such as: - Solvent-based paints, - Pesticides and other garden chemicals, Batteries (for example car, mobile phone or regular household batteries) - Motor oils (Petrol, kerosene, lubricants for vehicles), - Cleaning and polishing chemicals, Pharmaceuticals (all medicines), - Electronic waste (unwanted computer equipment – monitors, keyboards, laptops, CD, disc drives, phones, batteries, solar panels, meters, Laser and printer inkjet cartridges, fluorescent tubes and compact fluorescent globes (CFLs)) - Medical waste? |  |  |  |  |  |  |  |
| Lead to the transportation of hazardous waste. |  |  |  |  |  |  |  |
| Land Acquisition, Restrictions on Land Use and Involuntary Resettlement |  |  |  |  |  |  |  |
| Require changes to existing land tenure system? |  |  |  |  |  |  |  |
| Require acquisition of land (public or private, temporarily, or permanently) for its development? |  |  |  |  |  |  |  |
| Potentially cause or aggravate land-use conflicts? |  |  |  |  |  |  |  |
| Restrict land rights or land use rights? |  |  |  |  |  |  |  |
| Restrict access to natural resources that cause a community or groups within a community to lose access to resource usage where they have traditional or customary tenure, or recognizable usage rights? |  |  |  |  |  |  |  |
| Lead to the physical displacement. Physical displacement occurs when individuals or communities are fully or partially no longer able to occupy an area and must relocate to a new location due to project activity. |  |  |  |  |  |  |  |
| Lead to economic displacement. Economic displacement occurs when individuals or communities are fully or partially restricted in their access to land or resources that are important to their livelihoods and economic well-being |  |  |  |  |  |  |  |
| Cause a disruption on Power or other utility supply? |  |  |  |  |  |  |  |
| Affect livelihood opportunities of people? |  |  |  |  |  |  |  |
| Labor Issues |  |  |  |  |  |  |  |
| Involve the use of direct workers? Direct workers are people employed or engaged directly by the Borrower (including the project proponent and the project implementing agencies) to work specifically in relation to the project. |  |  |  |  |  |  |  |
| Involve the use of community workers? Community workers are people employed or engaged in providing community labour. |  |  |  |  |  |  |  |
| Involve the use of contracted workers? contracted workers are people employed or engaged through third parties to perform work related to core functions of the project, regardless of the location. |  |  |  |  |  |  |  |
| Involve the use of primary supply workers? Primary supply workers are people employed or engaged by the Borrower’s primary suppliers. |  |  |  |  |  |  |  |
| Involve the use of Children? |  |  |  |  |  |  |  |
| Cause the exclusion of vulnerable groups , poor, persons with disabilities, youth, women, men from Project benefits? Cause the exclusion of vulnerable groups, poor, persons with disabilities, youth, women, men from Project resettlement operations? |  |  |  |  |  |  |  |
| Cultural Heritage |  |  |  |  |  |  |  |
| Involve excavations, demolition, movement of earth, flooding or other changes in the physical environment? |  |  |  |  |  |  |  |
| Be located in, or in the vicinity of, a recognized cultural heritage site? |  |  |  |  |  |  |  |
| Affect culturally important sites in the community such as sacred areas, burial grounds or cemeteries? |  |  |  |  |  |  |  |
| Affect religious sites shrines, temples, mosques, churches? |  |  |  |  |  |  |  |
| Affect any archaeological or historical site? |  |  |  |  |  |  |  |
| Community Health and Safety |  |  |  |  |  |  |  |
| Lead to labour influx. Labour influx consists of the rapid migration to and settlement of workers in the project area, typically in circumstances where labour/skills and goods and services required for a project are not available locally. Projects also stimulate speculative influx (“followers”), including those seeking employment or enterprises hoping to sell goods and services to the temporary project workforce, as well as “associates” who often follow the first two groups to exploit opportunities for criminal or illicit behaviour (e.g. prostitution and crime). |  |  |  |  |  |  |  |
| Create conditions that can lead to community health problems such as community exposure to health risks and vector-borne diseases, communicable diseases, injuries, nutritional disorders, HIV/AIDS and infectious diseases? |  |  |  |  |  |  |  |
| Lead to increased road traffic, vehicles or fleets of vehicles for the purposes of the activity? |  |  |  |  |  |  |  |
| Involve the use of Security personnel? |  |  |  |  |  |  |  |
| Lead to increased GBV and SEA risks? |  |  |  |  |  |  |  |
| Other Areas |  |  |  |  |  |  |  |
| Production or use in any product or activity deemed illegal under host country laws or regulations or international conventions and agreements, or subject to international bans, such as pharmaceuticals, pesticides/herbicides, ozone depleting substances, PCB's, wildlife or products regulated under CITES. |  |  |  |  |  |  |  |
| Production or use in weapons and munitions. |  |  |  |  |  |  |  |
| Production or use in alcoholic beverages (excluding beer and wine). |  |  |  |  |  |  |  |
| Production or trade in tobacco |  |  |  |  |  |  |  |
| Gambling, casinos and equivalent enterprises. |  |  |  |  |  |  |  |
| Production or trade in radioactive materials. |  |  |  |  |  |  |  |
| Production or use of unbonded asbestos fibres. |  |  |  |  |  |  |  |

- Risks Classification

Based on the risks identified in section C the risks areas should be categorized as Low Risk, Moderate Risk, Substantial Risk or High Risk:

| Risk areas | Low Risk (Risk that can impact on a small scale) | Moderate Risk (Risk that can cause an impact but not a serious one) | Substantial Risk | High Risk (Risks that can cause result in huge impact) |
| --- | --- | --- | --- | --- |
| Air Quality and Noise |  |  |  |  |
| Biological Resources and Natural Resources |  |  |  |  |
| Water Quality and Hydrology |  |  |  |  |
| Agricultural and Forestry Production |  |  |  |  |
| Hazardous Waste and Materials |  |  |  |  |
| Land Acquisition, Restrictions on Land Use and Involuntary Resettlement |  |  |  |  |
| Socio-economic, Livelihood and Labour |  |  |  |  |
| Social Inclusion |  |  |  |  |
| Community Health and Safety |  |  |  |  |

Overall proposed activity risk classification: ………………………………………..

The activities that are Substantial or High risk are not subject to financing and cannot be eligible under this Project. In addition, the Project will not support any of the below:

- Significant interventions in protected areas

- Activities that require a full Environmental Impact Assessment as per Montenegrin law

- Production or trade in any product or activity deemed illegal under host country laws or regulations or international conventions and agreements. ƒ Production or trade in weapons and munitions.

- Trade in wildlife or wildlife products regulated under CITES

- Production or trade in pesticides/herbicides subject to international phase outs or bans.

- Recommendations for Instruments to be prepared

| Recommendation: | Tick as appropriate | Justification |
| --- | --- | --- |
| No further instrument required |  |  |
| Requires the preparation of: |  |  |
| Environmental and Social Management Plan (ESMP) |  |  |
| Resettlement Action plan (RAP or ARAP) |  |  |
| Cultural Heritage Management Plan |  |  |
| Biodiversity Management Plan |  |  |

- National Requirements

| No. | If implemented, would the activity require permit or approval from the following national regulatory agencies? | Yes | No | Justification |
| --- | --- | --- | --- | --- |
| 1 | Ministry of Agriculture, Forestry and Water Management |  |  |  |
| 2 | Directorate for Forestry, Hunting, and Wood Industry, Ministry of Agriculture, Forestry and Water Management |  |  |  |
| 3 | Environment Protection Agency |  |  |  |
| 4 | Municipalities |  |  |  |
| 5 | Other |  |  |  |

- Clearance

| Reviewed by: |  |
| --- | --- |
| Name: |  |
| Signature: |  |
| Date: |  |

## Appendix 5. Environmental and Social Code of Practices (ESCOP)

- Objectives

This Environmental and Social Codes of Practice (ESCOP) is prepared to manage small environmental impacts during construction. The ESCOPs will apply to manage small-scale infrastructure investments which develop and support the project. ESCOP will be a mandatory part of the construction contract or bidding documents so that the contractor complies with environmental covenants. The PIU and construction supervisors will be responsible for monitoring compliance with ESCOP and preparing the required reports.

- Responsibilities

The PIU and Contractors are the key entities responsible for implementation of this ESCOP. Key responsibilities of the PIU and the contractors are as follows:

  - The PIU

    - The PIU are responsible for ensuring that the ESCOP is effectively implemented. The PIU will assign a qualified staff to be responsible for checking implementation compliance of Contractors, include the following: (a) monitoring the contractors’ compliance with the environmental plan, (b) taking remedial actions in the event of non-compliance and/or adverse impacts occur, (c) investigating complaints, evaluating and identifying corrective measures; (d) advising the Contractor on environment improvement, awareness, proactive pollution prevention measures; and (e) monitoring the activities of Contractors on replying to complaints.

(b) 	Contractor

    - The contractor is responsible for carrying out civil works and informs PIU, local authority and community about construction plans and risks associated with civil works. As such, the contractor is responsible for implementing agreed measures to mitigate environmental risks associated with its civil work.

    - Contractors are required to obey other national relevant legal regulations and laws.

##### Part 1 – Contractor’s Responsibilities

This is an example and is not necessarily a full treatment of all requirements for a specific project. For example, there might be reasons to have contractors deal with STDs, medical and hazardous waste (e.g, oil from vehicle or furnace repair and similar, oily rags).

| Issue | Environmental and Social Prevention and Mitigation Measures |
| --- | --- |
| Contractor Awareness of E&S Risk Management | - All contractors will be responsible for conducting their work activities in consideration of these ESCOPs. Failure to do so could result in penalties or dismissal. |
| Pre-Construction |  |
| Initial Checklist | - That these ESCOPs have been reviewed by management and all workers. - Ensure all workers have appropriate PPE and are trained on potential health and safety risks related to their work. - Workers have signed the worker code of conduct. - Workers fully understand all prohibitions (e.g. illegal dumping of demolition material, use of alcohol by workers, etc.). - Consultation has been completed with the nearby community in regard to construction works and duration (working hours) or providing public information and site access. - All emergency procedures are developed, and workers are well informed. |
| Site Clearing | - All vegetation must be stripped from the area of construction. This has to be done very carefully. The valuable or reusable materials from the demolished construction should be kept as property of the health facility (health center or referral hospital) and should be stored in the storage area provided. - The Contractor shall dispose of all construction materials/rubbish from the demolition/construction away from the hospital property. |
| Set out of Works | - The Contractor shall set out the location of the works and clearly mark the location of corners with timber pegs. Offset pegs shall also be located at one-meter offsets so that all corner points can be located again after excavation of soil for the correct construction of footings. |
| Construction |  |
| Construction Activities | - When conducting construction activities, including any destruction, the Contractor shall consider the following measures: - Prepare a management plan as to how to avoid or minimize environmental and social impact during construction activities. - Maintain an adequate unoccupied buffer zone around the work areas to allow for construction traffic. - Ensure proper signage is in place alerting residents and the public to any construction related risk. - Post warning signs on barricades, construction zones, and other areas limiting access to authorized personnel only. - Implement adequate measures during demolition of existing infrastructure to protect workers and the public from falling debris and flying objects. - Isolate work areas from occupied areas using physical barriers, negative pressurization of the construction or renovation area relative to occupied areas, and use HEPA or other filtration, where possible, to remove particulates. - Bag all construction debris and set aside designated and restricted waste drop or discharge zones for safe movement of wastes. - Conduct sawing, cutting, grinding, sanding, chipping or chiseling with proper guards and anchoring as applicable. - Use of temporary fall protection measures in scaffolds and on edges of elevated work surfaces, such as handrails and toe boards to prevent materials from being dislodged. - Provide all workers with safety glasses with side shields, face shields, hard hats, and safety shoes. - Hearing protection should be provided where excessive noise levels are present. |
| Supervision during construction | - The Project Engineer will supervise compliance with these ESCOP specifications. - Major non-compliance of these ESCOPs by the Contractor will be cause for suspension of works and other penalties until the non-compliance has been resolved to the satisfaction of the Project Engineer. Contractors are also required to comply with national and municipal regulations governing the environment, public health, and safety. |
| Dust Generation / Air Quality | - Use work practices and materials that result in little or no generations of airborne contaminants during construction or renovation activities, such as wet methods to suppress dust generation as well as paint and carpeting with low volatile organic compound emissions. - For indoor dust control, the Contractor may use air filters, purifiers, or vacuums. - Avoid burning or incineration of construction waste materials outside of the building. - Keep outdoor stockpile of aggregate/sand materials covered to avoid suspension or dispersal of fine soil particles during windy days or disturbance from stray animals. - Reduce the operation hours of generators /machines /equipment /vehicles as much as possible. - Undertake regular maintenance of generators, machinery and equipment and vehicles. - Control vehicle speed when driving through community are as so that dust dispersion from vehicle transport is minimized. |
| Water Quality and Availability | - Activities should not affect the availability of water for drinking and hygienic purposes. - No soiling materials, solid waste, toxic or hazardous materials should be poured or thrown into water bodies for dilution or disposal. - Provide toilets with a temporary septic tank at the construction site. The flow of natural waters should not be obstructed or diverted to another direction, which may lead to drying up of riverbeds or flooding of settlements. - Keep concrete mixing separate from any drainages leading to waterways. |
| Noise | - Plan activities in consultation with people living in the immediate vicinity so that noisiest activities are undertaken during periods that will result in least disturbance. - Use noise-control methods such as fences, barriers, etc. - Maintain a buffer zone (such as open spaces, rows of trees or vegetated areas) between the project site and residential areas to lessen the impact of noise to the living quarters. - Avoid doing construction work at night-time. |
| Soil Erosion | - Disturb as little ground area as possible, stabilize that area as quickly as possible, control drainage through the area, and trap sediment onsite. - Erect erosion control barriers around perimeter of cuts, disposal pits, and roadways. - Schedule construction activities during dry season as much as possible. |
| Construction Waste | - Segregate construction waste as recyclable, hazardous and non-hazardous waste. - Collect, store and transport construction waste to appropriately designated/ controlled dump sites. - Enforce daily site clean-up and housekeeping procedures, including maintenance of adequate disposal facilities for construction debris. - On-site storage of waste prior to final disposal should be at least 50 meters from rivers, streams, lakes and wetlands. - After each construction site is decommissioned, all debris and waste shall be cleared and recycled or disposed of in an approved location. |
| Hazardous Waste | - Prior to initiation of renovation activities, a hazardous waste management plan/ asbestos management plan should be conducted to assess the presence of asbestos, mold, lead, mercury, and other potential contaminants that will need to be removed or isolated. - Collect and properly dispose of small amount of maintenance materials such as oily rags, oil filters, used oil, etc. - Never dispose of spent oils on the ground and in water courses as it can contaminate soil and groundwater (including drinking water aquifer). |
| Storage of Fuels and Chemicals | - Store fuels, oils and chemicals safely in areas on an impermeable surface with berms to contain 110% of the maximum volume of the storage tank. - Train workers on correct transfer and handling of fuels and other substances and require the use of gloves, boots, aprons, eyewear, hearing protection, and other protective equipment for protection in handling highly hazardous materials. - Have adequate spill kits readily available and clearly labelled on the work site and train workers in their use, application and spill clean-up procedures. |
| Occupational Health and Safety | - Contractors shall conduct site specific OHS risk assessments based on OHS management plans in line with the local legal requirements and WBG EHS guidelines. - Set up the construction site with sufficient supplies of clean drinking water, power, and sanitation facilities. - Mandate the use of personal protective equipment for workers as necessary (gloves, dust masks, hard hats, boots, goggles, eye, and hearing protection). - Follow the below measures for construction involving work at height (e.g. 2 meters above ground). - Do as much work as possible from the ground. - Only allow people with sufficient skills, knowledge, and experience to perform the construction activity. - Ensure that proper training and equipment for working at heights is provided. - Checking that the place where work at height is to be undertaken is safe. - Where possible provide fall-protection measures e.g., safety harness, simple scaffolding/guard rail for works over 4 meters from ground. - Take precautions when working near fragile surfaces. - Clean up oil, grease, paint, and dirt immediately to prevent slipping and possible injury. - Keep the site clean and free of debris daily. - Provide an on-site first aid kit with bandages, alcohol or non-alcohol antiseptic wipes, dressings, etc. at the construction site. - Keep corrosive fluids and other toxic materials in properly sealed containers for collection and disposal in properly secured areas. - Ensure structural openings are covered/protected adequately. Secure loose or light material that is stored on roofs or open floors. During heavy rains or emergencies of any kind, suspend all work. - Apply good electricity practices such as the use of safe extension cords, voltage regulators and circuit breakers, labels on electrical wiring for safety measures, awareness on identifying burning smell from wires, etc. at construction sites and provision of voltage detectors, multi-meters and receptacle testers as necessary. - Ensure adequate toilet facilities for workers, at least one toilet compartment for every 25 workers, with separate facilities for males and females. - Make sure workers are aware of GRM and can access it. - As needed, necessary PPE equipment to prevent COVID transmission, hand sanitizer, physical distancing, etc. as per current government directives. |
| Incident Reporting | The borrower is responsible for incident investigation - Investigation should start as soon as possible as information, evidence and data are fresh - The borrower/PIU should quickly agree who is best placed to investigate, as well as the scope of the investigation (lead investigator should be competent) - The Task Team should provide advice, but Borrower/PIU is ultimately responsible for conducting the investigation - Local regulatory framework may require a regulatory authority to conduct an incident (e.g. police investigation, OSHA/Labor department) - Regulatory investigation focuses on legal compliance (i.e. who is at fault) and may not include root causes (adequacy or lack of safeguards) in projects - Borrower/PIU needs to conduct internal investigation/review of their safeguards and risk management - Corrective actions with clearly defined timelines and people responsible for implementation. - Recommendations for further improvement. |
| Community Health and Safety | - Rope off construction area and secure materials stockpiles/ storage areas from the public and display warning signs including at unsafe locations. - Do not allow children to play in and around construction areas. - If school children are in the vicinity, include traffic safety personnel to direct traffic during school hours, if needed. - Control the driving speed of vehicles particularly when passing through community or nearby school, health center or other sensitive areas. - Fill in all earth borrow-pits once construction is completed to avoid standing water, water-borne diseases and possible drowning. - Avoid occurring labor influx around construction sites. - Avoid working at night. - Recommend hiring construction workers from nearby communities. - Inform communities on the sexual exploitation and abuse (SEA), sexual harassment (SH), gender-based violence (GBV), and violence against children (VAC) policies. - Make sure that the community is aware of GRM and can access it. - Implementation of COVID-19 prevention measures following government directives. |
| Labor and hiring | - Wherever possible hire workers from the local community and encourage hiring of women, the poor, people with disabilities, and/or other vulnerable persons. - Ensure equal pay for the same job for both men and women. - Ensure the minimum working age of 18 years. - No child (under 18 years) or forced labor to be hired for the project. - Train local workers within a reasonable time frame to meet project requirements. Costs for training will be borne by contractors. - Avoid and when avoidance is not possible, minimize and manage labor influx. - Prepare the Code of Conduct (CoC), inform and train workers in the CoC and ensure it is signed by all workers (See Annex 14 Sample CoC for Contractor staff). - Implement sexual exploitation and abuse (SEA), sexual harassment (SH), gender-based violence (GBV), and violence against children (VAC) training. |
| Workforce and Camps | - Provide adequate lavatory facilities for men and women at the worksite (toilets and washing areas) for the expected number of workers. Toilet facilities should also be provided with adequate supplies of hot and cold running water, soap, and hand drying devices. - Where needed, install, and maintain a temporary septic tank system for the collection of sanitary waste without causing pollution of nearby watercourses. - Establish a method and system for storing and disposing of all solid waste generated at the work site. - Do not allow the use of wood fuel for cooking or heating in any cooking or kitchen facilities and provide alternate fuels. - Ensure that site offices, depots, asphalt plants and workshops are located in appropriate areas as approved by the Project Engineer and not within 500 meters of existing residential settlements. - Ensure that site offices, depots and particularly storage areas for diesel fuel and bitumen and asphalt plants are not located within 500 meters of watercourses, and are operated so that no pollutants enter watercourses, either overland or through groundwater seepage, especially during periods of rain. Require lubricants to be recycled and a ditch to be constructed around the refueling area with an approved settling pond/oil trap at the outlet. - As needed, necessary PPE equipment to prevent COVID transmission, hand sanitizer, physical distancing, etc. as per current government directives. |
| Cultural Heritage | - Responsible local authorities and the National Culture Administration will oversee protecting and preserving the site before deciding on subsequent appropriate procedures. This would require a preliminary evaluation of the findings to be performed by the archaeologists in the Directorate of Cultural Heritage in the Ministry Culture. The significance and importance of the findings should be assessed according to the various criteria relevant to cultural heritage; those include the aesthetic, historic, scientific or research, social and economic values. - Decisions on how to handle the findings shall be taken by the responsible authorities and Directorate of Cultural Heritage in the Ministry Culture. This could include changes in the layout (such as when finding an irremovable remain of cultural or archaeological importance) conservation, preservation, restoration and salvage. - Implementation for the authority decision concerning the management of the finding shall be communicated in writing by relevant local authorities; and - Construction work could resume only after permission is given from the local authorities responsible or Directorate of Cultural Heritage in the Ministry Culture concerning safeguarding of the heritage. |
| Prohibitions | - The following activities are prohibited on the construction site: - Cutting of trees for any reason outside the approved construction area. - Hunting, fishing, wildlife capture, or plant collection. - Use of unapproved toxic materials, including lead-based paints, asbestos, etc. - Disturbance to anything with architectural or historical value. - Building of fires. - Use of firearms (except authorized security guards, if any). - Use of alcohol or drugs by workers. |
| Post-Construction |  |
| Site Decommissioning | - The contractor will clean the site carefully and remove all construction waste materials and dump it at a designated dumping site. - Open burning of waste should not be encouraged. |

Part 2 – Contractor’s Workers Environmental Code of Conducts

| Do: | Do Not |
| --- | --- |
| - Use The Toilet Facilities Provided – Report Dirty or Full Facilities - Clear Your Work Areas of Litter and Building Rubbish at The End Of - Each Day – Use the Waste Bins Provided and Ensure That Litter Will Not Blow Away. - Report All Fuel or Oil Spills Immediately & Stop the Spill from Continuing. - Smoke In Designated Areas Only and Dispose of Cigarettes And - Matches Carefully. (Littering Is an Offence.) - Confine Work and Storage of Equipment to Within the Immediate Work Area. - Use All Safety Equipment and Comply with All Safety Procedures. - Prevent Contamination or Pollution of Streams and Water Channels. - Ensure A Working Fire Extinguisher - Is Immediately at Hand If Any “Hot - Work” Is Undertaken E.G. Welding, Grinding, Gas Cutting Etc. - Report Any Injury of Workers or Animals. - Drive On Designated Routes Only. - Prevent Excessive Dust and Noise | - Remove Or Damage Vegetation Without Direct Instruction. - Make Any Fires. - Poach, Injure, Trap, Feed or Harm Any Animals – This - Includes Birds, Frogs, Snakes, Etc. - Enter Any Fenced Off or Marked Area. - Drive Recklessly or Above Speed Limit - Allow Waste, Litter, Oils or Foreign Materials into The Stream - Litter Or Leave Food Lying Around. - Cut Trees for Any Reason Outside the Approved Construction Area - Buy Any Wild Animals for Food. - Use Unapproved Toxic Materials, Including Lead-Based Paints, Asbestos, Etc. - Disturb Anything with Architectural or Historical Value - Use Of Firearms (Except Authorized Security Guards) - Use Of Alcohol by Workers During Work Hours - Wash Cars or Machinery in Streams or Creek - Do Any Maintenance (Change of Oils and Filters) Of Cars and Equipment Outside Authorized Areas - Dispose of Trash in Unauthorized Places - Have Caged Wild Animals (Especially Birds) In Camps - Work Without Safety Equipment (Including Boots and Helmets) - Creating Nuisances and Disturbances in Or Near Communities - Use Rivers and Streams for Washing Clothes - Dispose Indiscriminately of Rubbish or Construction Wastes or Rubble - Spill Potential Pollutants, Such as Petroleum Products - Collect Firewood - Explosive And Chemical Fishing - Use Latrines Outside the Designated Facilities; And - Burn Wastes And/Or Cleared Vegetation. |

## Appendix 6. Environmental and Social Management Plan (ESMP) Template

To be prepared during implementation as needed; define detailed mitigation, monitoring, and management measures for identifying impacts from specific subprojects.

Environmental and social risks and impacts are strongly linked to subproject location and scope of activities. This ESMP should be customized for each specific subproject location and activities.

1. Subproject Information

| Subproject Title: |  |
| --- | --- |
| Estimated Cost: |  |
| Start/Completion Date: |  |

2. Site/Location Description

This section concisely describes the proposed location and its geographic, ecological, social and temporal context including any offsite investments that may be required (e.g., access roads, water supply, etc.). Please attach a map of the location to the ESMP.

3. Subproject Description and Activities

This section lists all the activities that will take place under the subproject, including any associated activities (such as building of access roads or transmission lines, or communication campaigns that accompany service provision).

4. ESMP Matrix: Risk and Impacts, Mitigation, Monitoring

This section should identify anticipated site-specific adverse environmental and social risks and impacts; describe mitigation measures to address these risks and impact; and list the monitoring measures necessary to ensure effective implementation of the mitigation measures. It may draw from the ESMF’s pre-identification of potential risks/impacts and mitigation measures, as applicable, and drill down further to ensure relevance and comprehensiveness at the site-specific level. For subprojects involving construction, two sets of tables may be needed, for the construction phase and the operation phase.

| Anticipated E&S Risks and Impacts | Risk Mitigation and Management Measures | Impact Mitigation |  | Impact/Mitigation Monitoring |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Location/Timing/Frequency | Responsibility | Parameter to be monitored | Methodology, including Location and Frequency | Responsibility |

5. Capacity Development and Training

Based on the implementation arrangements and responsible parties proposed above, this section outlines any capacity building, training or new staffing that may be necessary for effective implementation.

6. Implementation Schedule and Cost Estimates

This section states the implementation timeline for the mitigation measures and capacity development measures described above, as well as a cost estimate for the implementation. The cost estimate can focus on the line items that will be covered by the project implementing agency, with costs of mitigation measures to be implemented by the contractor left to the contractor to calculate.

7. Attachments

ESCOPs, site specific SEP etc.

IV. Review and Approval

| Prepared By: ……………………………(Signature) Position: ……………………… Date …………………… |  |
| --- | --- |
| Reviewed By: ………………………(Signature) Position: ………………………Date …………………… | Approved By: ……………………………(Signature) Position: ……………………… Date ………………… |

## Appendix 7: Indicative Outline- Forest and Biodiversity Management Plan (BMP)

Executive Summary

- Purpose and scope of the Forest and Biodiversity Management Plan

- Summary of key biodiversity risks and mitigation strategies

Introduction

- Project background and rationale

- Description of project and components

- Objectives of the Forest and Biodiversity Management Plan (e.g., avoid, minimize, mitigate, and offset impacts on biodiversity)

Regulatory and Policy Framework

- Applicable national laws and regulations (Montenegro)

- World Bank Environmental and Social Standard 6 (ESS6)

- International conventions (e.g., Convention on Biological Diversity)

- Other relevant standards and guidelines

Project Description

- Overview of the project

- Description of project

- Construction and operational activities with potential biodiversity impacts

Baseline Biodiversity Assessment

- Methodology for baseline surveys

- Description of habitats

- Key species present

- Identification of critical, natural, and modified habitats

- Mapping of sensitive areas

Impact Assessment

- Identification and analysis of potential impacts during construction, operation, and decommissioning:

Mitigation Measures and Management Actions

- Application of the mitigation hierarchy (avoid, minimize, restore, offset)

- Avoidance of critical habitats

- Minimization of vegetation clearance

- Control of artificial lighting and noise

- Waste management and spill response

- Restoration of disturbed habitats

Forest and Biodiversity Monitoring Plan

- Pre-construction, construction, and post-construction monitoring

- Indicators and parameters (e.g., species abundance, habitat condition, water quality)

- Frequency and methods of monitoring (e.g., surveys, remote sensing, water sampling)

- Adaptive management: corrective actions if monitoring shows unexpected impacts

Roles, Responsibilities, and Capacity Building

- Organizational structure for the Forest and Biodiversity Management Plan implementation (PIU, contractors, biodiversity specialists)

- Roles and responsibilities for monitoring, reporting, and management

- Capacity building and training requirements for staff and contractors

Stakeholder Engagement and Disclosure

- Identification of stakeholders (local communities, fishers, conservation groups, authorities)

- Consultation process and feedback integration

- Information disclosure and grievance redress mechanism

Reporting and Documentation

- Internal and external reporting requirements (monthly, quarterly, annual)

- Field evaluation reports after surveys and monitoring

- Annual biodiversity monitoring and evaluation reports

- Documentation of incidents, corrective actions, and BMP updates

Budget and Resources

- Indicative budget for the Forest and Biodiversity Management Plan implementation (surveys, monitoring, restoration, training)

- Allocation of resources and funding sources

Timeline

- Implementation schedule for the Forest and Biodiversity Management Plan actions and monitoring

- Review and update procedures (living document, updated as new information becomes available)

Annexes

- Maps

- Baseline survey data and species lists

- Monitoring protocols and templates

- Training materials

- Regulatory permits and approvals

## Appendix 10: Screening Form for Land Acquisition and Resettlement

Name of sub-component: ______________________

District: ________________________

County: ______________________

Name of person completing the form:    	_________________________

Position of person completing the form:	_________________________

Section 1:

Is the land to be used for the sub-component owned entirely by the Ministry or by another government agency and is this ownership uncontested?

Yes_______      No_______

If Yes, Skip Section 2.  Go directly to Section 3. If No, Proceed to Section 2

Section 2:

Is any of the land owned by individuals or households?    Yes _______    No _______

[note: the land does not need to have official ownership deeds, but can be recognized by the community as owned by individuals or households]

If Yes, about how many individuals or households?  __________

What is the size of the land area (m2)? _____________

Is any of the land considered community property?   Yes ________  No ___________

If Yes, what is the size of the land area (m2)? ___________

If answered ‘Yes’ to any of the questions in Section 2, please discuss this with Project manager and Social Specialist for next step.

Section 3:

Is anyone living on the land (even if it is not their property)? Yes ______   No _______

If Yes, how many individuals ______ or households _______?

Is anyone using the land for agriculture (even if it is not their property)? Yes ______   No _______

If Yes, how many individuals ______ or households _______?

Is anyone using the land for another non-agricultural type of livelihood? Yes, _____   No _______

If Yes, what type of use? ____________ how many individuals ______ or households _______?

Is anyone using the land for any other purpose? Yes, _____   No _______

If Yes, what type of use? ____________ how many individuals ______ or households _______?

If answered ‘Yes’ to any of the questions in Section 3, please discuss this with Project manager and Social Specialist for next step.

## Appendix 12: ESF Implementation Reporting Template

- Executive Summary

- Key Highlights: Summary of the key environmental and social achievements.

- Current civil works:

- Brief description of site in bullet form:

- Located at this site over XYZ ha

- Works started in XYZ, expected to be completed by XYZ

- Supervision consultant

- Number of supervision field visits done by Project Implementation Unit

- PIU monitoring of contractors

- etc

- Contractor Information:

Name:

| Activity | Status | Comments |
| --- | --- | --- |
| ESMP submitted before start of civil works |  |  |
| ESMP reviewed and cleared |  |  |
| LMP and OHS plan |  |  |
| Traffic Management Plan if needed |  |  |
| Monthly reports submitted by contractor |  |  |
| Training conducted by contractor |  |  |

Name:

| Activity | Status | Comments |
| --- | --- | --- |
| ESMP submitted before start of civil works |  |  |
| ESMP reviewed and cleared |  |  |
| LMP and OHS plan |  |  |
| Traffic Management Plan if needed |  |  |
| Monthly reports submitted by contractor |  |  |
| Training conducted by contractor |  |  |

- Status of E&S standards:

The following table should be filled out based on observations from supervision consultant report and field visit findings and observations:

|  | Status | Comments; follow-up |
| --- | --- | --- |
| Waste Management |  |  |
| Materials sourcing | Quality; type; registered etc |  |
| Labor conditions |  |  |
| Occupational Health and Safety | PPE usage; Training etc |  |
| Incidents |  |  |
| Community health and safety | Barricades; lighting; etc |  |
| Biodiversity | Not relevant |  |
| Land acquisition | Not relevant |  |
| Stakeholder engagement |  |  |
| GBV |  |  |
| Grievances | Yes/no; log; feedback etc |  |
| Communications on ESF |  |  |

- Synopsis of key Observations of the Supervision Consultant

| Report dated |  | Comments |
| --- | --- | --- |
| Month, 2025 | 1. 2. 3. |  |
| Month, 2025 |  |  |

- Observations of PIU E&S Specialists:

| Good practices undertaken | Challenges faced | Comments; suggestions |
| --- | --- | --- |

ANNEX I:

#### Add photographs; before, during and after

#### ANNEX II:

#### Any other attachments; documents etc

## Appendix 13: Waste Management Plan

1.0	INTRODUCTION

The following Waste Management Plan (WMP) presents a framework outlining the general requirements essential for effective management of waste generated onsite during the construction works. The WMP outlines measures required to manage and mitigate the impact of waste generation and resource consumption during the construction works of the project. The plan includes details on the following:

- The types waste generated during construction activities;

- Procedures to collect and dispose of waste;

- Measures that will be implemented to minimize waste generation associated with the development; and program for monitoring the effectiveness of these measures.

This Plan also considers other aspects to waste management such as waste reduction, segregation of waste, disposal of waste.

2.0	ROLES AND RESPONSIBILITIES

The relevant roles and responsibilities to this plan are as outlined:

Project Manager

- Coordinate the implementation of this Construction Waste Management Plan.

- Coordinate site team to ensure site inspections and audits are conducted.

- Ensure environmental inspections are undertaken and records are kept.

- Coordinate the implementation of corrective and preventative action and incident response.

- Activate resources to ensure technical advice regarding environmental obligations, measures and protection is available.

Site Manager

- Ensure adequate waste management infrastructure, equipment (bins and trucks) and services are provided as required.

- Ensure that any incidents or observations that may occur during waste storage and/or handling events are properly managed.

- Implement approved waste management and minimization strategies as highlighted in this plan.

- Ensure that this plan is implemented and conduct Monthly Audit in coordination with the HSE Officer.

- Shall maintain the record of audits and training conducted.

HSE Officer

- Ensure that appointed waste transport vendor completes waste certificates prior to transporting.

- Ensure all waste bins are correctly labelled and stored in the appropriate designated area.

- Verify that all personnel, including contractors, have received the appropriate training in waste management practices and keep records of training as per Section 5 of this plan.

- Ensure Waste Inspections are being carried out on a weekly basis and Waste Inventories are being maintained.

All Personnel

- Implement the requirements of this Waste Management Plan in all aspects of the construction works.

- Ensure that the site is kept tidy, free from litter and that waste is put in the correct bins.

- Ensure that all incidents and observations relevant to waste are reported to Project Manager.

3.0	AWARENESS AND TRAINING

The Project will implement an awareness and training program that will be delivered to all construction workers. This training will include, but not be limited to:

- The application of the waste management hierarchy;

- Common waste streams produced in the construction site. ;

- Dangerous materials segregation and hazard classification codes.

- Efficient waste segregation.

- Spill Response; and

- Community impacts of poor waste management.

4.0	WASTE MANAGEMENT REQUIREMENTS

4.1 	Waste Elimination and Minimization

The Project shall meet or exceed the requirements of this plan by implementing and maintaining a waste minimization strategy, as a minimum standard. The waste minimization strategy shall eliminate, minimize and manage waste during the construction activities through the following:

- Identification of waste streams and quantities;

- Implementation of management strategies for each waste stream;

- Defined roles and responsibilities;

- Training and awareness;

- Monitoring of waste streams and management activities;

- Encouraging sustainable waste management practices in the supply chain;

- Minimizing wastes from excess materials including but not limited to using surplus materials prior to re-ordering and reducing packaging waste;

4.2 	Types of Waste, Classification and Handling Method

Construction site waste can be categorized as general (non-hazardous) or regulated (hazardous) waste. Regulated wastes are hazardous waste such as waste containing asbestos, oil or chemicals substances. All other waste streams are considered general waste, unless contaminated with a regulated waste.

In the event that an unknown material is discovered (e.g. liquid in a drum), it will be the responsibility of the site HSE Officer to identify the waste in coordination with the Site Manager and Store Supervisor. The person accountable in the event that the waste is not identified correctly and disposed of in the appropriate manner is the Site Manager.

Table 1 presents the waste types, classification and proposed handling methods to be implemented during the construction works.

Types of Wastes, Classification and Handling Method

| Waste Type | Classification | Handling Method |
| --- | --- | --- |
| Aluminum cans | General | Recycling |
| Batteries (cadmium and nickel/cadmium (NiCad), lead acid, lithium and other) | Regulated | Recycling |
| Paper | General | Recycling |
| Cardboard | General | Recycling |
| Printer cartridges | Regulated | Recycling |
| Plastics – bottles, drums and other containers | General (drums, depends on contaminant) | Recycle |
| General municipal waste | General | Treatment/Landfill |
| Organic waste | General | Recycle |
| Concrete | General | Recycle |
| Spent chemicals, Solvent, Paint | Regulated | Recycle |
| Oily waste | Regulated | Recycle |
| Scrap Metal (steel, aluminum, brass, copper, lead, other nonferrous metal, stainless steel and zinc) | General | Recycle |
| Used Filters – Oily filters | Regulated | Recycle |
| Septic/Effluent | Regulated | Regulated Site |
| Contaminated Soil | Not a waste | Treated* |
| High density polyethylene (HDPE) waste | General | Recycle |
| Rubber | Regulated | Recycle |
| Tires | Regulated | Recycle |
| Textiles and rags | General (unless contaminated with a regulated waste) | Reuse/ Recycle |
| Other solid regulated waste | Regulated | Regulated Landfill |
| Concrete –solid form left over | General | Recycled |
| Spent spill Clean Up | Regulated | Regulated Landfill |

Note: General – Non-Hazardous Wasted, Regulated – Hazardous Waste

5.0	WASTE STORAGE REQUIREMENTS

5.1	General Waste

The following must be considered as minimum requirement for general waste storage areas:

- General waste bins and containers (e.g. food scrap bins, recyclable bins, recyclable paper bins) 
are to be placed in easily accessible locations around the worksite. Recyclable waste shall be stored separately from general waste; ensuring maximized segregation potential has been met to
minimize waste sent to landfill.

- Liquid and solid wastes shall be segregated to allow for maximized recycling, bins will be color
coded for the waste stream, where practicable.

- Where a waste material or product does not have a specific bin, the bin used must be compatible
with the waste and must then be labelled.

- Spare bins shall be made available to accommodate for unforeseeable events.

- Waste bins shall be maintained in good condition to prevent leaks or spills. Defective containers hall not be used for waste storage or transport.

- Containers used for waste storage (such as waste oil drums) shall not be opened, handled,
transported or stored in a manner that may rupture the container, cause it to leak or subject it to
overpressure.

- The waste storage area shall be of an adequate capacity to handle the volume of waste stored
there without a risk to the environment.

- The waste storage area shall be located in an easily accessible area to provide vehicle access to
materials and waste storage areas for the collection and transport of wastes.

- Waste storage areas shall have adequate firefighting equipment suitable for the type of waste
stored at site.

- The location of the waste storage area shall also consider the proximity to neighbors and environmentally sensitive areas to minimize impacts on people and the surrounding environment (e.g. impacts due to dust, windblown rubbish, pests, odour, visual amenity, noise and light).

- Suitably sized spill kits and spill containment systems relevant to the activities within the site shall be available in the vicinity of the waste storage areas. Maintenance of spill kits shall be kept
up to date, ensuring that no equipment is missing from the kit. Spills shall not be cleaned by hosing
or activities resulting in the further spread of the contaminant to land or water.

- All waste storage bins shall have secure lids and if required, clasps.

- All waste containers shall be appropriately identified and clearly labelled.

- All lids and if applicable clasps shall be maintained on waste storage bins to ensure that the
waste does not cause an odor nuisance.

- Lids on general waste bins containing food scraps shall be suitable to prevent access by birds.

- Maximum retention times for wastes that may produce odors shall not exceed 7 days.

- Waste shall not be burned.

5.2	Regulated (Hazardous) Waste

Regulated wastes shall be stored in the designated waste storage area. The area shall be clearly marked and records of the waste streams stored at site shall be held by the Site Manager. An assessment of the regulated waste storage area shall be undertaken by the HSE Officer on a regular basis to ensure that incompatible wastes are segregated.

To assist in the collection and transfer of regulated wastes, designated regulated waste bins, drums and skips shall be used where applicable. The following measures shall be implemented:

- There will be dedicated regulated waste storage areas, to prevent the mixing of regulated wastes with other stored material.

- An inventory will be kept and maintained of all regulated waste stored.

- Loading and unloading procedures shall be undertaken in a manner that ensures wastes will not spill or containers break.

- Containers storing regulated wastes shall be securely closed where practical.

- Waste storage areas shall be clearly signed designating what wastes are to be deposited at storage location and any specific directions/hazards.

- All containers shall be labelled at all times for clear interpretation of the contents.

- There will be adequate containment measures to prevent off-site migration of spills.

- Sufficient and appropriate clean equipment (spill kit) shall be provided together with appropriate instructions and training.

- Spills shall not be cleaned by hosing or activities resulting in the further spread of the contaminant to land or water through the drainage channel.

- No liquid wastes, wash down waters or storm water waste contaminated with hazardous waste will be disposed of via the storm water drainage system.

- As soon as practicable, all regulated waste shall be removed to an approved waste disposal facility or recycling facility.

- Waste shall not be burned or allowed to burn.

6.0	 WASTE LABELLING

All wastes shall be labelled in accordance with examples provided in line with the following guidelines:

- Ensure that there are no other labels on the waste container except a label that refers to the current contents of the specific storage vessel or container.

- Containers shall be labelled as soon as the waste is added.

- Labels shall not be placed on a waste storage vessel or container prior to the addition of the waste as any spills may destroy such labels.

- Labels shall be of a reasonable size and clarity so that the waste material is easily identified.

- Labels shall be placed on the side of the containers; however, in the event a label cannot be placed on the side it shall be placed on the top of the container.

- Label shall be positioned such that it can be easily read.

- Do not cover the manufacturer ‘s product label (should the original drum be used) with waste labels.

7.0	WASTE DISPOSAL

All waste generated on site shall be disposed of in accordance with the S.I.15 National Environmental Protection (Management of Solid and Hazardous Wastes) Regulations 1999. Waste management options shall be done in accordance with the waste hierarchy. All other disposal options shall be considered first before sending waste to landfill and all opportunities to reduce waste volumes generated shall be explored.

7.1	Surplus Materials Identification, Classification and Declaration

- Identification

The Site Manager in coordination with Store Supervisor, shall identify materials that are surplus on an ongoing basis during the construction works to avoid unnecessary purchase that may lead to waste generation.

- Classification

Surplus Materials shall be classified by the Project as:

- Obsolete: Where a design change has rendered materials no longer required for incorporation into the construction works.

- Damaged: Where rectification of the damaged Material is not cost effective.

- Scrap and waste materials: Scrap are waste Materials that have no intended Project use which 8.0	WASTE TRANSPORT AND DISPOSAL

Waste shall be segregated accordingly until collection and off-site processing or disposal occurs. All waste volumes shall be transported by a licensed contractor and must be recorded on the Site Waste Report Register.

The following procedure shall be followed when waste collection occurs:

- The waste collector must complete a Waste Consignment note by ensuring that:

- The register has been filled out correctly.

- The type of waste is identified in detail.

- The area where the waste is to be collected is identified.

- The amount of waste to be transported is identified.

- Site contact for the collection of the waste is noted.

- Handling requirements of waste have been identified from the MSDS where applicable or another relevant reference.

- A contact for the waste destination has been identified and notified, where required.

- During the loading of waste, spill kits and firefighting equipment must be made available as applicable.

- If at any time during the load out and transporting event, it is considered unsafe to proceed or there is an increased potential that a waste material may be released to the environment, the activity shall cease, the Site Manager must be informed of the event, and an assessment of the situation must be undertaken.

- All reasonable and practical measures shall be taken to ensure that wastes are adequately secured prior to the waste being transported.

- The appointed waste vendor shall ensure that vehicles and equipment used for the transfer and transportation of wastes are not overloaded or loaded in a manner which could lead to a loss of containment during transportation. This shall be stated as a contract requirement.

- The handling and management of wastes during transport shall be closely monitored to ensure there is no risk of a release to the environment.

9.0 	INSPECTION CHECKLIST AND INVENTORY MANAGEMENT

Weekly visual inspections shall be performed. Evidence of inspection shall be retained and provided as may be required. The inspection checklist and inventory to be applied shall include but not be limited to:

- Labeling

- Bin condition

- House keeping

- Waste Segregation

- Availability of Spill kits

- Materials and Waste Inventory

7.BUDGET

The budget for implementing the ESMP covers activities to be taken to implement this plan.

## Appendix 14: Chance Find Procedures

- INTRODUCTION

Both national regulations and World Bank Environment and Social Standards especially, ESS8: Cultural Heritage, recognize the importance of cultural heritage for current and future generations. Though project sites are not yet known, the project design suggests that there will be no impacts on cultural resources. No works is expected to be carried out in cultural heritage areas. Nevertheless, this ESS is conservatively deemed relevant.

Therefore, the purpose of this chance find procedures is to provide MIC and other parties to the project with the appropriate response guidelines to be applied if previously unknown cultural heritage is encountered. This Chance Find Procedure considers international best practices such WB ESS8, 1972 UNESCO Convention on the Protection of World Cultural and Natural Heritage (World Heritage Convention) and Montenegrin policies and laws for cultural resources protection. Thus, Chance Find Procedures (CFPs) are part of the E&S instruments that may have relevance during Project implementation. The Procedure applies to potential cultural heritage objects features or sites identified because of construction activities in the project area and its surroundings.

- DEFINITIONS

A chance find procedure is a project-specific procedure that outlines actions to be taken if previously unknown cultural heritage is encountered. It is also defined as potential cultural heritage (or paleontological) whether movable or immovable objects, sites, structures, group of structures and natural features and landscapes that have archaeological, historical, religious, and other cultural significance. Cultural heritage recourses may include:

- Artefacts, whole or partial, such as ceramic sherds, stone items, glass fragments, bone, shell, metal, textiles, and plant and animal remains.

- Feature associated with human occupation such as trash dumps, middens, hearths, structural remains.

- Prehistoric or human remains found in formal graves, cemeteries, or as an isolated occurrence.

Non- Cultural Heritage Chance Finds many include modern objects, features, and burials and the decision about whether a Chance Find is a cultural heritage resource requiring additional treatment will be made by the PIU in consultation with the Directorate of Cultural Heritage in the Ministry Culture where necessary.

- PROCEDURES

If any person discovers a physical cultural resource, such as (but not limited to) archaeological sites, historical sites, remains and objects or a cemetery and/or individual graves during excavation or construction, the following procedures shall be applied:

- If the Contractor discovers archaeological sites, historical sites, remains and objects, including graveyard and /or individual graves during excavation or construction, the Contractor shall:

- Stop the construction activities in area of the chance find.

- Delineate the discovered site or area.

- Secure the site to prevent any damage or loss of removable objects. In cases of removable antiquities or sensitive remains, a night guard shall be arranged until the responsible local authorities or National Museum takes over.

- Notify the Environmental and Social Safeguard Specialist (ESSS) who in turn will notify responsible local or national authorities in charge of the Cultural Property i.e. the National Monuments and Relics Commission-NMRC (within 24 hours or less).

- Relevant local or national authorities would oversee protecting and preserving the site before deciding on subsequent appropriate procedures. This would require a preliminary evaluation of the findings to be performed. The significance and importance of the findings should be assessed according to the various criteria relevant to cultural heritage, those include the aesthetic, historic, scientific or research, social and economic values.

- Decision on how to handle the finding shall be taken by the responsible authorities. This could include changes in the layout (such as when finding an irremovable remain of cultural or archaeological importance) conservation, preservation, restoration, and salvage.

- If the cultural sites and /or relics are of high value and site preservation is recommended by the professionals and required design changes to accommodate the request and preserve the site.

- Decisions concerning the management of the finding shall be communicated in writing to relevant authorities.

- Construction works could resume only after permission is granted from the responsible local authorities concerning safeguarding of the heritage.

- DOCUMENTATION

The ESSS will ensure that contractors and sub-contractors staff maintain records of monitoring, Chance Finds, and it will include:

- Daily monitoring records indicating areas and activities monitored, report Chance finds and the results of any evaluations.

- Weekly reports summarising reporting period activities including Chance Finds, assessment and evaluations, internal and external communications and instructions and supporting photographic documentation (or other reference material as appropriate). An additional report aimed at fulfilling any specific Ministry requirements is also anticipated.

- Monthly reports summarising monitoring and evaluation results, status of any site treatment measure requiring instructions to contractor(s) sub-contractor(s), and other internal and external communication. Additional monthly reporting may be required by the respective MDA.

5.CULTURAL HERITAGE TRAINGING

All proposed project personnel are required to receive and comply with the Code of Conduct and receive training and demonstrate competency in (1) the identification of Chance Finds cultural heritage sites, objects, or features and (2) Chance Finds Management Procedure, that is those actions that are required in the case of suspected Chance Find. This training will be incorporated into the overall induction process for firms, contractor (s), and sub-contractor (s) personnel and will include a quick reference hand-out. All employees must be aware of the Montenegrin Policies and Laws on cultural heritage and WB ESS 8 that forbids disturbance or removal of cultural heritage objects offsite for personal gain. Disciplinary action should be taken against any personnel who violate this requirement.

6.REPORTING AND COMMUNICATION

Monitoring, review and reporting will be along with the conduct of ESIA/ESMP/ESMF and RAP/ARAP for the proposed project. Contractor (s); Sub-contractor (s) shall report all records on observational monitoring, protection measures, complaints, and damages to the ESSS on monthly and quarterly basis. The ESSS shall report their monitoring records and the Contractor’s records to MIC which will in turn inform relevant authorities e.g., NMRC on case-to-case basis and on a quarterly basis.

7.IMPLEMNETATION ARRANGEMENTS

The implementation arrangement and responsibilities of the Chance Find Procedures shall be as follows:

| No. | STAKEHOLDER | RESPONSIBILITY | RESPONSIBLE PERSON |
| --- | --- | --- | --- |
| 1 | PIU | -Overall coordination - Lead consultation with relevant authorities and local communities -Implement the procedure and provide required funds. - Monitoring the implementation of chance finds procedures and - Prepared required reports. | ESSS |
| 2 | Contractors and Sub-Contractors | -Stop the construction activities in the chance find -Install temporary site protection measures; and -Inform the client and document chance finds. | Site engineer/Site foreman |
| 3 | MTCA/NMRC | -Verification of chance finds -Approval of the treatment measures; in consultation with stakeholders. -provide the authorisation to resume works in the chance find area | In charge of tourism, culture, relics and monuments |
| 4 | Local Communities | -To attend consultation meetings. -To provide required information. -Participate in treatment measures | Local Population |

8. BUDGET

The budget will depend on the chance finds and the proposed treatment measures. However, a provisional sum has been provided in the main ESMF implementation budget.

9. CONCLUSION

The present Chance Find Procedures serve as international best practice policy for the accidental discovery of heritage resources and provide the framework to handle them. Based on the definitions provided within this document and the proposed procedures of communication and handling chance finds, MTCA will be able to deal properly with the accidental discovery of heritage resources throughout the various phase of the project implementation especially during the construction phase.

## Appendix 15: Sample Incident Form

Part C: To be completed by Borrower (following investigation)

C1: Investigation Findings

For example: - Where and when the incident took place: - Who was involved, and how many people/households were affected: - What happened and what conditions and actions influenced the incident: - what were the expected working procedures and were they followed: - Did the organization or arrangement of the work influence the incident: - Were there adequate training/competent persons for the job, and was necessary and suitable equipment available: - What were the underlying causes; where there any absent risk control measures or any system failures:

C2: Corrective Actions from the investigation to be implemented (To be fully described in Corrective Action Plan)

| Action | Responsible Party | Expected Date |
| --- | --- | --- |

Part C cont.: To be completed by Borrower (following investigation)

| C3a: Fatality/Lost time Injury information Immediate cause of fatality/injury for worker or member of the public (please check all that apply) 2: 1. Caught in or between objects ☐ 2. Struck by falling objects ☐ 3. Stepping on, striking against, or struck by objects ☐ 4. Drowning ☐ 5. Chemical, biochemical, material exposure ☐ 6. Falls, trips, slips ☐ 7. Fire & explosion ☐ 8. Electrocution ☐ 9. Homicide ☐ 10. Medical Issue ☐ 11. Suicide ☐ 12. Others ☐ Vehicle Traffic: 13. Project Vehicle Work Travel ☐ 14. Non-project Vehicle Work Travel ☐ 15. Project Vehicle Commuting ☐ 16. Non-project Vehicle Commuting ☐ 17.Vehicle Traffic Accident (Members of Public Only) ☐ |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Name | Age/DOB | Date of Death/Injury | Gender | Nationality | Cause of Fatality/Injury | Worker (Employer)/Public |

2See Annex 2 for definitions

| C3b: Financial Support/Compensation Types (To be fully described in Corrective Action Plan template) 1. Contractor Direct ☐ 2. Contractor Insurance ☐ 3. Workman’s Compensation/National Insurance ☐ 4. Court Determined Judicial Process ☐ 5. Other ☐ 6. No Compensation Required ☐ |  |  |  |
| --- | --- | --- | --- |
| Name | Compensation Type | Amount (US$) | Responsible Party |

C4: Supplementary Narrative

## Appendix 16: Occupational Health and Safety (OHS) Procedures

The objective of the procedure is to achieve and maintain a healthy and safe work environment for all project workers (contracted workers and community workers) and the host community.

- On procurement for contractors, PIU will avail the ESMF to the aspiring contractors so that contractors include the budgetary requirements for OHS measures in their respective bids.

- The contractor will develop and maintain an OHS management system that is consistent with the scope of work, which must include measures and procedures to address all the following topics listed below and in accordance with local legislation and GIIP (as defined by World Bank Group EHSGs). The management system must be consistent with the duration of contract and the LMP to be prepared under the project.

- Contractor will conduct workplace hazards identification and adopt all applicable E&S risk mitigation measures in accordance with Montenegrin legislation requirements and WBG EHSGs.

- The contractor designates a responsible person to oversee OHS related issues at the project site and define OHS roles and responsibilities for task leaders and contract managers.

- Contractors should put in place processes for workers to report work situations that they believe are not safe or healthy, and to remove themselves from a work situation which they have reasonable justification to believe presents an imminent and serious danger to their life or health, without fear of retaliation.

- Contractor provides preventive and protective measures, including modification, substitution, or elimination of hazardous conditions or substances informed by assessment and plan. Whenever PPEs are required for the work, it must be provided at no cost for the workers.

- Contractors should assess workers’ exposure to hazardous agents (noise, vibration, heat, cold, vapors, chemicals, airborne contaminants etc.) and adopt adequate control measures in accordance with local regulations and WB EHSGs.

- Contractors provide facilities appropriate to the circumstances of the work, including access to canteens, hygiene facilities, and appropriate areas for rest. Where accommodation services are provided to project workers, policies will be put in place and implemented on the management and quality of accommodation to protect and promote the health, safety, and well-being of the project workers, and to provide access to or provision of services that accommodate their physical, social and cultural needs.

- Contractor provides appropriate training/induction of project workers and maintenance of training records on OHS subjects.

- Contractor documents and reports on occupational incidents, diseases and incidents as per ESMF guidance.

- Contractor provides emergency prevention and preparedness and response arrangements to emergency situations including and not limited to workplace accidents, workplace illnesses, flooding, fire outbreak, disease outbreak, labor unrest and security.

- Contractor provides remedies for adverse impacts such as occupational injuries, deaths, disability and disease in accordance with local regulatory requirements and Good International Industry Practices.

- Contractors shall maintain all such record for activities related to safety health and environmental management for inspection by the Ministry of Agriculture, Forestry and Water Management’s PIU or the World Bank.

Appendix 17: World Bank general EHS guidelines

Air Emissions and Ambient Air Quality

Water Quality and Availability

| WHO Ambient Air Quality Guidelines |  |  |
| --- | --- | --- |
|  | Averaging Period | Value in μg/m3 |
| SO2 | 24-hour 10 min | 125 (Interim target-1) 50 (Interim target-2) 20 (guideline) 500 (guideline) |
| NO2 | 1 year 1 hour | 40 (guideline) 200 (guideline) |
| PM 10 | 1 year 24-hour | 70 (Interim target-1) 50 (Interim target-2) 30 (Interim target-3) 20 (guideline) 150 (Interim target-1) 100 (Interim target-2) 75 (Interim target-3) 50 (guideline) |
| PM 2.5 | 1 year 24-hour | 35 (Interim target-1) 25 (Interim target-2) 15 (Interim target-3) 10 (guideline) 75 (Interim target-1) 50 (Interim target-2) 37.5 (Interim target-3) 25 (guideline) |
| Ozone | 8-hour daily maximum | 160 (Interim target-1) 100 (guideline) |

| WHO Guideline values for some chemicals that are of health significance in drinking water |  |
| --- | --- |
| Chemical | mg/l |
| Arsenic | 0.01 |
| Benzene | 0.01 |
| Cadmium | 0.003 |
| Carbon tetrachloride | 0.004 |
| Chlorine | 5 |
| Copper | 2 |
| Fluoride | 1.5 |
| Lead | 0.01 |
| Mercury | 0.0006 |
| Nickel | 0.07 |
| Nitrate | 50 |
| Nitrite | 3 |
| Trichloro acetate | 0.2 |

Ambient Noise Quality

| Applicable Noise Guidelines |  |  |
| --- | --- | --- |
|  | One Hour LAeq (dBA) |  |
| Receptor | Daytime 07:00 - 22:00 | Nighttime 22:00 - 07:00 |
| Residential; institutional; educational | 55 | 45 |
| Industrial; commercial | 70 | 70 |

## Appendix 18: Attendance log

| s/n | Name | Organization | Designation | Email |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| 6 |  |  |  |  |
| 7 |  |  |  |  |
| 8 |  |  |  |  |
| 9 |  |  |  |  |
| 10 |  |  |  |  |
| 11 |  |  |  |  |
| 12 |  |  |  |  |
| 13 |  |  |  |  |
| 14 |  |  |  |  |

Appendix 19: Sample Code of Conduct for Contractors’ GBV/SEA/SH Prevention and Response

To build a system for SEA/SH risk prevention and mitigation, projects must:

- Have all employees of contractors (including sub-contractors), supervising Engineers and other consultants with a footprint on the ground in the project area sign CoCs.

- Have an effective SEA/SH Prevention and Response Action Plan so that workers understand behavior expectations and policies, as well as an effective GM. This Action Plan should include training and communication. It should also include plans to make the project-affected community aware of the CoC the project staff have just signed; and

- As part of the SEA/SH Prevention and Response Action Plan, define accountability and response protocols, which set out the procedures followed for holding individuals accountable and penalizing staff that have violated SEA/SH policies.

Sample Code of Conduct for Contractor’s Personnel

We are the Contractor, [enter name of Contractor]. We have signed a contract with [enter name of Employer] for [enter description of the Works]. These Works will be carried out at [enter the Site and other locations where the Works will be carried out]. Our contract requires us to implement measures to address environmental and social risks related to the Works, including the risks of sexual exploitation and abuse and gender-based violence.

This Code of Conduct is part of our measures to deal with environmental and social risks related to the Works. It applies to all our staff, laborers and other employees at the Works Site or other places where the Works are being carried out. It also applies to the personnel of each subcontractor and any other personnel assisting us in the execution of the Works. All such persons are referred to as “Contractor’s Personnel” and are subject to this Code of Conduct.

This Code of Conduct identifies the behavior that we require from all Contractor’s Personnel.

Our workplace is an environment where unsafe, offensive, abusive or violent behavior will not be tolerated and where all persons should feel comfortable raising issues or concerns without fear of retaliation.

REQUIRED CONDUCT

Contractor’s Personnel shall:

- carry out his/her duties competently and diligently

- comply with this Code of Conduct and all applicable laws, regulations and other requirements, including requirements to protect the health, safety and well-being of other Contractor’s Personnel and any other person

- maintain a safe working environment including by:

  - ensuring that workplaces, machinery, equipment and processes under each person’s control are safe and without risk to health

  - wearing required personal protective equipment

  - using appropriate measures relating to chemical, physical and biological substances and agents; and

  - following applicable emergency operating procedures.

- report work situations that he/she believes are not safe or healthy and remove himself/herself from a work situation which he/she reasonably believes presents an imminent and serious danger to his/her life or health;

- treat other people with respect, and not discriminate against specific groups such as women, people with disabilities, migrant workers or children;

- not engage in any form of sexual harassment including unwelcome sexual advances, requests for sexual favors, and other unwanted verbal or physical conduct of a sexual nature with other Contractor’s or Employer’s Personnel;

- not engage in Sexual Exploitation, which means any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another. In Bank- financed projects/operations, sexual exploitation occurs when access to or benefit from Bank- financed Goods, Works, Consulting or Non-consulting services is used to extract sexual gain;

- not engage in Rape, which means physically forced or otherwise coerced penetration—even if slight—of the vagina, anus or mouth with a penis or other body part. It also includes penetration of the vagina or anus with an object. Rape includes marital rape and anal rape/sodomy. The attempt to do so is known as attempted rape. Rape of a person by two or more perpetrators is known as gang rape;

- not engage in Sexual Assault, which means any form of non-consensual sexual contact that does not result in or include penetration. Examples include: attempted rape, as well as unwanted kissing, fondling, or touching of genitalia and buttocks not engage in any form of sexual activity with individuals under the age of 18, except in case of pre-existing marriage;

- complete relevant training courses that will be provided related to the environmental and social aspects of the Contract, including on health and safety matters, and Sexual Exploitation, and Sexual Abuse (SEA);

- report violations of this Code of Conduct; and

- not retaliate against any person who reports violations of this Code of Conduct, whether to us or the Employer, or who makes use of the [Project Grievance [Redress] Mechanism].

RAISING CONCERNS

If any person observes behavior that he/she believes may represent a violation of this Code of Conduct, or that otherwise concerns him/her, he/she should raise the issue promptly. This can be done in either of the following ways:

- Contact [enter name of the Contractor’s Social Expert with relevant experience in handling gender- based violence, or if such person is not required under the Contract, another individual designated by the Contractor to handle these matters] in writing at this address [  ] or by telephone at [ ] or in person at [ ]; or

- Call [ ] to reach the Contractor’s hotline (if any) and leave a message.

The person’s identity will be kept confidential, unless reporting of allegations is mandated by the country law. Anonymous complaints or allegations may also be submitted and will be given all due and appropriate consideration. We take seriously all reports of possible misconduct and will investigate and take appropriate action. We will provide warm referrals to service providers that may help support the person who experienced the alleged incident, as appropriate.

There will be no retaliation against any person who raises a concern in good faith about any behavior prohibited by this Code of Conduct. Such retaliation would be a violation of this Code of Conduct.

CONSEQUENCES OF VIOLATING THE CODE OF CONDUCT

Any violation of this Code of Conduct by Contractor’s Personnel may result in serious consequences, up to and including termination and possible referral to legal authorities. FOR CONTRACTOR’S PERSONNEL:

I have received a copy of this Code of Conduct written in a language that I comprehend. I understand that if I have any questions about this Code of Conduct, I can contact [enter name of Contractor’s contact person with relevant experience in handling gender-based violence] requesting an explanation.

Name of Contractor’s Personnel: [insert name]

Signature:

Date: (day month year):

Counter signature of authorized representative of the Contractor:

Signature:                 _______________Date: (day month year):  		_______________

## Appendix 19: Sample Contractor ESMP (C-ESMP)

#### a. Project Background and Description

#### c. Environmental and Social Management Measures

Occupational Health and Safety (OHS)

Community Health and Safety

Labor Management

- Labor Management Procedures (LMP): Local hiring, prevention of child and forced labor, fair working conditions, and workers’ accommodation standards.

- Code of Conduct for all workers, including SEA/SH (Sexual Exploitation and Abuse/Sexual Harassment) prevention and sanctions

Waste and Resource Management

- Solid and liquid waste management plans, including safe disposal of construction debris and hazardous materials.

- Resource efficiency measures (water, energy, materials).

Cultural Heritage

- Chance Finds Procedure: Protocols for unexpected archaeological or cultural discoveries during excavation

#### d. Monitoring and Reporting

- Regular site inspections and audits by the contractor and PIU.

- Monthly and quarterly E&S compliance reports, including incident logs, training records, and grievance logs.

- Third-party audits as required by the ESCP (Environmental and Social Commitment Plan)

#### e. Training and Capacity Building

- Induction and ongoing training for all workers on ESMP implementation, OHS, SEA/SH, and grievance procedures.

- Community awareness sessions prior to commencement of works

Official Gazette of Montenegro, No. 4/2019, 8/2021, 59/2021, 68/2021 i 145/2021.

Official Gazette of Montenegro, No. 34/14, 44/18

https://www.monstat.org/uploads/files/popis%202021/pr.podaci/Preliminarni%20rezultati%20popisa%2025.01.2024.pdf

SAOPSTENJE_Popis stanovnistva 2023 I_cg.pdf (monstat.org)

A 1.82 conversion factor used here, derived from the reported value for Croatia in the FAO 2020 Forest Product

Conversion Factors report. See: https://openknowledge.fao.org/server/api/core/bitstreams/eebaeee6-cd98-4b35-9143-21f96fad16af/content.

2024 Country Market Statement for Montenegro: https://unece.org/sites/default/files/2024-09/mtn-country-market-statement-2024-COFFI.pdf

By comparison, most internationally competitive sawmills and wood-furniture manufacturing firms need to have assets and revenues in excess of €50 million.

https://www.monstat.org/cg/page.php?id=17&pageid=17

https://www.monstat.org/uploads/files/BDP/BDP%202023/Godisnji%20BDP%202023_crn.pdf

file:///C:/Users/kristina.lapcevic/Desktop/Sumarstvo%20SB/cbcg_annual_report_2023.pdf

https://monstat.org/cg/publikacije_page.php?id=2324

ESSPROS -2022-22.07.2024--eng.pdf (monstat.org)

https://openknowledge.worldbank.org/server/api/core/bitstreams/03382077-6525-4e15-aa34-f7db5674a5e8/content

Healthcare development strategy for 2023-2027

https://documents1.worldbank.org/curated/en/157871484635724258/pdf/112110-WP-Final-General-EHS-Guidelines.pdf?_gl=1*1o0flug*_gcl_au*MjUzMzQ3OTI3LjE3MTkzMjI0MDA.

https://cdn.who.int/media/docs/default-source/wash-documents/water-safety-and-quality/dwq-guidelines-4/gdwq4-with-add1-annex3.pdf?sfvrsn=f5f6be22_3

For acceptable indoor noise levels for residential, institutional, and educational settings refer to WHO (1999).