VOLUME 2

SECTION 3

PARTICULAR CONDITIONS OF CONTRACT

PARTICULAR CONDITIONS OF CONTRACT

The Particular Conditions are set out hereunder and include amendments and additions to the General Conditions.

In case of ambiguities and discrepancies between the Clauses in the General Conditions and their corresponding Clauses in the Particular Conditions, the Particular Conditions shall prevail.

| Sub-Clause reference | Text |  |
| --- | --- | --- |
| 1 | General Provisions |  |
| 1.1 | Definitions |  |
| 1.1.1.1 | Replace Sub-Clause 1.1.1 with: ““Contract” means the Contract Agreement and the documents listed in Article 2 therein.” |  |
| 1.1.1.2 | Delete” if any” from the definition. |  |
| 1.1.1.3 | Replace Sub-Clause 1.1.1.3 with: A Letter of Acceptance will not be issued. All references to the Letter of Acceptance shall be deemed to mean the Contract Agreement. |  |
| 1.1.1.4 | Replace Sub-Clause 1.1.1.4 with: “Letter of tender” should be read as “Tender Form”. |  |
| 1.1.1.5 | Replace the Sub-Clause 1.1.1.5 with: The "Employer's Requirements" comprise Volume 3 of the Tender Dossier, as completed by the Schedules referred below. |  |
| 1.1.1.8 | Insert the following sentence at the end: The word Tender is synonymous with Bid and the words Appendix to Tender with Appendix to Bid, and the words Tender Documents with Bidding Documents. |  |
| 1.1.1.11 | Add new sub-clause 1.1.1.11: “PRAG” means Practical Guide to contract procedures for EU external actions, dated March 2014. |  |
| 1.1.1.12 | Add new sub-clause 1.1.1.12: “Addendum to Contract” means a document prepared by the Employer which is to be signed by the Contractor in accordance with PRAG section 5.7 as and when required for refinancing purposes by the Employer. This requirement does not relieve the parties from their responsibilities under the Contract. |  |
| 1.1.1.13 | Add new sub-clause 1.1.1.13: "Construction Diary" is a document which in the period of works performance, permanently and day to day is managed on the construction site and in which as a minimum are included the following data: date, working time, weather conditions, the number, the structure and qualification of the labour and the Contractor personnel, the assigned construction equipment, plants and Contractors equipment, description of the performed works with precise indication of the items according to Breakdown of prices contained in the Schedule of Prices, different types of information which the Contractor and the Engineer exchange, guidelines, orders of the Engineer and similar. The Contractor manages the Construction Diary in original and copy, where upon the original is for the Engineer and the copy remains for the Contractor. In each moment the Construction Diary should be on disposal to the Engineer in order to be able to make checks, comments, corrections, remarks and signature. |  |
| 1.1.1.14 | Add new sub-clause 1.1.1.14: "Construction Book" is a document which, during the period of performance on Construction works is permanently managed on the construction site, and in which based on the measurements which are executed by both, the Contractor and the Engineer or are performed by the Contractor, are checked and approved by the Engineer, the quantities of the performed construction works are including by items within the Breakdown of prices contained in the Schedule of Prices. The Contractor manages the Construction Book in original and copy, where upon the original is for the Engineer and the copy remains for the Contractor. In each moment the Construction Book should be on disposal to the Engineer in order to be able to make checks, comments, corrections, remarks and signature. The Construction Book shall be basis for preparation of the Interim Payment Certificates. |  |
| 1.1.2.2 | Insert at the end of Sub-Clause: Employer is synonymous to Contracting Authority as used under PRAG and in the tender documents. |  |
| 1.1.2.6 | Insert at the end of Sub-Clause: Subject to notification, Employer’s Personnel may include persons acting for the Beneficiary. |  |
| 1.1.2.11 | Add new Sub-Clause: “Beneficiary” means the final beneficiary of the contract works and is the entity named as such in the Appendix to Tender and the legal successors in title to this person. |  |
| 1.1.3.10 | Add new Sub-Clause 1.1.3.10: “Signature Date” means the date of signature of the Contract by the last party. |  |
| 1.1.6.1 | In Sub-Clause 1.1.6.1, after ‘computer programs and other software’, add: “(including the coding)” In the 3rd line, after the word “nature”, insert the following: “including documents created on disks, diskettes, tapes or other electronically readable media.” |  |
| 1.1.6.2 | Delete the definition and replace with: “Country” means the Beneficiary Country. |  |
| 1.1.6.3 | Replace Sub-Clause 1.1.6.3 with: “Employer’s Equipment” means apparatus, machinery and vehicles (if any) made available by the Employer for use by the Contractor in the execution of the Works. |  |
| 1.1.6.6 | Add as last sentence to Sub-Clause 1.1.6.6; “Performance Security” is synonymous to “Performance Guarantee” as used under PRAG and in the tender documents. |  |
| 1.1.6.7 | Insert as last sentence to Sub-Clause 1.1.6.7; Additional working areas required by the Contractor for the sole purpose of this contract, and the areas required for any temporary traffic diversions, shall be arranged and provided by the Contractor, but shall be deemed to form part of the Site. |  |
| 1.1.6.10 | Add new Sub-Clause 1.1.6.10: "Eligible Country" means the Member States of the European Union or a country or territory of the regions covered and/or authorised by the specific instruments applicable to the IPA programme, [Council Regulation (EC) No 1085/2006 of 17 July 2006 establishing the Instrument for Pre-Accession Assistance (IPA). (OJ L 210 of 31/07/2006)], under which the contract is financed. |  |
| 1.2 | Interpretation In Sub-Clause 1.2, after sub-paragraph (d), insert the following paragraphs: (e) Wherever throughout the Contract reference is made to the date of the Letter of Acceptance, the date considered shall be the Signature Date. (f) In these Conditions, provisions including the expression "Cost plus reasonable profit " require this profit to be one-twentieth (5%) of this Cost. |  |
| 1.5 | Priority of Documents Delete the sub-clause and replace with: “The documents forming the Contract are to be taken as mutually explanatory of one another. For the purpose of interpretation, the priority of the documents shall be as listed in the Contract Agreement. If an ambiguity or discrepancy is found in the documents, the Engineer shall issue any necessary clarification or instruction” |  |
| 1.6 | Contract Agreement Delete the first sentence of the sub-clause and replace with: Contract preparation and signature procedure is described in the Item 2.9.2. Contract Preparation and Signature of the PRAG |  |
| 1.10 | Employer's Use of Contractor's Documents In the second sentence, after the word “Employer”, insert: and the Beneficiary, and, after "Contractor’s Documents", insert: and other design documents made by (or on behalf of) the Contractor. In the last sentence, after the word “Employer", insert: and the Beneficiary |  |
| 1.12 | ### Confidential Details Insert the following paragraph to Sub-Clause 1.12: The Contractor shall treat the details of the Contract as private and confidential, save insofar as may be necessary for the purposes thereof, and shall not publish or disclose the same or any particulars thereof in any trade or technical paper or elsewhere without the previous consent in writing of the Employer. If any dispute arises as to the necessity of any publication or disclosure for the purpose of the Contract the same shall be referred to the Employer, whose decision shall be final. |  |
| 1.13 | Compliance with Laws In Sub-Clause 1.13, paragraph (a), replace the first two occurrences of ‘Employer’ with ‘Beneficiary’. In paragraph (b), 1st line, after “Contractor” insert: “(in his or the Beneficiary’s name, as the authority in charge may request)” In paragraph (b), last phrase, after “Employer” insert “and the Beneficiary” |  |
| 1.15 | Electronic Formats Add new Sub-Clause 1.15: All notices and documents required to be submitted by the Contractor shall also be submitted electronically in formats that can be read by: - Microsoft Word 2003 – for text - AutoCAD version 2005 – for drawings - Microsoft Project 2003 – for planning - Microsoft Excel 2003 – for numerical information. Where any documents, programmes, graphics or the like are provided in electronic format, other than above listed, then, on the request, software necessary for the reading of such documents shall be provided to the Employer and the Engineer together with a hard copy of such document. |  |
| 1.16 | European Commission Audit Add new Sub-Clause 1.16 : The Contractor shall afford full access and co-operation to representatives of the European Commission and the European Court of Auditors to enable them to inspect and audit any aspect of the Contract. Throughout the performance of the Contract and for a period of seven years following the date of the Taking-Over Certificate for the whole of the Works, the Contractor shall ensure that the services of the European Commission, the European Court of Auditors and the authorities of the recipient countries are given access (including by any Subcontractors) to all supporting documents required for carrying out the necessary checks. To this end, the Contractor shall undertake, having been given a notice of eight working days, to authorise access to his premises to all persons authorised to carry out these checks. |  |
| 2 | The Employer |  |
| 2.1 | Right of Access to the Site After the first paragraph insert: “The Contractor shall be responsible for obtaining and observing all necessary permits (excluding Building permit, which shall be obtained and provided by, or on behalf of the Beneficiary), including their payment, and all additional costs incurred by having to conduct the Works in the specified area”. |  |
| 2.2 | Sub-Clause 2.2. Permits, Licences or Approvals In Sub-Clause 2.2, beginning of first line, after “The Employer”, add: “and/or the Beneficiary.” Add at the end of the Sub-clause : “It is the sole responsibility of the Contractor to obtain, in due time, all other necessary permissions, licences or approvals for construction and operation than the above mentioned (i), (ii) and (iii).“ |  |
| 2.6 | The Beneficiary Add new Sub-Clause 2.6: “The Employer may assign any of his rights or duties under the Contract to the Beneficiary. The Employer shall notify, in accordance with Sub-Clause 1.3 [Communications] of Conditions of Contract, the Contractor and the Engineer of the powers delegated. The Beneficiary shall have no authority to amend the Contract, to issue instructions under it, or to assign any part of the Contract or any benefit or interest in or under it, except as may be agreed by the Employer and the Beneficiary. If the Contractor takes any action pursuant to an Beneficiary’s communication without first obtaining confirmation of the communication from the Employer and/or the Engineer, the Contractor shall not be entitled to additional payment, or an extension of the Time for Completion, and the Employer shall be discharged from all liability in connection with any claim in respect of the Beneficiary’s communication. This Particular Condition 2.6 will remain in effect throughout the life of the Contact, including after taking over of the Works, and the possible transfer of title and ownership of the Works to the Beneficiary has occurred. Whenever the Employer takes over the Works or a Section or other part of the Works under Clause 10 [Employer’s Taking Over], or whenever, the ownership of any materials, Plant or Works is transferred to the Employer, such Works, Section, Plant or Materials are simultaneously transferred to the Beneficiary that shall undertake all Employer’s responsibilities under the law, in that respect.” |  |
| 3 | The Engineer |  |
| 3.1 | Engineer’s Duties and Authority At the end of Sub-Clause 3.1, insert: “The Engineer shall obtain the specific approval of the Employer before taking action under the following Sub-Clauses of these Conditions: - Sub-Clause 3.5: agreeing or determining any matter, which will increase the Accepted Contract Amount; - Sub-Clause 4.4(b): giving consent to a subcontractor for a subcontract for which a different subcontractor is named in the Contract; - Sub-Clause 8.4: instructing, agreeing or determining an extension of the Time for Completion; - Clause 13: instructing a Variation which is expected to increase the Contract Price or in any substantial way change the scope, character or quality of the Works and in particular any instruction concerning the use of the provisional sums. - Sub-Clause 10.1: before issuing any Taking-Over Certificate; - Sub-Clause 11.9: before issuing the Performance Certificate. Notwithstanding the obligation, as set out above, to obtain approval, if, in the opinion of the Engineer, an emergency occurs affecting the safety of life or of the Works or of adjoining property, he may, without relieving the Contractor of any of his duties and responsibilities under the Contract, instruct the Contractor to execute all such work or to do all such things as may, in the opinion of the Engineer, be necessary to abate or reduce the risk. If such instruction constitutes a Variation, it shall be evaluated in accordance with Clause 13. The Engineer is required to continuously monitor the Contractor’s compliance with the proposed and approved Safety Methodology, and shall ensure certification of compliance. |  |
| 3.5 | Determinations Replace second sentence of the first paragraph with: “If agreement is not achieved, the Engineer shall, within 28 days after failure to reach agreement, make a fair determination in accordance with the Contract, taking due regard of all relevant circumstances.” |  |
| 3.6 | Management Site Meetings Add new Sub-Clause 3.6: “The Engineer or the Contractor’s Representative may require the other to attend a management meeting in order to review the arrangements for future work. The Engineer shall record the business of management meetings and shall supply copies of the records to those attending the meeting and to the Employer. Progress meetings shall be held at regular intervals but not exceeding once a month. These meetings shall be attended by the Contractor’s Representative and other key personnel, site agents of Sub-Contractors and the Engineer. The Employer may but is not obliged to attend the progress meetings. The agenda for such meetings shall cover a review of progress attained, a review of schedules and plans for future activities, the status of staffing, engineering, safety, equipment, material supply, payments, current and anticipated difficulties, interface with other Contractors, claims for extras, and other pertinent topics. The Progress Report produced by the Contractor under Sub-Clause 4.21 [Progress Reports] for the previous month shall be issued to the Engineer 5 days before the Progress Meeting and shall be approved (or otherwise) by the Engineer during such meetings. The minutes of meetings signed by the Contractor, the Engineer and the Employer (if attending) shall constitute an official record of matters discussed, but shall not replace any requirement in the Contract for approvals, instructions, decisions or notices to be submitted in writing. The Contractor’s Representative shall, when so requested with reasonable notice, attend any other meetings convened by the Engineer to review Works progress or other relevant matters together with representatives of the Employer and/or any other representatives of concerned authorities.” “The Contractor’s Representative shall attend Management Meetings and Progress Meetings at dates and times agreed with the Engineer throughout the continuance of the Contract. The Contractor’s Site Manager shall attend weekly site meetings with the Engineer throughout the continuance of the Contract.” |  |
| 3.7 | Accommodation for the Engineer Add new Sub-Clause 3.7: If applicable, within 14 days from the commencement of the works the Contractor shall provide the offices and equipment required by the Engineer’s staff, according to the Breakdown of tender price and Employer’s Requirements. Until such offices and equipment are provided, the Contractor shall make available, free of charge, temporary offices and equipment necessary for normal implementation of the Engineer duties. |  |
| 4 | The Contractor |  |
| 4.1 | Contractor’s General Obligations Insert after the first paragraph the following text: The Contractor shall carry out and be responsible for design of all temporary works. Drawings submitted to the Engineer for approval shall be submitted in sufficient time to afford the Engineer adequate opportunity to examine, check and call for any necessary modification by the Contractor before approval is given while complying with deadline stipulated in the Sub-Clause 5.2. No examination by the Engineer of any drawings submitted by the Contractor or the approval expressed by the Engineer thereto shall relieve the Contractor of any liability imposed by any provisions of the Contract, or of his responsibilities under the Contract. Add to Sub-Clause 4.1 the following: The Contractor shall promptly notify the Employer and the Engineer of any error, omission, fault or any other defect in the Design, Drawings, Technical Specifications and geodetic data (benchmarks, control points and structures) or other information provided for the Works, which the Contractor discovers during the process of execution of the Works. If the Contractor fails to do this and delays and other deviations from the Contract appear as a consequence of this, then the Contractor has no right to make claims for any costs and will be responsible for such consequences whenever the Employer suffers any of such damages. The Contractor shall keep a Construction Diary in the form acceptable to the Engineer. The Diary shall be kept daily, the pages shall have running numbering and the Diary shall be signed daily by the Contractor and the Engineer. Distribution of copies of the pages shall be as instructed by the Engineer. |  |
| 4.2 | Performance Security After the first paragraph add: “The Performance Security, submitted by the Contractor, shall be in the format given in Volume 2 of the Tender Dossier and shall be furnished by a bank registered in one of the Member States of the European Community or the state in which the Contractor is established or licensed to do business.” Delete the 1st sentence of the 2nd paragraph and replace with: “The Contractor shall, together with the return of the countersigned Contract, furnish the Contracting Authority with a Performance Security for the full and proper performance of the contract.” Insert at the end of the third paragraph the following text: Where more than one Taking-over Certificate is issued, the Performance Security shall remain in effect until the Works have been completed and any defects have been remedied with relation to the last section taken–over. Delete the last paragraph of Sub-Clause and substitute: “The Performance Security shall be released within 45 days after completion of the following events whichever occurs last: a) the issuance of the Performance Certificate under Sub-Clause 11.9 [Performance Certificate] . b) the receipt from the Contractor of a written discharge together with a letter of release issued by Ministry of Labour and Social Security confirming the Contractor has fulfilled all his statutory Social Security obligations arising out of or in connection with the performance of the Contract to the Employer provided that the laws and regulations require so.” Add at the end of the Sub-Clause: Whenever the Engineer determines an addition or a reduction to the Contract Price as a result of a change in cost and/or legislation, or as a result of a Variation amounting to more than 10 percent of the portion of the Contract Price, the Contractor shall, at the Engineer’s written request promptly increase, or decrease, as the case may be, the value of the Performance Security by a corresponding percentage. Where the Contractor is a joint venture/consortium, the Performance Security shall be in the form of a single security, and shall be either in the name of the joint venture/ consortium or in the name of the leader. |  |
| 4.3 | Contractor’s Representative Add at the end of the Sub-Clause: “The Contractor’s Representative shall be able to communicate competently in written and spoken English. The Contractor’s Representative, or a suitable temporary replacement, shall be available on the site every working day” |  |
| 4.4 | Subcontractors Insert at the beginning of the sub clause: “The Contractor shall not subcontract any part of the works without the prior consent of the Engineer and afterwards the written authorization of the Contracting Authority/Employer. The elements of the Contract to be subcontracted and the identity of the subcontractors should be notified to the Contracting Authority/Employer and the Engineer by the Contractor. After getting the approval of the Contracting Authority/Employer, the Engineer shall notify the Contractor of its decision within 14 days of receiving the Contractor’s request, stating its reasons if authorization is withheld. The Contractor shall be responsible for the acts, defaults and negligence of his subcontractors and their agents or employees, as if they were the acts, defaults or negligence of the Contractor, his agents or employees. The approval by the Contracting Authority/Employer of the subcontracting of any part of the contract or of the subcontractor to perform any part of the works, after consent of the Engineer, shall not relieve the Contractor of any of his obligations under the contract.” Replace first sentence with: “The Contractor shall not subcontract above percentage stated in the Contract Data (Appendix to tender).” At the end of Sub-Clause 4.4, add: “(d) Where Subcontractors are named in the Contract as carrying out certain activities, the Contractor may not change the scope or scale or limits of such activities without prior written approval of the Engineer. The Contractor shall ensure that all its Subcontractors and suppliers are natural and/or legal person from one of the Eligible Source Countries as defined under Particular Condition, Sub‐Clause 1.1.6.10 [Other Definitions]. Subcontractors must satisfy the eligibility criteria applicable for the award of the Contract and they cannot be in any of the situations excluding them from participating in contracts which are listed in the current Section 2.3.3 [Grounds for exclusion] of the Practical Guide to Contract Procedure for EU External Actions.” |  |
| 4.6 | Co-operation In Sub-Clause 4.6, sub-paragraph (a), after “Employer’s”, insert: or the Beneficiary’s. In sub-paragraph (b), after “Employer”, insert: or the Beneficiary. In last paragraph, first line, after “Employer” insert: or the Beneficiary. |  |
| 4.8 | ## Safety Procedures Add the following sub-paragraphs at the end of the Sub-clause: (f) comply with all safety regulations and systems made and operated by the Beneficiary. Safety issues shall be on the agenda of all site meetings and plans shall be jointly agreed between the Engineer and the Contractor’s Representative for minimising the risk of unsafe events and working practices in forthcoming work. The Site shall be a “hard hat” Site and safety hats shall be worn at all times, (g) comply with all applicable current rules, regulations and specifications, with respect to all measures, operations and administrative steps required for the full protection and safeguarding of the environment. (h) the Contractor will be responsible for the proper disposal of all solid and fluid waste from all places within the Site and shall comply strictly with the regulations of the relevant authorities. (i) the Contractor shall report to the Engineer details of any accident as soon as possible after its occurrence. In the case of any fatality or serious accident the contractor shall, in addition, notify the Engineer immediately by the quickest available means. The Contractor shall also report such accident to the competent authority, whenever such report is required by law. |  |
| 4.9 | Quality Assurance Add after the last paragraph: The Quality Assurance system shall: (a) ensure that all materials and plant delivered to site are traceable as compliant with a recognised international standard for the material or plant, (b) include procedures for checking compliance and filing of compliance certificates, and (c) include an electronic and paper filing system for storing all certificates and delivery dates. |  |
| 4.10 | Site Data In Sub-Clause 4.10, 1st line, after “Employer” insert: and the Beneficiary, In 2nd line, after “Employer’s” insert: or the Beneficiary’s, In 3rd/4th line after “Employer” insert: and the Beneficiary, In 5th line, after “Employer’s” insert: or the Beneficiary’s. |  |
| 4.14 | Avoidance of Interference At the end of point (b of the first paragraph, insert “or” and add the following point (c): (c) the Beneficiary's or any other local body's supplies and services on the Site including, without limitation, oil, electricity, water, telephone, buried cables and sewerage. In the first line of the last paragraph, after “Employer”, insert: and the Beneficiary. Add the following final paragraphs: “The Contractor shall acquaint himself by whatever means necessary with the position of all existing railroads, any rail equipment and the like, roads and services of any kind including drains, telephone, electricity lines and poles, water pipes, sewers and the like, before any excavation or other work likely to affect the existing services is commenced. The Contractor will be liable for all damage to railroads, any rail equipment and the like, roads and services of any kind caused by him or his Sub-contractors in the execution of the Works. He shall make good any such damage at his own expense and to the complete satisfaction of the Engineer as soon as possible and in any event within the Time for Completion. The Contractor shall make all necessary arrangements with the relevant local bodies and owners for the removal and reinstatement of all services as agreed with or instructed by the Engineer. The Contractor shall bear the cost of these works.” |  |
| 4.17 | Contractor’s Equipment Insert the following first paragraph: The Contractor shall use for the execution of the works equipment of not lower quality than the equipment proposed in the tender. No equipment given in the tender shall be removed from the site without prior permission of the Engineer. |  |
| 4.18 | Protection of the Environment Add the following paragraphs: The Contractor shall comply will all applicable current legislation, regulations and specifications with respect to all measures, operations and administrative steps required for the full protection and safeguarding of the environment. The Contractor will be responsible for the proper disposal of sewage from all places within the Site and shall comply strictly with the regulations of the relevant authorities. The Contractor shall comply with the regulations of the Employer and the fire fighting authorities and take all necessary precautions throughout the execution and completion of the Works to prevent outbreak of fire. During the execution and completion of the Works, the Contractor shall protect the environment on and off the Site from contamination. Accordingly, the Contractor shall collect all kinds of waste, including offal, production and communal wastes, and transport them to a waste landfill approved by the Engineer. The Contractor shall not release, or permit to be released into the air, water and land area at or in the vicinity of the Site any toxic or harmful effluent or substance, and shall indemnify the Employer against any claims or liability arising from any breach of his obligation. Where the Contractor’s activity is subject to regulation under applicable environmental Laws, the Engineer may require the Contractor to submit evidence of his compliance with such Laws, including but not limited to, the submission of any required permits, payment of fees, or compliance with any obligatory administrative procedures. |  |
| 4.19 | Electricity, Water and Gas In the second paragraph of Sub-Clause 4.19 after „are given in the Employer's requirements“ insert : or in accordance with valid act and prices of the provider or the Beneficiary In the last sentence of Sub-Clause 4.19, delete full stop and after ‘Employer’ insert: or the Beneficiary, according to the provider of the services. |  |
| 4.21 | Progress Reports Add at the end of the sub-clause: “(i) Records of personnel and Contractor's equipment on site” “(ii) Progress reports shall be submitted in English with a Montenegrin translation” |  |
| 4.22 | Security of the Site Insert at the end of this Sub-Clause 4.22: “For the purposes of this Sub-Clause, the railways users and repairman shall not be considered as unauthorised persons in the normal use of the railways and access to repairman properties. Such use and access shall be regulated as part of the Contractor’s traffic management plan.” |  |
| 4.23 | Contractor's Operations on Site At the end of the second paragraph, add the following paragraph: “If the Contractor fails to remove equipment, plant, materials or temporary works from the Site within a period of 28 days after completion of the Works, the Employer may remove them at the expense of the Contractor.” Add at the end of Sub-Clause: No important operation of any kind, especially cutting through or closing existing roads, water conduits or public utilities shall be carried out without the written consent of the Engineer. The Contractor shall apply to the Engineer in writing for such consent, at least 14 days prior to the proposed start of such operation. He shall include with the application full details of the operation, the programme, the major items of plant to be employed and enclose copies of all necessary permits obtained in accordance with Sub-Clause 1.13. |  |
| 4.24 | ## Fossils Replace 1st phrase of 1st paragraph with: “All fossils, coins, articles of value or antiquity, and structures and other remains or items of geological or archaeological interest found on the Site are the property of the Beneficiary’s Country, as per Beneficiary Country’s legislation and the Contractor shall place any such item under the care and authority of the relevant Beneficiary Country’s Authorities as directed by the Engineer” |  |
| 4.25 | ## Breakdown of Prices and Rates Add new Sub-Clause as follows: Where appropriate and within a period of not more than 21 days following the Engineer’s reasoned request, the Contractor shall provide a detailed breakdown of all his rates and prices including unit price analyses where such breakdown is required for any purpose under the contract. |  |
| 4.26 | Works Diary Add new Sub-Clause as follows: Works Diary, being a synonymous for Works register, and technical rules drawing up the statements shall be as set out in the Regulation on the Contents and the Method of Keeping the Building Log Book, Works Register and Inspection Records [Pravilnik o sadržini i načinu vođenja građevinskog dnevnika, građevinske knjige i knjige inspekcije ("Sl. list Crne Gore", br. 81/08 od 26.12.2008)], including amendments, if any. “The Contractor shall draw up a daily works diary in duplicate for contemporary records, in a format agreed by the Engineer. The works diary shall be held on Site and the Contractor’s Representative shall daily record the following information (as a minimum): a) Atmospheric conditions, the work breaks due to adverse meteorological conditions, the working hours, the number and the qualification of the personnel working on Site, the supplied materials, the materials incorporated into the works, the equipment out of order, the tests completed, the sent samples, the unforeseen events, as well as verbal orders given to the Contractor. b) Attachments with detailed data on all elements which are checked on Site and used for the calculation of the payments to the Contractor, such as completed Works, actual quantities, supplies accepted for incorporation into the Works. These attachments are part of the works diaries, but can be signed, if need be, as separate documents. c) Work achieved that day and list of any obstructions and other difficulties encountered by the Contractor in the execution of the Works, during the reported period, including accidents or other Health & Safety related data. d) The number of persons employed the Contractor’s Equipment in use on site, broken down by trade and grade. At the Engineer’s request, the Contractor has to provide all necessary information for the daily completion of the works diary and attachments. The information provided is noted in the works diary and attachments, signed by the Contractor’s Representative and countersigned by the Engineer or his representative. The Engineer shall keep one of the signed copies and the Contractor the other. In case of disagreement on a subject noted in the works diary or attachments, the Contractor has to inform in writing the Engineer about his remarks within 14 days from the date when the notice has been recorded in the works diary or attachments.” The Contractor shall prepare a weekly report in a format to be agreed with the Engineer. Copies of this report shall be faxed or otherwise transmitted weekly to the Engineer one day before the weekly site meeting or as otherwise agreed. The Contractor shall sign the original of the report and the Engineer shall retain the original. The Contractor shall maintain and keep up to date all official records and reports required according to local requirements.” |  |
| 4.27 | Site Information Boards Add new Sub-Clause as follows: “The Contractor shall provide erect and maintain for the duration of the contract a water resistant signboard at the entrance to the Sites (at least 4 locations), or other location approved by the Engineer. The design of the signboard and information given is to be approved by the Engineer prior to manufacture and erection. Further requirements regarding the signboard can be found in the “Communication and Visibility Manual for EU External Actions” on the following address: http://ec.europa.eu/europeaid/work/visibility/index_en.htm The signboard and in particular its construction design and location should be approved also by the Employer. After completion of all the works, the signboard shall be replaced by commemorative plaque. The commemorative plaque shall be installed as stationary on the approved location by the Beneficiary. The Contractor will be responsible for the maintenance of the commemorative plaque during the Defects Notification period. No other advertisements may be placed on the site unless the prior approval of the Employer is given. |  |
| 5 | Design |  |
| 5.1 | General Design Obligations At the end of the first paragraph, insert: If consent is withheld or subsequently revoked, or if the appointed person fails to act, the Contractor shall similarly submit the names and particulars of an alternative, having at least the same qualification, skills and expertise as the person initially appointed. At the end of Sub -Clause 5.1 add the following paragraph: The design should be in full compliance with the contract Employer’s Requirements (Volume 3). |  |
| 5.2 | Contractor’s Documents Add at the end of the third paragraph of Sub-Clause: In addition, an electronic version of these documents shall be provided to the Engineer. |  |
| 5.5 | Training Replace "Employer's personnel" with "Beneficiary’s Personnel" in the first line of this Sub-Clause. |  |
| 5.6 | As-Built Documents Add to the Sub-clause: Prior to the commencement of the Tests on Completion, and prior to issue of Taking-Over Certificate, as-built documentation shall be supplied in 4 copies in English and in the language of the beneficiary country. In addition, an electronic version of the above documents shall be provided to the Engineer. |  |
| 5.7 | Operation and Maintenance Manuals In Sub-Clause 5.7, after each occurrence of “operation and maintenance manuals” insert: in English and in the language of the beneficiary country In the first sentence of Sub-Clause 5.7, replace “Employer” with: “Beneficiary”. |  |
| 6 | Staff and Labour |  |
| 6.1 | Engagement of Staff and Labour Add at the end of the Sub-clause: The Contractor shall document and communicate to all workers their working conditions and terms of employment, including their entitlement to wages, hours of work, overtime arrangements and overtime compensation, and any benefits (such as leave for illness, maternity / paternity or holiday). The employment of foreign personnel and labour shall be subject to the applicable Statutes, Ordinances, Regulations and by-laws and no personnel or labour shall be employed by the Contractor without first obtaining the necessary permits or passports in sufficient time to ensure that all formalities are cleared before the permits are required. The Contractor is encouraged, to the extent practicable and reasonable, to employ staff and labour with appropriate qualifications and experience from sources within the Employer Country. |  |
| 6.3 | Persons in the Service of Employer Add at the end of Sub-Clause: and the Beneficiary's or Engineer’s personnel. |  |
| 6.6 | Facilities for Staff and Labour At the end of Sub-Clause delete: within the structures forming part of the Permanent Works and replace with: within the Site. |  |
| 6.7 | Health and Safety At the beginning of the Sub-Clause 6.7 insert: Within 21 days after the Commencement Date, the Contractor shall submit a document entitled “Health, Safety and Environmental Plan” giving a detailed description of his proposed methods to ensure safety of the Works during all stages of construction and commissioning. The Health, Safety and Environmental Plan shall be presented in sufficient detail to ensure that there can be no ambiguity in its interpretation at a later date. The Health, Safety and Environmental Plan shall be subject to the approval of the Engineer, who will not allow any work on Site to proceed until such time as it has been fully and formally approved. Approval of the Health, Safety and Environmental Plan shall not relieve the Contractor of any of his responsibilities with regard to safety. The Health, Safety and Environmental Plan shall be revised as necessary during the course of the works and resubmitted to the Engineer for his acceptance. At the end of the paragraph 3 insert: ‘The Contractor shall also report such accident to the relevant authority, as may be required under local rules and regulations.’ At the end of Sub-Clause 6.7, insert: ‘The Contractor shall provide his personnel with individual or team safety equipment and instruction in their use. The Contractor shall ensure the use of the safety equipment is made obligatory so that the entire Works can be carried out in a safe manner. The Contractor shall provide regular safety instruction sessions in the form of short lectures or films with the purpose of developing a safety culture at the sites under the Contractor’s control. Attendance at the instruction shall be compulsory for all Contractor’s, sub-Contractors and Employer’s staff at the site. The Contractor shall fulfil requirements of the applicable local rules and regulations concerning safety on the construction site’. |  |
| 6.8 | Contractor's Superintendence Add at the end of Sub-Clause: A reasonable proportion of the Contractor's superintending staff shall also have a working knowledge of the language of the Beneficiary Country, or the Contractor shall have a sufficient number of competent interpreters available on Site during all working hours, to ensure the proper transmission of instructions and information. |  |
| 6.10 | ## Records of Contractor’s Personnel and Equipment Replace 2nd phrase as follows: “Details shall be submitted each week, in a form agreed with the Engineer within 28 days after Notice to Commence, but in any event, prior to any notice under this Sub-Clause 20.1 [Contractor’s Claims], until the Contractor has completed all work which is known to be outstanding at the completion date, stated in the Taking-Over Certificate for the Works. The actual contemporary records, items/ format, shall be agreed in advance with the Engineer |  |
| 6.11 | Disorderly Conduct Add as separate paragraphs at the end of Sub-Clause 6.11: With respect to the Contractor, Sub-contractors and all their respective employees: (a) The Contractor shall not allow the bringing, selling or consumption of alcoholic drinks or drugs on Site; (b) The Contractor shall not allow the bringing, selling or illegal carrying of weapons and ammunition on Site; (c) The Contractor shall bear any additional cost and expenses (taxes, duties, penalties, insurance, overtime, etc.) arising as a consequence of contravention of this Clause by the Contractor’s personnel. |  |
|  | Add new Sub-Clauses 6.12 through 6.15, as follows: |  |
| 6.12 | Festivals and Religious Customs In dealing with his staff and labour, the Contractor shall respect the local recognised festivals, days of rest and religious or other customs. |  |
| 6.13 | Employment of Foreign Personnel and Labour “The Contractor may import any personnel who are necessary for the execution of the Works. The Contractor must ensure that these personnel are provided with the required residence visas and work permits. The Contractor shall be responsible for the return to the places where they were recruited or to their domicile of imported Contractor's Personnel. In the event of death of any of these personnel or members of their families, the Contractor shall similarly be responsible for making the appropriate arrangements for their return or burial.” |  |
| 6.14 | Measures against Insect and Pest Nuisance “The Contractor shall at all times take necessary precautions to protect all staff and labour employed on the Site from insect nuisance, rats and other pests and reduce the dangers to health and the general nuisance by the same. The Contractor shall provide suitable prophylactics for the Contractor's Personnel and shall comply with all regulations and the local health authorities, including use of appropriate insecticide” |  |
| 6.15 | Epidemics In the event of outbreak of illness of an epidemic nature, the Contractor shall comply with and carry out such regulating orders and requirements as may be made by the relevant local bodies or the local medical or sanitary bodies for the purpose of dealing with and overcoming the same. |  |
| 7 | Plant, Materials and Workmanship |  |
| 7.4 | ## Testing In the 2nd paragraph, revise the wording “The Contractor shall provide…” to “The Contractor shall provide at his own cost…” Insert after 2nd Paragraph: “All Equipments/Plants shall be tested at the place of manufacture prior to shipment. Upon successful completion of such testing, a certificate of compliance shall be issued by the manufacturer and a copy shall be provided to the Engineer. The Employer, Beneficiary, or their representative(s) may attend such testing at their discretion.” In 5th paragraph, 2nd line, after ‘Employer’ insert: or the Beneficiary |  |
| 7.7 | Ownership of Plant and Materials Add the following after the word “Employer”: “… or Beneficiary” The following text is hereby added to the Sub clause: “All materials to be removed from the site as result of demolition; dislocations etc. are the property of the Beneficiary. Irrespective of such items of Plant and Materials becoming the property of the Employer the Contractor shall be responsible for their security and safe keeping until a Taking-Over Certificate is issued for the concerned part of Works. Irrespective of the use to which the Beneficiary intends to put the materials or articles over which it retains ownership, all costs incurred in transporting and storing them at the place indicated by Beneficiary /Engineer shall be borne by the Contractor. They shall be stored in places designated by the Beneficiary and handed over to the Engineer, clean and in good order, based on a written handing-over document, signed by the Engineer and witnessed by the Beneficiary, which shall both, made themselves available for that. It is the sole responsibility of the Contractor to displace the demolished materials upon written approval by the Engineer in case that Beneficiary will decide to not keep and store the demolished materials.” |  |
| 7.8 | Royalties Add final paragraph: “The Contractor shall also be liable for all payments or compensation, if any, levied in relation to the dumping of part or all of such materials, waste piles, debris and hazardous waste.” |  |
| 7.9 | Origin of Plant, Materials and Services Add new Sub-Clause 7.9: “Any Equipment and Materials which will be incorporated in the Works, or Services used for the execution of the Works, shall comply with the rules of origin published in the PRAG current at the Base Date and shall have their origin in an Eligible Country including the areas. - The origin of Goods is distinct from nationality of the Supplier. - The origin is to be determined according to the Community Customs Code. A product can not originate in a country in which no production process has taken place. On the other hand, the country of production is not necessarily the country of origin but only when the relevant provisions of Council Regulation (EEC) 2913/92 and its implementing regulation are fulfilled. Furthermore, the country of origin is not necessarily the country from which the goods have been shipped and supplied. Where there is only one country of production, the origin of the finished product is easily established. However, in cases where more than one country is involved in the production of Goods it is necessary to determine which of those countries confers origin on the finished goods. The country of origin is deemed to be the country in which the Goods have undergone their last, economically justified, substantial transformation and the provisions of Article 24 of the Community Customs Code must therefore be applied on a case by case basis to those goods. The Contractor must certify that the Goods tendered comply with the origin requirement specifying the country or countries of origin. To this end, the Contractor shall provide “Certificate of Origin”, which must be made out by the competent authorities of the supplies’ or supplier’s country of origin and comply with the international agreements to which that country is a signatory. The official Certificates of Origin must be submitted latest before Taking‐Over. Failing this, the Contracting Authority can not release any funds to the Contractor in payment for such goods.” |  |
| 8 | COMMENCEMENT, DELAYS AND SUSPENSION |  |
| 8.1 | Commencement of Work In the second sentence of this Sub-clause delete: receives the Letter of Acceptance and substitute with: returns the signed Contract Agreement and Performance Security to the Employer. |  |
| 8.3 | Programme After sub-paragraph (d) (ii) add : (iii) an updated cash-flow estimate Add final paragraphs: “Such revised programme shall be submitted within 21 days from the date of the Engineer’s notice. Should the Contractor fail in submitting a revised programme, within stipulated time, the Employer may withhold an amount, as stated in the Appendix to Tender, until such programme is submitted. Any withheld money shall be paid with the payment following the next Payment Certificate after receipt of requested up-dated programme.” |  |
| 8.4 | Extension of Time for Completion Add at the end of Sub-Clause: Extension of Time for Completion does not by itself entitle the Contractor to additional money. The Contractor shall not be entitled to a separate Extension of Time for Completion for each one of several causes of delay running concurrently but only for the actual period of delay determined by the Engineer irrespective of the causes contributing to produce such delay. If one of several causes of delay operating concurrently is due to the fault of the Contractor and would in itself, irrespective of the concurrent causes, have delayed the completion of the Works, or Section or part thereof, no Extension of Time for Completion shall be granted for the period of such delay. An extension of Time for Completion made by the Engineer, or by the Dispute Adjudication Board shall be formalised as an Addendum to Contract. |  |
| 8.8 | Suspension of Work In Sub-Clause 8.8, insert at the end of the first paragraph: The Contractor shall use all reasonable endeavours to minimise and mitigate all costs associated with any such suspension. Unless otherwise instructed by the Engineer, the Contractor shall, during any suspension affecting the progress of the Works, maintain the Contractor’s personnel and Contractor’s Equipment on or near the Site ready to proceed with the Works upon receipt of further instructions from the Engineer. |  |
| 8.10 | Payment for Plant and Materials in Event of Suspension In Sub-Clause 8.10, in sub-paragraph (b), after “the Contractor”, insert: “...has presented satisfactory evidence that the Plant and/or Materials are fully owned by the Contractor and are not subject to any retention of title and...” |  |
| 9 | Tests on Completion |  |
| 9.1 | ## Contractor’s Obligations Insert after the first paragraph: Prior to the commencement of the Test on Completion, and prior to issue of Taking Over Certificate, as-built documentation and Operation and Maintenance Manuals shall be supplied in 3 (three) copies in each of the languages English and Montenegrin. The Works shall not be considered to be completed for the purposes of Taking Over under Sub-Clause 10.1 (Taking Over of the Works and Sections) until the Engineer has received and accepted these documents. |  |
| 9.2 | Delayed Tests In Sub-Clause 9.2, in the first sentence, after ”Employer” insert: ”or the Beneficiary,” |  |
| 10 | Employer’s Taking Over |  |
| 10.1 | Taking over of the Works and Sections Insert after 1st paragraph: “The Taking Over shall take place in a first step in accordance with related legislation of Montenegro, including issuance of Use Permit, based on which, the Engineer shall issue the Taking Over Certificate, in a second step. The Contractor will take all the measures to coordinate the issuance of the Taking Over certificate with the "Use Permit" to be issued by the relevant Authorities according with the Beneficiary's Country legislation ("Official Gazette of Montenegro, No 51/08 dated 22.08.2008, 40/10 dated 22.07.2010 and 34/11 dated 12.07.2011; or any other relevant legislation). If the "Taking Over Certificate" and "Use Permit" will be issued at different calendar dates, then, the last of the two dates will be considered in sub-clause 11 of Special Conditions and will be considered the starting date for the Defects Liability Period.” Delete phrase “The Engineer shall, within 28 days after receiving the Contractor’s application:” at the beginning of the third paragraph of Sub-Clause 10.1 and substitute with: “The Contractor shall fulfil the related procedure provided for in the Montenegrin legislation (which includes issuance of Use Permit by relevant authorities) and subsequently the Engineer shall, within 28 days after receiving the Contractor’s application:...” |  |
| 10.2 | Taking Over of Parts of the Works In Sub-Clause 10.2, 2nd paragraph, line 1, delete: The Employer shall not and replace with: Neither the Employer nor the Beneficiary shall |  |
| 10.3 | Interference with Tests on Completion In the first sentence of the Sub-Clause 10.3, after “for which the Employer” insert: “or the Beneficiary”. |  |
| 10.5 | Taking Over by the Beneficiary Add new Sub-Clause 10.5: The Contractor acknowledges that whenever the Employer takes over the Works or a Section or other part of the Works under this clause (Clause 10), then the entire and all and any responsibility for the care of the Works, Section or part the Works so taken over immediately passes to the Beneficiary. |  |
| 11 | Defects Liability |  |
| 11.7 | Right of Access In Sub-Clause 11.7, 3rd line, after “Employer's”, insert: and/or Beneficiary's. |  |
| 11.9 | Performance Certificate Add at the beginning of 2nd paragraph: “Upon fulfillment by Contractor of requirements under the Beneficiary’e law, in relation to Final Acceptance, including obtaining related documents/ certificates, ...” |  |
| 11.10 | Unfulfilled Obligations Add new final paragraph: “The Contractor shall be responsible for the quality of provided works according to law of Montenegro and/or Belgium. The issuing of the Performance Guarantee shall maintain Contractor’s liability of his obligations imposed by law of Montenegro and shall be without prejudice to the Contractor’s liability for the latent defects of the Works during the periods of liability imposed by the Governing Law.” |  |
| 12 | Tests After Completion |  |
| 12.1 | Procedure of test after completion Replace the first paragraph with: The Contractor shall be responsible for carrying out all specified tests after completion, under the direction of the Employer, and shall be liable for all costs associated with such tests. |  |
| 12.2 | Delayed Tests In the first sentence, after “the Employer” insert: or the Beneficiary. |  |
| 12.3 | Retesting In the third line of the second paragraph of Sub-Clause, after “the Employer” insert: or the Beneficiary. In the last line of the second paragraph of Sub-Clause 12.3, delete full stop and after ‘Employer’ insert: or the Beneficiary. |  |
| 12.4 | Failure to Pass Tests after Completion After each occurrence of “the Employer”, insert: or the Beneficiary. |  |
| 13 | VARIATIONS AND ADJUSTMENTS |  |
| 13.1 | ## Right to Vary Add at the end of the Sub-Clause the following provisions: Substantial changes can, however, only be made by means of a formal addendum to the contract. The following types of changes shall be regarded as substantial: - Changes with technical impact that: - modify the scope of works as defined in the Contract, or - alter the conditions on which the contract was evaluated and awarded (e.g. substantial changes in the Contractor’s Proposals in a design-build contract, technical specifications in a construction contract, minimum standards for materials; etc.). (b). Changes with financial impact that lead to an increase in the total contract price such that it is no longer covered by the Accepted Contract Amount, (c). Changes to the legal form or the contractual essence, such as changes to the conditions of contract, the contract agreement, the appendix to tender or other such parts of the contract. |  |
| 13.2 | Value Engineering In the first paragraph, after each occurrence of “the Employer”, insert: and/or the Beneficiary. Add final paragraph: “The Contractor shall be fully responsible for any proposal made under this Sub-Clause, including for the period required for its review and approval. The Contractor shall not be entitled to any extension of time, Cost or profit related to such period of review and approval.” |  |
| 13.5 | Provisional Sums Delete point (b) (ii) of this Sub-Clause 13.5 and substitute with: “a sum for overhead charges and profit, calculated as a percentage of these actual amounts by applying the relevant percentage specified in the Appendix to Tender.” |  |
| 13.6 | Dayworks add at the beginning of the second paragraph ''To the extent not already contained in the Daywork schedules, before...'' |  |
| 13.8 | Adjustment for Changes in Cost Delete this Sub-Clause |  |
| 13.9 | Procedures for Addendum Add new Sub-Clauses 13.9 as follows: “Should a necessity arise for major modification of the Contract during its implementation period, which is due to a change of the circumstances affecting the implementation of the project, then any such modification of the Contract shall be formalised through an Addendum to the Contract. Such Addendum shall be prepared by the Employer pursuant to the terms set out in the PRAG.” |  |
| 14 | Contract Price and Payment |  |
| 14.1 | The Contract Price ### Add the following after sub-paragraph 14.1.(d): “(e) The Contract Price shall exclude all taxes, including VAT, customs and import duties and any other charges that may be levied in accordance with the local rules and regulations in force in the areas on the Base Date, due account being taken of Clause 21 [Taxes and Customs issues] of these Particular Conditions. (f) The Contract Price shall be deemed to include all taxes, duties and other charges required to be paid by the Contractor under the Contract outside the Beneficiary Country.” |  |
| 14.2 | Advance Payment Add the following after the first paragraph The contractor shall provide calculation of the amount of (20 %) the cost for design, materials, plant, equipment, machines, tools and of any other substantial prior expenses such as the acquisition of patents or study costs, necessary for the execution of the contract, while requesting the pre-financing. |  |
| 14.3 | Application for Interim Payment Certificates ### Replace in the first sentence “… in six copies …” with “… in 4 (four) copies …”. |  |
| 14.5 | Plant and Materials intended for the Works Add the following text to paragraph (c): (iii) they are in accordance with the Specifications; (iv) the Contractor’s records of requirements, usage, orders, and receipts are kept in a form approved by the Engineer and made available for inspection by the Engineer; (v) the Contractor has submitted with his monthly statement documents required by the Engineer for their valuation and providing evidence of the Contractor’s ownership and payment; (vi) ownership of such materials is proved by the Contractor. |  |
| 14.6 | Issue of Interim Payment Certificates Add in 1st paragraph after “Interim Payment Certificates”, ” in four copies,” Add new point c) to 3rd paragraph: “c) if the Contractor was or is failing to issue Monthly Progress Reports as per Sub-Clause 4.21 [Progress Reports] of Conditions of Contract for the period included in the Payment Application” |  |
| 14.7 | ###### Payment Replace sub-paragraphs (a), (b) and (c) by: - the first instalment of the advance payment within 42 days after the Employer receives the documents in accordance with Sub-Clause 4.2 [Performance Security] and Sub-Clause 14.2 [Advance Payment], whichever is later, and in line with the provisions of this Sub-Clause, last paragraph below. - the amount certified in each interim Payment Certificate (passed for payment), within no more than 56 calendar days from the date on which the Engineer’s Certificate is received by the Employer, and in line with the provisions of this Sub-Clause, last paragraph below. - the amount certified in the Final Payment Certificate within 56 days after the Employer receives this Final Statement At the end of Sub-Clause 14.7,insert: “The bank account shall be the one mentioned on the financial identification form completed by the Contractor. The same form, annexed to the payment request, must be used to report changes of bank account.“ The Employer shall not be held liable for reimbursement to the Contractor of any fees, charges or costs levied by the Contractor’s bank in connection with the transfer of any amount paid to the Contractor by the Employer under the Contract.“ |  |
| 14.8 | Delayed Payment Replace Sub-Clause 14.8 in its entirety with: If the period laid down for payment in Sub-Clause 14.7 has been exceeded, the Contractor shall qualify for interest calculated pro-rata on the basis of the number of days delay at the rate applied by the European Central Bank to its main refinancing transactions in euro on the first day of the month in which the deadline expired, plus 3,5 percentage points. The late-payment interest shall apply to the time which elapses between the date of the payment deadline, and the date on which the Employer’s account is debited. By way of exception, when the interest calculated in accordance with this provision is lower than or equal to EUR 200, it shall be paid to the Contractor only upon a demand submitted within two months of receiving late payment. The Member States are not entitled to late-payment interest. The Contractor shall be entitled to such payment without prejudice to any other right or remedy under the Contract. In the case of the Final Payment Certificate, the interest for the delayed payment shall be calculated on a daily basis at the rate specified above. |  |
| 14.9 | Payment of Retention Money Add at the end of Sub-Clause: Alternatively, the second half of Retention Money will be certified for payment after: (a) the Engineer has issued a Taking-Over certificate for the whole of the Works, and (b) the Employer has received a Retention Money Guarantee in the form provided in the Contract and from a Bank, approved by the Employer. The Retention Money Guarantee shall provide a surety for the second half of the Retention Money for the whole of the Works held for the rectification of defects arising during the remainder of the Contract Period and the completion of any remaining work to be executed under Clause 11 [Defects Liability] or Clause 12 [Tests after Completion]. The terms and conditions for the Retention Money Guarantee shall be the same as those stated in Sub-Clause 4.2 for a Performance Security. Within 45 days at the latest of receipt by the Employer of the Performance Certificate, the Employer shall return the Retention Money Guarantee to the Contractor. |  |
| 14.11 | Application for Final Payment Certificate Replace in the first sentence “… in six copies …” with “… in 4 (four) copies …”. |  |
| 14.13 | Issue of Final Payment Certificate Add in 1st paragraph after “Final Payment Certificates”: ”, in four copies,” |  |
| 14.16 | Repayment Add new Sub-Clause 14.16: “The Contractor undertakes to repay any amounts paid in excess of the final amount due to the Employer before the deadline indicated in the debit note, which is 42 days from the issuing of that note. Should the Contractor fail to make repayment within the deadline set by the Employer, the Employer may increase the amounts due by adding interest at the rate applied by the European Central Bank to its main refinancing transactions in Euro on the first day of the month in which the time-limit expired, plus three and a half percentage points. The default interest shall be incurred over the time which elapses between the date of the payment deadline set by the Employer, and the date on which payment is actually made. Any partial payments shall first cover the interest thus established. Amounts to be repaid to the Employer may be offset against amounts of any kind due to the Contractor. This shall not affect the Parties' right to agree on payment in instalments. Bank charges involved in the repayment of amounts due to the Employer shall be borne entirely by the Contractor.” |  |
| 15 | Termination by Employer |  |
| 15.4 | Payment after Termination In Sub-Clause 15.4, sub-paragraph (b), after 'Employer,' insert: ”or the Beneficiary”. In sub-paragraph (c), first line after 'Employer,' insert: ”or the Beneficiary”. |  |
| 17 | Risk and Responsibility |  |
| 17.1 | Indemnities In 1st paragraph, first line: after “the Employer, the Employer’s Personnel” insert: “or the Beneficiary and the Beneficiary’s Personnel,” |  |
| 17.2 | Contractor’s Care of the Works Add the following paragraph after the first paragraph: “Until the Taking-Over Certificate is issued the Contractor shall maintain an alarm and information system such that the Contractor’s personnel can be rapidly called out at night, weekends, and holidays and at other times when the site is not working to deal with site incidents and site emergencies.” |  |
| 17.3 | Employer's Risks In sub-paragraph (f), after ‘Employer’ insert: “or the Beneficiary”. Add at the end of this Sub-Clause 17.3: - “damage to components of the Beneficiary’s property on the Site and damage done to the Works resulting from any accident while the public use of the Works is authorised by the Beneficiary, where it can be demonstrated by the Contractor that the accident cannot be partly or wholly attributed to any deficiency in the Contractor’s Traffic Management Plan.” |  |
| 17.5 | Intellectual and Industrial Property Rights In paragraph (b) after ‘Employer’ insert: “or by the Beneficiary” In 4th paragraph: After ‘Employer’ insert: “and the Beneficiary”. |  |
| 18 | Insurance |  |
| 18.1 | General Requirements for Insurances Replace in 1st paragraph “... the Party responsible …” with “... the Contractor, which is responsible …” Delete in 2nd paragraph “Wherever the Contractor is the insuring Party,”. Delete 3rd paragraph. Add at the end of 7th paragraph: “... , which shall dully check such insurances or evidences and notify with details the Contractor in respect of their endorsement or rejection” |  |
| 18.2 | Insurance for Works and Contractor's Equipment In the 4th paragraph, sub-paragraph (d) after ‘Employer’ insert: or the Beneficiary Add the following paragraph: It shall be the responsibility of the Contractor to notify the insurance company of any change in the nature, extent or programme for the execution of the Works and to ensure adequacy of the insurance coverage at all times during the period of the Contract. |  |
| 18.3 | Insurance against Injury to Persons and Damage to Property In 3rd paragraph, sub-paragraph (c), after “Employer’s” insert: and the Beneficiary’s In 3rd paragraph, sub-paragraph (d)(i), after “Employer’s” insert: and/or the Beneficiary’s |  |
| 18.4 | Insurance for Contractor’s Personnel In 2nd paragraph, first line, after “The Employer”, insert: “the Beneficiary” In 2nd paragraph, third line, after “Employer” insert: “, or the Beneficiary” In 2nd paragraph, third line, after “Employer’s” insert: “, or the Beneficiary’s,” |  |
|  | Add the following paragraph at the end of the Sub-clause 18.4: “The Contractor shall check whether the compulsory insurance of the employees, provided according to the regulations in force in Montenegro or equivalent insurance in the country of origin of Contractor, meets the basic requirements for insurance of the Contractor’s personnel. If not, the Contractor shall do all necessary provisions to comply with the Montenegro regulations. However, the Contractor may have arrangements for additional insurance of his personnel.” |  |
| 18.5 | Professional Indemnity Insurance for Design Add new Sub-Clause 18.5: “The Contractor shall effect professional indemnity insurance, which shall cover the risk of professional negligence in the design of the Works. The minimum amount and time limits of Professional indemnity insurance for design shall be not less than as indicated in the Appendix to Tender. The Contractor undertakes to notify the Employer of any extending, renewing or reinstating this insurance.” |  |
| 20 | Claims, Disputes and Arbitration |  |
| 20.7 | Failure to Comply with Dispute Adjudication Board’s Decision Delete Sub-Clause 20.7 and substitute with: “In the event that a Party fails to comply with any decision of the DAB, whether binding or final and binding, then the other Party may, without prejudice to any other rights it may have, refer the failure itself to arbitration under Sub-Clause 20.6 [Arbitration] for summary or other expedited relief, as may be appropriate. Sub-Clause 20.4 [Obtaining Dispute Adjudication Board’s Decision] and Sub-Clause 20.5 [Amicable Settlement] shall not apply to this reference.” |  |
| 21 | Taxes and Customs Issues Add new Clause 21,”Taxes and Custom Issues” as follows: The Employer understands that the prevailing situation in the areas is the following: The Contractor will not be requested to pay custom duties, import taxes, fees and VAT or any other similar taxes on goods entering the areas for the contract financed by the EU ("the Contract") and will receive the necessary documents to that effect. All imported goods, which are not incorporated in or expended in connection with the Contract, should be exported on completion of the Contract. The Employer understands that the Contractor will not be requested to pay VAT for the contract value and will receive the necessary documents to that effect. The Employer will not be involved in the preparation or presentation of any documentation that the Contractor may need in order to bring the goods to the place where they are supposed to be installed or used. The Contractor shall be deemed to have checked the locally applying technical and administrative conditions before submitting the Tender. |  |
| 22 | Ethics Clauses Add new Clause 22, “Ethics Clauses”, as follows: |  |
| 22.1 | Ethics Clause “The effect of the terms of this Clause 22 shall be included by the Contractor in all subcontracts he enters into under this Contract.” |  |
| 22.2 | Conflict of Interest “Without the Employer’s prior written authorisation, a Contractor and his staff or any other company with which the Contractor is associated or linked shall not, even on an ancillary or subcontracting basis, perform other services, carry out works or supply equipment for the project of which the Works form a part. This prohibition also applies to any other programmes or projects that could, owing to the nature of the contract, give rise to a conflict of interest on the part of the Contractor. When putting forward a tender, the tenderer shall declare that it is affected by no conflict of interest and has no particular link with other tenderers or parties involved in the project. Should such a situation arise during the execution of the Contract, the Contractor must immediately inform the Employer” |  |
| 22.3 | Code of Conduct “The Contractor shall at all times act honourably and impartially and as a faithful adviser in accordance with the code of conduct of his profession. He shall refrain from making public statements about the Works without the Employer’s prior approval. He may not commit the Employer in any way without its prior written consent.” |  |
| 22.4 | Human Rights “For the duration of the contract, the Contractor and his staff must respect human rights and undertake not to violate the political, cultural and religious mores prevailing in the areas.” |  |
| 22.5 | No Other Payments “The Contractor shall not accept any payment connected with the Contract other than that provided for therein. The Contractor and his staff shall not exercise any activity or receive any advantage inconsistent with their obligations to the Employer.” |  |
| 22.6 | Professional Secrecy “The Contractor and his staff shall be obliged to maintain professional secrecy for the entire duration of the Contract and after its completion. The Contract and all reports and documents drawn up or received by the Contractor in respect of the Contract shall be confidential. . The Contract shall govern the Parties’ use of all reports and documents drawn up, received or presented by them during the execution of the Contract.” |  |
| 22.7 | Independence “The Contractor shall refrain from any relationship likely to compromise his independence or that of his staff. If the Contractor ceases to be independent, the Employer may, regardless of injury, terminate the contract without further notice and without the Contractor having any claim to compensation.” |  |
| 22.8 | Corrupt Practices “The European Commission reserves the right to suspend or cancel project financing if corrupt practices of any kind are discovered at any stage of the award process or contract implementation and if the Employer fails to take all appropriate measures to remedy the situation. For the purposes of this provision, “corrupt practices” are the offer of a bribe, gift, gratuity or commission to any person as an inducement or reward for performing or refraining from any act relating to the award of a contract or implementation of a contract already concluded with the Employer.” |  |
| 22.9 | Unusual Commercial Expenses “For the purposes of this Sub-Clause, ‘unusual commercial expenses’ are commissions not mentioned in the Contract or not stemming from a properly concluded contract relating to the Contract, commissions not paid in return for any actual and legitimate service, commissions remitted to a tax haven, commissions paid to a recipient who is not clearly identified or commissions paid to a company which has every appearance of being a front company. |  |
| 22.10 | Supporting Evidence “The Contractor undertakes to provide the European Commission on request with all supporting documents relating to the conditions of the contract’s execution. The European Commission may carry out whatever documentary or on-the-spot checks it deems necessary to find evidence in cases of suspected unusual commercial expenses.” |  |
| 23 | Administrative and Financial Penalties Add new Clause 23, “Administrative and Financial penalties”, as follows: |  |
| 23.1 | “Without prejudice to the application of penalties laid down in the contract, a Contractor who has been guilty of making false declarations, has made substantial errors or committed irregularities and fraud, or has been found in serious breach of its contractual obligations, may be excluded from all contracts and grants financed by the European Community budget for a maximum of five years from the time when the infringement is established, as confirmed after an adversarial procedure with the Contractor. The Contractor may present his arguments against this penalty within 30 days of notification of the penalty by registered letter with acknowledgement of receipt or any equivalent means. In the absence of any reaction on the part of the Contractor, or of withdrawal of the penalty by the European Commission within 30 days of receipt of the Contractor's arguments against it, the decision imposing the penalty shall become enforceable. That period may be increased to ten years in the event of a repeat offence within five years of the first infringement.” |  |
| 23.2 | “If the Contractor is found to have seriously failed to meet its contractual obligations, it shall incur financial penalties representing 2-10% of the total value of the contract in question. That rate may be increased to 4-20% in the event of a repeat offence within five years of the first infringement.” |  |
| 23.3 | “Where, after the award of the Contract, the award procedure or the performance of the Contract prove to have been subject to substantial errors, irregularities or fraud, and where this is attributable to the Contractor, the Employer may refuse to make payments, may recover amounts already paid or may terminate all the contracts concluded with this Contractor, in proportion to the seriousness of the errors, irregularities of fraud” |  |
| 24 | Checks and Audits by Community Bodies Add new Clause 24, “Checks and Audits by Community Bodies”, as follows: |  |
| 24.1 | “The Contractor will allow the European Commission, the European Anti-Fraud Office and the European Court of Auditors to verify, by examining the documents or by means of on-the-spot checks, the implementation of the project and conduct a full audit, if necessary, on the basis of supporting documents for the accounts, accounting documents and any other document relevant to the financing of the project. These inspections may take place up to 7 years after the final payment.” |  |
| 24.2 | “Furthermore, the Contractor will allow the European Anti-Fraud Office to carry out checks and verification on the spot in accordance with the procedures set out in the European Community legislation for the protection of the financial interests of the European Communities against fraud and other irregularities. |  |
| 24.3 | “To this end, the Contractor undertakes to give appropriate access to staff or agents of the European Commission, of the European Anti-Fraud Office and of the European Court of Auditors to the sites and locations at which the Contract is carried out, including its information systems, as well as all documents and databases concerning the technical and financial management of the project and to take all steps to facilitate their work. Access given to agents of the European Commission, European Anti-Fraud Office and the European Court of Auditors shall be on the basis of confidentiality with respect to third parties, without prejudice to the obligations of public law to which they are subject. Documents must be easily accessible and filed so as to facilitate their examination and the Consultant must inform the Employer of their precise location.” |  |
| 24.4 | “The Contractor guaranties that the rights of the European Commission, of the European Anti-Fraud Office and of the European Court of Auditors to carry out audits, checks and verification will be equally applicable, under the same conditions and according to the same rules as those set out in this Clause, to any sub-contractor or any other party benefiting from EC funds.” |  |