Annex V.2: Programme of Implementation of tasks - Lot 2

Based on Article 13 of the Special Conditions, the table will be filled in by the Contracting Authority and sent to the contractor together with the Commencement Order.

The Contractor shall countersign it and return it within 15 days to the Contracting Authority. The Contractor will adhere to the time limits set therein.

| Activity | Deadlines (as per contract, in calendar days) | Period (cumulated number of days, maximum) | Dates (to be filled in by the Contracting Authority) |
| --- | --- | --- | --- |
| Contract signature (S.C., Article 18) | At the latest Signature of the contract + 30 | 0 | DD/MM/YY |
| Delivery order (G.C., Article 29) | Delivery – 1 (or more) day(s), upon Contractor’s request | 29 | DD/MM/YYYY |
| Delivery (I.T.T., Article 1) | Commencement date + 30 days | 30 | DD/MM/YYYY |
| Verification Operations: (Annex II: Technical Specifications) - Unloading - Installation | Delivery + 7 days | 37 | DD/MM/YYYY |
| Request for Provisional Acceptance (G.C., Article 31) | Provisional Acceptance – 30 days | 42 | DD/MM/YYYY |
| Provisional Acceptance (G.C., Article 31) | Request for Provisional Acceptance + 30 days | 72 | DD/MM/YYYY |
| End of Warranty (S.C., Article 32) | Provisional Acceptance + 365 days | 437 | DD/MM/YYYY |
| Final Acceptance (G.C., Article 34) | Expiration of Warranty period + 30 days | 467 | DD/MM/YYYY |
| Release of Performance guarantee (GC, Article 11.7) | Final Acceptance + 60 days | 527 | DD/MM/YYYY |

NOTE: All deadlines except the end of warranty period and end of after-sales services are final deadlines on which relevant activity must be executed, meaning that activities can be executed earlier which will be reflected in the updated Programme of implementation of tasks. Only the warranty shall remain valid for exactly one year after provisional acceptance as stipulated in Article 32 of the Special Conditions and the after-sales services shall last as stipulated in Article 33 of the Special Conditions.