## ALL EN
Note: The degree of implementation of activities in the Action Plan is shown in such a way that the green colour indicates the activity that is fully implemented (more than 80%), with further implementation planned in the future to improve more. Yellow colour indicates partially implemented activity (from 50%-80%), while red one indicates activity that has not been implemented (below 50%). Also, activities not coloured have not been implemented.
Note: The difference between the planned funds as compared to the total planned funds is the amount of funds for activities that were implemented in the previous period within the Strategic objective
2021 ACTION PLAN
Strategic objective 1._ A) Sustainable fiscal framework, public expenditure planning and budgeting
Operational objective 4.1._ A.1. Medium-term budgetary framework (MTBF), including fiscal strategy
Performance indicators
|  | 1 | Share of new medium-term sector strategies in the total number of strategies that include estimates of implementation costs, including potential donor funding | PV (2014): 60% | TV 2017: 80% | Actual value in 2017: 70% | TV 2018: 85% | Actual value in 2018: 75% | TV 2019: 90% | Actual value in 2019: 85% | TV 2020: 100% | Actual value in 2020 100%
|  | 2 | Average deviation between MTBF budget ceilings and actual annual budget expenditure limits | PV (2014): 9% | TV 2017: 7% | Actual value in 2017: 6% | TV 2018: 6% | Actual value in 2018: 0.87% | TV 2019: 5% | Actual value in 2019: 0.11% | TV 2020: 5% | Actual value in 2020 2.13%
|  | 3 | Number of staff trained for top-down medium-term budget planning | PV (2014): 0 | TV 2017: 52 | Actual value in 2017: 0 | TV 2018: 35 | Actual value in 2018: 0 | TV 2019: 52 | Actual value in 2019: 0.11% | TV 2020: 72 | Actual value in 2020: 100
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required (IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUBSYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| *2) |  | A.1.3 Training of staff with a view to improving medium-term expenditures planning (target group: technical staff) | Training | Training materials prepared. A number of employees have been trained. | IPA II | MoF - BD | 2 (A.1.5) | 2018 | 2020 | 2021 | IPA II (A I) Budget | 135000 | Realization of IPA II funds
| *2) |  | A.1.4 Training for multi-year budget planning with a view to better alignment of the budget programme goals with Government policies (target group: managerial staff) | Training | Training materials prepared. A number of employees have been trained. | IPA II | MoF - BD | 2 (A.1.5) | 2018 | 2019/2020 | 2021 | IPA II (A I) Budget | 50000 | Realization of IPA II funds
|  |  | A.1.8 Improvement of planning and presentation of multiannual commitments in the budget | Legal act (new / revised) | Presentation of multiannual commitments in budget documentation. A review of multiannual commitments in the budget law. | IPA II | MoF - BD | 2 | Q4 2017 | 2019/2021 | 2021 | IPA II (A I) Budget | 30000 | SIGMA
| *6) |  | A.1.9 Develop and upgrade current budget planning IT to enable medium-term planning | Computerisation | Specifications for the development and upgrade of the budget planning system prepared. Individual upgrades / improvements / modules developed. | IPA II | MoF - BD | 1 (A.2.9) (A.3.9) | 2018 | 2019/2020 | 2021 | IPA II (A II) Budget | 300000 | Realization of IPA II funds
[8 empty] | TOTAL: |  |  |  |  | 570000 | 120.000,00
A) Sustainable fiscal framework, public expenditures planning and budgeting
Operational objective 4.1.2._ A.2. Annual Budgeting
Creating an efficient system for measuring the impact of budget programmes with a view to increasing efficiency and transparency of public expenditures
Performance indicators
|  | 4 | Share of first level budget organisations that provide comprehensive information with their annual budget requests | PV (2014): 40% | TV 2017: 75% | Actual value in 2017: 70% | TV 2018: 80% | Actual value in 2018: 80% | TV 2019:90% | Actual value in 2019: 90% | TV 2020: 100% | Actual value in 2020. 100%
|  | 5 | Level of performance information included in budget planning | PV (2014): Programme headings are defined by all budget organisations | TV 2017: Programme structure is developed in all budget organisations | Actual value in 2017: Programme headings are defined by all budget organisations | TV 2018: Programme structure is developed in all budget organisations | Actual value in 2018. Programme structure is developed in all budget organisations in terms of Programme headings defined | TV 2019: Level 1 upgrade with definied set of Performance indicators for pilot projects | Actual value in 2019. Programme headings are defined by all budget organisations | TV 2020: Created a set of indicators for all programmes to monitor the success in achieving goals | Actual value in 2020. Defined headings of main programmes, programmes and subprogrammes
|  | 6 | The number of staff trained for planning and monitoring expenditures in line with programme budgeting principles | PV (2014): 0 | TV 2017: 20 | Actual value in 2017: 0 | TV 2018: 35 | Actual value in 2018: 0 | TV 2019: 70 | Actual value in 2019: 17 | TV 2020: 130 | Actual value in 2020. 100
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required (IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| *8) *13) |  | A.2.6 Define performance indicators for programmes or sub-programmes | Legal act (new/revised) | Performance indicators defined (and published in the Budget Documentation) | IPA II | MoF - BD | 2 (A.2.4) (A.2.5) (C.1.4) (D.1.10) | 2019 | 2020/2021 | 2021 | IPA II (A I) Budget | 310000 | /
| *6) |  | A.2.9 Review and improve the functionality of the existing IT system for budget planning | Computerisation | Specifications for the development and upgrade of the budget planning system prepared. Individual upgrades / improvements / modules developed. | IPA II | MoF - BD | 1 (A.1.10) (A.3.9) | 2018 | 2020 | 2021 | IPA II (A II) Budget | 295000 | /
|  |  | A.2.10 Improve budget transparency by providing better visual presentation | Computerisation | Budget presentation designed and web pages created. Budget Law format revised and updated. | IPA II | MoF - BD | 2 | 2019 | 2020/2021 | 2021 | IPA II (A I) Budget | 20000 | /
|  |  | A.2.11 In accordance with the best international standards explore and implement measures for the improved presentation and visualisation in annual reports (monthly and quarterly) | Computerisation | Monthly and quarterly reports prepared and published on the MoF website. | IPA II | MoF - BD | 2 | 2019 | 2020/2021 | 2021 | IPA II (A I) Budget | 45000 | /
12 | *9) |  | A.2.12 Improve resources for better management of the EU`s own resources | Training | Draft Manual prepared. Employees trained. | IPA II | MoF - BD | 1 (B.1.6) (B.2.8) | 2017 | Implemented / continuous implementation | 2021 | IPA II (A I) Budget | Implemented using existing capacities
[8 empty] | TOTAL: |  |  |  |  | 895000 | 522.000,00
A) Sustainable fiscal framework, public expenditures planning and budgeting
Operational objective 4.1.3._ A.3. Capital Budget
Performance indicators
|  | 7 | Level of detail in public presentation of capital budget | PV (2014): Projects in the Capital Budget presented grouped by areas (education, health, culture, sports…) | TV (2017): Projects in the Capital Budget presented grouped by areas (education, health, culture, sports…) | Actual value in 2017: Projects in the Budget Law are presented grouped by areas, while in the Explanation of the Law they are presented by individual projects | TV (2018): Projects in the Capital Budget presented grouped by areas (education, health, culture, sports…) | Actual value in 2018: Projects in the Budget Law are presented grouped by areas, while in the Explanatory Note of the Law they are presented by individual projects | TV (2019): Overview of all individual projects implemented in the Budget Year and implementation of selected pilot projects by phases | Actual value in 2019: ojects in the Budget Law are presented grouped by areas, while in the Explanation of the Law they are presented by individual projects | TV (2020): Review by individual projects and phases of project implementation | Actual value in 2020. Presentation by individual projects
|  | 8 | Actual capital spending in the current year as a share of the capital budget plan | Actual capital spending in the current year as a share of the capital budget plan | PV (2014): 70% | Actual value in 2017: 82% | TV (2018): 83% | Actual value in 2018: 91%/111% | TV (2019): 86% | Actual value in 2019: 92% 112.3% | TV (2020): 90% | 180.60% 107.6%
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  | A.3.1 Improve capital budget planning in the medium term as a part of the MTBF | Legal act (new/revised) | New Legal act (new / revised) / guidelines prescribing the manner and content of capital budget planning. | IPA II | MoF - BD | 1 | 2018 | 2020/2021 | 2021 | IPA II (A I) Budget | 30000 | /
|  |  | A.3.2 Introduce stages of capital projects in the preparation and planning of capital budgets (preparatory stage and construction stage) | Legal act (new/revised) | New format of the Budget Law (Capital Budget) prepared. | IPA II | MoF - BD | 2 | 2018 | 2020/2021 | 2021 | IPA II (A I) Budget | 25000 | /
|  |  | A.3.3 Improve the overview of projects in the capital budget through detailed presentation of individual projects by project and economic classification | Legal act (new/revised) | New format of the Budget Law (Capital Budget) prepared. | IPA II | MoF - BD | 1 | 2018 | 2020 | 2021 | IPA II (A I) Budget | 25000 | /
|  |  | A.3.4 Improve the capital budget’s statement of reasons as regards the overall estimated project value and schedule | Guidelines / Manual | Guidelines prepared. Explanation of each project prepared. | IPA II | MoF - BD | 2 | 2018 | 2020 | 2021 | IPA II (A I) Budget | 15000 | /
| *17) |  | A.3.5 Establish a public register of all the projects which are financed from the capital budget | Computerisation | Public register established. Register published on the MoF website. | IPA II | MoF - BD MoF - Treasury. MSDT - DPV MTMA - DT | 1 (D.1.7) | 2018 | 2020/2021 | 2021 | IPA II (A I) Budget | 35000 | /
|  |  | A.3.6 Training of staff in line ministries involved in planning and implementation of capital projects with a view of better planning of investment project costs in the medium term | Training | Training materials prepared. A number of employees have been trained. | IPA II | MoF - BD | 2 | 2018 | 2020/2021 | 2021 | IPA II (A I) Budget | 50000 | /
|  |  | A.3.7 Improve the overview of capital projects by separating the new ones from the ones already being implemented | Legal act (new/revised) | New format of the Budget Law (Capital Budget) prepared. | IPA II | MoF - BD | 2 | 2018 | 2020 | 2021 | IPA II (A I) Budget | 10000 | /
9 | *6) |  | A.3.8 Improve the functionality of the exiting capital budget planning IT tool | Computerisation | Specifications for the development and upgrade of the Budget planning system prepared. Individual upgrades / improvements/ modules developed. | IPA II | MoF - BD | 1 (A.1.10) (A.2.9) | 2018 | 2020/2021 | 2021 | IPA II (A II) Budget | See A.2.9 | /
[8 empty] | TOTAL: |  |  |  |  | 190000 | 99.000,00
A) Sustainable fiscal framework, public expenditures planning and budgeting
Operational objective 4.1.4._ A.4. Upgrade the model for macroeconomic projections
Performance indicators
|  | 9 | Staged implementation of the upgraded model for macroeconomic projections and structural reform impacts | PV (2014): The existing model used in the Directorate for Economic and Development Policy is based on the financial programming model, and the projection of certain parameters is based on expert assessment | TV (2017): Analysis and upgrade of the existing macroeconomic model for projections | Actual value in 2017: Target value for 2017 met | TV (2018): A new model for projections of macroeconomic indicators and the impact of structural reforms developed, and employees trained | Actual value in 2018:A new model for projections of macroeconomic indicators and the impact of structural reforms developed, and employees trained | TV (2019): Preconditions fulfilled for the use of the new model by employees in the Directorate for Economic Policy and Development | Actual value in 2019: Preconditions for the use of the new model by employees in the Directorate for Economic Policy and Development fulfilled | TV (2020): Full implementation and full ability to use the model | Actual value in 2020: Partially implemented. The project is being continuously implemented, in accordance with the recommendations of experts for the full implementation of the model, which is planned for the end of 2024.
|  | 10 | The difference between actual and projected real GDP growth rate | PV (2014):1,8 p.p. | TV (2017):Less than 0.5 p.p | Actual value in 2017: The target value for 2017 has not been met | TV (2018): Less than 0.3 p.p | Actual value in 2018: 0.8 p.p | TV (2019): Less than 0.2 p.p. | Actual value in 2019: Target value for 2019 partially met, further recommendations given | TV (2020): Less than 0.2 p.p. | Actual value in 2020: The projection could not be realized due to market disturbances and external shocks
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| *20) |  | A.4.2 Upgrade of the existing macroeconomic forecasting model | Manual | Manual for the new model | IPA II | MoF - DEPD | 1 | Q3 2017 | implemented / continuous implementation | 2021 | IPA | / | /
| *20) *21) |  | A.4.3 Training of staff to use the new model (both modules) | Training | A number of employees trained | IPA II Budget CG | MoF - DEPD Other line ministries | 1 | Q3 2017 | implemented / continuous implementation | 2021 | IPA & Budget | / | /
|  |  | A.4.4 Data gathering and analysis for the needs of developing the two modules | Procedure | Creating assumptions for the improvement of Module II | IPA II | MoF - DEPD Other line ministries | 1 | Q2 2017 | implemented / continuous implementation | 2021 | IPA | / | /
6 |  |  | A.4.6 The new model implemented and staff trained to use it | Regulations/ Procedure/ Training/ Computerisation | Application of the new model and training of DEP employees to work on the model, and line ministries to use the model | IPA II | MoF - DEPD | 1 | Q1 2018 | 2024 | 2024 | IPA | / | /
[8 empty] | TOTAL: |  |  |  |  | 200.000,00 | 130.000,00
Strategic objective 2. _ B) Budget execution
Operational objective 4.1.3.1._ B.1. Revenue collection - Tax Administration
Performance indicators
|  | 11 | Share of submitted e-returns (income tax, VAT) in comparison to total number of submissions | PV (2014): 27% | TV (2017): VAT 50% INCOME 95% | Actual value in 2017: VAT 50% INCOME 95% | TV (2018): VAT 65% INCOME 97% | Actual value in 2018: VAT 70% INCOME 99% | TV (2019): VAT 75% INCOME 97% | Actual value in 2019: VAT 77,37 % INCOME 99,5% | TV (2020): VAT 80% INCOME 99% | Actual value in 2020: VAT 88 % INCOME 99,6%
|  | 12 | EU VAT regulations concerning EU common market successfully implemented | PV (2014): Completed screening process | TV (2017): Negotiations in Chapter 16 open | Actual value in 2017: A certain degree of legislative harmonization has been achieved, a higher degree has been achieved in the field of VAT, harmonization in income tax area (transfer prices) administrative cooperation and mutual assistance remains still to be done | TV (2018): Law on Amendments to the Law on Corporate Income Tax (Q4 2018) -Law on Amendments to the Law on Tax Administration (Q4 2018) | Actual value in 2018: Actual value in 2018: Draft Laws on Amendments to the Law on Corporate Income Tax, as well as the Law on Amendments to the Law on Tax Administration have been prepared in order to further harmonize with EU legislation, especially in the area of administrative cooperation and exchange of information | TV (2019): Law on Amendments to Value Added Tax (Q4 2019) | Actual value in 2019: Higher degree of compliance compared to the previous year; | TV (2020): Implemented channeled activities from the Accession Programme - Chapter 16. | Actual value 2020: Higher degree of compliance compared to the previous year
|  | 13 | Share of collected tax revenue compared to the planned tax revenue in the annual budget law | PV (2014: 100% (2015): 100% (2016): 100% | TV (2017): TV (2017): 100% | Actual value in 2017: More than 100% of planned (24 million above the plan for 2017) and 34 million above the achievement in 2016 | TV (2018): 100% | Actual value in 2018: Above the plan for 2018, achieved 73 million or 117 million above the achievement from 2017. | TV (2019): 100% | All proposed amendments to the law passed by the Legislative Committee. After which they were submitted to the EC for an opinion. | TV (2020): 100% | Actual value in 2020: 65 mil. euros above the plan according to the budget revision, but still 79 mil. euros (7%) below the 2019 achievement
|  | 14 | Share of collected VAT revenues in GDP | PV (2014): 13.5% | TV (2017): 13.5% | Actual value in 2017: 13.0% | TV (2018): 14.7% | Actual value in 2018: 13.6% | TV (2019): 14.6% | Actual value in 2019: 14.44% | TV (2020): 14.6% | Actual value in 2020 12.6%
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  | B.1.1 DFurther improvement in efficiency, taxpayer services and tax compliance through capacity building and systems improvement in MTA. | Procedure, Computerisation | Growth in the share of submitted electronic tax returns (INCOME tax, VAT) | IPA II | MoF - TA | 2 | 2018 | 2020 | 2023 | World Bank | 1000000 | /
|  |  | B.1.2 Strengthen MTA’s administrative and institutional capabilities to apply EU’s common VAT system | Legal act (new/revised) Computerisation | Software implemented. | IPA II | MoF - TA | 2 | 2019 | 2025 | 2025 | IPA II 2017 (proposa), Budget | 2000000 | /
|  |  | B.1.3 Upgrade capacity of the MTA and its IT systems in the area of risk analysis and inspections control (e-control) | Procedure, Computerisation | Software implemented. | IPA II | MoF - TA | 2 | 2017 | 2020 | 2023 | World Bank | 500000 | /
|  |  | B.1.5 MTA Reform | Business processes,, Computerisation | Implementation of an integrated revenue management system (IRMS) in line with business processes |  | MoF - TA | 1 | Q1 2017 | 2021 (5 years) | 2023 (5 years) | Budget WB loan | 14000000 | /
[8 empty] | TOTAL: |  |  |  |  | 18.500.000,00 | 850.000,00
Strategic objective 2. _ B) Budget execution
Operational objective 4.1.3.2._ B.2. Revenue collection - Customs Administration
Performance indicators
|  | 15 | Change in revenue collection compared to the previous year | PV (2014): 15% | TV (2017): 17.64 % | Actual value in 2017: 17.64 % | TV (2018): 5% | Actual value in 2018: 11.03% | TV (2019): 5% | Actual value in 2019: 5.17% | TV (2020): 5% | Actual value in 2020. -18%
|  | 16 | Harmonisation of customs and excise legislation with the EU Acquis | PV (2014): Completed screening process Chapter 16 Taxation | TV (2017): Law on Amendments to the Customs Law Law on Amendments to the Law on Excise Duties Customs Tariff Regulations for 2017 Regulations on amendments to the Regulation on the implementation of the Customs Law | Actual value in 2017: 4 regulations enacted | TV (2018): Adoption of 3 regulations | Actual value in 2018: Adopted 3 regulations | TV (2019): Adoption of 3 regulations | Actual value in 2019: Adopted 3 regulations | TV (2020): Adopted 2 regulations | Actual value in 2020. Adopted 1 regulation
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  | B.2.1 Implement excise IT system at the national level | Procedure/ Computerisation | Procedures established. Software implemented. | IPA II | MoF - CA. | 1 | 2019 | 2020 | 2021 | IPA II (C) Budget | 299000 | 119200
|  |  | B.2.2 Implement modernised customs clearance procedures at the national level | Procedure/ Computerisation | Procedures established. Software implemented. | IPA II | MoF - CA. | 1 | 2018 | 2020 | 2021 | IPA II/ Budget/Other | 3300000 | 1269647.34
|  |  | B.2.4 Upgrade risk management system | Training/ Computerisation | Officers trained. Software upgraded | IPA II | MoF - CA. | 2 | 2018 | 2020 | 2021 | IPA II/ Budget/Other | / | /
|  |  | B.2.5 Increase the number of economic operators authorised for simplified procedures | Preparation of economic entities for obtaining approval | Increased number of economic entities | IPA II | MoF - CA. | 2 | 2018 | 2020 | 2021 | World Bank project | / | /
|  |  | B.2.6 Development of AEO programme | Regulations/ Procedure/ Training/ Computerisation | Regulations updated. Procedures established. Software implemented. | IPA II | MoF - CA. | 2 | 2018 | 2020 | 2021 | World Bank project | / | /
[8 empty] | TOTAL: |  |  |  |  | 3599000 | 1388847.34
Strategic objective 2. _ B) Budget execution
Operational objective 4.1.3.3._ B.3. Public procurements
Performance indicators
|  | 17 | Level of harmonisation and completeness of the procurement framework in line with the EU acquis | PV (2014): Open negotiations in the negotiating chapter 5 | TV (2017): Open negotiations in the negotiating chapter 5 | Actual value in 2017: Open negotiations in the negotiating chapter 5 | TV (2018): Further harmonization with the package of Directives from 2014 in this area | Actual value in 2018: Open negotiations in the negotiating chapter 5 | TV (2019): Further harmonization with the package of Directives from 2014 in this area (implementation of the new Law on Public Procurement, introduction of the electronic system of public procurement ...) | Actual value in 2019: Adoption of the new Law on Public Procurement by implementing the provisions in accordance with the new directives | TV (2020): Implemented planned activities from the Accession Programme Chapter 5. | Actual value in 2020. A new Law on Public Procurement was adopted, which came into force on July 7, 2020
|  | 18 | Average number of bidders received per procurement procedure | PV (2014): 3.52 bids per tender | TV (2017): 3.2 | Actual value in 2017: 2.66 | TV (2018): 3.48 | Actual value in 2018: 3.14 | TV (2019): 3.58 | Actual value in 2019: 2.01 | TV (2020): 3.8 | Actual value in 2020. 2.27
|  | 19 | Share of e-procurement of all procurement contracts awarded during the year. | PV (2014): 0% (There is no electronic public procurement system) | TV (2017): 0% (There is no electronic public procurement system) | Actual value in 2017: 0% (There is no electronic public procurement system) | TV (2018): Selection of the most favorable bidder | Actual value in 2019: The project of creating an e-public procurement system has started | TV (2019): 30% | Actual value in 2019: Pilot phase of the e-system | TV (2020): 80% | Actual value in 2020. System established, in house testing completed and trainings for users of the electronic public procurement system started
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  | B.3.4 Provide training for civil servants involved in public procurement (as PP officers, members of Tender Opening and Evaluation Commissions, as well as for inspectors, prosecutors and judges) | Training | Training materials prepared. A number of employees have been trained. | IPA II | MoF - PPD | 2 | Q1 2017 | Implemented/ continuous | 2021 | IPA II (A IV) Budget | 35000 | /
|  |  | B.3.5 Training material for special target groups involved in public procurement | Training | Training materials prepared. A number of employees have been trained. | IPA II | MoF - PPD | 2 | Q1 2017 | Q3/42020 | 2021 | IPA II (A IV) Budget | 50000 | /
|  |  | B.3.6 Awareness raising campaign | Training | Campaign launched and ended. | IPA II | MoF - PPD | 1 | Q3 2017 | Q3/42020 | 2021 | IPA II (A IV) Budget | 40000 | /
7 |  |  | B.3.7 e-Procurement | Computerisation | Software implemented. | IPA II | MoF - PPD | 1 | Q1 2017 | 2020/2021 | 2021 | IPA II (D) Budget | 1650000 | /
[8 empty] | TOTAL: |  |  |  |  | 1775000 | 721.500,00
Strategic objective 2. _ B) Budget execution
Operational objective 1._ B.4. State Aid reform
Performance indicators
|  | 20 | The number of state aid grantors and beneficiaries, private sector representatives and judges attending state aid seminars and training events | PV (2014): 50 | TV (2017): 50 | Actual value in 2017: 0 | TV (2018): 30 | Actual value in 2018: 0 | TV (2019): 60 | Actual value in 2019: 56 | TV (2020): 100 | Actual value in 2020. 171
|  | 21 | The share of staff of the State Aid Division and the Commission for State Aid Control undergoing training with a view to strengthening the legal framework, reducing the level of illegal state aid and conducting ex-post controls | PV (2014): 30% | TV (2017):30% | Actual value in 2017: 33% | TV (2018): 50% | Actual value in 2018: 0% | TV (2019): 70% | Actual value in 2019: 70% | TV (2020): 80% | Actual value in 2020. 75%
|  | 22 | Number of ex-officio cases closed | PV (2014): 5 | TV (2017): 3 | Actual value in 2017: 0 | TV (2018): up to 2 | Actual value in 2018: 0 | TV (2019): up to 2 | Actual value in 2019: 0 (2 ex-officio cases have been opened, we expect them to close in the next period) | TV (2020): up to 1 | Actual value in 2020. 1
|  | 23 | Number of documents reviewed and assessed by the State Aid Division | PV (2014): 11 | TV (2017): 20 | Actual value in 2017: 14 | TV (2018): up to 20 | Actual value in 2018: 22 | TV (2019): up to 23 | Actual value in 2019: 35 | TV (2020): 25 | Actual value in 2020. 41
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  | B.4.1 Upgrade and strengthen the institutional framework and national legal system regarding the implementation of state aid rules and procedures | Organ. /managerial changes | Organizational change implemented, special body (organisationally independent, part of the MoF or with another ministry) | IPA II | MoF - DP | 1 | Q2 2018 | Q4 2020 | 2021 | IPA II (A IV) Budget | 50000 | 25000
| *10) |  | B.4.2 Support through the negotiation process and meeting the requirements of Chapter 8; | Legal act (new/revised) | Fulfillment of benchmarks | IPA II | MoF - DP | 1 (B.4.3) | Q3 2018 | Continuous implementation | 2021 | IPA II (A IV) Budget | 150000 | 25000
| *10) |  | B.4.3 Monitor achievements by analysing state aid cases in the EC customary law | Guidelines / Manual | Analysis of 3-4 cases performed. | IPA II | MoF - DP | 1 (B.4.2) | Q3 2017 | Continuous implementation | 2021 | IPA II (A IV) Budget | 200000 | 25000
|  |  | B.4.4 Technical Support for the Montenegro State Aid’s IT Tool, development of a special register for de minimis state aid and the application for state aid grantors to be included in a single IT component | Computerisation | Software implemented. | IPA II | MoF - DP | 1 | Q4 2018 | Q4 2020 | 2021 | IPA II (A IV) Budget | 200000 | IPA II funds
5 |  |  | B.4.5 Strengthen administrative capacities through training and experience sharing | Training | Training materials prepared. A number of employees have been trained. | IPA II | MoF - DP | 2 | Q3 2018 | Continuous implementation | 2021 | IPA II (A IV) Budget | 100000 | 25000
[8 empty] | TOTAL: |  |  |  |  | 700000 | 100000
Strategic objective 2. _ B) Budget execution
Operational objective 4.1.4._ B.5. Debt Management, Debt Analysis, Cash Management and Foreign Relations Department Reform
Performance indicators
|  | 24 | Public debt servicing costs as a share of GDP | PV (2014): 2.2 % | TV (2017): 2.5 % | Actual value in 2017: 2.3 % | TV (2018): 1.9 % | Actual value in 2018: 2.1% | TV (2019): 2.0 % | Actual value in 2019:2.2% | TV (2020): 2.3% | Actual value in 2020. 2.64%
|  | 25 | Difference between planned and achieved level of public debt | PV (2014): 1.5% | TV (2017): 1.5% | Actual value in 2017: Public debt is 3.2% lower than planned | TV (2018): 1.5% | Actual value in 2018: Public debt is 3.07% higher than planned | TV (2019): 1.5% | Actual value in 2019: Realized difference in gross public debt 16.6% | TV (2020): 1.5% | Actual value in 2020. Realized difference in gross public debt 16%
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  | B.5.2 Training of staff at the Debt Management Department regarding different financial operations, awareness and training for different financial derivatives, debt preparation and analysis, better debt management | Training | Training materials prepared and available. A number of employees have been trained. | IMF SIGMA | MoF - Treasury | 1 | Q1 2016 | Continuous implementation | 2021 | Budget | 50000 | Donation[1]
|  |  | B.5.4 Upgrade of the software tool for public debt and cash management | Computerisation | Upgrading implemented software. |  | MoF - Treasury | 3 | Q1 2016 | 2020 | 2021 | Budget | 500000 | 0,000
[8 empty] | TOTAL: |  |  |  |  | 780000 | 0
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Strategic objective1._ A) Sustainable fiscal framework, public expenditures planning and budgeting
Operational objective 4. 1._ B.6. Public sector payroll system reform
2 | *12) |  | B.6.2 Implementation of new software for calculation and control of salaries in the public sector | Computerisation | Software implemented. |  | MoF - BD | 1 (B.6.1) | Q4 2016 | 2020 | 2021 | IPA II (A III) Budget | 600000 | 304.697,72
[8 empty] | TOTAL: |  |  |  |  | 600000 | 304.697,72
Strategic objective3_C) Development of public internal financial control (PIFC)
Performance indicators
|  | 26 | The percentage of ministries that formally delegated decision-making responsibilities and authorities to the line managers to improve managerial accountability | PV (2014): 6.25% 2015: 6.3% 2016: 6.3% (Report: 2016: 22.22%) | TV (2017): 30% | Actual value in 2017: 11.11% | TV (2018): 16% | Actual value in 2018: 18% | TV (2019): 50% | Actual value in 2019: 12% | TV (2020): 90% | Actual value in 2020. 8.3%
|  | 27 | Percentage of the budget users on central and local level submitting annual FMC reports | PV (2014): 69% 2015: 76% 2016: 76% | TV (2017): 75% | Actual value in 2017: 80% | TV (2018): 80% | Actual value in 2018: 90% | TV (2019): 90% | Actual value in 2019: 94% | TV (2020): 95% | Actual value in 2020. 93%
|  | 28 | Percentage of appointed internal auditors per unit | PV (2014): 1.76 | TV (2017): 2 | Actual value in 2017: 2 | TV (2018): 2.3 | Actual value in 2018: 2.21 | TV (2019): 2.5 | Actual value in 2019: 2.1 | TV (2020): 2.7 | Actual value in 2020. 2.1
|  | 29 | Percentage of appointed certified internal auditors | PV (2014): 60% | TV (2017): 75% | Actual value in 2017: 90.90% | TV (2018): 80% | Actual value in 2018: 94.05% | TV (2019): 85% | Actual value in 2019: 100.00% | TV (2020):90% | Actual value in 2020. 93.1%
|  | 30 | Percentage of appointed certified internal auditors who undergo CPD | PV (2014): 0% | TV (2017): 70% | Actual value in 2017: 74% | TV (2018): 75% | Actual value in 2018: 83.64% | TV (2019): 80% | Actual value in 2019: 81.36% | TV (2020): 90% | Actual value in 2020. 80%
|  | 31 | Percentage of implemented and partially implemented recommendations given by internal auditors in the previous year that were implemented by the end of the current year | PV (2014): 48% (2016): 74.2% | TV (2017): 55% | SActual value in 2017: 73.5% | TV (2018): 60% | Actual value in 2018: 79.16% | TV (2019): 65% | Actual value in 2019: 84.46% | TV (2020): 70% | Actual value in 2020. 79.4%
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| *16) |  | C.1.4 Conduct training for managers | Training | Training materials prepared. Number of trained employees. | IPA II | MoF - CHU HRA | 2 (C.1.6) (C.1.7) | Q3 2017 | Continuous. | 2021 | Budget- Uprava za kadrove | 20000 | 12.000,00
| *16) |  | C.1.5 Training for newly appointed internal auditors | Training | Training materials prepared. Number of trained employees. | IPA II | MoF - CHU HRA Ger. Gvnmt. | 2 (C.1.5) (C.1.7) | Q3 2017 | Continuous. | 2021 | IPA II (A I) Budget | 10000 | 10.000,00
| *16) |  | C.1.6 Organise and deliver CPD training for certified public internal auditors | Training | Training materials prepared. Number of trained employees. | IPA II | MoF / CHU HRA | 2 (C.1.5) (C.1.6) | Q3 2017 | Continuous. | 2021 | IPA II (A I) Budget | 20000 | 17.500,00
| *14) |  | C.1.8 Strengthen the CHU capacities for assessing the FMC and IA quality | Guidelines / Manual | Guidelines prepared. | IPA II SIGMA | MoF - CHU | 1 (C.1.1) | Q2 2016 | 2020 | 2021 | IPA II (A I) Budget | 25000 | /
[8 empty] | TOTAL: |  |  |  |  | 175000 | 39.500,00
NOTE: Activities in this area that are continuous are considered completed for 2017, taking into account that they are implemented every year.
Strategic objective 4._D) Financial reporting and accounting
Operational objective 4.3. _D.1. Transition from the cash-based to the accrual accounting and financial reporting
Performance indicators
|  | 32 | Public sector accountants trained for accrual accounting (based on the CIPFA methodology) | PV (2014): 0 | TV (2017): 40 | Actual value in 2017: 40 u 2016 | TV (2018): 40 | Actual value in 2018: 80 | TV (2019): 20 | Actual value in 2019: 40 | TV (2020): 100 | Actual value in 2020. 120
|  | 33 | Property register and double entry book-keeping system for the property implemented | PV (2014): Development of the property register has begun | TV (2017): Entered property data in the register | Actual value in 2017: 0 | TV (2018): (direct and indirect Budget users) and collection of information on the condition of property | Actual value in 2018: 0 | TV (2019): Training (indirect Budget users) and migration of funds to ARS and commissioning of records | Actual value in 2019: 9 groups 100 public authorities 0 migration | TV (2020): Implemented property register and asset register system | Actual value in 2020. Public authorities (99) Public services (322) DCM (39) Local government (24) Municipal authorities (196) 0 migration
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required (IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  | D.1.2 Develop new accrual-based accounting policies | Legal act (new/revised) | Law on Public Sector Accounting approved |  | MoF - Treasury | 1 | Q1 2017 | 2020 | 2021 | Budget | / | Budget
| *20) |  | D.1.3 Adapt the Chart of Accounts to new accounting requirements | Legal act (new/revised) | Updated classifications (organizational, functional, property…) | UNDP | MoF - Treasury | 2 (D.2.1) (D.2.2) (D.2.3) | Q1 2018 | 2020 | 2021 | Budget UNDP | / | /
|  |  | D.1.4 Develop the IT system to support double-entry bookkeeping | Computerisation | IT system implemented |  | MoF - Treasury | 2 | 2019 | 2020 | 2021 | Budget | / | Budget/Donation
|  |  | D.1.5 Develop new implementing legislation and reporting templates | Legal act (new/revised) | New regulations and report forms approved. |  | MoF - Treasury | 2 | 2019 | 2020 | 2021 | Budget | / | /
|  |  | D.1.6 Provide training for public sector accountants on new implementing legislation, templates and the IT system | Training | Training materials prepared and available. A number of employees have been trained. |  | MoF - Treasury | 2 | 2020 | 2020 | 2021 | Budget | / | Budget/Donation
| *18) |  | D.1.9 Deliver training for public accountants on the new implementingregulation and the use of the new Asset Management Module | Training | A number of employees trained. |  | MoF - PrA | 2 (D.1.8) | Q3 2015 | 2020 | 2021 | Budget | 34.666,50 | 34.666,50
10 | *13) *19) |  | D.1.10 Legislative changes, annual reports should feature assets data and performance indicators | Legal act (new/revised) | Regulation amended and approved. |  | MoF - Treasury MoF - DfP MoF-PrA. | 2 (A.2.6) (C.1.4) (D.1.8) | 2019 | 2020 | 2021 | Budget | / | /
[8 empty] | TOTAL: |  |  |  |  | 34.666,50 | 34.666,50
Strategic objective 5._E) Development and strengthening of external audit
Operational objective 4.5.1._State Audit Institution strengthening
Performance indicators
|  | 34 | Level of realisation of SAI’s Annual Audit Plan | PV (2014):60% (2017):80% | N/A | N/A | TV (2018): 83% | Actual value in 2018: 86.27% | TV (2019): 86% | Actual value in 2019: 88.68% | TV (2020):90% | Actual value in 2020. 72.50%
|  | 35 | Application of ISSAI-compliant methodology for financial, regularity and performance audits | PV (2014): 2015 – Methodological Instruction for financial and regularity audits compliant with ISSAI 200 and ISSAI 400, Methodological Instruction for performance audits compliant with ISSAI 300 and Guidelines for Audit Quality Control | N/A | N/A | TV (2018): Guidelines for Auditing Annual Financial Statements of Political Entities; Guidelines for Auditing Final Budget Accounts; | Actual value in 2018: Guidelines for Auditing Annual Financial Statements of Political Entities adopted in January 2018; Guidelines for Auditing Final Budget Accounts adopted in September 2018; | TV (2019): n / a The activities listed in the action plan start from Q1 2019. | Actual value in 2019: Manual for Performance Audits compliant with ISSAI 4th level adopted in December 2019. | TV (2020): Manual for Financial and Regularity Audits compliant with ISSAI 4th level adopted Manual for Performance Audits compliant with ISSAI 4th level upgraded Guide for Monitoring the Implementation of Recommendations from Audit Reports adopted | Manual for Financial and Regularity Audits compliant with ISSAI 4th level adopted in July 2020 and applied. Manual for Performance Audits compliant with ISSAI 4th level adopted in December 2019 and applied Guide for Monitoring the Implementation of Recommendations from Audit Reports adopted in June 2020 and applied
|  | 36 | No of trainings/seminars/ workshops for auditors delivered | (2014): Minimum 3 trainings delivered (2017): Delivered additional 9 trainings | N/A | N/A | TV (2018): additional 6 trainings delivered | Actual value in 2018: 13 Trainings (3 internally organized and 10 regionally and internationally) | TV (2019): additional 7 trainings delivered | Actual value in 2019: 13 Trainings (3 domestically and 10 regionally and internationally) | TV (2020): additional 10 trainings delivered | Actual value in 2020. 32 trainings (22 at the domestic level and 10 at the regional and international level)
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Potrebna tehnička pomoć (IPA, IMoF, UNDP…) | Implementaciona agencija / Direktorat | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
8 |  |  | E.1.8 Procure necessary office space for SAI to be able to increase auditor staffing capacities | Premises | Premises provided |  | DRI | 1 | 2018 | 2020 | 2021 | Budget | 2500000 | 0,000
[8 empty] | TOTAL: |  |  |  |  | 2695000 | 189.900,00
Strategic objective 4.5._E) Development and strengthening of external audit
E.2. Audit Authority
Operational objective 4.5.2._Audit Authority
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required (IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Source of funding | Planned funds | Spent funds
SUB-SYSTEM
ACTIVITY
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[8 empty] | TOTAL |  |  |  |  | 475.000,00 | 446.115,00
NOTE: Activities in this area have been fully implemented.