PUBLIC FINANCE MANAGEMENT REFORM

PROGRAMME

FINAL IMPLEMENTATION REPORT

WITH OVERVIEW OF ACTIVITIES FOR 2020

MONTENEGRO

MINISTRY OF FINANCE AND SOCIAL WELFARE

July 2021

INTRODUCTORY SUMMARY

# Contents

Contents	3

I GENERAL INFORMATION	5

GENERAL OVERVIEW	5

DEGREE OF IMPLEMENTATION	7

KEY ACHIEVEMENTS	9

CHALLENGES IN IMPLEMENTATION	10

II INFORMATION ON THE STATUS OF PERFORMANCE INDICATORS (OVERVIEW OF ACHIEVED STRATEGIC AND OPERATIONAL OBJECTIVES)	13

OBJECTIVE 1 . SUSTAINABLE FISCAL FRAMEWORK, PUBLIC EXPENDITURE PLANNING AND BUDGETING	13

PHASED IMPLEMENTATION OF PROGRAMME-BASED BUDGETING	14

IMPROVING MODELS FOR MACROECONOMIC PROJECTIONS	20

GOAL 2. BUDGET EXECUTION	23

TAX ADMINISTRATION	23

STRENGTHENING CUSTOMS ADMINISTRATION CAPACITIES	27

PUBLIC PROCUREMENT	30

STATE AID REFORM	35

PUBLIC DEBT MANAGEMENT, DEBT ANALYSIS, CASH MANAGEMENT AND FOREIGN RELATIONS DEPARTMENT REFORM	38

OBJECTIVE 3. PUBLIC INTERNAL FINANCIAL CONTROL DEVELOPMENT	40

OBJECTIVE 4 TRANSPARENT FINANCIAL REPORTING AND ACCOUNTING	43

OBJECTIVE 5. STRENGTHENING EXTERNAL AUDIT CAPACITIES	49

STATE AUDIT INSTITUTION	49

AUDIT AUTHORITY	51

III TABLE FOR REPORTING ON IMPLEMENTATION OF AP FOR THE LAST YEAR OF IMPLEMENTATION OF THE STRATEGIC DOCUMENT	54

IMPLEMENTATION OF DONOR FUNDS	82

IV RECOMMENDATIONS FOR THE NEXT PHASES OF THE PROGRAMME IMPLEMENTATION	83

APPENDIX 1 – PERFORMANCE INDICATOR PASSPORTS FOR THE 2016-2020 PUBLIC FINANCE MANAGEMENT REFORM PROGRAMME	86

1.	SUSTAINABLE FISCAL FRAMEWORK, PUBLIC EXPENDITURE PLANNING AND BUDGETING	87

1.1     Medium-term budgetary framework, including fiscal strategy	87

1.1.1      PERFORMANCE INDICATOR 1 PASSPORT	87

1.1.2      PERFORMANCE INDICATOR 2 PASSPORT	88

1.1.3      PERFORMANCE INDICATOR 3 PASSPORT	88

1.2     Annual budgeting	89

1.2.1      PERFORMANCE INDICATOR 4 PASSPORT	89

1.2.2      PERFORMANCE INDICATOR 5 PASSPORT	89

1.2.3      PERFORMANCE INDICATOR 6 PASSPORT	90

1.3     Capital budget	91

1.3.1      PERFORMANCE INDICATOR 7 PASSPORT	91

1.3.2      PERFORMANCE INDICATOR 8 PASSPORT	91

1.4     Improving models for macroeconomic projections	92

1.4.1      PERFORMANCE INDICATOR 9 PASSPORT	92

1.4.2      PERFORMANCE INDICATOR 10 PASSPORT	93

2.    BUDGET EXECUTION	94

2.1     Revenue collection- Tax Administration	94

2.1.1      PERFORMANCE INDICATOR 11 PASSPORT	94

2.1.2      PERFORMANCE INDICATOR 12 PASSPORT	94

2.1.3 PERFORMANCE INDICATOR 13 PASSPORT	96

2.1.4 PERFORMANCE INDICATOR 14 PASSPORT	96

2.2     Revenue collection - Customs Administration	97

2.2.1      PERFORMANCE INDICATOR 15 PASSPORT	97

2.2.2      PERFORMANCE INDICATOR 16 PASSPORT	97

2.3     Revenue collection - Public procurement	98

2.3.1      PERFORMANCE INDICATOR 17 PASSPORT	98

2.3.2      PERFORMANCE INDICATOR 18 PASSPORT	99

2.3.3      PERFORMANCE INDICATOR 19 PASSPORT	100

2.4     State aid reform	101

2.4.1      PERFORMANCE INDICATOR 20 PASSPORT	101

2.4.2      PERFORMANCE INDICATOR 21 PASSPORT	102

2.4.3      PERFORMANCE INDICATOR 22 PASSPORT	102

2.4.4      PERFORMANCE INDICATOR 23 PASSPORT	103

2.5     Public Debt Management, Debt Analysis, Cash Management and Foreign Relations Department Reform	103

2.5.1      PERFORMANCE INDICATOR 24 PASSPORT	103

2.5.2      PERFORMANCE INDICATOR 25 PASSPORT	104

3.    Public Internal Financial Control Development	104

3.1     Managing public finances in an efficient, economical, effective and transparent way by all spending units	105

3.1.1      PERFORMANCE INDICATOR 26 PASSPORT	105

3.1.2      PERFORMANCE INDICATOR 27 PASSPORT	105

3.1.3      PERFORMANCE INDICATOR 28 PASSPORT	106

3.1.4      PERFORMANCE INDICATOR 29 PASSPORT	106

3.1.5      PERFORMANCE INDICATOR 30 PASSPORT	107

3.1.6      PERFORMANCE INDICATOR 31 PASSPORT	107

4. Transparent financial reporting and accounting	108

4.1     Transition from the cash-based to the accrual accounting and financial reporting	108

4.1.1      PERFORMANCE INDICATOR 32 PASSPORT	108

4.1.2      PERFORMANCE INDICATOR 33 PASSPORT	109

5. STRENGTHENING EXTERNAL AUDIT CAPACITIES	110

5.1     Improving the audit process, strengthening audit capacities and transparency in the use of public finances - State Audit Institution	110

5.1.1      PERFORMANCE INDICATOR 34 PASSPORT	110

5.1.2 PERFORMANCE INDICATOR 35 PASSPORT	110

5.1.3      PERFORMANCE INDICATOR 36 PASSPORT	112

5.2. Building capacities and improving audit procedure - Audit Authority	112

5.2.1      PERFORMANCE INDICATOR 37 PASSPORT	112

5.2.2      PERFORMANCE INDICATOR 38 PASSPORT	113

5.2.3      PERFORMANCE INDICATOR 39 PASSPORT	113

5.2.4      PERFORMANCE INDICATOR 40 PASSPORT	114

5.2.5      PERFORMANCE INDICATOR 41 PASSPORT	114

# I GENERAL INFORMATION

## GENERAL OVERVIEW

In order to continue monitoring the process of the 2016-2020 Public Finance Management Reform Programme (hereinafter: the Programme) implementation, the Ministry of Finance and Social Welfare, with the active participation of 14 different organisational units, representatives of which are members of the Coordination Group and the Operational Team, prepared the Final Implementation Report for the 2016-2020 Public Finance Management Reform Programme (hereinafter: the Report). High quality and valuable monitoring and reporting in accordance with the Regulation on the Procedure for Drafting, Harmonising and Monitoring the Implementation of Strategic Documents and the Methodology for Policy Development, Preparation and Monitoring of Document Implementation, has been provided. In addition, full cooperation was achieved with the Ministry of Public Administration, Digital Society and Media, through the Special Group for Public Administration Reform.

The Report was prepared in accordance with the commitment of the Ministry of Finance and Social Welfare to report to the Government on a regular basis, starting from 2017, and to inform the European Commission twice a year on the progress made through the implementation of the Programme. In addition, the process of preparation of the Draft Report involved other stakeholders, non-governmental organisations associated with the process of public administration reform (Institute Alternative and Center for Democratic Transition), in order for them to provide suggestions and comments.

The purpose of the Report is the provision of information concerning the results and assessment of performance indicators for the further implementation and improvement of the overall status of the 2016- 2020 Programme, with the main focus on the year 2020, as well as to stress the advantages and disadvantages of the entire public finance system, challenges and recommendations for further development and improvement; while the 2020 Action Plan for the implementation of the Programme (hereinafter: 2020 AP) is intended to show the degree of implementation of activities where progress has been achieved, and forecast financial resources necessary to implement certain objectives of the Programme. Within the Report, in addition to the above, 2020 AP also included Performance Indicator Passports, thereby improving the reliability and transparency of the Report.

Note must be taken that with the adoption of the Report, the 2016-2020 Public Finance Management Reform Programme, as well as the accompanying 2020 Action Plan, cease to be valid.

The 2016-2020 Public Finance Management Reform Programme was originally adopted on December 3, 2015 and amended in June 2017. Following the adoption of the Programme Implementation Report and the accompanying 2020 AP for the period January - December 2017, and in line with the identified challenges for the period, a need arose to update the Programme (in cooperation with SIGMA), all with the aim of making it better and more specific for more efficient implementation and monitoring. In this regard, the Government of Montenegro at its session of June 28, 2018, adopted a significantly revised version of the 2016-2020 Public Finance Management Reform Programme with the Action Plan for the same period, and confirmed the readiness to continue reforms in the field of public finance management. Note must be taken that the new Programme was implemented through three Action Plans, which were updated on an annual basis during the period 2018, 2019 and 2020, which form an integral part of the report.

In order to promote and assist in ensuring sound financial management and good implementation of Government policies, through the eighth meeting of the Public Administration Reform Special Group (PAR SG) in 2020, the 3rd special regular meeting on the Public Finance Management Reform Programme Dialogue between the Government of Montenegro and the EC Directorate-General for European Neighbourhood Policy and Enlargement Negotiations (DG NEAR) was held on 19 October 2020. This established practice is a good indicator of commitment of the Government of Montenegro to the reform of public finance management and transparency, and also provides an opportunity for civil society and other donors/ international financial institutions to gain the same level of understanding of the current progress and challenges in the context of such reform.

The importance placed on the Ministry of Finance and Social Welfare, which is leading the public finance management reform, was stressed, as well as the continuation of the reform in the coming period through the development of the new 2022-2026 Programme, which will be an opportunity to intensify efforts to further implement reforms, given that progress under the Programme is also a condition for the withdrawal of Sector Budget Support funds under the IPA Programme. Also, the adopted conclusions envisage the adoption of the transitional 2021 Action Plan, based on the 2020 Report.

Note must be taken that the Public Finance Management Reform has a dual goal: The first relates to Montenegro’s readiness to identify, preclude and manage fiscal risks, excessive fiscal deficits and harmful macroeconomic imbalances, while the second relates to the fact that the reform should ensure that public spending is structured in such a way as to maximise the development impact on the economy and ensure a better quality of life for all citizens.

Regarding the implementation of the planned activities within the reform process, the dominant support is provided through projects financed from the EU funds, through the IPA instrument, within the 2014 Country Action Programme - CAP 2014, while the implementation of certain activities was predominantly conditioned by their realisation. In this respect, 2019 was a particularly significant year given that the previous one was marked by the finalisation of tender procedures for the PFM projects, which is why it was possible to start with the implementation of the remaining activities planned under the Programme. The focus was placed on the implementation of a number of important activities, including the preparation of the medium-term budgetary framework, programme-based budgeting, capital budgeting, as well as the Law on Public Sector Accounting, with note that the former activities were carried out predominantly from own resources, using the existing capacities of institutions.

During the implementation of the Programme, institutions responsible for the implementation provided key contribution using own capacities. In this regard, in addition to the funds spent within their regular activities planned in the state budget, the following funds came from donations, by strategic objectives:

- funds in the amount of € 1.17 million were used for the implementation of activities within the strategic objective Sustainable fiscal framework, public expenditures planning and budgeting;

- funds in the amount of € 3.06 million were used for the implementation of activities within the strategic objective Budget Execution;

- funds in the amount of € 0.04 million were used for the implementation of activities within the strategic objective Public Internal Financial Control Development (PIFC);

- funds in the amount of € 0.08 million were used for the implementation of activities within the strategic objective Financial Reporting and Accounting;

- funds in the amount of € 0.64 million were used for the implementation of activities within the strategic objective Development and Strengthening of External Audit.

Given the above, and the fact that certain activities under the 2016-2020 Public Finance Management Reform Programme were not finalised until the end of 2020, as provided for by the Programme and the Action Plan, they are now carried out continuously, or their implementation period is not tied to the year of completion of the Programme, therefore, in this respect, there was a need to continue the implementation of the 2020 AP and the need to ensure continuation of the implementation of the public policy. For the purpose of implementation of the remaining activities planned in the framework of the current Action Plan, the Ministry of Finance and Social Welfare has prepared draft one-year 2021 Interim Action Plan. Namely, the 2021 Interim Action Plan will include new deadlines needed to complete the planned activities.

An examination of the overall status of the fulfillment of the reform objectives, despite the global situation caused by the COVID-19 pandemic, showed a positive trend in the implementation of the Public Finance Management Programme during 2020. As the initiator of the reform, the Programme, among others, is an instrument for integration and monitoring the implementation of reforms in the overall public finance domain. It is important to note that a reporting structure has been established, which has resulted in an additional incentive to implement the projected activities. However, there are challenges when it comes to achievement of performance indicators, which is reflected in the percentage of implemented indicators, as well as the level of not implemented or partly implemented activities. However, in spite of the identified challenges, the 2016-2020 Public Finance Management Reform Programme indicates that there is room for further progress in order to achieve the final results through the 2021 Interim Action Plan.

In addition, note must be taken that the achieved results and the postponement of the implementation of the projected activities for 2020 need to be carefully interpreted, bearing in mind that most activities are not annual, but multi-annual activities. Additionally, the global situation caused by the outbreak of the COVID-19 pandemic greatly influenced further implementation of final activities, as well as the achievement of the overall positive trend.

## DEGREE OF IMPLEMENTATION

The 2016-2020 Public Finance Management Reform Programme envisages the implementation of 5 reform goals, which include 11 objectives. The reform goals contain a total of 41 performance indicators that represent important criteria to assess progress in the set direction of development. Also, the initial Action Plan includes a total of 98 activities, which are crucial for achieving the set reform goals.

Out of a total of 41 performance indicators contained in the Report, 24 performance indicators (59%) reached the target value, while 17 performance indicators (41%) did not reach the target value for 2020.

Out of a total of 41 performance indicators contained in the Report, 26 performance indicators (63%) indicate a positive trend, while 15 performance indicators (37%) indicate a negative trend compared to the previous year.

Likewise, taking into consideration the period of the beginning of implementation of all activities envisaged under the initial Action Plan for implementation of the Programme, it can be concluded that out of a total of 98 activities, 94 activities are due for implementation, whereas 4 activities are expected to be implemented in the future.

When it comes to the implementation of those 94 activities under the Programme, 64 activities were fully implemented (68%), 24 activities were partly implemented (26%), while 6 activities were not implemented at all (6%). When it comes to the 2020 Action Plan, which includes a total of 70 activities, 66 activities were implemented, while other 4 have not yet commenced with implementation. Namely, during 2020, 39 activities were implemented, with further improvement of certain activities provided continuously, 22 activities were partly implemented, while 5 activities were not implemented at all, while the degree of implementation is as follows:

- 60 % of activities have been fully implemented;

- 33 % of activities have been partly implemented;

- 7 % of activities have not been implemented at all.

In line with the conclusions of the PFM Dialogue, the ‘Evaluation of the Public Finance Management Reform Programme’ has been launched, supported by the Delegation of the European Union (DEU) through the EU Integration Facility (EUIF). The draft Evaluation Report assessed the criteria related to: relevance, coherence, efficiency and effectiveness. In addition, the importance of public finance management as an instrument for coordinating public finance management reforms in Montenegro was discussed. With regard to the reform objectives of the Programme, the draft Evaluation Report concluded that the Programme accurately identified important priorities in the PFM system, whose weaknesses are intended to be addressed by relevant activities.

Also, internal, inter-sector coordination and cooperation with reform development partners was quite good, especially in those areas where responsibility for implementation was limited to a single entity (e.g. tax reform, customs administration, audit). For more complex reforms, such as medium-term budgetary framework (MTBF), programme-based budgeting (PBB) and the transition to multi-entity accrual accounting, there is further room for improvement. As far as external coordination is concerned, it was found that the reforms benefited from a wide range of external support with a large share of projects financed by funds from EU pre-accession support - IPA. However, the coherence was negatively influenced by delays in the process of contracting, which resulted in mismatches between the time of project implementation and the timeframe in the PFMRP-Action Plan (AP).

The discrepancy between the commencement of EU IPA projects and the PFMRP-AP has negatively affected the effectiveness of the Programme implementation, given that the implementation of a number of activities has been delayed due to the delayed beginning of related EU technical assistance projects. However, by the end of 2020 significant rate of implementation of activities has been achieved. Given that most activities (almost 70%) were completed in 2019 and 2020, despite the COVID- 19 outbreak, there is reason to consider the last two years of the PFMR implementation extremely successful. In order for the reform to be successfully implemented, more efforts are needed in certain areas. However, it should be borne in mind that the evaluation was conducted until 2020, while the implementation of the unfinished part of activities is expected during 2021.

The use of the PFMRP as a comprehensive tool for initiating and linking reforms in the public finance system and monitoring their implementation has contributed to some positive trends in the set reform objectives, namely:

- Initiating reforms in areas where a sector strategy has not yet existed;

- Uniformity and consistency in information in the entire domain of public finances;

- Establishment of a supervisory structure with two reporting deadlines per year, which contributed to an additional incentive to implement activities within the given deadline.

On the other hand, shortcomings were recorded as well:

- The implementation of reforms and the necessary funding relied heavily on donor support, which led to delays in the implementation of PFMRP when it comes to donor-funded projects;

- The implementation of public finance management reforms has been implemented as a series of highly separated activities;

- In certain reform areas, e.g. state property register, there was no high-level coordination;

- Limited progress in transparency, activities that required modification of the SAP system slowed down the implementation of certain PFMRP activities.

Given the above, in many areas of public finance management, the reform objectives have not yet been fully achieved. Based on the findings and conclusions, the draft evaluation provides recommendations that should be useful in the preparation of the new PFMRP for the period 2022-2026, which relate to:

- the importance of the timeframe for preparation,

- analysis of the situation and use of internal knowledge that would help identify measures;

- the necessary combination of modalities for the implementation of the new PFMRP to balance donor-supported and government-funded activities;

- engaging other development partners in the formulation and implementation of the new PFMRP; setting realistic ambitions for complex reforms;

- the possibility of including specific targets for cross-topics that are crucial for the public finance management system, including transparency, human resources expertise and IT systems;

- improving the oversight function of the PFMRP through a number of operational measures, greater parliamentary involvement and representation of the importance of the PFM Programme.

## KEY ACHIEVEMENTS

After the expiry of the four-year period of the 2016-2020 Public Finance Management Reform Programme, one can conclude that three subsystems can be considered complete:

- Upgraded model for macroeconomic projections enables simulation analysis and forecast of macroeconomic indicators and a module for assessing the impact of structural reforms, which also allows quantification of impact (including policies proposed in the Economic Reform Programme, ERP) on economic development in order to support the preparation of strategic documents;

- Development of the public internal financial control system (PIFC) - strengthening managerial accountability, as a key component for good governance in public administration. During the reporting period, the Analysis of Barriers to Managerial Accountability was prepared, which stressed the importance of delegating authority to successfully achieve goals and strengthen accountability in the public sector, as well as obstacles to the implementation of this concept;

- The ability of the State Audit Institution to adequately respond to INTOSAI standards through the application of audit methodology for financial audits, regularity and performance audits in accordance with international standards.

In addition, last year was marked by other key results, as follows:

- Adoption of the Concept of Integrated Policy-based Planning and Budgeting Procedure and Methodology;

- The new classifications of the programme-based budget;

- Adoption of the Manual for Programme-based Budgeting and Training;

- Application and improvement of the IT system for budget planning for 2021;

- Implementation of the Law on Public Procurement;

- Introduction of the electronic public procurement system (EPPS);

- Improving managerial accountability in the area of ​​devolution in pilot institutions;

- Draft bylaws for the implementation of the Law on Public Sector Accounting have been prepared;

- Manual for Financial and Regularity Audits and Guidelines for Development, Monitoring and Control of Implementation of Recommendations;

- The Guidelines for Proposing and Selecting Financial and Regularity Audits for Annual Audit Plan of the State Audit Institution (SAI);

- 2020 - 2024 SAI Communication Strategy and the Action Plan for its implementation have been adopted, as well as the 2020-2024 SAI Medium-term Plan to carry out performance  audits.

## CHALLENGES IN IMPLEMENTATION

- In order to achieve the objective of the Sustainable Fiscal Framework, Public Expenditure Planning and Budgeting, education and training of personnel needs to be provided. The current situation with the COVID-19 pandemic is a significant risk for the successful implementation of the training process. This circumstance can significantly slow down further dynamics in the execution of the planned activities.

- Certain inaccuracy of data and results obtained by model assessment within the Upgraded Model for Macroeconomic Projections, which is a general feature of model solutions in the existing economic shocks, indicates that the model used a certain degree of experiential and expert assessment to predict macroeconomic parameters. COVID-19 crisis showed the weaknesses of the Model in case of external market shocks.

- Within the Tax Administration, it is necessary to further strengthen administrative capacities in light of the creation of new business processes imposed by the implementation of the digitalisation project and processes. The outflow of staff remains a challenge in this regard. Also, within the Customs Administration, the main challenge in the coming period is the continuation of the improvement of the IT system or implementation of modernised information systems applied by EU customs services in order to achieve interconnectivity and interoperability.

- As concerns the improvement of the reform of public procurement policy, the challenge is to conduct continuous training and development intended for public procurement officers and persons participating in public procurement procedures. Thorough regulation and monitoring of the implementation of procurements with value below the threshold provided by the Law (simple procurement) is to be overcome by standardising simple procurement procedures as exemptions from the application of the Public Procurement Law and prescribing a single act that will apply to all contracting authorities, so to unify the procedure of these procurements at the level of the entire system. With further progression of electronic public procurement system, which began with the application on 1 January 2021, it is planned for the employees of the Ministry to continuously support system users.

- Further establishment of the delegation of accountability system, as well as further strengthening of the capacity of internal auditors.

- Implementation of data on state property in a single ARS database, depending on the authority to be found in the records, which is why there is a need for their full cooperation and participation with proposals and suggestions.

- In the forthcoming period, the challenge for SAI is still considered to be insufficient space that affects the dynamics of hiring new staff. In order to overcome the challenges, Terms of Reference have been prepared for the architectural competition for the conceptual design of the SAI building with defined needs, in accordance with the Law.

- Within the Audit Authority (AA), significant audit activities are forthcoming and an increased workload is expected regarding the audits of the IPA II Programme, their closure and the start of implementation of approved projects under the new financial perspective (IPA III 2021-2027). The challenge is recruitment of staff capacity to vacant systematised working positions, compliance with auditing standards and new legal requirements that require certain amendments to the AA legislation, as well as strengthening the visibility of the AA.

It is important to note that Montenegro, for the third time, conducted the PEFA assessment  (Public Expenditure and Financial Accountability), for the period 2016-2018 (2009, 2013, 2019), through the World Bank project, in cooperation with the EU Delegation to Montenegro and the Ministry of Finance of Montenegro, with financial support of the SAFE Trust Fund. The final version of the Report was published in late October 2019. Note must be taken that the PEFA assessment concluded that there is progress compared to the previous assessment within 11 performance indicators in public finances and financial accountability. Likewise, major areas in public finance management that need to be improved in the coming period have been identified. Therefore, the mentioned Report indirectly represents the basis for the next public finance management strategy.

Bearing in mind that the EU Sector Budget Support is recognition of Montenegro’s efforts to fully implement the Integrated Border Management Strategy (IBM) and the Public Administration Reform Strategy, it is important to note that satisfactory progress is needed in the areas of public finance management and budget transparency, which comprise the two criteria of compliance. In this regard, during the implementation of the Programme, the Ministry of the Interior received a total of €19,868,000 in support, which represents 99.34% of the funds allocated through the implementation of the IBM Strategy, while the Ministry of Public Administration, Digital Society and Media through the Public Administration Reform Strategy  of the total planned € 12 million in direct budget support, received € 6.1 million.

When it comes to the transparency of public finances, some progress has been made in this area in the previous period. Namely, data on budget execution on a monthly, quarterly and annual level are regularly published on the website of the Ministry. The report on budget receipts and expenditures is published once a month, while the analysis of consolidated public expenditure (data on the central budget and local government budgets) is published quarterly. Analyses of macroeconomic developments and structural reforms are prepared twice a year, while projections of public finances and macroeconomic developments are updated twice a year. The Government Debt Report is published quarterly, while the Public Debt Report is published once a year.

Budget transparency remains a challenge, and accordingly PFM activities are planned to contribute to the increased level of information contained in the budget, improved presentation of multi-annual liabilities and capital projects, better budget visualisation and budget reporting, all with the aim of more transparent use of public resources. In this regard, activities to improve the transparency and quality of budgeting are implemented continuously, and will continue in the future, predominantly through further implementation of the programme budget, preparation of the budget for citizens and performance-based budgeting (within the EU co-financed project), then through the implementation of international standards in the domain of state statistics (ESA 2010), as well as the transition from cash-based to accrual accounting.

Also, the 2020 Montenegro Progress Report states that, as regards the budget transparency, the government continues to systematically publish the budget proposal and the adopted budget, as well as budget execution reports. However, there is no mechanism to ensure the quality, comprehensiveness and readability of the published data, especially larger integration of civil society in monitoring the implementation of the 2016 – 2020 Public Finance Management Reform Programme.

# II INFORMATION ON THE STATUS OF PERFORMANCE INDICATORS (OVERVIEW OF ACHIEVED STRATEGIC AND OPERATIONAL OBJECTIVES)

## OBJECTIVE 1 . SUSTAINABLE FISCAL FRAMEWORK, PUBLIC EXPENDITURE PLANNING AND BUDGETING

In the context of the reform, key activities for the above mentioned objective were reflected in the development of the methodology of medium-term budgetary framework, the introduction of a comprehensive programme-based budgeting and improvement of planning and execution of the capital budget. Also, the focus was on adapting and expanding legal and regulatory framework, as well as capacity building of human resources. At the same time, the development of the new information system for budget planning – BMIS is ongoing, in order to establish a modern system of preparation and planning, and to connect with other IT systems, which will enable access to all relevant information and process automation, and provide adequate support to the reforms.

In order to implement the aforementioned reform, the Government session of 20 February 2020 adopted Communication on the enhancement of budgeting and multiannual financial framework, which comprises the proposed methodology and approach for the medium-term budgetary framework, the introduction of programme-based budgeting and further improvement of capital budgeting. The document provides recommendations and further steps when it comes to amendments to the legal and regulatory framework, the development of the IT system and preparation and institutionalisation of the promotion of human resources capacities.

Accordingly, in the process of 2021 budget drafting, the new Methodology of programme-based budgeting has been implemented, which is in line with international standards and practices in this area, with adequate adjustment to Montenegrin conditions and legislation.

Namely, the programme-based budget, in addition to the economic, functional and organisational classification, provides for the continuation of the development of the programme-based classification, which enables better connection with public policies. The programme-based classification has the following dimensions: 1) main programme, 2) programme, 3) sub-programme 4) activities and capital projects.

With the introduction of the main programmes, the programmes of spending units are grouped by sectors. The main purpose of introducing ‘main programmes’ is to combine several spending units and their programmes into one policy domain, in order to provide an integrated overview of the fiscal impact of all key policies and public investment projects in that policy area. 12 main programmes were identified, as shown in the following table:

| 11 | Political system and governance | 17 | Transportation |
| --- | --- | --- | --- |
| 12 | Judiciary | 18 | Sustainable development, environment and tourism |
| 13 | Public safety and defense | 19 | Education, science, sports and youth |
| 14 | Public finances | 20 | Culture |
| 15 | Economy | 21 | Healthcare |
| 16 | Agriculture, rural development and forestry | 22 | Labour and social care |

Within the main programme, a system of programmes and sub-programmes has been established that correspond to the competencies of the spending units. The implementation of the activities of spending units is based primarily on: i) regulations relating to sectors and spending units, ii) legal competencies of spending units, iii) strategic plans and other strategic documents, iv) medium-term work plans, c) best practices and standards.

The implementation and development of programme-based budgeting and programme structure creates preconditions for performance-based budgeting. Through the establishment and monitoring of the fulfillment of all general, individual and specific performance targets and related strategic and operational indicators for programmes and sub-programmes, decision-makers and the Government will dispose of adequate information that may affect the level of allocation of funds for specific activities when determining the annual Budget Law.

In order to create legal basis for the implementation of above mentioned activities, amendments to the Decision on the method of preparation and content of the programme-based budgeting of spending units has been adopted, which enabled comprehensive application of the programme-based budgeting through the establishment of the detailed programme structure formalised through the programme-based classification on several levels and performance indicators, in order to ensure better linking with the organisational classification, public policies and priorities of the Government and to improve the transparency of the budget.

### PHASED IMPLEMENTATION OF PROGRAMME-BASED BUDGETING

In the mentioned period, a new programme-based and organisational classification was developed, which includes main programmes, programmes, sub-programmes and projects, with the possibility of including activities as the lowest level of classification, as well as harmonisation of the status of spending units, in accordance with the Law on Budget and Fiscal Responsibility. On the basis of this classification, 2021 Technical Instruction for Budget Preparation – the Budget Circular was prepared and delivered to the spending units, which contained Macroeconomic and Fiscal Policy Guidelines, Programme-based Budget Manual, the Guidelines for the Use of the Information System for Budget Planning, as well as other guidelines for the preparation of the budget, based on which first level spending units submit their requests for budget funds for 2021. The Budget Circular pays special attention to systemic changes related to the application of the new programme-based and organisational classification, additional information on capital projects, implementation of the new budget management information system, competencies and establishment of communication between first level spending units and spending units supervised by them and the Ministry of Finance and Social Welfare, as well as the implementation of the statement on gender-responsive budgeting.

The requests of spending units have been prepared in accordance with the new programme-based and organisational structure (with established new coding system of the classification) and were submitted electronically, using new information system - BMIS, through which other communication with the spending units was performed to improve the quality of submitted requests.

However, in order to ensure security of the public finance system and adequate implementation of the reform process, as well as budget execution in accordance with all levels of programme-based classification, the programme-based budgeting is planned to be implemented in phases. Namely, the implementation of the programme-based budget and budget execution is closely related to treasury operations. In this regard, due to the need to provide the functional connection and interconnection between all relevant information systems, budget execution in 2021 will be conducted at the level of main programmes and programmes, while budget execution at the level of sub-programmes and capital projects is planned for the next year.

In addition, the first phase of the implementation of programme-based budget reforms was predominantly related to ex-ante budgeting, while the next phase will include ex-post reporting on budget implementation and performance. The following activities are planned for the next period:

- Implementation of the medium-term budgetary framework: training of spending units to draft proposals for new activities for the medium-term budgetary framework;

- Change in the scope and content of the medium-term budgetary framework in the Macroeconomic and Fiscal Policy Guidelines;

- Finalisation of the Capital Budget Manual and organisation of capital budget training for administrations responsible for capital budget implementation;

- Preparation of the Manual for Monitoring and Reporting on the Impact of the Programme-based Budget, which would during 2021 be used as the basis for training on reporting the performance of spending units and defining performance indicators that will be implemented in 2022 budget;

- In-house training for the spending units to formulate information - performance indicators -in accordance with the Decision and the Manual governing the programme-based budget and their monitoring by the Ministry of Finance and Social Welfare, as well as gender-responsive indicators;

- Drafting the budget for citizens, in order to improve the visibility of the budget.

Preliminary software solution for budget planning was presented in September 2019, after which rating of the functionality and exchange of information was made in order to further improve it. In the first half of 2020 trainings planned for representatives of the Ministries of Finance and Social Welfare and all spending units were successfully implemented, therefore, requests for the 2021 budget were filled in using the new budget planning IT system. In this regard, it can be considered that the first phase of system development (electronic filling of budget requests by spending units in all elements of the programme-based budget, data entry for further work on budget planning and their implementation in the form prescribed by the law, for consideration in the parliamentary procedure) was implemented, after which during 2021 further activities will be carried out to develop IT systems, which will lead to the full implementation of software for the budget planning and execution, and reporting.

Under the IPA project Development of IT Payroll System, relevant laws and regulations were analysed as an initial step, data collection from institutions was conducted, numerous meetings were held with representatives of the Human Resources Administration, Ministry of Public Administration, Digital Society and Media, and other ministries and spending units.

According to the obligations stipulated under the contract, during 2019, objectives of the first year of the contract execution (until 09 January 2020), technical deliverables in the form of documents adopted and the estimated level of fulfillment of results in percentages based on the assessment of the users, are shown in the table below:

| Results / output data | Document | Technical deliverables | Estimated degree of target fulfillment by the users |
| --- | --- | --- | --- |
| Diagnosis of the initial situation including an audit of activities and a detailed action plan. | Project implementation phase report | D1. Diagnostic Report D2. Implementation options D3. Action Plan D4. Tender for procurement of server equipment | 100% |
| A system for centralised payroll has been established and is fully interoperable and harmonised with existing IT systems and the legal framework | The First Interim Progress Report (as of 09 January 2020) | D5. System design | 50% |
| Technical specifications of the system and all other relevant documents explaining how the system functionally and technically operates are provided in the Montenegrin language. |  | D6. Technical specifications D7. User guide D8. Operating instructions | 50% |

During 2020, as foreseen in the framework of a series of activities planned within the project ‘Implementation of Centralised Payroll System’, following the planned tender procedure and selection of bidders, the contract for the purchase of equipment with server licenses for the operation of the new centralised payroll system and budget planning was signed, after which the process of purchase of the necessary equipment was completed. In the reporting period, technical and adaptation works were completed that constituted a precondition for the equipment, as well as adequate preparation of server rooms within the Ministry of Finance and Social Welfare in accordance with technical specification. In accordance with the contract, training was conducted (in late 2020) for basic handling of delivered equipment for two employees of the Ministry of Finance and Social Welfare, as well as the planned installation of new software on the purchased equipment, while planned data migration is expected in 2021. After the installation of the equipment, the implementation of the training plan for key users and IT administrators started. The start of the planned training of end users of the centralised payroll system was postponed due to delays in the procurement and installation of equipment and the negative impact of the COVID-19 pandemic. Training for key users is planned to take place shortly before the beginning of use of the new centralised payroll system application.

In order to link the payroll records of employed civil servants and state employees with the Human Resources Administration system, the interface between SCCoE and the Human Resources Administration was developed; the initial presentation of the service was held at the Ministry of Finance and Social Welfare in late September 2020.

The objectives and results envisaged for the second half of the year, with the estimated degree of fulfillment of the results in percentages, based on the user assessment, are shown in the table below:

| Results / output data |  | Document |  | Technical deliverables |  | Estimated degree of goal fulfillment by the user |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Successfully conducted training for IT administrators and key users |  | The Second Interim Progress Report (as of 9 January 2021) |  | D9. Training needs analysis D10. Methodology and training plan D11. Training materials |  | 25% |  |
| The centralised payroll IT system has been adjusted, all shortcomings and failures have been eliminated, interoperability has been ensured. |  |  |  | D12. Testing plans D13. Cases to be tested D14. UAT specification D15. Delivery plan, including backup plan |  | 25% |  |

It is important to note that access to the test version of the application and trial use of the system functionalities developed so far is provided to users in the Directorate for Payroll Calculation and Control. The trainings included two key groups; key users within the Directorate for Payroll Calculation and Control in the Ministry of Finance and Social Welfare, and after acquiring a satisfactory level of knowledge, the trained key users continue training for end users in all spending units outside the Ministry of Finance and Social Welfare. The planned training for key users should take place shortly before the beginning of use of the new centralised payroll system application. Interface for connection with the system of the Human Resources Administration was created, and a service demonstration was performed.

| Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | 2020 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Implemented | Target values | Implemented | Target values | Implemented | Target values | Implemented |  |
| Share of new medium-term sector strategies that include estimates of implementation costs, including potential donor funding | 60% | 80% | 70% | 85% | 75% | 90% | 85% | 100% | 100% |  |
| Average deviation between MTBF budget ceilings and actual annual budget expenditure limits | 9% | 7% | 6% | 6% | 0,87% | 5% | 0,11% | 5% | 2,13% |  |
| Number of staff trained for top-down medium-term budget planning | 0 | 52 | 0 | 35 | 0 | 52 | 17 | 72 | 100 |  |

| Performance Indicator |  | Planned 2014 | 2017 |  |  |  |  | 2018 |  |  | 2019 |  |  |  | 2020 |  |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target values |  | Implemented |  |  | Target values | Implemented |  | Target values |  | Implemented |  | Target values | Implemented |  |  |
| Share of first level budget organisations that provide comprehensive information with their annual budget requests | 40% |  |  | 75% |  | 70% | 80% |  |  | 80% |  | 90% |  | 90% | 100% |  | 100% |  |
| Level of performance information included in budget planning | Programme headings are defined by all budget organisations |  |  | Programme structure is developed in all budget organisations, including their mission statements, programme descriptions and goals |  | Developed program structure as regard defining the programme headings of all spending units | Developed programme structure as regard defining the programme heading of all spending units |  |  | Defined programme headings of all spending units |  | Level 1 upgrade with defining a set of performance indicators for pilot projects |  | Defined programme headings of all spending units | Level 3 |  | Defined heading of main programmes, programmes and subprogrammes |  |
| The number of staff trained for planning and monitoring expenditures in line with programme budgeting principles | 0 |  |  | 20 |  | 0 | 35 |  |  | 0 |  | 70 |  | 17 | 130 |  | 100 |  |

The implementation of the above stated activities as regards the medium-term budgetary framework and programme-based budgeting has contributed to the positive trend and achievement of the target values of most of the indicators within the objective of Sustainable Fiscal Framework, Public Expenditure Planning and Budgeting.

The share of medium-term sector strategies that include cost estimates for their implementation, as defined by the performance indicator, is at the level of the planned value for 2020. Planning has been improved due to the insistence on providing better information in the process of reviewing strategic documents, as regards financial impact assessment. These data are important when setting spending limits in the Macroeconomic and Fiscal Policy Guidelines, and later in the annual Budget Law. Also, the level of development of medium-term planning and activities aimed at upgrading it, primarily improved due to training implemented during 2020. In addition to the above, we will be working in continuity on improvement, having in mind that the IT solutions in this field will be upgraded in the future period.

The performance indicator related to the average deviation between MTBF budget ceilings and actual annual budget expenditure limits planned by the annual Budget Law shows a high degree of fulfillment, and proves that the limits of budget expenditures planned under the Budget Law for 2020 deviate from the amount of the expenditure limit planned by the 2020 - 2022 Macroeconomic and Fiscal Policy Guidelines less than the amount of the target value.

The performance indicator referring to the number of staff trained for medium-term planning is above the target value level. The trainings were delivered in a larger number compared to the target value, bearing in mind that during 2020 there was a special emphasis on the implementation of the reform, by the adoption of Communication on the enhancement of budgeting and multiannual financial framework by the Government and trainings for both management and expert level.

The performance indicator related to the comprehensiveness of budget requests meets the target value. Budget requests obtained by budget users are in the format prescribed by the Ministry of Finance and Social Welfare in the Budget Circular. During 2020, in the preparation of the Draft Budget Law for 2021, budget requests were filled in and submitted electronically using the new IT system for budget planning in the set format, and were returned back to the spending units by the Ministry of Finance and Social Welfare until completely filled in, and quality information obtained. The Ministry of Finance and Social Welfare also receives additional information from the spending units in the meetings in the framework of the process of preparation and planning of the annual budget law, during the preparation process, which puts the value of the performance indicator, observed in total, at a satisfactory level.

As regards the fulfillment of the performance indicators Level of performance information included in budget planning, the main elements of the programme-based budget have not been fully developed during 2020. In this regard, activities on the development of the programme-based budget elements have been intensified during 2020, programme structure has been elaborated to the level of sub-programmes, while full implementation of the programme structure is envisaged in 2021, with full implementation of the programme-based budget expected in the coming period, at the level of activities and performance indicators at all levels.

The performance indicator referring to the number of staff trained in accordance with the principles of programme-based budgeting has not been fully met. Bearing in mind that during most of 2019 preparatory activities have been implemented, such as the situation analyses and development of the concept, trainings during 2020 were related to the improvement of multi-annual planning, programme-based budgeting, programme structure revision, establishment of the activities and performance indicators, and the like. However, the trainings were not implemented fully, having in mind the COVID-19 outbreak, which conditioned trainings to be delivered online exclusively. The delivery of trainings will continue during 2021.

| Performance Indicator |  | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | 2020 |  | Trend |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target values | Implemented | Target values | Implemented | Target values | Implemented | Target values | Implemented |  |  |
| Level of detail in public presentation of capital budget | Projects in the capital budget presented grouped by areas (education, health, culture, sports …) |  | Overview of all individual projects implemented in the budget year | Projects in the capital budget presented grouped by areas (education, health, culture, sports…) | Overview of all individual projects implemented in the budget year | Projects in the capital budget presented grouped by areas (education, health, culture, sports…) | Overview of all individual projects implemented in the budget year | Projects in the capital budget presented grouped by areas (education, health, culture, sports…) | Level 3 | Projects in the capital budget presented grouped by areas (education, health, culture, sports…) |  |  |
| Actual capital spending in the current year as a share of the capital budget plan | 70% |  | 80% | 82% | 80% | 91%/111% | 86% | 92%/112,3% | 90% | 180.60% 107.6% |  |  |

The performance indicator related to the level of detail in the public presentation of the capital budget shows a negative trend of value in relation to the target value for 2020. However, bearing in mind the implemented activities in the capital budget planning and IT system implementation during 2020, it is forecasted that the said indicator will be completely implemented during 2021. In the coming period, intensive activities are planned in order to meet the target value. Also, with the implementation of the mentioned project, a more transparent presentation of capital projects is planned through the establishment of the register of public investments.

Challenge:

Having in mind that the fulfillment of the planned objectives requires further training and education of staff, the timeframe for the planned activities for the next period, which concerns the implementation of training for key users, future administrators and end users in individual spending units, is questioned due to the current situation with the COVID-19 pandemic, and poses a significant risk to the successful conduct of the training process. We conclude that this objective circumstance can significantly slow down the further dynamics of fulfillment of the planned activities on the project. Having in mind the period of validity of the implementation of the programme, which expires at the end of 2020, an extended time of implementation of the Action Plan during 2021 will be proposed in order to finalise activities that are not expected to be implemented by the end of 2020.

Indicator related to the creation of capital spending, that is, the implementation of the capital budget in 2020 is fulfilled and shows a positive trend. Such a high level of implementation is the result of intensive work on already started projects, all in order to complete the activity and put facilities in operation. Also, intensified activities related to new significant infrastructure projects in order to start the execution of works.

### IMPROVING MODELS FOR MACROECONOMIC PROJECTIONS

Directorate for Economic Policy and Development (DEPD) in March 2018 developed Montenegro Macroeconomic Model, MMM, which will enable simulation analysis and module for assessment of the impact of structural reforms, which enables the assessment of the impact of structural reform measures (including policies proposed in the Economic Reform Programme -ERP) on economic development, in order to support preparation of strategic documents.

During the reporting period, the Directorate for Economic and Development Policy worked on improving the newly developed model for macroeconomic projections (MMM). The Montenegro Macroeconomic Model (MMM) is constantly updated in accordance with the latest available data, and at the end of 2020 it was updated with official statistics of MONSTAT for Q3 2020 in terms of gross domestic product, relevant labour market indicators (survey on labour force), as well as with data on fiscal costs of individual structural reforms and infrastructure projects. Despite the exercised legal right of three employees in 2020 to the old-age pension, in accordance with the public administration reorganisation, the quality of work was maintained in the previous year in the context of the staff structure of the Directorate, where one person was additionally hired to work on the MMM model.

During the reporting period, employees who are actively working on the implementation and use of model solutions in the Directorate have successfully completed several trainings organised by CEF (Center of Excellence in Finance) of the International Monetary Fund. The trainings organised by CEF were related to the fiscal costs of structural reforms, their integration into national budgets and measuring the impact of structural reforms on macroeconomic indicators. All these trainings are of great importance for the Economic Reform Programme, a key strategic document in the economic dialogue of Montenegro with the EU, where Chapter III - Macroeconomic Framework, relies on the MMM model to project the most important macroeconomic indicators in combination with the existing model of the Directorate, and the assessment of the impact of the construction of infrastructure projects on the economy is being assessed also. The employees also successfully completed the trainings - Macroeconometric Design and Financial Programming, organised online by the International Monetary Fund.

These have also been identified as the most significant risks in the Directorate in terms of full implementation of the new model (MMM), insufficient number of employees qualified for macroeconomic projections and insufficient number of trainings related to macroeconomic and financial programming. As stated, the Directorate carried out a number of activities in the reporting period in order to improve work processes and increase the quality of macroeconomic forecasts. Continuous training of employees gradually fulfilled the recommendations of experts who have worked on the development and establishment of the MMM Model. In order to maximise the full capacity and functionality of the model, the Directorate for Economic and Development Policy in the reporting period initiated additional project cycle and asked for professional and technical assistance, which will, among other things, include improved econometric knowledge of employees, management of newly developed models, as well as developing programming skills in EViews econometric software, which is an integral part of the model software solution.

The new model for macroeconomic projections MMM was also used to develop several scenarios of economic trends and the impact of the COVID-19 crisis on economic parameters in the current year and in medium-term. For further development of the Model, through the implementation of the project ‘Strengthening transparent and responsible management of public finances in Montenegro’ technical assistance of Slovak experts was provided, which was not implemented at the desired pace due to the global COVID-19 pandemic.

The target value of the performance indicator, which refers to the improvement of macroeconomic indicator projections and further training of employees to work on the MMM model, was partially implemented in the reporting period, as it is a continuous process, which is expected to be completed by the end of 2024. After that, according to the recommendations of experts, the MMM model is expected to be fully operational.

The target value of the second performance indicator, minimisation of the difference between the plan and implementation, has not been realised due to a lower consistency of MMM conditioned by COVID-19 crisis, which is generally characteristic of the macroeconomic models in conditions of strong external, unforeseen shocks. Therefore, the realised GDP growth rate deviated significantly from the projected one.

| Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | 2020 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Implemented | Target values | Implemented | Target values | Implemented |  |
| Staged implementation of the upgraded model for macroeconomic projections and structural reform impacts | The existing model used in the Directorate for Economic and Development Policy is based on a model of financial programming and projection of certain parameters is based on expert assessment | A new model for projections of macroeconomic indicators and the impact of structural reforms is developed and employees trained | A new model for projections of macroeconomic indicators and the impact of structural reforms is developed and employees trained | The requirements for utilisation of the new model by the employees in the Directorate for Economic Policy and Development are met | The requirements for utilisation of the new model by the employees in the Directorate for Economic Policy and Development are met | Full implementation and full training of employees to use the model | Partially implemented. The project is being continuously implemented, in accordance with the recommendations of experts for the full implementation of the model, which is planned for the end of 2024 |  |
| The difference between actual and projected real GDP growth rate | 1.8 p.p. | Less than 0.3 pp | Target value for 2018 met (0.2 pp) | Less than 0.3 pp | Target value for 2019, partly met, given further recommendations | Less than 0.2 pp | Target value projections are not met due to market disruption and external shocks |  |

Challenge:

Some inaccuracy of data and results obtained by model estimation, which is a general feature of model solutions in times of economic shocks, indicates that the model used a certain degree of experiential and expert forecasting to predict macroeconomic parameters.

The COVID-19 crisis showed the weaknesses of the Model in cases of external market shocks. It is necessary to further develop the model to assess the impact of new investments in certain sectors of the economy, as well as medium and long-term forecasts in case of endogenous and exogenous economic disorders, for which it is necessary to seek international expert support for further development of economic simulation models.

## GOAL 2. BUDGET EXECUTION

In this area and in the original PFMRP, three priority areas have been identified: revenue collection, public procurement and debt management. In the revised PFMRP (2018), two priority areas were added: customs administration and state aid reform.

### TAX ADMINISTRATION

The analysis of revenue collection shows that the Montenegrin economy, when it comes to income tax, has a high degree of voluntary compliance with tax regulations and awareness of the importance of proper tax filing and payment, taking into account the fact that in the challenges of the economic crisis, tax collection exceeding €45 million was delayed. When it comes to value added tax (VAT), the Tax Administration faced the biggest challenges in collecting this type of revenue since the tourist season did not meet expectations and due to which there was a drastic drop in turnover in all industries, especially catering and hospitality.

It is evident that efforts in the implementation of budget execution in the conditions of the pandemic gave certain results, that is, the value of indicators of tax revenue collection in 2020 were as follows: €65 million above the budget plan and €79 million (7%) below the result from 2019.

According to records during 2020, revenue collection was:

- Total gross collection: €1,098,146,781.23  - €65 million over the plan, and €79 million less than in 2019 (7%);

- Revenue on the basis of VAT amounted to €529.8 mil., or 12.6% of estimated GDP.

Also, the performance indicator related to the growth of the share of submitted e-returns is above the expected value for 2020. Special emphasis should be placed on the increase of e-returns for VAT - 89%. Namely, a novelty was introduced and now monthly VAT returns are submitted electronically exclusively, which is in accordance with the European tax legislation. Also, e-filing of IOPPD returns is enabled. Income tax target is at 99.6%, which achieved the predicted value of the performance indicator and continued the positive trend.

Harmonisation of legislation with the EU acquis takes place with a delay due to the fact that the adoption and amendments to legislation are based on comments submitted by the European Commission. The Law on Corporate Income Tax, VAT Law, the Law on Tax Administration after they obtained a positive opinion from the European Commission, are pending re-adoption procedure. There are ongoing activities to prepare Draft Law on Amendments to the Law on Corporate Income Tax, which will, in order to harmonise national tax legislation with the directives of the European Union, harmonise the applicable law with Council Directive 2011/96/EU (last amended by Council Directive 2014/0086/EU and 2015/0121/EU) on the common system of taxation applicable in the case of parent companies and subsidiaries of different Member States and Council Directive 32003L0049 on the common system of taxation applicable to interest and royalty payments made between associated companies of different Member States. Draft Law on Amendments to the Law on Corporate Income Tax, with the table of concordance and appropriate documentation, was submitted to the Office for European Integration of the European Commission in Brussels and a positive opinion was obtained. After the adoption of the Law, a rulebook on transfer prices will be adopted, which will regulate in more detail the application of the rules on transfer prices, in accordance with the guidelines of the Organisation for Economic Co-operation and Development (OECD).

There are ongoing activities to prepare Draft Law on Amendments to the Law on Tax Administration, which obtained the opinion of the European Commission and will be submitted to the Government of Montenegro for consideration and determination.  The said Draft Law shall harmonise the existing Law on Tax Administration with Council Directive 2011/16/EU on administrative cooperation in the field of taxation (DAC 1), as well as changes to that Directive, namely: the Council Directive 2014/107/EC as regards mandatory automatic exchange of information in the field of taxation (DAC 2), Council Directive 2016/881/EU on the provision of information on transactions between related parties (DAC 4) and Council Directive 2016/2258 as regards access to anti-money-laundering information by tax authorities ( DAC 5), which will provide a legal framework for the development of information exchange systems between competent authorities, and contribute to strengthening national tax system and improving tax collection.

After its adoption, the Parliament of Montenegro will pass bylaws for its implementation, which will be sent to the European Commission for an opinion, as follows:

- Ordinance on the detailed manner of reporting on the accounts of residents of EU Member States, other countries or territories of countries;

- Rulebook on the manner of exchanging information with the competent authorities of the EU Member States, other states or territories of states;

- Rulebook on more detailed manner of reporting on the operations of related parties.

Activities related to the project ‘Tax Administration Reform in Montenegro’ continued (RARP), which consists of four components: 1. Institutional Development, 2. Business Processes, 3. Taxpayer Services, and 4. Electronic Fiscal Invoicing (EFI). So far, the initial report with an action plan, budget and implementation stages has been prepared. Final activities on the preparation of the Functional Requirements Document of the future IT system are in progress. Also, the challenge in achieving the objective is fully reflected in the implementation of the project Electronic Fiscal Invoicing and reform of the Tax Administration, which includes an integrated IT system and reengineering of business processes.

Under the 1st Component - Institutional Development, the methodology for calculating the tax gap for VAT, income and contributions for 2017, 2018 was prepared, while in the reporting period, the activities on the collection of data for 2019 have been initiated. In the previous period, a detailed methodology for assessing the tax gap by type of tax was prepared and tax gap calculations were made, a report on the new analytical function with recommendations for organisational/personnel changes was prepared and training was held for employees to use the methodology. Also, an internal procedure for calculating the tax gap by type of tax has been prepared.

Furthermore, in order to provide quality control services during the project implementation, that is, a detailed overview, guidelines, as well as evaluation of key results in the introduction of a new integrated information system, a contract was signed with the consulting company KPMG. FRD (Functional Requirements Document) development is the most important task and implementation phase of the RARP project and represents a description of future business processes for the IT system to support. The Functional Requirements Document was completed in December 2020, after the quality control carried out by KPMG, therefore, the first phase of the Contract, the review of Functional Requirements Document, was successfully implemented. Based on the adopted plan, the delay in the preparation of the Functional Requirements Document was 14 months. In view of the new situation caused by COVID-19 outbreak, a number of teams spent more time than anticipated in producing the Functional Requirements Document because the documentation was upgraded in several instances.

Under the 2nd Component– Business Processes, consulting firm (Coming-Computer Engineering) began its engagement, which, inter alia, includes the preparation of a Data Cleansing Strategy and a general plan for data cleansing and conversion; a detailed procedure for data cleansing, training and management of the internal data cleansing team (business and IT users); process implementation control and data cleansing advice; preparation of systems for data migration from old systems to the new system, as well as consulting services in the process of preparation of test and production data migration. In March 2020, the agreed first phase was formally completed, that is, the Data Cleansing Strategy, the Action Plan, data catalogue, as well as a checklist of identified problems, were prepared, while in April 2020, the second contract phase was completed, involving the development of cleansing procedures, as well as training of employees who will be involved in the cleansing process itself. The third phase has started, which specifically refers to the process of data cleansing, in accordance with the adopted documents and plans. In addition, two progress reports were prepared in the 3rd phase of the data cleansing.

The Terms of Reference for the introduction of the Data Warehouse System have been completed, followed by the selection of a company for its implementation. The implementation of the Terms of Reference consists of two phases. The first phase will follow e-fiscalisation, while the second phase of implementation is related to the implementation of the RMS system.

Under the 3rd Component, consulting firm (IPSOS Strategic Marketing/Belgrade, in September 2019) was engaged to prepare, implement and analyse results of two surveys – ‘taxpayer satisfaction survey’ and ‘satisfaction survey of employees in the Tax Administration of Montenegro’. In order to monitor a set of indicators concerning the success of the project, the beginning of a new round of survey is planned, which will be realised annually until the end of the project.

Under the 4th Component– EFI, the agreement was concluded on implementation of the e-fiscalisation project with the consulting firm OSA-NEOS in July, 2020. The Terms of Reference, the Project Charter have been prepared and adopted, and the implementation has started in accordance with them. The phase of the project that allows EFI system from 01 January 2021 to be available 100% of the time for cash and cashless transactions, was also completed. On December 29, 2020, the Parliament of Montenegro passed the Law on Amendments to the Law on Fiscal Invoicing in Trade in Products and Services (Official Gazette of Montenegro, No. 08/21), in order to adjust taxpayers to the new system of recording trade in products and services via electronic toll booths. The process of implementation of this Law, as indicated by a large number of entrepreneurs, is further complicated by the situation caused by the COVID – 19 outbreak, which led to a decrease in economic activity of economic entities. Due to all the above, as well as taking into account the needs of the business community, this Law provided the possibility of a transitional period, until June 1, 2021, to establish a system of electronic fiscal invoicing in real time (online). Accordingly, taxpayers in the first five months of 2021 had a choice of methods to record trade in goods and services, with the obligation to introduce the application of the online real time fiscal invoicing system from June 1, 2021, by all taxpayers in accordance with the law.

Under the project financed by the European Commission - Multi-beneficiary IPA, implemented by the consultants of the International Monetary Fund, relating to the strengtheningof administrative capacity, in H1 2020, online workshops were held on the following topics: Large Taxpayers; Tax Control; as well as VAT Refund.

In February 2020, the annual IMF Mission was implemented, which monitors the implementation of recommendations from the previous year, with guidelines and recommendations for next year. Based on the recommendations through the Action Plan, the quarterly implementation of the recommendations based on the Missions reports is monitored.

| Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | 2020 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target value | Implemented | Target value | Implemented | Target value | Implemented | Target value | Implemented |  |
| Share of submitted e-returns (Profit tax, VAT) in comparison to total number of submissions | 27% | VAT 50% | VAT 50% | VAT 65% | VAT 70% | 75% | 77,37% | VAT 80% | VAT 89% |  |
|  |  | INCOME 95% | INCOME 95% | INCOME 97% | INCOME 99% | 99% | 99,5% | INCOME 99% | INCOME 99,6% |  |
| EU VAT regulations concerning EU common market successfully implemented | Screening process completed | Negotiations in Chapter 16 open | A certain degree of legislative harmonisation has been achieved, a higher degree has been achieved in the field of VAT, harmonisation in the field of income tax (transfer prices), of administrative cooperation and mutual assistance remains. | Law on Amendments to the Law on Corporate Income Tax (Q4 2018) Law on Amendments to the Law on Tax Administration VAT law (Q4 2018) | Submitted draft versions of amendments to the Law on VAT, the Law on Income Tax and the Law on Tax Administration in the area of information exchange (automatic) and mutual assistance in order to further harmonise domestic legislation with the acquis communautaire | Law on Amendments to the Law on Corporate Income Tax (Q4 2018) Law on Amendments to the Law on Tax Administration VAT law (Q4) | All proposed amendments to the law were approved by the Legislative Committee. After which they were submitted to the EC for an opinion. | Implemented planned activities under the Accession Programme - Chapter 16. Taxes (PPCG document | Higher degree of compliance compared to the previous year |  |
| Share of collected tax revenue compared to the planned tax revenue in the annual budget law | 100% | More than 100% of the planned (24 million above the plan for 2017) and 34 million above the implementation in 2016. | More than 100% of the planned | 100% | Above the plan for 2018, 73 million or 117 million above the implementation from 2017. | 100% | Above the plan for 2019, 80 million were implemented above the plan. | 100% | 100% €65 mil. above the plan according to the budget revision, and €79 mil. (7%) below the implementation from 2019. |  |
| Share of collected VAT revenues in GDP | 13.5% | 13.5% | 13.0%[1] | 14.7% | 13.6% | 13.6% | 14.44% | 14.6% | 12.6% |  |

Challenge:

Further strengthening of administrative capacities in the light of the creation of new business processes imposed by the project implementation and digitisation processes. The outflow of staff remains a challenge in this domain

It is important to continue with the training of employees, prepare the Human Resources Management Strategy, not only at the level of the Administration but also beyond.

### STRENGTHENING CUSTOMS ADMINISTRATION CAPACITIES

In order to efficiently collect revenues, the Customs Administration continuously conducts activities for proper and timely collection of revenues, based on the calculation of customs, tax, excise and other duties.

In 2020, net collection of revenue amounted to €661,379,779.21. In the conditions caused by the economic crisis due to the COVID-19 pandemic, the decline in revenue in domestic and foreign trade as well as the reduction of economic activity caused the generated revenues to be lower by 18% compared to the previous year.

During 2020, in order to harmonise the customs and excise legislation, the Regulation on the Customs Tariff for 2020 was adopted, which harmonised the nomenclature of the customs tariff with the Combined Nomenclature of the European Union.

The Draft Customs Law has been prepared in accordance with the EU Customs Law and the national procedure is being finalised and sent to the European Commission for review.

In order to implement the IT system for excise duties at the national level, activities continued in accordance with the planned dynamics through the implementation of the project ‘Support to the Customs Administration in the field of excise duties’ under EUIF funds. The implementation of the new national application for excises in the Customs Information System will enable electronic communication between the Customs Administration and excise taxpayers, among other things, as well as electronic monitoring of excise products in the regime of deferred excise payment, using electronic excise documents as important prerequisites for future connection with EU Excise Movement and Control System (EMCS). The duration of the project has been extended until February 1, 2021, when it will end and when the new application will be released into production.

As regards the Implementation of modernised customs procedures at the national level, in the framework of the project ‘Support to the Customs Administration’ at the end of February and July 2020 the third and fourth meeting of the Steering Committee of the project ‘Support to the accession to Common Transit Convention and the Convention on Facilitation of Trade in Goods’ was held, as well as the third and fourth meeting of the Steering Committee of the project ‘Implementation of the New Computerised Transit System (NCTS)’, which are implemented under the IPA 2014 project ‘Support to the Customs Administration’. At the meetings of the Steering Committees, the second and third Interim Reports were adopted, which contain the activities and tasks performed by the consortium in the reporting period from 1 July, 2019 to 31 January 2020 and from 01 February 2020 to 30 June 2020, as well as the plan for the following periods. Also, the impact of the COVID-19 pandemic on planned activities was considered, as well as measures that can reduce the impact. At the end of 2020, two meetings were held - Technical e-mission of DG TAXUD, on the topic of NCTS-P5 & Geographical expansion, where a summary of the status of completed and planned activities was given, while experts gave their views on updating our National Project Plan (NPP) and listed the challenges that await us, due to the COVID pandemic, in view of application testing and training of customs officers. In cooperation with the Chamber of Commerce of Montenegro, trainings were delivered for the economy and the banking sector on the Common Transit Convention, the benefits it brings and the novelty that await them. The application for Guarantee Management System (GMS) was tested, and work continued on national instructions (transit, guarantees, etc. ), which will be harmonised with the new Customs Law. The connection with the Joint Communication Network of the Member States (CCN/ CSI) managed by the Directorate General for Taxation and Customs (DG TAXUD) is being successfully implemented under the project, which will be used to test this and all other IT systems implemented in the Customs Information System through Chapter 29 Customs Union, and which after Montenegro’s accession to the EU will serve as a security link for the exchange of data in the field of customs and taxes. With the implementation of this Project, the conditions for Montenegro’s accession to the Common Transit Convention and the Convention on Facilitation of Trade in Goods, which is one of the conditions for accession to the European Union, will be met. The project is expected to be completed in 2021, when the largest number of activities will be implemented.

Also, during 2020, activities were carried out under the Project for the introduction of a system for electronic management of excise stamps in order to implement the Decree on labeling tobacco products and alcoholic beverages with excise stamps (Official Gazette of Montenegro, No. 28/19). The aim of the project is to introduce advanced technology to improve the efficiency of the customs service in combating the illicit trade in tobacco products, which is the recommendation of the EC from the annual progress reports. Under the Project, activities of delivery of hardware (server and storage) equipment, printed excise stamps for marking tobacco products and printed excise stamps for marking alcoholic beverages and software licenses for the electronic management system for excise stamps were implemented. The completion of this project is expected in February 2021.

Under the ‘Support to the Implementation of the Integrated Border Management Strategy’ IPA SBS IBM 2015 Project, in September 2020, ‘Strengthening the Administrative Capacities of the Customs Administration for Full Implementation of the Information System for Inspection Management’ project was completed, which enabled analytical work and reporting for the purposes of inspection management, case management records, as well as the development of an objective and impartial annual ex-post control plan. The procurement of equipment for the customs laboratory for testing petroleum and petroleum products was also implemented under the project, and was installed in the customs laboratory. Trainings of customs laboratory employees were implemented. The new modernly equipped laboratory for the analysis of petroleum and petroleum products started operating in September 2020. The customs laboratory performs the physical-chemical analysis of high-risk excise goods and provides expert opinions on the classification of goods in the customs tariff, to ensure proper calculation of customs duties, improve fight against the gray economy and prevent illegal traffic of goods. Additionally, the purchase of computer equipment for border crossings was made and completed work to improve the operation of the Customs Security and Control Division. All planned activities of the Customs Administration under the project have been completed.

The nCEN network of the World Customs Organization has been established, which contributes to the efficient exchange of information between the countries of the Western Balkans, related to increasingly significant seizures of narcotics, precursors, psychotropic substances, cigarettes, goods infringing intellectual property rights and more.

During 2020, the Customs Administration continued its activities on finalising the terms of reference and technical specifications for activities approved to be implemented under IPA 2018, among which is the project ‘Support to the Customs Administration to Improve Customs Information System’. Also, the preparation of documentation for the approved project of the Customs Administration ‘Support to the Customs Administration for the Implementation of the National Customs Decisions System’ under the EUIF 2017 continued.

When it comes to improving customs system for risk management, in the framework of the project ‘Support to the Customs Administration’ intensive activities continued to build a new and modern system of risk management. The following documents were prepared in cooperation with experts: Concept of common risk criteria and standards in accordance with the Customs Law of Montenegro; Concept of priority control areas; Risk Management Framework in the Customs Administration; Customs Administration Risk Management Strategy; Functional Specification for the RMS of the Customs Administration and Process Design in the Risk Management System as part of the business architecture and processes in the Customs Administration.

World Customs Organization (WCO), in the period from 9 until 13 November, 2020, organised an online workshop on risk management, with a focus on risk assessment and selectivity. SEED system functionality is continuously improving, especially for the common risk analysis to enable the information exchange at the regional CEFTA level.

| Performance Indicator | Planned 2014 | 2018 |  | 2019 |  | 2020 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target values | Implemented | Target values | Implemented | Target values | Implemented |  |
| Change in revenue collection compared to the previous year | 15% | 5% | 11,03% | 5% | 5,17% | 5% | -18% |  |
| Harmonisation of customs and excise legislation with the EU Acquis | Completed screening process for Chapter 16 Taxation | Adoption of 3 regulations | Adoption of 3 regulations | Adoption of 3 regulations | Adoption of 3 regulations | Adoption of 3 regulations | Adoption of 1 regulation |  |

In order to increase the number of economic entities that have been issued approvals for simplified procedures, in 2020, the Customs Administration issued 2 approvals based on the accounting entry and 37 approvals based on the trade document or invoice.

When it comes to continuing the development of AEO Programmes, Customs Administration during 2020 gave two approvals for AEO status. In order to harmonise the procedures in the field of development of AEO Programmes in Montenegro with the AEO COMPACT model of the EU, the Risk Matrix of economic entities in electronic form has been implemented. Also, the official Instruction for filling in the Risk Matrix of economic entities was adopted, with the support of GIZ.

Challenge:

The main challenge in the coming period is to continue improving the IT system, that is, the implementation of modernised information systems applied by EU customs services in order to achieve interconnectivity and interoperability while strengthening administrative capacity.

### PUBLIC PROCUREMENT

In order to meet the obligations of the Negotiating Chapter 5 - Public Procurement related to the harmonisation of legislation with relevant regulations and EU standards, activities aimed at adopting a new regulatory framework in public procurement, as well as public-private partnership, included: harmonisation of the text with the European Commission; securing approval from the European Commission, the organisation of public hearings and public consultations, the organisation of consultative meetings with contracting authorities to screen the difficulty in the implementation of the Law on Public Procurement, which all together resulted in the adoption of the new Law on Public Procurement and the Public Private Partnership Law.

The Law on Public Procurement started to be applied on July 7, 2020, with previously implemented professional training and educational process for contracting authorities and bidders in connection with the application of the new legal framework.

Adoption of regulations was preceded by public consultations that the Ministry of Finance and Social Welfare conducted regarding the text of the Draft Law on Public Procurement, revised compared to the version submitted for public consultation in the period February - March 2018. The Ministry of Finance and Social Welfare has revised all suggestions submitted at the 2018 public consultation, prepared tables of concordance with Directive 2014/24/EU, Directive 2014/25/EU, Directive 2007/66/EC and Directive 2009/81/EC and Regulatory Impact Assessment (RIA).

The new regulatory framework, made with a view to achieving compliance with the regulations and standards of the European Union, has resulted in new provisions relating to:

- introduction of electronic public procurement and establishment of the first electronic public procurement system (ESJN) in Montenegro, managed by the Directorate for Public Procurement Policies;

- standardisation of simple procurements and procurements that are implemented in the defense and security sector in accordance with EU standards and recommendations of the European Commission;

- reduction of formalism, business barriers and the cost of preparation of bids - fulfillment of conditions for participation in the public procurement procedure is proven by the Statement of the economic entity;

- the introduction of new principles in the criteria for the evaluation of bids – economically the most advantageous bid  becomes the only criterion for the selection of the most advantageous bid;

- termination of the public procurement contract, amendments to the public procurement contract and execution of the public procurement contract have for the first time been standardised under the public procurement legislation;

- contract management, for the first time to be regulated through the introduction of obligations for contracting authorities to exercise control of execution of the public procurement contract, while achieving greater transparency in the execution of contracts, by publishing execution reports;

- exemptions from the application of the Law are more clearly defined in accordance with EU standards;

- protection of rights as a corrective mechanism, not to be a barrier to investment development due to abuse by bidders, while increasing transparency through the publication of decisions of the appellate body through the electronic public procurement system;

- as concerns supervision, an additional mechanism for monitoring and increasing transparency is envisaged in terms of preparation of the Report for the Government by the Ministry of Finance and Social Welfare - Directorate for Public Procurement Policy, by monitoring public procurement procedures semi-annually as well;

The Law on Public Procurement in the legal sense has changed the way of public procurement implementation, while the additional introduction of the electronic public procurement system has completely changed the concept of public procurement in Montenegro. During 2020, in-house testing of the electronic public procurement system was completed, and after the internal verification of the system, training of employees in the Directorate for Public Procurement Policy began, in order to prepare support for contracting authorities and bidders for more efficient application and use of the new e-system. The ESJN, after intensive preparation during 2020, the trainings that the Directorate for Public Procurement Policy delivered for contracting authorities and bidders, began to be applied on January 1, 2021. The ESJN is the result of the ‘Implementation of Electronic Public Procurement System in Montenegro’ project, financed under the IPA 2014 assistance of the European Union, started on 01 December 2018.

Bylaws accompanying the new Law (20 in total) were prepared and adopted in order for the new Law to come into force. The bylaws are a further step in transposing the standards of EU directives and improving the public procurement system and are available at the following link: http://www.ujn.gov.me/podzakonska-regulativa-zakona-o-javnim-nabavkama-sluzbeni-list-crne- above-br-074-19 /

As regards bylaws, the following is noted in particular:

- With the aim of regulating the manner of procurement in the field of defense and security, for the first time a bylaw was adopted called the Decree on the list of military equipment and products, procedure and manner of conducting public procurement in the field of defense and security (Official Gazette of Montenegro, No. 076/20), which systematically regulates procurement in the field of defense and security in accordance with the Directives of the European Union.

- A new act regulating simple procurements has been adopted, that is, procurements whose value is below the thresholds prescribed by the Law - Rulebook on the manner of conducting simple procurements (Official Gazette of Montenegro, No. 102/20), which repealed more than 650 individual acts of the contracting authorities. In accordance with the same act, simple procurements are regulated in a unique way, they are initiated exclusively by publication through the electronic public procurement system. Contracting authorities are obliged to publish all acts related to this type of procurement, which significantly improved the scope of transparency and participation of economic entities in simple procurements.

- Urgent procurements are conducted through a negotiated procedure without prior publication of a call for tenders in accordance with the Law, which also repealed about 650 individual acts of contracting authorities which regulated emergency procurements in the previous system. In this way, a unique principle and procedure for urgency procurement has been established, in accordance with EU regulations.

After a number of years of harmonisation of the legal framework in the field of concessions and public-private partnership, the Public-Private Partnership Law (Official Gazette of Montenegro, No. 073/19, available on the website www.ujn.gov.me) was adopted. The law reflects the standards of Directive 2014/23/EU of the European Parliament and of the Council of 26 February 2014 on the award of concession contracts. By-laws in this area were adopted and published in the Official Gazette of Montenegro, and are available at the following link: http://www.ujn.gov.me/podzakonska-regulativa-zakona-o-javno-privatnom-partnerstvu-sluzbeni- list-crne-gore-br-73-19 /.

In the reporting period, in order to meet the final criteria from the negotiating Chapter 5 - Public Procurement, the development of the 2021-2025 Strategy for Improving Public Procurement Policy and Public-Private Partnership was started, including the annual Action Plans during the period of implementation of the Strategy, which after the public consultation will represent a new framework of action in the public procurement system.

The goal of adopting the strategic document is to reform the public procurement system in order to achieve sustainability, modernisation, strengthen efficiency, functionality and strength of the foundations on which the public procurement system is based. The first performance indicator, which refers to the harmonisation and completion of the legislative framework in public procurement procedures with EU legislation, has been met by the adoption and implementation of the Law on Public Procurement.

| Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | 2020 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target value | Implemented | Target value | Implemented | Target value | Implemented | Target value | Implemented |  |
| Level of harmonisation and completeness of the procurement framework in line with the EU acquis | Open negotiations in the negotiating chapter 5 | Open negotiations in the negotiating chapter 5 | Open negotiations in the negotiating chapter 5 | Further harmonisation with the package of Directives from 2014 in this area | Open negotiations in the negotiating chapter 5 | Open negotiations in the negotiating chapter 5 | Adoption of a new Law on Public Procurement by implementing the provisions in accordance with the new directives | Implemented planned activities under the Accession Programme - Chapter 5. | The new Law on Public Procurement was adopted, which came into force on July 7, 2020 |  |
| Average number of bidders participating in public tenders | 3.1 bids per tender | 3.2 | 2.66 | 3.48 | 3.14 | 3.58 | 2.01 | 3.8 | 2.27 |  |
| Share of e-procurement of all procurement contracts awarded during the year. | 0% (There is no electronic public procurement system) | 0% (There is no electronic public procurement system) | 0% (There is no electronic public procurement system) | Selection of the most favorable bidder | The project of creating an e-public procurement system has started | 30% | Pilot phase of the e-system | 80% | System established, in-house testing completed and trainings for users of the electronic public procurement system started |  |

Performance Indicator Average number of submitted bids in public procurement procedures for 2019 recorded a downward trend (2.01 bids per public procurement procedure) compared to 2018. It is important to note that the intensity of competition for the previous four years recorded certain variations, mostly due to the small market and the limited number of bidders for certain public procurement items.

Regarding the statistics related to the level of competitiveness for 2020, the Public Procurement Report for 2020 shows that the average number of bids under the public procurement procedure in that year was 2.27. This indicates a growing degree of competition in the system, with increasing transparency in the implementation of procedures in accordance with the new legislation. The successful implementation of the project ‘Implementation of the Electronic Public Procurement System’ created a precondition for the introduction of a complete electronic public procurement system in Montenegro, thus fulfilling the indicator of the share of e-procurement in all procurement contracts awarded in Montenegro. Procurements, including simple procurements, are implemented from the day of introduction of the ESJN exclusively through the system.

The application of the new regulatory framework, as well as the new technical solutions of the electronic system, will achieve a significantly higher degree of transparency and thus lead to a reduction in irregularities of the public procurement system.

Challenge:

- Introduction of continuous training and advanced training intended for public procurement officers and persons participating in public procurement procedures; The practical application of the Law on Public Procurement will be overcome through the planning of thematic trainings for contracting authorities, as well as further work on the systematic improvement of cooperation and education in accordance with the new standards of the Law.

- Comprehensive regulation and monitoring of procurement with value below the thresholds provided by law - simple procurement, will be achieved by standardising single procurement as an exception to the application of the Law on Public Procurement, and by prescribing a single act that will apply to all contracting authorities, the procedure concerning these procurements at the level of the entire system will be unified.

- Further improvement of the Electronic Public Procurement System, which started to be implemented on January 1, 2021, continuous support to system users provided by employees of the Ministry.

Therefore we can conclude that two of the three indicators have been met, while the average number of bidders decreased significantly in 2019 and the target value has not been met. The target value for 2020 is not met, but growth competitiveness index compared to the previous period was recorded (number of bids per procedure in 2020 rose to 2.27).

The above challenges are continuously addressed through the regular activities of the Directorate for Public Procurement Policy, through:

- Trainings that the Directorate for Public Procurement Policy continuously conducts, both on the topic of the regulatory framework and the use of electronic procurement systems;

- Strengthening monitoring through semi-annual reporting, as well as the implementation of monitoring for certain segments of public procurement;

- The electronic public procurement system has been operational since January 1, 2021, new functions are planned to be upgraded, and customer support is provided continuously, on a daily basis by employees in the Directorate (there are about 1,350 active bidders and 645 registered contracting authorities).

### STATE AID REFORM

Under this sub-objective, on February 14, 2018, the Parliament of Montenegro adopted a new Law on State Aid Control. The adoption of the Law fulfilled the condition to open the Chapter Competition, and thus brought a new institutional framework. The activities in the field of state aid, which until then had been the responsibility of the Ministry of Finance and Social Welfare of Montenegro and the Commission for State Aid Control, transferred to the jurisdiction of the Competition Protection Agency. Chapter 8 - Competition was officially opened at the Intergovernmental Conference held on June 30, 2020 in Brussels.

State Aid Control Division in the Competition Protection Agency carried out binding activities under the IPA project ‘Improvement and Strengthening of the Institutional and Legal Framework in the Field of State Aid and Public Procurement, provided by CAP 2014 Programme (started in September 2018). Since there was a change in the project manager, the completion of the project was originally scheduled for Q2 2019, and was postponed to September 2020 when it ended. It is important to note that the project is to be continued in order to spend the unused funds, and implement relevant additional activities.

As part of this project, in order to strengthen administrative capacity and raise public awareness of state aid, a seminar for judges and prosecutors ‘State Aid - The Role of National Courts’ was held in June 2019 (12 judges and 3 prosecutors were trained). Also, during 2019, trainings were held for state aid providers in the Ministry of Education, Science, Culture and Sports, the Employment Agency of Montenegro and the Municipality of Bar (31 state prosecutors were trained). Also, under the ‘Strengthening the Capacity to Accelerate the EU Accession Negotiations’ project, funded by the Norwegian Ministry of Foreign Affairs, and implemented by the United Nations Development Programme (UNDP), on June 6, 2019, an expert seminar was held on ‘Training - Implementation of Rules on State Aid in the EU with an Emphasis on Transport and Infrastructure Aid’ in order to educate state aid providers and employees of the Agency (a total of 10 officials). Within all 5 conducted trainings in the reporting period, 56 employees were trained in 2019, while in 2020 administrative capacity was additionally strengthened through the training of 124 officials, representatives of donors or the private sector, as well as officials of the Agency and members of the Agency Council.

The set Performance Indicator for 2020, which refers to grantors and beneficiaries of state aid, representatives of the private sector and judges who undergo seminars and trainings in the field of state aid, has fully reached and exceeded the target value. Namely, during 2020, trainings were provided for 100 participants, but 124 participants were trained.

In order to strengthen the legal framework, reduce illegal state aid and implement ex-post control a Performance  Indicator was set - The share of staff of the Competition Protection Agency and members of the Agency Council undergoing seminars, training and daily work with employees, and it can be concluded that the target value was achieved (80%).

However, within the Performance indicator that refers to the number of completed procedures initiated ex officio, a negative trend was noted. Namely, in addition to 2 complex examination procedures opened in 2019, at the end of 2020, the Agency initiated 5 new examination procedures. Due to the complexity of the cases, the closing of procedures is planned in the coming period.

The target value for Performance Indicator - Number of documents reviewed and assessed by the Agency is achieved and exceeded in the period analysed. Specifically, the plan was 25, while 41 cases were completed and analysed. Bearing in mind that the increase in the number of analysed applications is accompanied by an increase in the level of awareness of institutions on the obligation to report on state aid, we can say that there has been an increase in public awareness on state aid issues.

| Performance Indicator | Planned 2014 | 2018 |  | 2019 |  | 2020 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target value | Implemented | Target value | Implemented | Target value | Implemented |  |
| The number of state aid grantors and beneficiaries, private sector representatives and judges attending state aid seminars and trainings | 50 | 30 | 0 | 60 | 56 | 100 | 124 |  |
| Share of employees of the Competition Protection Agency and members of the Council who undergo professional seminars in with a view to strengthening the legal framework, reducing the level of illegal state aid and conducting ex-post controls | 30% | 50% | 0% | 70% | 70% | 80% | 80% |  |
| Number of completed ex-officio cases | 5 | Up to 2 | 0 In 2018, no ex-officio case was initiated | 2 | (2 ex-officio cases opened, closure expected in the coming period) | 1 | (5 ex- officio cases opened , closure expected in the coming period ) |  |
| Number of documents reviewed and assessed by the Agency | 11 | Up to 20 | 22 | 23 | 35 | 25 | 41 |  |

In addition, the institutional framework was strengthened as well as the national legal system related to the implementation of the rules and procedures of state aid, through draft bylaws issued by the Ministry of Finance and Social Welfare of Montenegro:

- Communication from the Commission (EU) on the application of State aid rules from 1 August 2013 to support measures in favor of banks in the context of the financial crisis (‘Banking Communication’) ( 2013/C 216/01);

- Commission Notice (EU) on the notion of State aid as referred to in Article 107 (1) of the Treaty on the Functioning of the European Union (2016/C 262/01);

- Temporary framework for state aid measures to support the economy in the current COVID-19 outbreak (2020/C 1863).

- Within 2020, through technical support for the software ‘Information system of state aid in Montenegro’, a register of de minimis aid and COVID-19 aid was established. In future period, production of ‘regular’ register of state aid was planned.

### PUBLIC DEBT MANAGEMENT, DEBT ANALYSIS, CASH MANAGEMENT AND FOREIGN RELATIONS DEPARTMENT REFORM

Based on the recommendations of the expert teams of the International Monetary Fund and the World Bank, the Ministry of Finance and Social Welfare has started the reform of the Public Debt Management, Debt Analysis, Cash Management and Foreign Relations Department.

The Department is divided into two directorates: the Directorate for Debt Management, Debt Analysis and Foreign Relations (front office) and the Directorate for Cash Management, Debt Servicing, Government and Public Debt Records (back office). This reorganisation was formalised under the Rulebook on Internal Organisation and Systematisation of the Ministry of Finance, which was adopted by the Government of Montenegro in November 2017.

This organisational change has led to a gradual separation of business processes in a way that reflects the standards of functioning of the front office and back office in the financial sector. The separation of business processes is still ongoing, along with the training of new staff. Namely, both Directorates face a significant outflow of staff, which requires continuous repetition of on-the-job training, both by employees in the Directorates and by external experts.

Accordingly, employees in the front office during the period 2016-2020 attended trainings related to the development of the Medium-Term Debt Management Strategy, training for the preparation and implementation of bond issues on the international market, as well as training related to financial derivatives and hedging. These trainings were conducted within the regular cooperation between Montenegro and the IMF, as well as using the services of independent experts (2019). In 2020, no training was conducted by external experts due to the COVID-19 pandemic, but training was provided to new employees by colleagues who work in the Directorate.

In 2018, Montenegro adopted the 2018-2020 Debt Management Strategy, which, as a guideline, defined the equalisation of debt repayment through the improvement of indicators of average debt maturity. In addition to the above, one of the guidelines for debt management is the reduction of borrowing costs, which is reflected in the indicator of the average weighted interest rate. In addition to the above mentioned, one of the guidelines is the development of the domestic market of government securities, that is, bond market, but also reducing currency risk. In 2019, the development of the updated Public Debt Management Strategy has been planned, however, certain borrowing transactions were carried out before the Updated Strategy was prepared, and guidelines for activities that have already been implemented were not retroactively published. As for 2020, no update of the Strategy was carried out due to the COVID-19 crisis, which required the urgent implementation of borrowing procedures. What is important to emphasise is the fact that borrowing in 2019, as well as in 2020, was carried out in accordance with the initial strategy in terms of borrowing based on the principle of the longest possible maturity and the lowest possible interest rates. This extended the average debt maturity from 5.2 years at the end of 2018 to 5.9 years at the end of 2019, and further to 6.9 years, at the end of 2020. The structure of government debt at the end of 2020 has a real weighted average interest rate of 2.7%, which means that the cost of borrowing decreased by 0.1% compared to the end of 2019, and 0.3% compared to 2018. Debt trends in the period 2016-2020 can be displayed as follows:

| Year | GDP | Domestic debt |  | Foreign debt |  | Government debt |  | Public debt |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | In € mill. | %GDP | In € mill. | %GDP | In € mill. | %GDP | In € mill. | %GDP |
| 2016 | 3,954.0 | 400.2 | 10.1% | 2,002.8 | 50.7% | 2,403.0 | 60.8% | 2,546.1 | 64.4% |
| 2017 | 4,299.0 | 413.9 | 9.6% | 2,214.0 | 51.5% | 2,627.9 | 61.1% | 2,758.8 | 64.2% |
| 2018 | 4,663.0 | 392.98 | 8.4% | 2,760.0 | 59.2% | 3,153.0 | 67.6% | 3,268.2 | 70.1% |
| 2019 | 4,951.0 | 579.96 | 11.7% | 3,128.7 | 63.2% | 3,708.7 | 74.9% | 3,789.3 | 76.5% |
| 2020 | 4,193.2 | 495.56 | 11.8% | 3,835.3 | 91.5% | 4,330.8 | 103.3% | 4,409.0 | 105.15% |

In addition, there was continuous work on improving the efficiency in public debt management by unifying the records of public debt through a single database implementation of the new SAP software solution for public debt management. However, existing SAP module does not meet all the needs of debt management, especially from the point of reporting, so the Directorate of State Treasury initiated the development of software through the IPA project ‘Improvement of the budgeting system, multi-annual budget framework, and public internal financial control system.’ Development of the new software is expected to begin in the coming period.

| Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | 2020 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target value | Implemented | Target value | Implemented | Target value | Implemented | Target value | Implemented |  |
| Public debt servicing costs as a share of GDP | 2.20% | 2.50% | 2.3 % | 1.9 % | 2.1% | 2.0% | 2.2% | 2.3 | 2.64 |  |
| The difference between the planned and achieved level of public debt | 1.5% | 1.5% | Public debt is 3.2% lower than planned | 1.5% | 3.07% Growth | 1.5% | 16.6% Growth | 1.5 | 16% |  |

## OBJECTIVE 3. PUBLIC INTERNAL FINANCIAL CONTROL DEVELOPMENT

The Ministry of Finance and Social Welfare has implemented all activities defined under the Action Plan for the implementation of the 2016-2020 Public Finance Management Reform Programme. The most significant progress has been made in the area of ​​internal audit in terms of strengthening the capacity of internal auditors through training and certification.

The percentage of certified internal auditors each year is above the target values ​​by year. In accordance with the Rulebook on the training programme and the manner of taking the exam for obtaining the certificate of public sector internal auditor, in February 2020, the training programme for the public sector internal auditors for 25 candidates began. Despite the problems caused by the COVID outbreak by the end of 2020, lectures were held for all four subjects and knowledge tests for three subjects, while the last testing was postponed until the end of January 2021 due to epidemiological measures.

In addition, in order to maintain and further develop the competencies and skills of appointed internal auditors, the Programme of Continuing Professional Development of Internal Auditors in the Public Sector is adopted each year, and in cooperation with the Human Resources Administration, 21 trainings were held in 2021 on the following topics: New methodology of internal audit work in the public sector; Update of internal audit plans caused by the COVID virus pandemic and practical instructions; Introduction to internal audit and application of methodology for internal auditors; Strategic internal audit planning and development of strategic plans in accordance with the new methodology of internal audit work; Development of an annual internal audit plan and practical application of the Standard 2100 group; and Risk management and the role of the internal auditor.

In addition to these activities, through the implementation of the IPA ‘Improving budgeting system, multiyear BFP, the public internal financial control system’ project, in cooperation with project experts, the following activities were conducted:

- pilot management audits in four pilot institutions involving 20 internal auditors from central and local level;

- two online workshops for internal auditors on the topic ‘Performing periodic self-assessment’.

Although the indicators related to the delegation of responsibilities and authorities do not indicate progress, the Ministry of Finance and Social Welfare undertook activities during the reporting period to strengthen managerial accountability, as a key component for good governance in public administration. During the reporting period, the Analysis of Obstacles to Managerial Accountability was prepared, which pointed out the importance of delegating authority to successfully achieve goals and strengthen accountability in the public sector, as well as the obstacles to the implementation of this concept. In 2020, the Government of Montenegro adopted the Decree on the transfer of jobs and tasks of financial management and internal controls in the public sector (‘Official Gazette of Montenegro’, No. 079/20 of 02 August 2020) which prescribes the tasks that the head of the entity may transfer to the heads of organisational units or other employees in bodies, institutions and legal entities. In order to support the bodies in managing funds, the Ministry of Finance and Social Welfare has prepared a Methodology for the transfer of jobs and tasks of financial management and internal controls in the public sector, which is the starting point for establishing a system of accountability in the public sector. In order to better implement the legislative framework trainings were held for managers and employees at the central and local level on the topic: ‘Managerial accountability’, in cooperation with the Human Resources Administration. Also, under the IPA ‘Improvement of the budgeting system, multi-annual BFP and the public financial internal control system’ project, activities are planned to improve managerial accountability in the public sector, namely: the Conference on the topic Managerial Accountability for Heads of Institutions, as well as technical support to pilot institutions in devolution. Given the situation caused by the COVID - 19, most activities have been postponed to 2021.

In order to improve implementation of risk management, the Ministry of Finance and Social Welfare is continuously improving methodological guidelines and delivering trainings for employees at central and local level. During 2019 and 2020, through the implementation of the IPA project ‘Improvement of budgeting system, multi-year BFP and the public internal financial control system’, the quality of the process in the pilot institutions was assessed and organised trainings on the theme Risk Management, and then provided technical support in establishing the risk management system.

In order to provide more comprehensive annual reporting on management and internal controls, a system for detecting and acting on notifications of suspected irregularities and fraud, risk management, self-assessment of internal controls and managerial accountability, the trainings for managers and employees were held in cooperation with the Human Resources Administration at central and local level (14 in 2020), which has resulted in more and more institutions submitting annual reports on management and internal controls. As part of the mentioned IPA project, a step forward was made and an electronic questionnaire was prepared in order to facilitate the processing of collected data and the best possible preparation of the Consolidated Report on Management and Internal Control, which is submitted to the Government for adoption every year.

Strengthening the capacity of the Directorate for Central Harmonisation to assess the quality of management and internal controls has been carried out continuously during the previous period. In the reporting period, the methodology of work was improved and developed reference models for the COSO components, as well as aid in the assessment of the quality of management and internal control. The review of the quality of internal audit work during 2020 was not conducted by direct verification, due to the situation caused by COVID. The Directorate for Central Harmonisation will implement this activity by reviewing the final audit reports and audit documentation and performing an analysis and assessment of the level of understanding and level of application of the methodology by internal auditors.

| Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | 2020 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target value | Implemented | Target value | Implemented | Target value | Implemented | Target value | Implemented |  |
| The percentage of ministries that formally delegated decision-making responsibilities and authorities to the line managers which enhances managerial accountability | 6.25% | 30% | 11.11% | 16% | 18% | 50% | 12% | 90% | 8.3% |  |
| Percentage of the budget users on central and local level submitting annual FMC reports | 69% | 75% | 80% | 80% | 90% | 90% | 94% | 95% | 93% |  |
| Average number of internal auditors per unit | 1.76 | 2 | ≈2 | 2.3 | 2.21 | 2.5 | 2.1 | 2.7 | 2.1 |  |
| Percentage of appointed certified internal auditors | 60% | 75% | 90.90% | 80% | 94.05% | 85% | 100.00% | 90% | 93.1% |  |
| Percentage of appointed certified internal auditors who undergo CPD | 0% | 70% | 72.86% | 75% | 83.64% | 80% | 81.36% | 90% | 80.0% |  |
| Percentage of implemented and partially implemented recommendations given by internal auditors in the previous year that were implemented by the end of the current year | 48% | 55% | 73.5% | 60% | 79.16% | 65% | 84.11% | 70% | 79.4% |  |

Challenge:

In the forthcoming period, special attention should be paid to the establishment of a system of delegation of responsibilities as well as further strengthening of the capacity of internal auditors.

## OBJECTIVE 4 TRANSPARENT FINANCIAL REPORTING AND ACCOUNTING

The Strategy for the transition of the public sector to accrual accounting adopted in 2015 recognised the need for the training of public sector accountants in accordance with the principles of accrual accounting, the drafting of regulations in the field of accrual accounting and harmonisation of accounting information system in accordance with new accounting policies. In this period, the importance of improving human resources in this area was recognised as one of the key goals of the reform. In this regard, in 2016, a project for the training of public sector accountants was launched, which was organised in cooperation with the Center for Excellence in Finance from Ljubljana, according to the methodology and concept developed by the CIPFA Institute from Great Britain.

The project was completed in 2020, which, in addition to three generations and a total of 120 trained accountants from budget spending units and local self-government units, included other activities related to the education of accountants in the public sector. In this regard, in the previous period, an International Conference on Accrual Accounting in the Public Sector and a series of workshops for accountants were organised. In 2020, a workshop on ‘International Accounting Standards for the Public Sector’ was held, which was attended by renowned international and domestic experts in the field of accounting. In cooperation with the Center for Excellence in Finance and the Human Resources Administration, a final report on the project was prepared and submitted to the institutions involved in the project implementation.

As part of risk management, the risk of outflow of the staff of trained accountants has been identified. In this regard, under the contracts concluded with each of the participants, the Ministry of Finance and Social Welfare obliged the participants to stay in the public sector for at least three years after obtaining the certificate, which reduced the risk of outflow of trained and professional staff. Also, one of the risks was the continuation of localised training. In this regard, the Ministry of Finance and Social Welfare in 2015 established a working group for the localisation of the project, which is in charge to prepare draft acts that will formulate competences in the process of localisation. This risk has been reduced by preparing a bylaw defining the training programme and the manner of taking examinations for certification of public sector accountant, as well as an appropriate manual that fully defines the roles and activities of trainers of public sector accountants, so that trainings at the local level could function smoothly. Trainings of accountants were carried by the Human Resources Administration.

Action Plan for implementation of the Strategy for the transition of the public sector to accrual accounting, recognised as one of the key activities the drafting of the Public Sector Accounting Law, which will cover all the basic accounting principles in one place and will first introduce the principles of accrual accounting, public sector accountant, define the conditions for acquiring the title and introduce the concept of public sector register.

As part of the new accounting policies in 2019, the Public Sector Accounting Law was adopted, which stipulates the transition from cash-based to accrual accounting, with deferred application. The Law will contribute to achieving the goal of ‘Transparent Financial Reporting and Accounting’. The Law recognised a number of bylaws which need to be drafted to enable the application of the Law.

During 2020, five rulebooks and one manual were prepared. In this regard, the following drafts were prepared: Rulebook on Chart of Accounts, Rulebook on Accounting Methodology, Rulebook on Central and Municipal Public Sector Registry, Rulebook on Financial Reporting, Rulebook on Training Programme and Manner of Taking Examinations for Certification of Public Sector Accountants, Manual on Training and Certification Programme for Public Sector Accountants.

In the following period, work is planned on upgrading the accounting information system, as well as work on manuals for the application of accounting methodology, which will give more detailed instructions to users of the methodology.

| Performance Indicator | Planned 2014 | 2017 |  | 2018 |  | 2019 |  | 2020 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target value | Implemented | Target value | Implemented | Target value | Implemented | Target value | Implemented |  |
| Public sector accountants trained for accrual accounting (based on the CIPFA methodology) | 0 | 40 | 40 in 2016. | 40 | 80 | 20 | 40 | 100 | 120 |  |
| Property register and double entry book-keeping system for the property implemented | Beginning of the development of the property register | Property data entered into the register | 0 | Property data entered into the register | 0 | Training (direct budget users) and migration of funds to ARS and commissioning of records | 9 grupa 100 0 | Property register and double entry book-keeping system for the property implemented | Public authorities (99) Public services (322) DKP (39) Local government (24) Municipal authorities (196) 0 migrations |  |

CADASTRE AND STATE PROPERTY ADMINISTRATION

The establishment of the single record of state property system is not only a legal obligation but also an obligation to the public, bearing in mind the importance of this topic. In this regard, a number of activities were undertaken during the reporting period. The system of records of state property means independent data entry by public and municipal bodies and companies through a special web application called ARS (Asset Registry System). Therefore, the Cadastre and State Property Administration (formerly the Property Administration) is implementing the project ‘Expansion of the SAP system - implementation of SAP FI - AA module and external applications for state property records’ since 2015, which provides a complete insight into each movable and immovable property of the state, as well as the possibility of reviewing the total property and reporting on the same. The first phase of the project includes training of direct budget users and migration of their data. The second phase includes training of indirect budget users and migration of their data, while the third phase refers to local governments (municipalities).

During 2019, testing of ARS functions was performed, which determined that the adopted Conceptual Design from 2014 does not correspond to all functions supported by the ARS application, which led to additional needs for improvement. The project ‘Expansion of the SAP system - Implementation of SAP FI - AA modules and external applications for records of state property’ solved the problem when logging in ARS, that is, removed the existing certificates that hindered the operation of the application. In this context, administrative rights and authorisations were given to an employee in the Department for Keeping the State Property Register and Movable Property Records, as technical support to the ARS application. Also, for a test version of ARS application, accounts for key users were created.

In terms of complete insight into all movable and immovable property in the country during 2019, a training plan was developed for future users of ARS - an external application for a single record of state property. Therefore, in the period September-December 2019, the Property Directorate conducted a series of trainings for direct budget users (first-level spending units, independent spending units) in order to properly use ARS, namely: Training for the use of ARS application and Trainings for filling in the Excel table, the so-called migration document (9 groups, 99 public authorities, 200 civil servants). Following training, data tables on the assets provided by the authorities were prepared for migration to a test version of the software for records of movable and immovable property (ARS - Asset Registry System), while the rest needs to be processed by the bodies. Since the tables were not properly filled in, it took a long time to correct them. During the migration of the tables to the test version of the ARS, problems in the operation of the software were noticed and the intervention of the implementer was required. The authors have tested function of web application ARS (Asset Registry System), which currently does not respond to all the necessary functions, which led to additional costs for the upgrade and development of the application. Direct budget users of ARS application had been obliged by March 2020 to deliver data to the PD on the state of the property from the latest census on 31 December 2019 and to record that information in the test version of the ARS application only once, and thereafter users will enter data on the new property themselves.

During 2020, 99 public bodies submitted Excel migration tables on the status of property, which they were obliged to submit upon completion of the training. Also, during 2020, trainings were organised for the use of the ARS application and for filling in Excel migration tables, for public services, local self-government and municipal bodies.

Trainings for indirect budget users (public services, local self-government and municipal branches) in 2020 were conducted in full (9 trainings, with about 200 employees were trained), and accounts for the use of the ARS application were opened. Public authorities, 99 of them, have submitted tables, which have been tested, filtered and ready for migration to the ARS application.

Also, during 2020, trainings were organised for the use of the ARS application and for filling in Excel migration tables for public services, local self-government and municipal bodies. Due to the situation caused by COVID – 19, trainings were suspended. Cadastre and State Property Administration, that is, the Department for Keeping the State Property Register and Movable Property Records, solved the problem of interrupted trainings by recording a video presentation of trainings for the ARS (Asset Registry System) web application. Video training link is delivered to all future users, to conduct the training in full in order to overcome the obstacles that have arisen because of the situation with COVID-19. Trainings for indirect budget users that have started in June 2020 were suspended, due to recommendations of the National Coordination Body and were implemented via the link.

Pursuant to Article 56 of the Decree on the Organisation and Manner of Work of the Public Administration (‘Official Gazette of Montenegro’, No. 87/18 and 02/19), the Minister of Finance issued a Decision on the Establishment of a Working Team for Drafting a Proposal Decree on Amendments to the Decree on Manner of Keeping Records of Movable and Immovable State Property, that is, to legally regulate the one-time submission of data on already acquired assets in an Excel file adapted for the ARS application. Due to the situation caused by COVID - 19, there was no amendment to the Decree on the Manner of Keeping Records of Movable and Immovable State Property.

Part of this goal envisages the formation of a single record of state property. After the introduction of the application of the single register of state property, each user will be able to enter each new property procured in the single register. In this way, the Property Administration will have a complete insight into all movable and immovable property in the country, as well as the possibility to review the total property and report on the same. The project of a single record of state property is implemented with the help of web application ARS (Asset Registry System) through which fixed assets are recorded in the module of fixed assets in the SAP system (FI-AA). It is necessary to carry out a series of actions in order for the records to be put into operation.

After the completed trainings, all user tables will be collected and migrated for production, followed by the final release of the ARS application of the property register into operation.

It is important to note that 2020 was planned to be a test year for the Property Directorate in cooperation with users to upgrade and implement the fields in the ARS application, that is, the project will be fully implemented, while the planned transition from the test environment to production will be in March 2021. In this regard, due to the situation caused by COVID -19 the date of completion of the project cannot be already determined.

When it comes to the indicator that measures the implementation of the property register and double entry accounting, we can conclude that it has been partly achieved, bearing in mind that it is necessary to make additional efforts to achieve compliance. Key users who were responsible to submit Excel migration tables, because of the situation caused by COVID - 19 were not able to supply these tables.

Challenge:

The implementation of data on state property in a single ARS database depends entirely on the bodies that will be in the records, so we expect their full cooperation and participation with proposals and suggestions.

## OBJECTIVE 5. STRENGTHENING EXTERNAL AUDIT CAPACITIES

### STATE AUDIT INSTITUTION

The strategic objective for the field of external audit ‘Strengthening external audit capacities’ has two sub-objectives, which relate to the State Audit Institution with a focus on ‘Improving the audit process, build auditor capacity and increase transparency of public spending’ and the Audit Authority ‘Strengthening capacity and improving audit procedure’. The implementation of this strategic objective is supported through the IPA project ‘Development and capacity building of the State Audit Institution and the Audit Authority of Montenegro’.

Amendments to the original 2016-2020 Public Finance Management Reform Programme concerning the State Audit Institution were conditioned by the need for compliance with the strategic goals and activities of the 2018-2022 SAI Strategic Development Plan, by concretisation of indicators and adaptation to practice, as well as the fact that certain indicators were more of activities than indicators.

State Audit Institution in 2019 started the implementation of a large number of activities foreseen in the Programme, which were implemented by the end of 2020, and in this connection, there has been progress in meeting the objective of the State Audit Institution ‘Improve auditing process, build auditor capacities and increase transparency of public spending’.

A positive trend was achieved in 2020 with two performance indicators, while the realisation of the indicator ‘Level of realisation of the Annual SAI Audit Plan’ was largely conditioned by the circumstances and the development of the epidemiological situation caused by the COVID-19 virus.

| Performance indicator name | Planned 2014 | 2019 |  | 2020 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Target value | Implemented | Target value | Implemented |  |
| Level of realisation of SAI’s Annual Audit Plan | 60% | 86% | 88,68% | 90% | 72,50% |  |
| Application of ISSAI-compliant methodology for financial, regularity and performance audits | 2015 – Methodological Instruction for financial and regularity audits compliant with ISSAI 200 and ISSAI 400, Methodological Instruction for performance audits compliant with ISSAI 300 and Guidelines for Audit Quality Control | n / a The activities listed in the action plan start from Q1 2019 | Manual for Performance Audits compliant with ISSAI 4th level adopted in December 2019. | Manual for Financial and Regularity Audits compliant with ISSAI 4th level adopted and applied Manual for Performance Audits compliant with ISSAI 4th level upgraded and applied. Guide for Monitoring the Implementation of Recommendations from Audit Reports adopted and applied | Manual for Financial and Regularity Audits compliant with ISSAI 4th level adopted in July 2020 and applied. Manual for Performance Audits compliant with ISSAI 4th level adopted in December 2019 and applied Guide for Monitoring the Implementation of Recommendations from Audit Reports adopted in June 2020 and applied |  |
| No of trainings/seminars/ workshops for auditors delivered | Minimum 3 trainings delivered | 7 additional trainings delivered | 13 Trainings (3 internally organised and 10 regionally and internationally) | Additional 10 trainings delivered | 32 trainings (22 at the domestic level and 10 at the regional and international level) |  |

In order to apply the audit methodology for performing financial audit, regularity audit and performance audit in accordance with ISSAI standards, SAI has developed a new ‘Instruction for performance audits‘, while in 2020 the Manual for Financial and Regularity Audits and Guidelines for the development, monitoring and control of the implementation of SAI recommendations were developed and began to be applied.

By adopting ‘Guidelines for proposing and selecting financial and regularity audits for the SAI Annual Audit Plan’ the programming and annual audit planning process has been improved. In this regard, Instructions for the preparation of the Annual Audit Plan for 2021 were adopted, which provided planning at various levels of the SAI and on the basis of assessed risks and clearly defined criteria. In addition, the SAI Medium Term Plan for Performance Audits for the period 2020-2024 was adopted, which focuses on revisions of the sustainable development goals of the 2030 United Nations Sustainable Development Agenda.

The increase in the number of conducted trainings by 22 compared to the plan resulted in the improvement of knowledge and skills of audit staff in the field of accounting and auditing in the public sector. In addition, manuals for taking the exam for the title of state auditor have been innovated. The implementation of the Guidelines for the use of the advanced version of IDEA software, which were adopted in the reporting period, will further improve the institutional capacity in the field of usage of the software audit tool, as well as more efficient IT management.

In an effort to strengthen transparency and better understanding of its work and role in the public, the SAI has adopted the Communication Strategy of the State Audit Institution for the period 2020-2024 and the Action Plan for its implementation. Increasing the efficiency of work by improving human resources management, developing human resources and providing staff with high ethical values, knowledge, skills and integrity will be achieved through the implementation of the 2021 – 2025 Human Resources Management Strategy of the State Audit Institution, which was adopted in 2020.

Challenge:

The challenge related to the obligation to perform annual audits of financial statements of political entities with an annual income of over € 10,000.00 has been overcome through the adopted amendments to the Law on Financing of Political Entities and Election Campaigns from January 2020. In the forthcoming period, insufficient spatial capacities that affect the dynamics of hiring new staff are still considered a challenge. In order to overcome the challenges, the Terms of Reference were prepared for the architectural competition for the conceptual design of the building of the State Audit Institution with defined needs, in accordance with the law.

### AUDIT AUTHORITY

The Public Finance Management Reform Programme envisages the implementation of 5 activities of the Audit Authority. The implementation of the activities envisaged by the PFM began with the signing of the service agreement ‘Development and strengthening of the capacity of the State Audit Institution and the Audit Authority of Montenegro’ worth € 648,500.00, with a planned duration of 18 months. After the signing of the Agreement, the technical conditions (office and administrative staff) necessary for the implementation of the project were established, in order to more efficiently implement the activities during 2019. In addition, due to the COVID-19 outbreak, certain activities were postponed and the project was extended for an additional 4 months, more precisely until September 19, 2020. In the reporting period (2016-2020), the Audit Authority made full use of available funds and resources and fully implemented all project activities, which aim to contribute to the strengthening of the system of internal controls in the use of EU funds. The target and achieved values ​​of the indicators are shown below.

The target value for the performance indicator No of trainings/seminars/ workshops for auditors delivered is completely achieved. During 2019, an average of 11 trainings per auditor were organised, while in 2020, 9 trainings per auditor were organised, which exceeds the planned values ​​shown by the indicators. Most of the trainings were organised under the project ‘Development and strengthening of the capacity of the State Audit Institution and the Audit Authority of Montenegro’.

The target value for the performance indicator Degree of audit methodology improvement – Audit Manual, is completely achieved. This was achieved through 3 expert missions to improve the manual for different types of audits in accordance with international auditing standards and a Manual for areas 1, 2, 3, 5 was developed as well as IPARD Area 4 Manual, which were adopted and applied from 19 April 2019.

The target value for the performance indicator Share of audits conducting by using the audit software tool is completely achieved. The auditors of the Audit Authority used the audit software IDEA for 1/3 of the audits performed in 2019 (33.33%) and 2/3 of the audits performed in 2020 (66.66%). Two software licenses were purchased through the IPA project, while one was funded by the Audit Authority. Instructions for using the software have been prepared.

The target value for the performance indicator Progress in implementing the Strategic and Action Plan is partly achieved. The Strategic Plan of the Audit Authority and the Action Plan for its implementation were adopted on December 29, 2020 (the activity was planned for 2019, and was postponed for 2020). It is important to note that the Strategic Plan refers to the period 2021-2025, in which period the implementation of the Action Plan is expected. Given the nature of the set of performance indicators and the period covered by the strategic plan (2021-2025), by the adoption of strategic documents, the target value may be considered achieved.

The target value for the performance indicator - Level of implementing standards to ensure audit quality, is completely achieved. The manual for quality control and quality assurance with accompanying annexes was prepared and adopted in July 2020. When it comes to 2019 and 2020, 75% of audits performed were covered by quality control. The manual for quality control and quality assurance with the accompanying annexes was prepared and adopted in June 2020, when the testing of the same began in practice.

| Performance Indicator | PV 2014 | 2019 |  | 2020 |  | Trend |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Target value | Implemented | Target value | Implemented |  |
| Number of trainings / seminars / workshops per auditor | 3 trainings delivered | Minimum 9 trainings per auditor delivered | 11 trainings per auditor were organised | Organised a minimum of 7 audit trainings per auditor | 9 trainings per auditor were organised |  |
| Degree of implementation of the Strategic and Action Plan of the institution | n/a | Strategic plan adopted; Action plan adopted. | Activities have been postponed to 2020. | 20% of planned activities implemented | The Strategic Plan and the Action Plan for its implementation were adopted on December 29, 2020 and refer to the period 2021-2025. |  |
| Improving the audit manual | An audit manual has been prepared | 50% of deficiencies eliminated | 90% of deficiencies eliminated | 100% of deficiencies eliminated | 100% of deficiencies eliminated |  |
| Share of audits conducted by using the audit software tool | n/a | 20% | 33.33% audits conducted using software | 50% audits conducted using software | 66.66% audits conducted using software |  |
| Level of implementing standards to ensure audit quality | n/a | 30% | 75% of audits covered by quality control | 50% | 75% of audits covered by quality control |  |

Within the Audit Authority, a total of 32 vacancies were systematised, of which 21 vacancies were currently filled for an indefinite period, and in the following period the need for additional employment and filling vacancies was expressed.

Challenge:

Significant audit activities are forthcoming in the coming period and an increased workload is expected regarding the audits of the IPA II program, their closure and the beginning of the implementation of approved projects within the new financial perspective (IPA III 2021-2027). In order to fulfill all obligations in the coming period, it is necessary to fill the audit staff in vacant systematised positions.

In order to prepare for IPA III, and later for EU membership, the Law on Audit of EU Funds should provide the necessary assurances of compliance with auditing standards and new legal requirements, which requires certain amendments that are subject to changes in AA legislation.

AA's visibility measures are currently largely limited to the Audit Authority's website www.revizorskotijelo.me. and it is desirable to work on strengthening the visibility of AA work.

# III TABLE FOR REPORTING ON IMPLEMENTATION OF AP FOR THE LAST YEAR OF IMPLEMENTATION OF THE STRATEGIC DOCUMENT

| Strategic objective 1._ A) Sustainable fiscal framework, public expenditure planning and budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operational goal 4.1._ A.1. Medium-term budget framework (MTBF), including fiscal strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicators 1 | Share of new medium-term sector strategies in the total number of strategies that include estimates of implementation costs, including potential donor funding | PV (2014): 60% | TV 2017: 80% | Actual value in 2017: 70% | TV 2018: 85% | Actual value in 2018: 75% | TV 2019: 90% | Actual value in 2019: 85% | TV 2020: 100% | Actual value in 2020 100% |  |  |
|  | Performance indicator 2 | Average deviation between MTBF budget ceilings and actual annual budget expenditure limits | PV (2014): 9% | TV 2017: 7% | Actual value in 2017: 6% | TV 2018: 6% | Actual value in 2018: 0.87% | TV 2019: 5% | Actual value in 2019: 0.11% | TV 2020: 5% | Actual value in 2020 2.13% |  |  |
|  | Performance indicator 3 | Number of staff trained for top-down medium-term budget planning | PV (2014): 0 | TV 2017: 52 | Actual value in 2017: 0 | TV 2018: 35 | Actual value in 2018: 0 | TV 2019: 52 | Actual value in 2019: 0.11% | TV 2020: 72 | Actual value in 2020 100 |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator/objective | Technical assistance required (IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
|  | SUBSYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| *2) |  | A.1.3 Training of staff with a view of improving medium-term expenditures planning (target group: technical staff) | Training | Training materials prepared. A number of employees have been trained. | IPA II | MoF - BD | 2 (A.1.5) | 2018 | 2019 | 2020 | 135,000.00 | IPA II Budget | Training of budget analysts in the Ministry of Finance was held on April 7 and 8, 2021. On-line training for budget users planned for June 1 and 3, 2021. |
| *2) |  | A.1.4 Training for multi-year budget planning with a view of better alignment of the budget programme goals with Government policies (target group: managerial staff) | Training | Training materials prepared. A number of employees have been trained. | IPA II | MoF - BD | 2 (A.1.5) | 2018 | 2019 | 2020 | 50,000.00 | IPA II Budget | The training is planned for Q3 2021. Another option is currently being considered to make a presentation on the program budget reform that will be submitted to the leadership in the Government. |
|  |  | A.1.8 Improvement of planning and presentation of multiannual commitments in the budget | Legal act (new / revised) | Presentation of multi - year commitments in budget documentation. A review of multi-year commitments in the budget law. | IPA II | MoF - BD | 2 | Q4 2017 | 2019 | 2020 | 30,000.00 | IPA II Budget | The overview of multi-annual commitments is included in the form for budget documentation, it is provided for by a circular / instruction on budget preparation. Project recommendations related to the amendment of the Law on Budget and Fiscal Responsibility have been submitted to the MoF, and the dynamics of implementation depends on the MoF (planned for the second half of 2021) |
| *6) |  | A.1.9 Develop and upgrade current budget planning IT to enable medium-term planning | Computerisation | Specifications for the development and upgrade of the budget planning system prepared. Individual upgrades / improvements / modules developed. | IPA II | MoF - BD | 1 (A.2.9) (A.3.9) | 2018 | 2020 | 2019/2021 | 300,000.00 | IPA II) Budget | Functionality and / proposal related to medium-term planning was submitted to the IT project, on the framework of which in 2019 the first phase of software development in the part of electronic filling of budget requirements was realised Part will be implemented in 2020 and final changes / improvements in 2021. |
| *7) |  | A1.10 Upgrade the Budget Circular in the section on planning multiannual commitments | Guidelines Manual | Budget circular prepared (every year) | IPA II | MoF-BD | 1 (A.2.7) | Q2 2017 | 2019 | 2020 | 15,000.00 | IPA II budget | Fully implemented |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 570,000.00 | 120.000,00 |  |
| Strageic objective 1._A) Sustainable fiscal framework, public expenditures planning and budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational objective 4.1.2._ A.2. Annual Budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 4 | Share of first level budget organisations that provide comprehensive information with their annual budget requests | PV (2014): 40% | TV 2017: 75% | Actual value in 2017: 70% | TV 2018: 80% | Actual value in 2018: 80% | TV 2019:90% | Actual value in 2019: 90% | TV 2020: 100% | Actual value in 2020. 100% |  |  |
|  | Performance indicator 5 | Level of performance information included in budget planning | PV (2014): Programme headings are defined by all budget organisations | TV 2017: Programme structure is developed in all budget organisations | Actual value in 2017: Programme headings are defined by all budget organisations | TV 2018: Programme structure is developed in all budget organisations | Actual value in 2018. Programme structure is developed in all budget organisations in terms of Programme headings defined | TV 2019: Level 1 upgrade with defining a set of Performance indicators for pilot projects | Actual value in 2019. Programme headings are defined by all budget organisations | TV 2020: Created a set of indicators for all programs to monitor the success of achieving goals | Actual value in 2020. Defined headings of main programs, programs and subprograms |  |  |
|  | Performance indicator 6 | The number of staff trained for planning and monitoring expenditures in line with programme budgeting principles | PV (2014): 0 | TV 2017: 20 | Actual value in 2017: 0 | TV 2018: 35 | Actual value in 2018: 0 | TV 2019: 70 | Actual value in 2019: 17 | TV 2020: 130 | Actual value in 2020. 100 |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required (IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| *2) |  | A2.1 Review current budgeting legislation and procedures and based on the findings and the best practices and experiences in this field, amend national legislation with a view of putting in place the assumptions for the full implementation of programme budgeting | Legal act (new / revised) | New / updated Decision on the manner and content of the program budget (in 2016 and if necessary in 2017 and subsequent years). Another (new) legal act is possible if necessary. | IPA II | MoF-BD | 1 | Q2 2017 | 2018 | 2019/2020 | 20,000.00 | The activity was realised within the existing capacities, while possible improvement in the next period will be realised from IPA II | Fully implemented |
|  |  | A2.5 Define missions, goals and descriptions of programmes or sub-programmes | Legal act (new / revised) | Missions, objectives and program / sub-program descriptions defined (and published in the budget documentation) for the 2017 budget and required updates for the 2018 budget. | IPA II | MoF-BD | 1 (A.2.4) (A.2.6) | 2018 | 2019 | 2020 | 180,000.00 | IPA II budget | Fully implemented |
| *8) *13) |  | A.2.6 Define performance indicators for programmes or sub-programmes | Legal act (new/revised) | Performance indicators defined (and published in the Budget Documentatio) | IPA II | MoF - BD | 2 (A.2.4) (A.2.5) (C.1.4) (D.1.10) | 2019 | 2020 | 2020/2021 | 310,000.00 | IPA II Budget | Performance indicators defined in the process of drafting the budget for 2021. The project plans additional on-the-job training in the third quarter of 2021 to re-define performance indicators. |
| *6) |  | A.2.7 Review and amend the budget circular to reflect changed programme structures and introduce non-financial elements of the programme budget | Legal act (new / revised) | Budget circular prepared (every year) | IPA II | MoF - BD | 1 (A.1.11) | 2018 | 2019 | 2019/ 2021 | 30,000.00 | IPA II budget | Fully implemented |
| *7) |  | A.2.8 Organise training for employees of the MoF and budget organisations that will be involved in the implementation of the programme budget | Training | A number of employees have been trained. | IPA II | MF - BD | 1 | 2018 | 2019 | 2020 | 170,000,00 | IPA II budget | Fully implemented |
| *6) |  | A.2.9 Review and improve the functionality of the existing IT system for budget planning | Computerisation | Specifications for the development and upgrade of the Budget planning system prepared. Individual upgrades / improvements / modules developed. | IPA II | MoF - BD | 1 (A.1.10) (A.3.9) | 2018 | 2020 | 2020 | 295,000.00 | IPA II Budget | Implemented module for budget execution and connection to the SAP system. / |
|  |  | A.2.10 Improve budget transparency by providing better visual presentation | Computerisation | Budget view designed and web pages created. Budget Law format revised and updated. | IPA II | MoF - BD | 2 | 2019 | 2020 | 2020/2021 | 20,000.00 |  | Recommendations and changes to the programme classification were completed in 2019. In 2020, the budget overview was completed through a detailed programme and amended organisational classification. The programme classification was further revised to include activities and projects, as well as performance information (March 2021). The budget for citizens was prepared in May 2021, which improves the visualisation of the Draft Budget for 2021. |
|  |  | A.2.11In accordance with the best international standards explore and implement measures for the improved presentation and visualisation of the in year reports (monthly and quarterly) | Computerisation | Monthly and quarterly reports prepared and published on the MoF website. | IPA II | MoF - BD | 2 | 2019 | 2020 | 2020/2021 | 45,000.00 |  | The first draft of the guidelines for reporting on performance has been prepared (November 2020) Training material has been prepared (2020) Trainings for reporting on the results and success of the implementation of programmes and indicators and visualisation are planned for the third quarter of 2021 |
| *9) |  | A.2.12 Improve resources for better management of the EU`s own resources | Training | ‘Draft Manual prepared. Employees trained. ‘ | IPA II | MoF - BD | 1 (B.1.6) (B.2.8) | 2017 | 2019 | Implemented / continuous implementation | Implemented using existing capacities |  | Implemented / continuous implementation |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 895,000.00 | 522.000,00 |  |
| A) Sustainable fiscal framework, public expenditures planning and budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational objective 4.1.3._ A.3. Capital Budget |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicators 7 | Level of detail in public presentation of capital budget | PV (2014): Projects in the Capital Budget presented grouped by areas (education, health, culture, sports…) | TV (2017): Projects in the Capital Budget presented grouped by areas (education, health, culture, sports…) | Actual value in 2017: Projects in the Budget Law are presented grouped by areas, while in the Explanation of the Law they are presented by individual projects | TV (2018): Projects in the Capital Budget presented grouped by areas (education, health, culture, sports…) | Actual value in 2018: Projects in the Budget Law are presented grouped by areas, while in the Explanation of the Law they are presented by individual projects | TV (2019): Overview of all individual projects implemented in the Budget Year and implementation of selected pilot projects by phases | Actual value in 2019: Projects in the Budget Law are presented grouped by areas, while in the Explanation of the Law they are presented by individual projects | TV (2020): Review by individual projects and phases of project implementation | Actual value in 2020. Presentation by individual projects |  |  |
|  | Performance indicators 8 | Actual capital spending in the current year as a share of the capital budget plan | PV (2014): 70% | TV (2014): 80% | Actual value in 2017: 82% | TV (2018): 83% | Actual value in 2018: 91%/111% | TV (2019): 86% | Actual value in 2019: 92% 112,3% | TV (2020): 90% | 180.60% 107.6% |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| *2) |  | A.3.1 Improve capital budget planning in the medium term as a part of the MTBF | Legal act (new/revised) | New Legal act (new / revised) / guidelines prescribing the manner and content of capital budget planning. | IPA II | MoF - BD | 1 | 2018 | 2020 | 2020/2021 | 30,000.00 | The activity is realised within the existing capacities, while possible improvement in the next period will be realised from IPA II | A draft Manual for the capital budget has been drafted. Draft Manual for capital budget prepared(December 2020) Currently under consideration and further improvement by BD MoF (May-June 2021) |
| *2) |  | A.3.2 Introduce stages of capital projects in the preparation and planning of capital budgets (preparatory stage and construction stage) | Legal act (new/revised) | New format of the Budget Law (Capital Budget) prepared. | IPA II | MoF - BD | 2 | 2018 | 2020 | 2020/2021 | 25,000.00 | IPA funds | The implementation of the activities has started. Full implementation is expected at the end of Q3 2021 |
| *3) *4) *5) |  | A.3.3 Improve the overview of projects in the capital budget through detailed presentation of individual projects by project and economic classification | Legal act (new/revised) | New format of the Budget Law (Capital Budget) prepared. | IPA II | MoF - BD | 1 | 2018 | 2020 | 2020 | 25,000.00 | IPA II funds | Implemented / continuous implementation. The budget for 2021 is presented for the first time by projects and economic classification. Continuation of audit activities is envisaged. |
| *5 |  | A.3.4 Improve the capital budget’s statement of reasons as regards the overall estimated project value and schedule | Guidelines / Manual | Guidelines prepared. Explanation of each project prepared. | IPA II | MoF - BD | 2 | 2018 | 2020 | 2020 | 15,000.00 | IPA II funds | Partially implemented. Full implementation planned for 2021. |
|  |  | A.3.5 Establish a public register of all the projects which are financed from the capital budget | Computerisation | Public register established. Register published on the MoF website. | IPA II | MoF - BD MoF - Treasury. MSDT - DPV MTMA - DT | 1 (D.1.7) | 2018 | 2020 | 2020/2021 | 35,000.00 | IPA II funds | Draft public register done. Implementation continues throughout 2021. |
|  |  | A.3.6 Training of staff in line ministries involved in planning and implementation of capital projects with a view of better planning of investment project costs in the medium term | Training | Training materials prepared. A number of employees have been trained. | IPA II | MoF - BD | 2 | 2018 | 2019 | 2020/2021 | 50,000.00 | IPA II funds | Training of staff in line ministries is expected during Q2 2021. (June 2021) |
|  |  | A.3.7 Improve the overview of capital projects by separating the new ones from the ones already being implemented | Legal act (new/revised) | New format of the Budget Law (Capital Budget) prepared. | IPA II | MoF - BD | 2 | 2018 | 2019 | 2020 | 10,000.00 | IPA II funds | The activity will be implemented through the budget for 2022, as well as through planned trainings during 2021. |
| *6) |  | A.3.8 Improve the functionality of the exiting capital budget planning IT tool | Computerisation | Specifications for the development and upgrade of the Budget planning system prepared. Individual upgrades / improvements/ modules developed. | IPA II | MoF - BD | 1 (A.1.10) (A.2.9) | 2018 | 2020 | 2020/2021 | See A1.10 | IPA II funds | Budget planner developed, while the part for capital budget planning should be additionally harmonised during 2021 for the budget for 2022. |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 190,000.00 | 99.000,00 |  |
| Strategic objective 1._A) Sustainable fiscal framework, public expenditures planning and budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational objective 4.1.4._ A.4. Upgrade the model for macroeconomic projections |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicators 9 | Staged implementation of the upgraded model for macroeconomic projections and structural reform impacts | PV (2014): The existing model used in the Directorate for Economic and Development Policy is based on the financial programming model, and the projection of certain parameters is based on expert assessment | TV (2017): Analysis and upgrade of the existing macroeconomic model for projections | Actual value in 2017: Target value for 2017 met | TV (2018): A new model for projections of macroeconomic indicators and the impact of structural reforms and trained employees | Actual value in 2018: w model for projections of macroeconomic indicators and the impact of structural reforms and trained employees | TV (2019): Preconditions fulfilled for the use of the new model by employees in the Directorate for Economic Policy and Development | Actual value in 2019: Preconditions for the use of the new model by employees in the Directorate for Economic Policy and Development fulfilled | TV (2020): Full implementation and full ability to use the model | Actual value in 2020: Partially implemented. The project is being continuously implemented, in accordance with the recommendations of experts for the full implementation of the model, which is planned for the end of 2022. |  |  |
|  | Performance indicators 10 | The difference between actual and projected real GDP growth rate | PV (2014):1.8 p.p. | TV (2017):Less than 0.5 p.p | Actual value in 2017: The target value for 2017 has not been met | TV (2018): Less than 0.3 p.p | Actual value in 2018: 0.8 p.p | TV (2019): Less than 0.2 p.p. | Actual value in 2019: Target value for 2019 partially met, further recommendations given | TV (2020): Less than 0.2 p.p. | Actual value in 2020: The projection could not be realised due to market disturbances and external shocks |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| *2) |  | A.4.2 Upgrade of the existing macroeconomic forecasting model | Manual | Manual for the new model | IPA II | MoF - DEPD | 1 | Q3 2017 | Q1 2018 | Implemented/continuously implemented | Not specified | / | Implemented / continuous implementation. Working to improve the model is an ongoing process. |
| *2) |  | A.4.3 Training of staff to use the new model (both modules) | Training | A number of employees trained | IPA II Budget CG | MoF - DEPD Other line ministries | 1 | Q3 2017 | Q3 2018 | implemented / continuous implementation | Not specified | / | implemented / continuous implementation After the outflow of staff, it is necessary to hire new employees and train them to work on the model. |
| *3) *4) *5) |  | A.4.4 Data gathering and analysis for the needs of developing the two modules | Procedure | Creating assumptions for the improvement of Module II | IPA II | MoF - DEPD Other line ministries | 1 | Q2 2017 | Q1 2018 | implemented / continuous implementation | Not specified | / | implemented / continuous implementation |
| *5) |  | A4.5 Development of a module for the impact of structural reforms on macroeconomic performance indicators | Manual | Manual for using the model II module | IPA II | MoF - DEPD Other line ministries | 1 | Q1 2018 | Q3 2018 | implemented / continuous implementation | Not specified | / | Fully implemented |
|  |  | A.4.6 The new model implemented and staff trained to use it | Regulation/ Procedure/ Training/ Computerisation | Application of the new model and training of DEP employees to work on the model, and line ministries to use the model | IPA II | MoF - DEPD | 1 | Q1 2018 | Q4 2020 | 2024 | Not specified | / | - Adequate training of employees; -Hiring experts for modeling and programming; - It is necessary to hire IT experts, mathematicians and hire analysts who have the necessary knowledge for modeling, programming and understanding of macroeconomics |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 200.000,00 | 130.000,00 |  |
| Strategic objective 2. _ B) Budget execution |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational objective 4.1.3.1._ B.1. Revenue collection - Tax Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 11 | Share of submitted e-returns (income tax, VAT) in comparison to total number of submissions | PV (2014): 27% | TV (2017): VAT 50% INCOME 95% | Actual value in 2017: VAT 50% INCOME 95% | TV (2018): VAT 65% INCOME 97% | Actual value in 2018: VAT 70% INCOME 99% | TV (2019): VAT 75% INCOME 97% | Actual value in 2019: VAT 77.37 % INCOME 99.5% | TV (2020): VAT 80% INCOME 99% | Actual value in 2020: VAT 88 % INCOME 99,6% |  |  |
|  | Performance indicator 12 | EU VAT regulations concerning EU common market successfully implemented | PV (2014): Completed screening process | TV (2017): Negotiations in Chapter 16 open | Actual value in 2017: A certain degree of legislative harmonisation has been achieved, a higher degree has been achieved in the field of VAT, harmonisation in income tax area (transfer prices) administrative cooperation and mutual assistance remains | TV (2018): Law on Amendments to the Law on Corporate Income Tax (Q4 2018) -Law on Amendments to the Law on Tax Administration (Q4 2018) | Actual value in 2018: Actual value in 2018: Draft Laws on Amendments to the Law on Corporate Income Tax, as well as the Law on Amendments to the Law on Tax Administration have been prepared in order to further harmonise with EU legislation, especially in the area of administrative cooperation and exchange of information | TV (2019): Law on Amendments to Value Added Tax (Q4 2019) | Actual value in 2019: Higher degree of compliance compared to the previous year; All amendments to the law were approved by the Legislative Committee. After which they were submitted to the EC for an opinion. | TV (2020): Implemented channeled activities from the Accession Program - Chapter 16. | Actual value 2020: Higher degree of compliance compared to the previous year |  |  |
|  | Performance indicator 13 | Share of collected tax revenue compared to the planned tax revenue in the annual budget law | PV (2014: 100% (2015): 100% (2016): 100% | TV (2017): 100% | Actual value in 2017: More than 100% of planned (24 million above the plan for 2017) and 34 million above the achievement in 2016 | TV (2018): 100% | Actual value in 2018: Above the plan for 2018, achieved 73 million or 117 million above the achievement from 2017. | TV (2019): 100% | Actual value in 2019: Above the plan for 2019, 80 million was achieved above the plan | TV (2020): 100% | Actual value in 2020: 65 mil. euros above the plan according to the budget revision, while still 79 mil. euros (7%) below the 2019 achievement |  |  |
|  | Performance indicator 14 | Share of collected VAT revenues in GDP | PV (2014): 13.5% | TV (2017): 13.5% | Actual value in 2017: 13.0% | TV (2018): 14.7% | Actual value in 2018: 13.6% | TV (2019): 14;6% | Actual value in 2019: 14.44% | TV (2020): 14.6% | Actual value in 2020 12.6% |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
|  |  | B.1.1 DFurther improvement in efficiency, taxpayer services and tax compliance through capacity building and systems improvement in MTA. | Procedure, Computerisation | Growth in the share of submitted electronic tax returns (INCOME tax, VAT) | IPA II | MoF - TA | 2 | 2018 | 2019 | 2020 | 1,000,000 | / | The activity has not yet started with the implementation, because it was conditioned by IPA funds. From now on, the realisation of the activities will take place through a World Bank project |
|  |  | B.1.2 Strengthen MTA’s administrative and institutional capabilities to apply EU’s common VAT system | Legal act (new/revised) Computerisation | Software implemented. | IPA II | MoF - TA | 2 | 2019 | 2020 | 2025 | 2,000,000 | / | -The activity is being implemented with the anticipated dynamics, while the new deadline is related to the release of the VIES system, which must be in operation half a year before EU accession./ |
|  |  | B.1.3 Upgrade capacity of the MTA and its IT systems in the area of risk analysis and inspections control (e-control) | Procedure, Computerisation | Software implemented. | IPA II | MoF - TA | 2 | 2017 | 2018 | 2020 | 500,000 | /` | The activity was transferred within activity ‘B 1.5.’ so that it can be realised on time. E-control will be financed from project funds under a contract with the World Bank in order to improve the Tax Administration. The activities are expected to be fully implemented in early June 2021. |
|  |  | B.1.5 MTA Reform | Business processes, Computerisation | Implementation of an integrated revenue management system (IRMS) in line with business processes |  | MoF - TA | 1 | Q1 2017 | 2021 (5 years) | 2023 (5 years) | 14,000,000 | / | Partially implemented. Continuous implementation. |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 18.500.000,00 | 850.000,00 |  |
| Strategic objective 2. _ B) Budget execution |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational objective 4.1.3.2._ B.2. Revenue collection - Customs Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator15 | Change in revenue collection compared to the previous year | PV (2014): 15% | TV (2017): 17.64 % | Actual value in 2017: 17.64 % | TV (2018): 5% | Actual value in 2018: 11.03% | TV (2019): 5% | Actual value in 2019: 5.17% | TV (2020): 5% | Actual value in 2020. -18% |  |  |
|  | Performance indicator16 | Harmonisation of customs and excise legislation with the EU Acquis | PV (2014): Completed screening process Chapter 16 Taxation | TV (2017): Law on Amendments to the Customs Law Law on Amendments to the Law on Excise Duties Customs Tariff Regulations for 2017 Regulations on amendments to the Regulation on the implementation of the customs law | Actual value in 2017: 4 regulations enacted | TV (2018): Adoption of 3 regulations | Actual value in 2018: Adopted 3 regulations | TV (2019): Adoption of 3 regulations | Actual value in 2019: Adopted 3 regulations | TV (2020): Adopted 2 regulations | Actual value in 2020. Adopted 1 regulation |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
|  |  | B.2.1 Implement excise IT system at the national level | Procedure/ Computerisation | Procedures established. Software implemented. | IPA II | MoF - CA. | 1 | 2019 | 2020 | 2020 | 299,000.00 | 119,200.00 | Implemented |
| *2) |  | B.2.2 Implement modernised customs clearance procedures at the national level | Procedure/ Computerisation | Procedures established. Software implemented. | IPA II | MoF - CA. | 1 | 2018 | 2020 | 2021 | 3,300,000.00 | 1,269,647.34 | The IPA 2014 project ‘Support to the Customs Administration’ started with the implementation in November 2018 and will last for 36 months. The project is aimed at strengthening the administrative and operational capacity of the Customs Administration of Montenegro so that the national transit procedure is fully compliant with the requirements of the common transit of the European Union in order to implement the latest phase of the New Computerised Transit System (NCTS) -The value of the project is 3,300,000 EUR |
| *2) |  | B.2.3 Training of officials to prepare for the implementation of automated EU revenue reporting procedures (A-B accounts) | Training | Officers trained. | IPA II | MoF - CA. | 2 | 2018 | 2020 | 2020 | Not specified | 0.000 | Fully implemented. Conducting training of officials within the CUSTOMS 2020 program |
| *3) *4) *5) |  | B.2.4 Upgrade risk management system | Training/ Computerisation | Officers trained. Software Improvement » | IPA II | MoF - CA. | 2 | 2018 | 2020 | 2020/continuous | Not specified | 0.000 | Continuation of activities carried out with continuous technical support of TAIEX and other EU expert assistance programs, which ensures that the development of risk analysis in the Customs Administration is in line with best practices and guidelines of the EU and WCO in this area. |
| *5) |  | B.2.5 Increase the number of economic operators authorised for simplified procedures | Preparation of economic entities for obtaining approval | Increased number of economic entities | IPA II | MoF - CA. | 2 | 2018 | 2020 | 2020/continuous | Not specified | 0.000 | Continuation of the implementation of activities on the affirmation of economic entities to use simplified procedures. |
|  |  | B.2.6 Development of AEO programme | Regulation/ Procedure/ Training/ Computerisation | Regulations updated. Procedures established. Software implemented. | IPA II | MoF - CA. | 2 | 2018 | 2020 | 2020 | Not specified | 0.000 | The implementation of the AEO program is a process that has been evolving over a number of years. In 2018, preparatory activities for the development of the AEO program were carried out. In November 2019, the validation mission of the CEFTA contracting parties concluded that the Customs Administration had fulfilled the conditions for the implementation of the institute of authorised economic operator (AEO) and started issuing approvals to businessmen who meet the prescribed conditions. |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 3,599,000.00 | 1,388,847.34 |  |
| Strategic objective 2. _ B) Budget execution |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational objective 4.1.3.3._ B.3. Public procurements |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator17 | Level of harmonisation and completeness of the procurement framework in line with the EU acquis | PV (2014): Open negotiations in the negotiating chapter 5 | TV (2017): Open negotiations in the negotiating chapter 5 | Actual value in 2017: Open negotiations in the negotiating chapter 5 | TV (2018): Further harmonisation with the package of Directives from 2014 in this area | Actual value in 2018: Open negotiations in the negotiating chapter 5 | TV (2019): Further harmonisation with the package of Directives from 2014 in this area (implementation of the new Law on Public Procurement, introduction of the electronic system of Public Procurement ...) | Actual value in 2019: Adoption of the new Law on Public Procurement by implementing the provisions in accordance with the new directives | TV (2020): Implemented planned activities from the Accession Program Chapter 5. | Actual value in 2020. A new Law on Public Procurement was adopted, which came into force on July 7, 2020 |  |  |
|  | Performance indicator18 | Average number of bidders received per procurement procedure | PV (2014): 3.52 bids per tender | TV (2017): 3.2 | Actual value in 2017: 2.66 | TV (2018): 3.48 | Actual value in 2018: 3.14 | TV (2019): 3.58 | Actual value in 2019: 2.01 | TV (2020): 3.8 | Actual value in 2020. 2.27 |  |  |
|  | Performance indicator 19 | Share of e-procurement of all procurement contracts awarded during the year. | PV (2014): 0% (There is no electronic public procurement system) | TV (2017): 0% (There is no electronic public procurement system) | Actual value in 2017: 0% (There is no electronic public procurement system) | TV (2018): Selection of the most favorable bidder | Actual value in 2019: The project of creating an e-public procurement system has started | TV (2019): 30% | Actual value in 2019: Pilot phase of the e-system | TV (2020): 80% | Actual value in 2020. System established, in house testing completed and trainings for users of the electronic public procurement system started |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| *2) |  | B.3.4 Provide training for civil servants involved in public procurement (as PP officers, members of Tender Opening and Evaluation Commissions, as well as for inspectors, prosecutors and judges) | Training | Training materials prepared. A number of employees have been trained. | IPA II | MoF - PPD | 2 | Q1 2017 | Q4 2018 | Implemented/continuous | 35,000.00 |  | Implemented |
| *2) |  | B.3.5 Training material for special target groups involved in public procurement | Training | Training materials prepared. A number of employees have been trained. | IPA II | MoF - PPD | 2 | Q1 2017 | Q4 2018 | Q4 2019 Q3/4 2020 | 50,000.00 |  | Implemented 80%. Previously, there was a delay in implementation due to the adoption of the new Law on Public Procurement, which was adopted by the Parliament of Montenegro on December 30, 2019 (Official Gazette 074/19) This activity started with the implementation after the beginning of the application of the new law, from 07 July 2020 and refers to the development of Manuals, guidelines and other instructions for the implementation of new legislation in this area. |
| *3) *4) *5) |  | B.3.6 Awareness raising campaign | Training | Campaign launched and ended. | IPA II | MoF - PPD | 1 | Q3 2017 | Q4 2018 | Q4 2019 Q3/4 2020 | 40,000.00 |  | The activities are interconnected and interdependent, so for the implementation of this activity they had to wait for the bylaws, manuals to be fully completed, as well as for the electronic system to become operational. Also, due to the COVID pandemic, work and implementation of all activities on the project, including this one, have been slowed down and complicated. |
| *5) |  | B.3.7 e-Procurement | Computerisation | Software implemented. | IPA II | MoF - PPD | 1 | Q1 2017 | 2020/2021 | 2020/2021 | 1,650,000.00 |  | Activities realised through the IPA project called ‘Implementation of electronic public procurement system in Montenegro ‘. The project started in November 2018. In July 2020, the Pilot Phase started with several contracting authorities for testing purposes After the final design of the system, the public procurement portal will be replaced by the advanced IT system EPPS, with the expectation of January 2021. At the end of 2020, testing of the electronic public procurement system was completed, as well as trained administrators from the Directorate. From January 1, 2021, full use of the e-system is expected. |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 1,775,000.00 | 721.500,00 |  |
| Strategic objective 2. _ B) Budget execution |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational objective 1._ B.4. State Aid reform |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 20 | The number of state aid grantors and beneficiaries, private sector representatives and judges attending state aid seminars and training events | PV (2014): 50 | TV (2017): 50 | Actual value in 2017: 0 | TV (2018): 30 | Actual value in 2018: 0 | TV (2019): 60 | Actual value in 2019: 56 | TV (2020): 100 | Actual value in 2020. 171 |  |  |
|  | Performance indicator 21 | The share of staff of the State Aid Division and the Commission for State Aid Control undergoing training with a view of strengthening the legal framework, reducing the level of illegal state aid and conducting ex-post controls | PV (2014): 30% | TV (2017):30% | Actual value in 2017: 33% | TV (2018): 50% | Actual value in 2018: 0% | TV (2019): 70% | Actual value in 2019: 70% | TV (2020): 80% | Actual value in 2020. 75% |  |  |
|  | Performance indicator 22 | Number of ex-officio cases closed | PV (2014): 5 | TV (2017): 3 | Actual value in 2017: 0 | TV (2018): up to 2 | Actual value in 2018: 0 | TV (2019): up to 2 | Actual value in 2019: 0 (2 ex-officio cases have been opened, we expect them to close in the next period) | TV (2020): do 1 | Actual value in 2020. 1 |  |  |
|  | Performance indicator 23 | Number of documents reviewed and assessed by the State Aid Division | PV (2014): 11 | TV (2017): 20 | Actual value in 2017: 14 | TV (2018): do 20 | Actual value in 2018: 22 | TV (2019): up to 23 | Actual value in 2019: 35 | TV (2020): 25 | Actual value in 2020. 41 |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| *2) |  | B.4.1 Upgrade and strengthening of the institutional framework and national legal system regarding the implementation of state aid rules and procedures | Organ. /managerial changes | Organisational change implemented, special body (organisationally independent, part of the MoF or with another ministry) | IPA II | MoF - DP | 1 | Q2 2018 | Q4 2020 | Q4 2020 | 50,000.00 | 25,000.00 | The activity was implemented, but it is necessary to continue this activity in order to strengthen the national legal system. |
| *2) |  | B.4.2 Support through the negotiation process and meeting the requirements of Chapter 8; | Legal act (new/revised) | Fulfillment of benchmarks | IPA II | MoF - DP | 1 (B.4.3) | Q3 2018 | Continuous implementation | Continuous implementation | 150,000.00 | 25,000.00 | Implementation /Continuous implementation |
| *3) *4) *5) |  | B.4.3Monitor achievements by analysing state aid cases in the EC customary law | Guidelines / Manual | Analysis of 3-4 cases performed. | IPA II | MoF - DP | 1 (B.4.2) | Q3 2017 | Continuous implementation | Continuous implementation | 200,000.00 | 25,000.00 | Implementation /Continuous implementation |
| *5) |  | B.4.4 Technical Support for theMontenegro State Aid’s IT Tool, development of a special register for de minimis state aid and the application for state aid grantors to be included in a single IT component | Computerisation | Software implemented. | IPA II | MoF - DP | 1 | Q4 2018 | Q4 2020 | Q4 2020 | 200,000.00 | / | Partially implemented. Continuous implementation |
|  |  | B.4.5 Strengthen administrative capacities through training and experience sharing | Training | Training materials prepared. A number of employees have been trained. | IPA II | MoF - DP | 2 | Q3 2018 | Continuous implementation | Continuous implementation | 100,000.00 | 25,000.00 | The activity has been implemented, but it is necessary to continue with training through professional seminars and work exclusively with the mentoring of experts. Because of the extremely complex cases that carry a huge responsibility |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 700,000.00 | 100,000.00 |  |
| Strategic objective 2. _ B) Budget execution |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational objective 4.1.4._ B.5. Debt Management, Debt Analysis, Cash Management and Foreign Relations Department Reform |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 24 | Public debt servicing costs as a share of GDP | PV (2014): 2.2 % | TV (2017): 2.5 % | Actual value in 2017: 2.3 % | TV (2018): 1.9 % | Actual value in 2018: 2.1% | TV (2019): 2.0 % | Actual value in 2019:2.2% | TV (2020): 2.3% | Actual value in 2020. 2.64% |  |  |
|  | Performance indicator 25 | Difference between planned and achieved level of public debt | PV (2014): 1.5% | TV (2017): 1.5% | Actual value in 2017: Public debt is 3.2% lower than planned | TV (2018): 1.5% | Actual value in 2018: Public debt is 3.07% higher than planned | TV (2019): 1.5% | Actual value in 2019: Realised difference in gross public debt 16.6% | TV (2020): 1.5% | Actual value in 2020. Realised difference in gross public debt 16% |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| *2) |  | B.5.2 Training of staff at the Debt Management Department regarding different financial operations, awareness and training for different financial derivatives, debt preparation and analysis, better debt management | Training | Training materials prepared and available. A number of employees have been trained. | IMoF SIGMA | MoF - Treasury | 1 | Q1 2016 | Q4 2018 | Implemented /Continuous implementation | 50,000.00 | Donation | Conduct training of new employees continuously and based on the level of their training. |
| *2) |  | B.5.4 Upgrade of the software tool for public debt and cash management | Computerisation | Upgrading implemented software. |  | MoF - Treasury | 3 | Q1 2016 | 2019 | 2020 | 500,000.00 | 0.000 | Improve reporting within the software solution, and in accordance with the needs of debt management. |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 780,000.00 | 0 |  |
| Strategic objective 1._ A) Sustainable fiscal framework, public expenditure planning and budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OPERATIONAL OBJECTIVE 4. 1._ B.6. PUBLIC SECTOR PAYROLL SYSTEM REFORM |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| *2) |  | B.6.2 Implementation of new software for calculation and control of salaries in the public sector | Computerisation | Software implemented. |  | MoF - BD | 1 (B.6.1) | Q4 2016 | 2018 | 2020 | 600,000.00 |  | During 2021, activities will continue on the delivery of trainings for key users, future administrators, as well as end users of the system. It is possible to extend the duration of the contract in order to prevent the negative consequences and the impact of the coronavirus on the implementation of projects. |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 600,000.00 | 304.697,72 |  |
| Strategic objective 3_C) Development of public internal financial control (PIFC) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 26 | The percentage of ministries that formally delegated decision-making responsibilities and authorities to the line managers to improve managerial accountability | PV (2014): 6.25% 2015: 6.3% 2016: 6.3% (Report: 2016: 22.22%) | TV (2017): 30% | Actual value in 2017: 11.11% | TV (2018): 16% | Actual value in 2018: 18% | TV (2019): 50% | Actual value in 2019: 12% | TV (2020): 90% | Actual value in 2020. 8.3% |  |  |
|  | Performance indicator 27 | Percentage of the budget users on central and local level submitting annual FMC reports | PV (2014): 69% 2015: 76% 2016: 76% | TV (2017): 75% | Actual value in 2017: 80% | TV (2018): 80% | Actual value in 2018: 90% | TV (2019): 90% | Actual value in 2019: 94% | TV (2020): 95% | Actual value in 2020. 93% |  |  |
|  | Performance indicator 28 | Percentage of appointed internal auditors per unit | PV (2014): 1.76 | TV (2017): 2 | Actual value in 2017: 2 | TV (2018): 2.3 | Actual value in 2018: 2.21 | TV (2019): 2.5 | Actual value in 2019: 2.1 | TV (2020): 2.7 | Actual value in 2020. 2.1 |  |  |
|  | Performance indicator 29 | Percentage of appointed certified internal auditors | PV (2014): 60% | TV (2017): 75% | Actual value in 2017: 90.90% | TV (2018): 80% | Actual value in 2018: 94.05% | TV (2019): 85% | Actual value in 2019: 100.00% | TV (2020):90% | Actual value in 2020. 93.1% |  |  |
|  | Performance indicator 30 | Percentage of appointed certified internal auditors who undergo CPD | PV (2014): 0% | TV (2017): 70% | Actual value in 2017: 74% | TV (2018): 75% | Actual value in 2018: 83.64% | TV (2019): 80% | Actual value in 2019: 81.36% | TV (2020): 90% | Actual value in 2020. 80% |  |  |
|  | Performance indicator 31 | Percentage of implemented and partially implemented recommendations given by internal auditors in the previous year that were implemented by the end of the current year | PV (2014): 48% (2016): 74.2% | TV (2017): 55% | SActual value in 2017: 73.5% | TV (2018): 60% | Actual value in 2018: 79.16% | TV (2019): 65% | Actual value in 2019: 84.46% | TV (2020): 70% | Actual value in 2020. 79.4% |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required(IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| *2) |  | C.1.4 Conduct training for managers | Training | Training materials prepared. Number of trained. | IPA II | MoF - CHU HRA | 2 (C.1.6) (C.1.7) | Q3 2017 | Continuous. | Continuous | 20,000.00 | 12.000,00 | The Ministry of Finance and Social Welfare will continue to hold trainings for managers in the coming period. |
| *3) 4*) 5*) |  | C.1.5 Training for newly appointed internal auditors | Training | Training materials prepared. Number of trained. | IPA II | MoF - CHU HRA Ger. Gvnmt. | 2 (C.1.5) (C.1.7) | Q3 2017 | Continuous. | Continuous | 10,000.00 | 10.000,00 | The Ministry of Finance and Social Welfare will localise the Training Program in the next period, which will be implemented in cooperation with the Human Resources Administration. |
| *16) |  | C.1.6 Organise and deliver CPD training for certified public internal auditors | Training | Training materials prepared. Number of trained. | IPA II | MoF / CHU UZK | 2 (C.1.5) (C.1.6) | Q3 2017 | Continuous. | Continuous | 20,000.00 | 17.500,00 | The Ministry of Finance and Social Welfare will continue to hold trainings to improve the expertise of internal audit in the coming period. |
| *14) |  | C.1.8 Strengthen the CHU capacities for assessing the FMC and IA quality | Guidelines / Manual | Guidelines prepared. | IPA II SIGMA | MoF - CHU | 1 (C.1.1) | Q2 2016 | 2020 | 2020 Implemented – continuous | 25,000.00 | / | The implementation of the IPA project ‘Improvement of the budget system, multi-annual budget planning and the system of public financial internal control’ has begun, within which assistance will be provided for the implementation of this activity. |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 175,000.00 | 39.500,00 |  |
| Strategic objective 4._D) Financial reporting and accounting |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational objective 4.3. _D.1. Transition from the cash-based to the accrual accounting and financial reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 32 | Public sector accountants trained for accrual accounting (based on the CIPFA methodology) | PV (2014): 0 | TV (2017): 40 | Actual value in 2017: 40 in 2016 | TV (2018): 40 | Actual value in 2018: 80 | TV (2019): 20 | Actual value in 2019: 40 | TV (2020): 100 | Actual value in 2020. 120 |  |  |
|  | Performance indicator 33 | Property register and double entry book-keeping system for the property implemented | PV (2014): Development of the property register has begun | TV (2017): Entered property data in the register | Actual value in 2017: 0 | TV (2018): (direct and indirect Budget users) and collection of information on the condition of property | Actual value in 2018: 0 | TV (2019): Training (indirect Budget users) and migration of funds to ARS and commissioning of records | Actual value in 2019: 9 groups 100 state bodies 0 migration | TV (2020): Implemented property register and sufficient asset accounting system | Actual value in 2020. Public authorities (99) Public services (322) DCM (39) Local government (24) Municipal authorities (196) 0 migration |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required (IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| 2*) |  | D.1.2 Develop new accrual-based accounting policies | Legal act (new/revised) | Law on Public Sector Accounting approved |  | MoF - Treasury | 1 | Q1 2017 | Q4 2020 | 2020 | Not specified | Budget/donation | New policies have been drafted, although they have not yet been adopted |
| *3) *4) *5) |  | D.1.3 Adapt the Chart of Accounts to new accounting requirements | Legal act (new/revised) | Updated classifications (organisational, functional, property…) | UNDP | MoF - Treasury | 2 (D.2.1) (D.2.2) (D.2.3) | Q1 2018 | 2020 | 2020 | Not specified | Budget/donation | /A chart of accounts has been drafted |
|  |  | D.1.4Develop the IT system to support double-entry bookkeeping | Computerisation | IT system implemented |  | MoF - Treasury | 2 | 2019 | 2020 | 22020021 | Not specified | / | In 2021, preparatory activities will begin regarding the development of GAP analysis and process analysis necessary for the development of IT systems |
|  |  | D.1.5 Develop new implementing legislation and reporting templates | Legal act (new/revised) | New regulations and report forms approved. |  | MoF - Treasury | 2 | 2019 | 2020 | 2020 | Not specified | / | A draft Rulebook on financial reporting has been prepared |
|  |  | D.1.6 Provide training for public sector accountants on new implementing legislation, templates and the IT system | Training | Training materials prepared and available. A number of employees have been trained. |  | MoF - Treasury | 2 | 2020 | 2020 | 2020 | Not specified | / | The implementation of this activity will be possible after the development of the IT system and the adoption of bylaws, and the plan for the implementation of this activity was developed in part through IPA support |
| *5 |  | D.1.9 Deliver training for public accountants on the new implementingregulation and the use of the new Asset Management Module | Training | A number of employees trained. |  | MoF - PrA | 2 (D.1.8) | Q3 2015 | Q4 2016 | 2020 | Not specified | / | Regulatory changes began in June 2019, but due to the situation with the Corona pandemic, all activities were stopped. |
|  |  | D.1.10 Legislative changes, annual reports should feature assets data and performance indicators | Legal act (new/revised) | Regulation amended and approved. |  | MoF - Treasury MoF - DfP MoF-PrA. | 2 (A.2.6) (C.1.4) (D.1.8) | 2019 | 2020 | 2020 | 34,666.50 | 34,666.50 | Realisation of activities in progress. Modified fields in ARS application |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 34.666,50 | 34.666,50 |  |
| Strategic objective 5._E) Development and strengthening of external audit |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational objective 4.5.1._State Audit Institution strengthening |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 34 | Level of realisation of SAI’s Annual Audit Plan | PV (2014):60% (2017):80% | N/A | N/A | TV (2018): 83% | Actual value in 2018: 86.27% | TV (2019): 86% | Actual value in 2019: 88.68% | TV (2020):90% | Actual value in 2020. 72.50% |  |  |
|  | Performance indicator 35 | Application of ISSAI-compliant methodology for financial. regularity and performance audits | PV (2014): 2015 – Methodological Instruction for financial and regularity audits compliant with ISSAI 200 and ISSAI 400. Methodological Instruction for performance audits compliant with ISSAI 300 and Guidelines for Audit Quality Control | N/A | N/A | TV (2018): Guidelines for Auditing Annual Financial Statements of Political Entities; Guidelines for Auditing Final Budget Accounts; | Actual value in 2018: Guidelines for Auditing Annual Financial Statements of Political Entities adopted in January 2018; Guidelines for Auditing Final Budget Accounts adopted in September 2018; | TV (2019): n / a The activities listed in the action plan start from Q1 2019. | Actual value in 2019: Manual for Performance Audits compliant with ISSAI 4th level adopted in December 2019. | TV (2020): Manual for Financial and Regularity Audits compliant with ISSAI 4th level adopted Manual for Performance Audits compliant with ISSAI 4th level upgraded Guide for Monitoring the Implementation of Recommendations from Audit Reports adopted | Manual for Financial and Regularity Audits compliant with ISSAI 4th level adopted in July 2020 and applied. Manual for Performance Audits compliant with ISSAI 4th level adopted in December 2019 and applied Guide for Monitoring the Implementation of Recommendations from Audit Reports adopted in June 2020 and applied |  |  |
|  | Performance indicator 36 | No of trainings/seminars/ workshops for auditors delivered | (2014): Minimum 3 trainings delivered (2017): Delivered additional 9 trainings | N/A | N/A | TV (2018): additional 6 trainings delivered | Actual value in 2018: 13 Trainings (3 internally organised and 10 regionally and internationally) | TV (2019): additional 7 trainings delivered | Actual value in 2019: 13 Trainings (3 domestically and 10 regionally and internationally) | TV (2020): additional 10 trainings delivered | Actual value in 2020. 32 trainings (22 at the domestic level and 10 at the regional and international level) |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Potrebna tehnička pomoć (IPA, IMoF, UNDP…) | Implementaciona agencija / Direktorat | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
|  |  | E1.1.Review the Methodological Instruction for Financial and Regularity Audit and draft an ISSAI-complian Financial and Regularity Audit Manual | Manual | Draft Manual on Financial and Regularity Audit in Accordance with ISSAI Standards prepared. | IPA II | SAI | 1 (E.1.5) | Q1 2019 | Q2 2020 | Q2 2020 | 32,000.00 | 32,000.00 | Fully implemented |
|  |  | E1.3 Review current practices in monitoring the implementation of audit recommendations in the SAI compared to the best EU practices and draft guidance for monitoring audit recommendations | Guidelines | Draft Guidelines for monitoring the implementation of audit recommendations prepared. | IPA II | SAI | 1 | Q1 2019 | Q2 2020 | Q2 2020 | 24,000.00 | 22,200.00 | Fully implemented |
|  |  | E1.4 Develop HRM Strategy and the Communication Strategy | Strategic / Planning document | HRM Strategy And the Communication Strategy prepared | IPA II | SAI | 2 | Q1 2019 | Q2 2020 | Q2 2020 | 40,000.00 | 38,800.00 | Fully implemented |
|  |  | E1.5 Revise the manual for State Auditor exam; deliver training (1 1 pilot audit and training for using the Financial and Regularity Audit Manual) and build auditor capacity to apply IT tools | Manual / Guidelines/ Training / Computerisation | SAI auditor training manuals prepared. A number of auditors trained. Improved IT tool implemented. | IPA II | SAI | 2 (E.1.1) (E.1.2) | Q1 2019 | Q2 2020 | Q2 2020 | 87,000.00 | 84,900.00 | Fully implemented |
|  |  | E1.6 Develop guidance for auditing final budget accounts and deliver training for audit staff to implement the guidance | Manual/training | Draft Guidelines for the Audit of the Final Budget Account Prepared. A number of employees trained. | SIGMA | SAI | 1 | Q1 2018 | Q2 2018 | Q2 2020 | 0,000 | 0,000 | Fully implemented |
|  |  | E.1.8 Procure necessary office space for SAI to be able to increase auditor staffing capacities | Premises | Premises provided |  | SAI | 1 | 2018 | 2019 | 2020 | 2.500.000,00 | 0,000 | The realisation of activities is in progress and is taking place in accordance with the law. The state capital budget for 2019 plans funds to address the lack of office space for the needs of the State Audit Institution and the Statistics Administration within the multi-year capital subproject ‘Facilities for the needs of the State Audit Institution and the Statistics Administration’. |
|  |  |  |  |  |  |  | TOTAL: |  |  |  | 2,695,000.00 | 189.900,00 |  |
| Strategic objective 4.5._E) Development and strengthening of external audit |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational objective 4.5.2._Audit Authority |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Performance indicator 37 | No of trainings/seminars/ workshops for auditors delivered | PV (2014): Minimum 3 trainings delivered | N/A | N/A | TV (2018): Organised a minimum of 5 audit trainings per auditor | Actual value in 2018: 13 On average, 3 trainings were organised per auditor | TV (2019): additional 7 trainings delivered | Actual value in 2019: 11 trainings per auditor were organised | TV (2020): Organised a minimum of 7 audit trainings per auditor | Actual value in 2020 9 trainings per auditor were organised |  |  |
|  | Performance indicator 38 | Progress in implementing the Strategy and AP | PV (2014): N/A | N/A | N/A | TV (2018): The activities listed in the action plan will start in 2019 | Actual value in 2018: The activities listed in the AP start in 2019 | TV (2019): Strategic plan adopted / Action plan adopted | Actual value in 2019: Activities have been postponed to 2020. | TV (2020): 20% of planned activities realised | Actual value in 2020. The Strategic Plan and the Action Plan for its implementation were adopted on December 29, 2020 and refer to the period 2021-2025. |  |  |
|  | Performance indicator 39 | Degree of audit methodology improvement – Audit Manual | PV (2014): Audit Manual prepared | N/A | N/A | TV (2018): The activities listed in the action plan will start in 2019 | Actual value in 2018: The activities listed in the AP start in 2019 | TV (2019): 50% of deficiencies eliminated | Actual value in 2019: 90% of deficiencies eliminated | TV (2020): 100% of deficiencies eliminated | Actual value in 2020. 100% of deficiencies eliminated |  |  |
|  | Performance indicator 40 | Share of audits conducting by using the audit software tool | PV (2014): n/a | N/A | N/A | TV (2018): The activities listed in the action plan will start in 2019 | Actual value in 2018: The activities listed in the AP start in 2019 | TV (2019): 20% audit conducted using software | Actual value in 2019: 33.33% | TV (2020): 50% audit conducted using software | Actual value in 2020. 66.66% audit conducted using software |  |  |
|  | Performance indicator 41 | Level of implementing standards to ensure audit quality | PV (2014): n/a | N/A | N/A | TV (2018): The activities listed in the action plan will start in 2019 | Actual value in 2018: The activities listed in the AP start in 2019 | TV (2019): 30% | Actual value in 2019: 75% of audits covered by quality control | TV (2020): 50% | Actual value in 2020. 75% of audits covered by quality control |  |  |
| PUBLIC FINANCE MANAGEMENT |  |  | Type of activity | Result indicator | Technical assistance required (IPA, IMoF, UNDP…) | Implementation agency / Directorate | Priority | Planned start date | Planned date of completion | New deadline for implementation | Planned funding | Spent funds | Recommendations |
| SUB-SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ACTIVITY |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
|  |  | E2.1 Training needs assessment, development and delivery of auditor training programme | Strategic / Planning document Training | Number of organised trainings / seminars / workshops per auditor | IPA II | AA | 1 | 2019 | 2020 |  | 274,000.00 | 264,100.00 | Fully implemented |
|  |  | E2.3 Building skills for using certain audit tools (IT) | Computerisation Training | Percentage of audits performed using audit software | IPA II | AA | 2 | 2019 | 2020 |  | 20,000.00 | 11,000.00 | Fully implemented |
|  |  | E2.4 Development of the AA’s Strategic Plan and the implementing AP | Strategic / Planning document | Degree of implementation of the Strategic and Action Plan of the institution | IPA II | AA | 2 | 2019 | 2020 |  | 70,000.00 | 64,000.00 | Fully implemented |
|  |  | E.2.5 Develop guidelines for audit quality assurance | Guidelines/Manual | The degree of application of standards in order to ensure the quality of audit work | IPA II | AA | 2 | 2019 | 2020 |  | 70,000.00 | 64,000.00 | Fully implemented |
|  |  |  |  |  |  |  | TOTAL |  |  |  | 475.000,00 | 446.115,00 |  |

## IMPLEMENTATION OF DONOR FUNDS

The implementation of activities under the PFM Programme, is planned to be funded by EU funds through the IPA instrument, under the annual 2014 Country Action Programme - CAP 2014), and other donations with a corresponding part of national funding.

The IPA 2014 project ‘Support to Public Finance Management Policies’ is worth EUR 4,000,000.00, of which EUR 3,600,000.00 is the EU contribution; IPA 2014 project ‘Implementation of electronic public procurement system’ is worth EUR 1,650.00.00, of which EUR 1,500,000.00 represents the EU contribution; IPA 2014 project ‘Support to the Tax Administration’ is worth EUR1,000,000.00, of which EUR 900,000.00 is the EU contribution; IPA 2014 multi-beneficiary project ‘Strengthening economic and public finance management’ of which the EU contribution amounts to EUR8 million; and IPA 2014 project ‘Support to the Customs Administration’ is worth EUR3,300,000.00, of which EUR 2,970,000.00 is the EU contribution.

In terms of implementation of planned activities, the dominant support is provided through projects co-financed by donors. In addition, during the implementation of the project, the key contribution is evidently provided through own capacities of the institutions responsible for the implementation of activities. In this regard, in addition to the funds allocated for the regular activities in the state budget, the following funds were also provided from donations, by strategic objectives:

- Funds in the amount of € 1.17 million were spent for the implementation of activities within the strategic objective Sustainable Fiscal Framework, Public Expenditure Planning and Budgeting;

- Funds in the amount of € 3.06 million were spent for the implementation of activities within the strategic objective Budget Execution;

- Funds in the amount of € 0.04 million were spent for the implementation of activities within the strategic objective Development of Public Internal Financial Control (PIFC);

- Funds in the amount of € 0.08 million were spent for the implementation of activities within the strategic objective Financial Reporting and Accounting;

- Funds in the amount of € 0.64 million were spent for the implementation of activities within the strategic objective External Audit Development and Strengthening.

# IV RECOMMENDATIONS FOR THE NEXT PHASES OF THE PROGRAMME IMPLEMENTATION

2016-2020 Public Finance Management Reform Programme Final Report states that a certain number of activities have been implemented or their implementation is in progress, while there are also activities constantly being implemented, as well as some not implemented during the planned period. Therefore, it is necessary to make additional efforts to implement them.

Regarding the next period of the Programme implementation, specific recommendations were given for certain areas:

- The Ministry of Finance and Social Welfare needs to intensify activities on establishing full implementation of the programme-based budget at the level of performance indicators, and present individual projects in the capital budget;

- Intensify work on connecting software with the SAP system in order to exchange data and execute the budget;

- Continue trainings for key users and administrators of the new Budget Planning System and Centralised Payroll System for employees of the Ministry of Finance and Social Welfare, starting from the operational level of use by end users, to the level of acquiring administrative skills of system management;

- Take actions on continuous improvement of the system and achieving goals after the implementation of the Programme and the expiration of the signed contracts;

- In line with the identified challenges regarding macroeconomic forecasting, the employees working on the model adjusted the MMM model to the new situation in 2020 and used the expert assessment and experience from previous crises to a greater extent, as well as additional tools in macroeconomic forecasting. The aim was to increase the consistency of the model and provide more accurate projections of the most important economic indicators. In the forthcoming period, it is necessary to further improve the second module and include some of the structural reform measures listed in the Programme itself and assess their impact on the economic growth and other relevant parameters. Therefore, in the following period, it is expected to intensify the new project cycle concluded with the Directorate, which refers to the development of greater knowledge and implementation of training by Slovak experts, in accordance with the epidemiological situation;

- Strengthening the awareness of contracting authorities about the importance of the public procurement system and the ways of functioning of the same, as well as other actors in public procurement, in order to properly apply regulations in this area and professionalise public procurement employees and build internal operational capacities of contracting authorities;

- Developing the role of the Ministry of Finance and Social Welfare in policy making and coordination, building its administrative capacity and establishing effective mechanisms for coordination and consultative function;

- Improving the functionality of the public sector market and increasing its attractiveness to the private sector;

- Strengthening the institutional and operational capacity of key actors in the system to effectively support the implementation of the legal framework for concessions / PPPs;

- Continue the initiated reform of the Revenue and Customs Administration through development projects while fulfilling the obligations in accordance with the negotiating position from Chapter 16 - Taxation;

- Continue activities towards the completion of the started projects of modernisation of customs procedures, as well as activities on implementation of new projects in order to meet the requirements of the European Agenda and the objectives of the 2018-2022 Trade Facilitation Strategy of Montenegro;

- The main activities in the coming period will be focused on improving the results of competition policy and state aid control, with special emphasis on penal policy and specific cases of state aid. One of the key preconditions for progress in this chapter is capacity building for the implementation of legislation in this area;

- Continue to strengthen the capacity of the Audit Authority through the further training of staff and an increase in the number of employees. At the same time, it is necessary to make an analysis of legislation and its compliance with auditing standards and modern auditing trends, as well as work on strengthening the visibility of the work of the AA.

Also, in accordance with the conclusions of the PFM Dialogue, the Ministry of Finance and Social Welfare submitted an application form ‘Evaluation of the Public Finance Management Reform Programme’ supported by the Delegation of the European Union (DEU) through the EU Integration Facility (EUIF). To this end, on June 23, 2020, the Ministry of Finance and Social Welfare launched a tender procedure for the selection of an expert who will be responsible for conducting a comprehensive analysis of the achieved results of the Programme, including the current system of coordination and monitoring, and provide appropriate recommendations for the future. The Inception Report was submitted to the Ministry of Finance and Social Welfare on December 30, 2020.

The draft Evaluation Report assessed the criteria related to: relevance, coherence, efficiency and effectiveness. In addition, the importance of public finance management as an instrument for coordinating public finance management reforms in Montenegro was discussed. Considering the reform goals of the Programme, the draft evaluation concluded that the Programme accurately identified important priorities in the PFM system, the weaknesses of which are intended to be eliminated by relevant activities.

Also, internal, inter-ministerial coordination and cooperation with reform development partners was quite good, especially in those areas where the responsibility for implementation was limited to a single entity (e.g. tax reform, customs administration, audit). For more complex reforms, such as medium-term budgetary frameworks (MTBF), programme-based budgeting (PBB), and the transition to accrual accounting, there is further room for improvement. As regards external coordination, the reforms were found to benefit from a wide range of external support with a large share of EU-IPA-funded projects. However, the coherence was negatively influenced by delays in the process of contracting, which resulted in mismatches between the time of project implementation and the timeframe in the PFMRP-Action Plan (AP).

Some activities have been postponed due to the delayed start of related EU technical assistance projects. However, by the end of 2020, significant rate of implementation was achieved. Given that most (almost 70%) of the activities were completed in 2019 and 2020, despite the COVID outbreak, there is reason to consider the last two years of the PFMR implementation period extremely successful. In order for the reform to be successfully implemented, more efforts are needed in certain areas. However, it should be borne in mind that the evaluation was conducted until 2020, while the implementation of the unfinished part of activities is expected during 2021.

The use of PFMRP as a comprehensive tool for initiating and linking reforms in the PFM system and monitoring their implementation has contributed to some positive findings concerning the set reform objectives. Thus, it contributed to: Initiating reforms in areas where sector strategy did not yet exist; Uniformity and consistency in information in the whole domain of public finances; Establishment of a supervisory structure with two reporting deadlines per year, which contributed to an additional incentive to implement activities within the given deadline.

The implementation of reforms and the necessary funding relied heavily on donor support, resulting in delays in the implementation of the PFRMP when it comes to launching donor-funded projects; The implementation of public finance management reforms has been implemented as a series of highly separated activities; In certain reform areas, e.g. state property register, there was no high-level coordination; Limited progress in transparency, activities that required modification of the SAP system slowed down the implementation of certain PFMRP activities.

Given the above, in many areas of public finance management, the reform objectives have not yet been fully achieved. Based on the findings and conclusions, the draft evaluations provide recommendations that should be useful for the preparation of the new PFRMP for the period 2022-2026, which relate to the importance of time frame for development, analysis of the situation and use of internal knowledge to help identify measures; the necessary combination of modalities for the implementation of the new PFMRP to balance donor-supported activities and Government-funded activities; engaging other development partners in formulating and implementing the new PFMRP; setting realistic ambitions for complex reforms; the possibility of including specific targets for cross-topics that are crucial for the public finance management system, including transparency, human resources expertise and IT systems; improving the oversight function of the PFMRP through a number of operational measures, greater parliamentary involvement and representing the importance of the PFM Programme.

# APPENDIX 1 – PERFORMANCE INDICATOR PASSPORTS FOR THE 2016-2020 PUBLIC FINANCE MANAGEMENT REFORM PROGRAMME

Chapter 6 of the 2016-2020 Public Finance Management Reform Programme elaborates a system of monitoring and evaluation during the implementation of the Programme, the aim of which is to assess the concrete progress achieved in the implementation of activities of the Action Plan for the implementation of the 2016-2020 Programme (hereinafter: AP).

The goal is to consolidate and unify information on all identified Performance Indicators, including some of their key institutional and methodological aspects such as which institution collects data, how often, what is the equation for calculating the indicator, what is the verification source, what are the initial measurements for a given indicator and what are the target values ​​designed to measure the success of the implementation of reform activities. The measurement and monitoring of indicators should start with the second planned implementation report of the 2016-2020 Programme.

- SUSTAINABLE FISCAL FRAMEWORK, PUBLIC EXPENDITURE PLANNING AND BUDGETING

## 1.1     Medium-term budgetary framework, including fiscal strategy

### 1.1.1      PERFORMANCE INDICATOR 1 PASSPORT

| performance indicator | Share of new medium-term sector strategies that include estimates of implementation costs, including potential donor funding |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Sustainable fiscal framework, public expenditure planning and budgeting - Medium-term budgetary framework, including fiscal strategy Medium-term budgetary framework reflects the Government’s policy and strategic objectives and contains fixed spending limits for all first level spending units |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | In accordance with the PFM strategy, an activity planned is related to the development of the methodology for drafting strategic documents. According to the plan, one of the minimum requirements is predicted to include an estimate of the fiscal impact, indicating that after the adoption of appropriate legislation, the strategies will include the assessment of the fiscal impact. Data source for 2020 are the strategies adopted by the Government of Montenegro during 2020, which were submitted for opinion to the Ministry of Finance. |  |  |  |
| NAME OF DATA COLLECTION HOLDER | The Ministry of Finance and Social Welfare, Directorate for State Budget Tanja Musterović tanja.musterovic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA PUBLICATION | 1x per year, during Q1. |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | Account has been taken of the strategies adopted for a period of 2 years and over, and data, until their automatic calculation based on IT system database, will be calculated on the basis of information from the budget sectors on the assessment of the fiscal impact of the strategies which are submitted for opinion, that is, the Regulatory Impact Analysis. Data on the adopted strategies are taken over from the General Secretariat of the Government. The effect is measured on the basis of the data on the strategies adopted in the year concerned; strategies adopted in the previous period will not be the subject to consideration. Target value in 2020, and for years afterwards, which is provided in the value of 100%, means that every strategy that was adopted in 2020, will provide the estimate of the fiscal impact, while strategies adopted in the previous period should be considered if there is a need for changes and revisions of the Strategy. |  |  |  |
|  | FORMULA / EQUATION Number of adopted medium-term strategies that contain data on the total cost estimates for implementation in fiscal year X100 / The total number of medium-term strategies adopted in the fiscal year |  |  |  |
| BASELINE DATA | PV (2014): 60% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 80% | 85% | 90% | 100% |
| DATA ON VALUES ACHIEVED | 70% | 75% | 85% | 100% |

### 1.1.2      PERFORMANCE INDICATOR 2 PASSPORT

| performance indicator | Average deviation between MTBF budget ceilings and actual annual budget expenditure limits |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Sustainable fiscal framework, public expenditure planning and budgeting - Medium-term budgetary framework, including fiscal strategy Medium-term budgetary framework reflects the Government’s policy and strategic objectives and contains fixed spending limits for all first level spending units |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Official Gazette, Budget Law, (http://www.mf.gov.me/biblioteka/zakoni), Macroeconomic and Fiscal Policy Guidelines for the three-year period |  |  |  |
| NAME OF DATA COLLECTION HOLDER | The Ministry of Finance and Social Welfare, Directorate for State Budget Tanja Musterović tanja.musterovic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA PUBLICATION | 1 x per year, Q1 of the previous year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The Macroeconomic and Fiscal Policy Guidelines are used to define expenditure limits, which serve as the basis for the preparation of the Budget Law for the fiscal year. Fiscal Policy Guidelines are adopted annually for a period of three years. Limits are binding on the Budget Law for the first year and indicative for the second and third fiscal years. The Guidelines are used as an indication of the budgetary framework and limits on central government budget spending for the current budget, state fund budget, capital budget, budget reserves and budget expenditure limit for first level spending units, with the exception of debt and interest repayment costs, donation costs, co-financing costs and costs for financing material damage caused by natural disasters and other emergencies and unforeseen events. The expenditure limit for the corresponding year is compared with the amounts planned in the Budget Law for the corresponding year, e. g. if we ask for deviations in 2020, the data from the Budget Law for 2020 are compared with the data on limits from the 2019-2022 Guidelines. |  |  |  |
|  | FORMULA / EQUATION (amount according to the Budget Law - amount of expenditure limit) / Amount according to the Budget Law * 100 |  |  |  |
| BASELINE DATA | PV (2014): 9% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 7% | 6% | 5% | 5% |
| DATA ON VALUES ACHIEVED | 6% | 0.87% | 0.11% | 2.13% |

### 1.1.3      PERFORMANCE INDICATOR 3 PASSPORT

| performance indicator | Number of staff trained for top-down medium-term budget planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Sustainable fiscal framework, public expenditure planning and budgeting - Medium-term budgetary framework, including fiscal strategy Medium-term budgetary framework reflects the Government’s policy and strategic objectives and contains fixed spending limits for all first level spending units |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Ministry of Finance and Social Welfare, Directorate for State Budget and Spending Units, beneficiaries who attended the training, based on a database maintained by the Ministry of Finance and Social Welfare, Directorate for State Budget. The source of data is the Ministry of Finance and Social Welfare |  |  |  |
| NAME OF DATA COLLECTION HOLDER | The Ministry of Finance and Social Welfare, Directorate for State Budget Tanja Musterović tanja.musterovic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA PUBLICATION | 1 x per year, Q1 for the training delivered in the previous year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The Public Finance Management Reform Programme and Action Plan envisage training for multi-annual budget planning with the aim of better linking programme objectives to Government policies. The training is planned for the management level and the level of expert staff in institutions determined to be priorities, until 2020, when all institutions will be included. (President, Parliament, Judicial Bodies, Ministries and Independent Bodies). The performance indicator is measured on the basis of trainings completed in a calendar year, that is, the number of participants who attended the training. The trainings started with the trainings of the employees in the Directorate for State Budget in 2019, with the continuation during 2020. |  |  |  |
|  | FORMULA / EQUATION Number of persons who completed the training in accordance with a predefined program |  |  |  |
| BASELINE DATA | PV (2014): 0 |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 52 | 35 | 52 | 72 |
| DATA ON VALUES ACHIEVED | 0 | 0 | 17 | 100 |

## 1.2     Annual budgeting

### 1.2.1      PERFORMANCE INDICATOR 4 PASSPORT

| performance indicator | Share of first level budget organisations that provide comprehensive information with their annual budget requests |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Sustainable fiscal framework, public expenditure planning and budgeting - Annual budgeting |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Requests for budget funds submitted to the Budget Directorate during the budget planning procedure |  |  |  |
| NAME OF DATA COLLECTION HOLDER | The Ministry of Finance and Social Welfare, Directorate for State Budget Tanja Musterović tanja.musterovic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA PUBLICATION | 1x per year, after requests for budget funds were sent by spending units, that is, Q3 |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | A prerequisite for creating an efficient system for measuring the performance of budget programmes is the comprehensiveness of information submitted for budget planning for all programmes separately. In accordance with the Macroeconomic and Fiscal Policy Guidelines, the Ministry of Finance and Social Welfare sends expert instructions on budget preparation, with detailed instructions on financial and non-financial data. In 2020, during the preparation of the 2021 Draft Budget Law, budget requests were filled in and submitted electronically using the new IT system for budget planning in a predefined format, which the Ministry of Finance and Social Welfare was returning back to spending units until full completion and provision of quality information. Also, through meetings within the process of preparation and planning of the annual Budget Law, the Ministry of Finance and Social Welfare received additional information from the spending units considered during the preparation process, which makes the value of the performance indicator, observed overall, at a satisfactory level. |  |  |  |
|  | FORMULA / EQUATION Number of spending units providing comprehensive information / Total number of spending units X 100 |  |  |  |
| BASELINE DATA | PV (2014): 40% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 75% | 80% | 90% | 100% |
| DATA ON VALUES ACHIEVED | 70% | 80% | 90% | 100% |

### 1.2.2      PERFORMANCE INDICATOR 5 PASSPORT

| performance indicator | Level of performance information included in budget planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Sustainable fiscal framework, public expenditure planning and budgeting - Annual budgeting Create an efficient system for measuring the performance of budget programmes in order to increase the efficiency and transparency of public expenditure |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Law and Explanatory Note to the Budget Law for the fiscal year |  |  |  |
| NAME OF DATA COLLECTION HOLDER | The Ministry of Finance and Social Welfare, Directorate for State Budget Tanja Musterović tanja.musterovic@mif.gov.me phone number: 063262769 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | 1x per year, Q1 of the current for the previous year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The Public Finance Management Reform Programme envisages the definition of missions, objectives and descriptions of programmes and sub-programmes, while the definition of the performance indicator for the effectiveness of programmes and sub-programmes is envisaged by 2020. The legal basis is defined under the Law on Budget and Fiscal Responsibility, while the content and manner of preparation is defined by the Regulation. Increased level of information in the programme budget is given through the target values. Level 1 (2017) includes the developed programme structure for all budget users, including missions of spending units, defined descriptions and objectives of the programme; Level 2 (2019) includes an upgrade to the Level 1 with the definition of a set of performance indicators for pilot projects, while Level 3 (2020) includes a created set of performance indicators for all programmes in order to monitor the success in achieving the objectives. |  |  |  |
|  | FORMULA / EQUATION n/a |  |  |  |
| BASELINE DATA | PV (2014): Defined programme headings of all spending units |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | Level 1 | Level 1 | Level 2 | Level 3 |
| DATA ON VALUES ACHIEVED | Developed programme structure concerning headings of the programmes of all spending units | Developed programme structure concerning headings of the programmes of all spending units | Defined programme headings of all spending units | Defined headings of main programmes, programmes and subprogrammes |

### 1.2.3      PERFORMANCE INDICATOR 6 PASSPORT

| performance indicator | The number of staff trained for planning and monitoring expenditures in line with programme budgeting principles |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Sustainable fiscal framework, public expenditure planning and budgeting - Annual budgeting Create an efficient system for measuring the performance of budget programmes in order to increase the efficiency and transparency of public expenditure |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | The Ministry of Finance and Social Welfare, Directorate for State Budget |  |  |  |
| NAME OF DATA COLLECTION HOLDER | The Ministry of Finance and Social Welfare, Directorate for State Budget Tanja Musterović tanja.musterovic@mif.gov.me phone number: 063262769 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | 1x per year, Q1 of the current for the previous year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | In accordance with the Public Finance Management Reform Programme and the Action Plan, IPA II funds are planned to be used to organise trainings for employees of the Ministry of Finance and budget organisations that will be involved in the implementation of the programme budget. The training is planned for the management level and the expert staff in institutions determined to be priorities, until 2020, when all institutions will be included. The performance indicator is measured on the basis of trainings completed in one calendar year, that is, the number of participants who attended the training. During 2019, training for employees of the Directorate for State Budget was held, while in 2020, training for employees in budget spending units and other planned institutions was implemented, which will continue in 2021. |  |  |  |
|  | FORMULA / EQUATION The total number of employees who attended the trainings that began and ended during one calendar year |  |  |  |
| BASELINE DATA | PV (2014): 0 |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 20 | 35 | 70 | 130 |
| DATA ON VALUES ACHIEVED | 0 | 0 | 17 | 100 |

## 1.3     Capital budget

### 1.3.1      PERFORMANCE INDICATOR 7 PASSPORT

| performance indicator | Level of detail in public presentation of capital budget |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Sustainable fiscal framework, public expenditure planning and budgeting - Capital budget Improve capital budget planning and progress reporting for capital projects |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | At present, the source of data is the annual Budget Law and the Official Gazette. Presentation of the capital budget will be in accordance with the project for improving the planning and reporting on the implementation of the capital budget, that is, the data will be presented on the website of the Ministry of Finance and Social Welfare in the form of excel tables and corresponding diagrams. The register will present in more detail the data on the capital budget from the annual budget law. www.mf.gov.me |  |  |  |
| NAME OF DATA COLLECTION HOLDER | The Ministry of Finance and Social Welfare, Directorate for State Budget Slobodanka Burić slobodanka.buric@mif.gov.me Phone number: 063202933 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | 1x per year, in Q1 |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | Capital budget is an integral part of the annual Budget Law and contains an overview of capital projects to be implemented the next fiscal year. In order to implement a comprehensive reform of the budgeting process, it is necessary to improve the process of capital projects planning by improving the presentation and coverage of information on planned projects in the budget, as well as reports on their implementation. In accordance with the Public Finance Management Reform Programme, IPA II funds will be used to establish a public register of all projects financed under the capital budget. Namely, in the first phase, the plan is to present all individual projects, while in the following period, projects will be separated by phases of implementation (preparation phase and construction phase). At this moment, a detailed overview of all individual projects is provided through the explanatory note of the Budget Law, while the improved presentation of capital projects in the coming period, through the improved presentation of the Budget Law, will be given in a public presentation on the website of the Ministry of Finance and Social Welfare. Increased level of information in the public presentation of the capital budget is provided through target values. Level 1 (2017 and 2018) includes: Overview of all individual projects implemented in the budget year. Level 2 (2019) includes: Overview of all individual projects implemented in the budget year and the implementation of selected pilot projects in phases. Level 3 (2020) includes: Overview by individual projects and phases of project implementation |  |  |  |
|  | FORMULA / EQUATION n/a |  |  |  |
| BASELINE DATA | PV (2014): Projects in the capital budget presented grouped by areas (education, health, culture, sports…) |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | Level 1 | Level 1 | Level 2 | Level 3 |
| DATA ON VALUES ACHIEVED | Projects in the Budget Law are presented grouped by areas, while in the Explanatory Note of the Law they are presented by individual projects | Projects in the Budget Law are presented grouped by areas, while in the Explanatory Note of the Law they are presented by individual projects | Projects in the Budget Law are presented grouped by areas, while in the Explanatory Note of the Law they are presented by individual projects | View by individual projects |

### 1.3.2      PERFORMANCE INDICATOR 8 PASSPORT

| performance indicator | Actual capital spending in the current year as a share of the capital budget plan |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Sustainable fiscal framework, public expenditure planning and budgeting - Capital budget Improve capital budget planning and progress reporting for capital projects |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Official Gazette, Law on Final Budget Accounts, Budget Law for the fiscal year http://www.mf.gov.me/biblioteka/zakoni), |  |  |  |
| NAME OF DATA COLLECTION HOLDER | The Ministry of Finance and Social Welfare, Directorate for State Budget Slobodanka Burić slobodanka.buric@mif.gov.me Phone number: 063202933 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | 1x per year, in Q2 of the current year, after the adoption of the Law on the Final Budget Accounts. In Q1, we may have preliminary data, that is, data that are not official. |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | Capital budget is an integral part of the annual Budget Law, the implementation of which is the responsibility of the Transport Directorate and the Public Works Directorate in cooperation with the Ministry of Finance and Social Welfare. Data on the actual costs of the capital budget are contained in the Law on the Final Budget Accounts, while the amount of planned funds is defined under the Budget Law for the respective year. The performance indicator is calculated as a share of the actual expenditure of the capital budget in accordance with the Law on the Final Budget Accounts for the fiscal year in the amount of the capital budget planned by the Budget Law for the fiscal year. |  |  |  |
|  | FORMULA / EQUATION Amount of actual spending in the capital budget Amount of capital budget planned by the Budget Law x100=% |  |  |  |
| BASELINE DATA | PV (2014): 70% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 80% | 83 | 86% | 90% |
| DATA ON VALUES ACHIEVED | 82 | 91% 111% | 92% 112.3% | 180.60% 107.6% |

## 1.4     Improving models for macroeconomic projections

### 1.4.1      PERFORMANCE INDICATOR 9 PASSPORT

| performance indicator | Staged implementation of the upgraded model for macroeconomic projections and structural reform impacts |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Sustainable fiscal framework, public expenditure planning and budgeting - Upgrade the model for macroeconomic projections Improved projections of macroeconomic indicators as the basis for public finance projections and drafting the Budget Law, as well as other significant strategic documents. |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Data for indicator monitoring are collected at the national level, through the implementation of projections incorporated in documents of national importance: Economic Reform Programme; Macroeconomic and Fiscal Policy Guidelines: Updated Macroeconomic and Fiscal Indicator Projections |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare, Directorate for Economic Policy and Development Iva Vuković, Director General of the Directorate for Economic Policy and Development iva.vukovic@mif.gov.me Phone: 069820921 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Each of these documents is published once a year, and refers to the medium term. |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | A new macroeconomic model has been developed based on an econometric approach and the economy is viewed through four sectors: real, external, monetary and fiscal. The model will contain mechanisms that enable the inclusion of long-term effects of structural policies on aggregate supply, as well as the short-term impact on demand. The developed Montenegrin macroeconomic model will consist of: 1) a forecasting module, which will be used to generate projected values of macroeconomic indicators for the purpose of developing the baseline scenario; 2) impact assessment modules to be used for policy simulations based on different policy scenarios (what if analysis) |  |  |  |
|  | FORMULA / EQUATION n/a |  |  |  |
| BASELINE DATA | PV (2014): The existing model used in the Directorate for Economic and Development Policy is based on the financial programming model, and the projection of certain parameters is based on expert assessment. |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | Analysis and upgrade of the existing macro-economic projections model | New model built for projections of macroeconomic indicators and impact of structural reforms and trained employees | Preconditions for the use of the new model by employees in the Directorate for Economic Policy and Development have been met | Full implementation and staff competent to use the new model |
| DATA ON VALUES ACHIEVED | Target value for 2017 met | Target value for 2018 met | Preconditions for the use of the new model by employees in the Directorate for Economic Policy and Development have been met | The project has not been fully implemented due to the epidemiological situation, implementation is expected by the end of 2022. |

### 1.4.2      PERFORMANCE INDICATOR 10 PASSPORT

| performance indicator | The difference between actual and projected real GDP growth rate |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Sustainable fiscal framework, public expenditure planning and budgeting - Upgrade the model for macroeconomic projections Improved projections of macroeconomic indicators as the basis for public finance projections and drafting the Budget Law, as well as other significant strategic documents. At the same time, it will lead to compliance with Chapter III of the EU Directive 2011/85 concerning forecasting. The new model will allow minimising the difference between the plan and the implementation, and thus will contribute to the creation of preconditions for more realistic planning of the revenue side of the budget, which largely depends on the growth of economic activity. |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Data for monitoring indicators are collected at the national level. The estimate for the current year is published in the document Macroeconomic and Fiscal Indicator Forecasting. The implementation is published by the Statistical Office on the website: http://monstat.org/cg/page.php?id=166&pageid=19 |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare, Iva Vuković, Director General of the Directorate for Economic Policy and Development iva.vukovic@mif.gov.me Phone: 069820921 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Once a year An updated estimate is published in October The implementation is published in September of the current year for the previous year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | GDP is estimated on the basis of a new econometric model based on the principles of the System of National Accounts (SNA 2008) and the European System of National Accounts (ESA2010). Also, the realisation is based on the mentioned methodologies. ESA 2010 defines the concepts, definitions and accounting rules that apply to the calculation of national accounts data in order to achieve international comparability. ESA 2010 is a set of interconnected and consistent tables, accounts, classifications and balance sheets that represent the statistical and documentary basis for monitoring economic activities. Gross domestic product (GDP) measures the total value of goods and services provided by resident institutional units. |  |  |  |
|  | FORMULA / EQUATION X p.p. = achieved real growth rate - projected real growth rate |  |  |  |
| BASELINE DATA | PV (2014): 1.8 p.p. |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | Less than 0.5 p.p. | Less than 0.3 p.p. | Less than 0.2 p.p. | Less than 0.2 p.p. |
| DATA ON VALUES ACHIEVED | Target value for 2017 is not met | 0.8 p.p. | Target value for 2019 partly met, further recommendations given | The target value of the forecast could not be achieved due to market disruptions and external shocks |

# 2.    BUDGET EXECUTION

## 2.1     Revenue collection- Tax Administration

### 2.1.1      PERFORMANCE INDICATOR 11 PASSPORT

| performance indicator | Share of submitted e-returns (Profit tax, VAT) in comparison to total number of submissions |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - Revenue collection - Tax Administration Strengthening the administrative capacity of the Tax Administration of Montenegro to increase tax collection thus contributing to maximising the government’s fiscal revenues |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Data for monitoring indicators are collected at the national level https://eprijava.tax.gov.me/TaxisPortal (only financial statements can be viewed, not the statistics on the growth or decline of submitted e-returns) - Annual Report of the Tax Administration: www.poreskauprava.gov.me - Internal quarterly and semi-annual reports of the competent department for e-returns (not published on the website) |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Revenue & Customs Administration Phone: 020 - 448 -232 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Quarterly |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | For the 2017 calendar year, data are given for the 2016 fiscal year when it comes to income, because the due date is 31 March 2017, and when it comes to VAT, data are given for accounting periods becoming due in 2017. VAT is submitted up to 15th day of the month for the previous month. |  |  |  |
|  | FORMULA / EQUATION The total number of electronically submitted VAT returns delivered for the accounting periods of the calendar year Total number of submitted VAT returns for accounting periods of the calendar year x100 Total number of electronically submitted income tax returns for the accounting periods of the calendar year Total number of submitted income tax returns for the accounting periods of the calendar year |  |  |  |
| BASELINE DATA | PV (2014): 27% not in total because it is a paper way of submission |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | VAT 50% INCOME 95% | VAT 65% INCOME 97% | VAT 75% INCOME 97% | VAT 80% INCOME 99% |
| DATA ON VALUES ACHIEVED | VAT 50% INCOME 95% | VAT 70% INCOME 99% | VAT 77.37 % INCOME 99.5% | VAT 89% INCOME 99.6% |

### 2.1.2      PERFORMANCE INDICATOR 12 PASSPORT

| performance indicator | EU VAT regulations concerning EU common market successfully implemented |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - Revenue collection - Tax Administration Strengthening the administrative capacity of the Tax Administration of Montenegro to increase tax collection thus contributing to maximising the government’s fiscal revenues |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | At the national and international level -Official Gazette of Montenegro - Official Gazette of Montenegro - Project progress report (quarterly): www.poreskauprava.gov.me - EC report - Preparation of benchmark assessment reports - DG TAXUD report -Reports from the sessions of the Government published on the website of the Government of Montenegro on the adopted proposals: www.gov.me |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Revenue & Customs Administration Phone: 020 - 448 -232 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Quarterly at the request of the European Delegation to Montenegro |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | PPCG document showing the status of compliance 1. Status a) Strategic Framework, b) Legislative framework c) Administrative Cooperation and Mutual Assistance. 2. Plans and needs for all the three above areas 3. Administrative Framework-New Institutions. The level of implementation of plans and needs given in the document is monitored through reporting (the document can be found on the website of the Ministry of Foreign Affairs). www.mvp.gov.me The PPCG document sets deadlines for the adoption of CELEX. This document contains everything, on the basis of which the degree of harmonisation of tax regulations by years can be measured, related to three basic laws: the Law on VAT, the Law on Income Tax and the Law on Tax Administration. -Degree of legislative harmonisation with the acquis, based on the assessment at the beginning of the implementation of IPA 2014 draft versions of prepared laws and bylaws for adoption in order to further harmonise them Basic directives when it comes to direct and indirect taxation: -Directive 2011/16/EU as regards mandatory automatic exchange of information in the field of taxation; VAT Directive; Directive 2006/112/EC common system of VAT as amended; Council Directive 2008/9/EC as amended with regard to VAT refunds. Inome tax directives; Directive 2003/49/EU on a common system of taxation applicable in different Member States; Directive 2011/96/EU on a common system of taxation applicable to a Directive of the Council of the European Union; Council Directive 2009/133/EC. |  |  |  |
|  | FORMULA / EQUATION n/a |  |  |  |
| BASELINE DATA | PV (2014): screening process completed |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | Negotiations in Chapter 16 - Taxation open, activities undertaken for the purpose of harmonisation (assessment of the relevance of the CELEX, responsible persons) | -Law on Amendments to the Law on Corporate Income Tax (Q4 2018) -Law on Amendments to the Law on Tax Administration (Q42018) | -Law on Amendments to Value Added Tax (Q4 2019) | Implemented planned activities under the Accession Programme - Chapter 16. Taxes (PPCG document) |
| DATA ON VALUES ACHIEVED | - A certain degree of legislative harmonisation has been achieved, a higher degree has been achieved in the field of VAT; - harmonisation in the area of income tax (transfer prices) remains to be implemented until the end of Q4 - Amendments to the Law on Tax Administration concerning articles related to administrative cooperation and mutual assistance (until Q4). | Drafts have been prepared of the Law on Amendments to the Law on Corporate Income Tax, as well as the Law on Amendments to the Law on Tax Administration in order to further harmonise with EU legislation, especially in the area of administrative cooperation and exchange of information. | Higher degree of compliance compared to the previous year; All proposed amendments to the law adopted by the Legislative Committee. After which they were submitted to the EC for an opinion. | Higher degree of compliance compared to the previous year |

### 2.1.3 PERFORMANCE INDICATOR 13 PASSPORT

| performance indicator | Share of collected tax revenue compared to the planned tax revenue in the annual budget law |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - Revenue collection - Tax Administration Strengthening the administrative capacity of the Tax Administration of Montenegro to increase tax collection thus contributing to maximising the government’s fiscal revenues |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Data collection at the national level Annual Budget Plan of the Ministry of Finance and Social Welfare based on the Budget Law: www.mif.gov.me |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Revenue & Customs Administration Phone: 020 - 448 -232 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Quarterly, annually |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) |  |  |  |  |
|  | FORMULA / EQUATION Tax revenues collected during the fiscal yearPlanned tax revenues in the annual budget law x100 |  |  |  |
| BASELINE DATA | PV (2014): 100% (2015): 100% (2016): 100% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 100% | 100% | 100% | 100% |
| DATA ON VALUES ACHIEVED | More than 100% of the planned (24 million above the plan for 2017) and 34 million above the implementation in 2016. | Above the plan for 2018, 73 million or 117 million above the implementation from 2017. | Above the plan for 2019, 80 million above the plan | 65 mil. euros above the plan according to the budget revision, and 79 mil. euros (7%) below the implementation from 2019. |

### 2.1.4 PERFORMANCE INDICATOR 14 PASSPORT

| performance indicator | Share of collected VAT revenues in GDP |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - Revenue collection - Tax Administration Strengthening the administrative capacity of the Tax Administration of Montenegro to increase tax collection thus contributing to maximising the government’s fiscal revenues |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Data collection at the national level -Reports on the website of the Ministry of Finance and Social Welfare: www.mif.gov.me Within the Directorate for Economic Policy and Development -2017-2020 Fiscal Strategy where new projections are given including fiscal consolidation measures: www.mif.gov.me |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Revenue & Customs Administration Phone: 020 - 448 -232 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Quarterly |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) |  |  |  |  |
|  | FORMULA / EQUATION Total VAT Tax revenues in fiscal year / GDP x 100 |  |  |  |
| BASELINE DATA | PV (2014): 13.5% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 13.5% | 14.7% | 14;6% | 14.6% |
| DATA ON VALUES ACHIEVED | 13.0% | 13.6% | 14.44% | 12.6% |

## 2.2     Revenue collection - Customs Administration

### 2.2.1      PERFORMANCE INDICATOR 15 PASSPORT

| performance indicator | Change in revenue collection compared to the previous year |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - Revenue collection - Tax Administration Strengthen Customs Administration capacities for ensuring efficient revenue collection, customs area safety and protection of the society, as well as for creating an environment more conducive to business operation |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Report on the work of the Customs Administration http://www.upravacarina.gov.me/uprava/Slobodan_pristup_informacijama |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Revenue & Customs Administration Phone: 020 - 448 -232 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Report on the work of the Customs Administration in Q1 of the current year for the previous year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The performance indicator shows the rate of change in the collection of revenues of the Customs Administration in the reporting year compared to the previous year. |  |  |  |
|  | FORMULA / EQUATION Realised revenue collection in the reporting year / Realised revenue collection in the previous year X 100 |  |  |  |
| BASELINE DATA | PV (2014): 15% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 17.64 % | 5% | 5% | 5% |
| DATA ON VALUES ACHIEVED | 17.64 % | 11.03% | 5.17% | -18% |

### 2.2.2      PERFORMANCE INDICATOR 16 PASSPORT

| performance indicator | Change in revenue collection compared to the previous year |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - Revenue collection - Tax Administration Strengthen Customs Administration capacities for ensuring efficient revenue collection, customs area safety and protection of the society, as well as for creating an environment more conducive to business operation |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Report on the work of the Customs Administration http://www.upravacarina.gov.me/uprava/Slobodan_pristup_informacijama |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Revenue & Customs Administration Phone: 020 - 448 -232 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Report on the work of the Customs Administration in Q1 of the current year for the previous year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The performance indicator refers to the adoption of regulations related to the harmonisation of customs and excise legislation with EU legislation. |  |  |  |
|  | FORMULA / EQUATION Number of harmonised regulations adopted in the reporting year. |  |  |  |
| BASELINE DATA | PV (2014): Screening process for Chapters 29 Customs Union and 16 Taxation completed |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | Law on Amendments to the Customs Law; Law on Amendments to the Law on Excise Duties; Customs Tariff Regulations for 2017; Regulations on amendments to the Regulation for the implementation of the customs law. | Adoption of 3 regulations | Adoption of 2 regulations | Adoption of 2 regulations |
| DATA ON VALUES ACHIEVED | Adoption of 4 regulations | Adoption of 3 regulations | Adoption of 3 regulations | Adoption of 1 regulation |

## 2.3     Revenue collection - Public procurement

### 2.3.1      PERFORMANCE INDICATOR 17 PASSPORT

| performance indicator | Level of harmonisation and completeness of the procurement framework in line with the EU acquis |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - Revenue collection – Public procurement Align the public procurement system with the pertinent EU acquis with a view of setting an efficient, transparent and competitive public procurement system in Montenegro. |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Directives 23/2017, 24/2017 and 25/2017 http://www.ujn.gov.me/category/direktive/ Law on Public Procurement ("Official Gazette of Montenegro", No. 042/11 of 15/08/2011, 057/14 of 26/12/2014, 028/15 of 03/06/2015, 042/17 of 30/06/2017) Bylaws http://www.ujn.gov.me/category/nova-podzakonska/ Public Procurement System Development Strategy http://www.ujn.gov.me/strategija-razvoja-sistema-javnih-nabavki-u-crnoj-gori-za-period-2016-2020-godine/ Progress reports http://www.ujn.gov.me/category/eu-integracije/ |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare Dijana Vukčević, Department for Monitoring Public Procurement Procedures and Management of Electronic Public Procurement vukcevic.dijana@gmail.com Phone: 067373384 Sanja Poleksić, Department for Professional Training, Development and International Cooperation in the Field of Public Procurement s.p@t-com.me Phone: 067400191 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Semi-annually through the report of the coordinating body for the implementation of the AP strategy for the development of the public procurement system for Q1 and Q3 http://www.ujn.gov.me/category/koordinaciono-tijelo/ |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | September-October: The PPD coordinates the analysis, and, if necessary, the revision of the AP for the next year, in which all relevant parties participate; December: If necessary, the Government of Montenegro adopts a revised AP for next year. Using the AP as a means of monitoring and implementation, the Coordinating Body will report to the Government on a semi-annual basis on the progress made in the implementation, according to the following dynamics: January: PPD collects information on the execution of the plan for the previous year from all relevant parties in charge of the implementation of the AP; February: PPD prepares a report on the implementation of the AP and submits it to the Government. The 2016-2020 Strategy for the Development of the Public Procurement System in Montenegro has been developed in a way that follows all the activities necessary for the closure of the Negotiating Chapter 5 Public Procurement, and the AP proceeds from the same. List of directives: 1. Directive 2014/24/EU of the European Parliament and of the Council of 26 February 2014 on public procurement and repealing Directive 2004/18/EC (OJ L 94, 28.3.2014), as last amended by Commission Delegated Regulation (EU) 2017/2365 of 18 December 2017 amending Directive 2014/24/EU of the European Parliament and of the Council as regards application thresholds for contract award procedures (OJ L-337 of 19.12.2017); 2. Directive 2014/25/EU of the European Parliament and of the Council of 26 February 2014 on procurement by entities operating in the water, energy, transport and postal services sectors and repealing Directive 2004/17/EC (OJ 2014 L 94, 28.3.2014), as last amended by Commission Delegated Regulation (EU) 2017/2364 of 18 December 2017 amending Directive 2014/25/EU of the European Parliament and of the Council as regards application thresholds for contract award procedures (OJ L-337 dated 19/12/2017); 3. Council Directive 89/665/EEC of 21 December 1989 on the coordination of the laws, regulations and administrative provisions relating to the application of review procedures to the award of public supply contracts and public works contracts (OJ L 395, 30/12/1989), last amended by Directive 2014/23/EU of the European Parliament and of the Council of 26 February 2014 on the award of concession contracts (OJ L 94, 28/3/2014); 4. Council Directive 92/13/EEC of 25 February 1992 coordinating the laws, regulations and administrative provisions relating to the application of Community rules on the procurement procedures of entities operating in the water, energy, transport and telecommunications sectors (OJ L 76, 23/3/1992), as last amended by Directive 2014/23/EU of the European Parliament and of the Council of 26 February 2014 on the award of concession contracts (OJ L 94, 28/3/2014); 5. Articles 2, 12 and 13 of Directive 2009/81/EC of the European Parliament and of the Council of 13 July 2009 on the coordination of procedures for the award of certain works contracts, supply contracts and service contracts by contracting authorities or entities as well as amendments to Directives 2004/17/EC and 2004/18/EC (OJ L 216, 20/8/2009) and Commission Regulation (EU) 2017/2367 of 18 December 2017, amending Directive 2009/81/EC of the European Parliament and of the Council as regards application thresholds for contract award procedures (OJ L-337 of 19/12/2017). |  |  |  |
|  | FORMULA / EQUATION |  |  |  |
| BASELINE DATA | PV (2014): Open negotiations in the negotiating chapter 5. Public procurement |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | Open negotiations in the negotiating chapter 5. | Further harmonisation with the package of Directives from 2014 in this area | Further harmonisation with the package of Directives from 2014 in this area (implementation of the new Law on Public Procurement, introduction of the electronic system of public procurement ...) | Implemented planned activities under the Accession Programme - Chapter 5. |
| DATA ON VALUES ACHIEVED | Open negotiations in the negotiating chapter 5. | Open negotiations in the negotiating chapter 5. | Adoption of the new Law on Public Procurement by implementing the provisions in accordance with the new directives | A new Law on Public Procurement was adopted, which came into force on July 7, 2020 |

### 2.3.2      PERFORMANCE INDICATOR 18 PASSPORT

| performance indicator | Average number of bidders participating per procurement procedure |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - Revenue collection – Public procurement Align the public procurement system with the pertinent EU acquis with a view of setting an efficient, transparent and competitive public procurement system in Montenegro. |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Annual Report on conducted public procurement procedures prepared by the Public Procurement Directorate: http://www.ujn.gov.me/category/izvjestaji/ |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare Dijana Vukčević, Department for Monitoring Public Procurement Procedures and Management of Electronic Public Procurement vukcevic.dijana@gmail.com Phone: 067373384 Sanja Poleksić, Department for Professional Training, Development and International Cooperation in the Field of Public Procurement s.p@t-com.me Phone: 067400191 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | The Public Procurement Directorate submits the Annual Report on the conducted public procurement procedures to the Government of Montenegro for adoption by May 31 of the current year for the previous year. |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The performance indicator shows the number of bids received under the public procurement procedure, which means that a higher value of the performance indicator indicates greater competitiveness. |  |  |  |
|  | FORMULA / EQUATION number of bids received during one calendar year / total number of procedures in that calendar year |  |  |  |
| BASELINE DATA | PV (2014): 3.52 bids per tender http://www.ujn.gov.me/2015/06/godisnji-izvjestaj-o-javnim-nabavkama-u-crnoj-gori-za-2014-godinu/ |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 3.2 | 3.48 | 3.58 | 3.8 |
| DATA ON VALUES ACHIEVED | 2.65 | 3.14 | 2.01 | 2.27 |

### 2.3.3      PERFORMANCE INDICATOR 19 PASSPORT

| performance indicator | Share of e-procurement of all procurement contracts awarded during the year. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - Revenue collection – Public procurement Align the public procurement system with the pertinent EU acquis with a view of setting an efficient, transparent and competitive public procurement system in Montenegro. |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | The tender procedure for the selection of the most favorable bidder for the introduction of the electronic public procurement system in Montenegro is underway. http://www.mif.gov.me/rubrike/CFCU_tenderi/Tenderi/Otvoreni/156772/Klariifikacije-za-ugovor-o-uslugama-Implementacija-Elektronskog-sistema-javnih-nabavki.html http://www.ujn.gov.me/category/izvjestaji/ |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare Dijana Vukčević, Department for Monitoring Public Procurement Procedures and Management of Electronic Public Procurement vukcevic.dijana@gmail.com Phone: 067373384 Sanja Poleksić, Department for Professional Training, Development and International Cooperation in the Field of Public Procurement s.p@t-com.me Phone: 067400191 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Daily |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The e - system supports the complete public procurement procedure from the publication of electronic submission of bids to the award of the contract. Please note that the use of the electronic system will be mandatory for all those taxpayers obliged to apply the Law on Public Procurement. |  |  |  |
|  | FORMULA / EQUATION Number of total contracts awarded via e-system in one calendar year / total number of contracts awarded in one calendar year X 100 |  |  |  |
| BASELINE DATA | PV (2014): 0% (There is no electronic public procurement system) |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 0% (There is no electronic public procurement system) | Selection of the most favorable bidder | 30% | 80% |
| DATA ON VALUES ACHIEVED | 0% (There is no electronic public procurement system) | The project of creating an e-public procurement system has started | Pilot phase of the e-system | System established, in-house testing completed and trainings for users of the electronic public procurement system started |

## 2.4     State aid reform

### 2.4.1      PERFORMANCE INDICATOR 20 PASSPORT

| performance indicator | The number of state aid grantors and beneficiaries, private sector representatives and judges attending state aid seminars and training events |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - State Aid Reform Increase efficiency, effectiveness and transparency of state aid control in Montenegro to be EU-compliant. |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Archives of the Competition Protection Agency, also archives of the organisers of the project ‘Improvement and strengthening of the institutional and legal framework in the field of state aid and public procurement’, which is envisaged under the IPA 2014-2020 programme. |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Competition Protection Agency Ivana Paprenica, drzavna.pomoc@azzk.me Phone: 063262830 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | After the seminar, a cross-section can be made at the end of each calendar year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | Final number of seminar participants in one calendar year. The organiser of the project ‘Improvement and strengthening of the institutional and legal framework in the field of state aid and public procurement’, which is foreseen under the IPA 2014-2020 programme, will organise seminars on state aid for different groups of state aid grantors and beneficiaries, aimed at raising public awareness on the issue of state aid (refers to grantors and users of state aid, representatives of the private sector and judges). The performance indicator is the total number of people who attended the seminars that ended during one calendar year. |  |  |  |
|  | FORMULA / EQUATION n/a |  |  |  |
| BASELINE DATA | PV (2014):50 |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 50 | 30 | 60 | 100 |
| DATA ON VALUES ACHIEVED | 0 | 0 | 56 | 124 |

### 2.4.2      PERFORMANCE INDICATOR 21 PASSPORT

| performance indicator | The share of staff of the State Aid Division and the Commission for State Aid Control undergoing training with a view to strengthening the legal framework, reducing the level of illegal state aid and conducting ex-post controls |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - State Aid Reform Increase efficiency, effectiveness and transparency of state aid control in Montenegro to be EU-compliant. |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Archives of the Competition Protection Agency |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Competition Protection Agency Ivana Paprenica, drzavna.pomoc@azzk.me Phone: 063262830 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Cross-section can be made at the end of each calendar year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The State Aid Department currently has 6 employees, the Council of the Competition Protection Agency, has 3 members. The topic of seminars and trainings is exclusively state aid. |  |  |  |
|  | FORMULA / EQUATION Number of people in the State Aid Division + members of the Council of the Competition Protection Agency who attended professional seminars (completed) during the calendar year / Total number of people in the State Aid Division + members of the Council of the Competition Protection Agency during the calendar year X 100 |  |  |  |
| BASELINE DATA | PV (2014):30% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 30% | 50% | 70% | 80% |
| DATA ON VALUES ACHIEVED | 33% | 0% | 70% | 80% |

### 2.4.3      PERFORMANCE INDICATOR 22 PASSPORT

| performance indicator | Number of ex-officio cases closed |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - State Aid Reform Increase efficiency, effectiveness and transparency of state aid control in Montenegro to be EU-compliant. |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Website of the Competition Protection Agency http://www.azzk.me/novi/joomlanovi/ |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Competition Protection Agency Ivana Paprenica, drzavna.pomoc@azzk.me Phone: 063262830 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Cross-section can be made at the end of each calendar year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The level of information of institutions on the obligation to report state aid is considered better if the performance indicator is declining (which means that the institutions are more informed on the obligation to report state aid), i.e. institutions notify State Aid Commission/Agency/before the moment of award (there is no need to open an ex officio process). |  |  |  |
|  | FORMULA / EQUATION Number of completed ex officio cases during one calendar year |  |  |  |
| BASELINE DATA | PV (2014):5 |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 3 | Up to 2 | Up to 2 | Up to 1 |
| DATA ON VALUES ACHIEVED | (0) In 2017, no ex-officio case was initiated | (0) In 2018, no ex-officio case was initiated | (0) (2 ex-officio cases have been opened, we expect them to close in the following period) | (0) (5 ex-officio cases opened, closure expected in the coming period) |

### 2.4.4      PERFORMANCE INDICATOR 23 PASSPORT

| performance indicator | Number of legal acts, analysed and evaluated by the department (state aid applications). |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - State Aid Reform Increase efficiency, effectiveness and transparency of state aid control in Montenegro to be EU-compliant. |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Website of the Competition Protection Agency http://www.azzk.me/novi/joomlanovi/ |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Competition Protection Agency Ivana Paprenica, drzavna.pomoc@azzk.me Phone: 063262830 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Upon completion of the cases, they are immediately published on the website of the Competition Protection Agency |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The factual situation concerning the number of analysed state aid reports during one calendar year, a slight increase may be accompanied by an increase in the level of awareness of institutions on the obligation to report state aid. The Council of the Agency makes decisions in the form of decisions and opinions. |  |  |  |
|  | FORMULA / EQUATION Number of legal acts analysed and evaluated by the Division during one calendar year |  |  |  |
| BASELINE DATA | PV (2014): 11 |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 20 | Up to 20 | Up to 23 | Up to 25 |
| DATA ON VALUES ACHIEVED | 14 | 22 | 35 | 41 |

## 2.5     Public Debt Management, Debt Analysis, Cash Management and Foreign Relations Department Reform

### 2.5.1      PERFORMANCE INDICATOR 24 PASSPORT

| performance indicator | Public debt servicing costs as a share of GDP |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - Public Debt Management, Debt Analysis, Cash Management and Foreign Relations Department Reform Better public debt monitoring and reporting, definition and adoption of clear debt management procedures and debt analysis, cash management and debt repayment transactions management. |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | http://www.mf.gov.me/rubrike/drzavni-dug/ The data are published on the MoF website as part of the Public Debt Report. The Public Debt Report shows the annual debt service costs, as well as the GDP used. |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare Katarina Živković, Head of the State Treasury Directorate Katarina.zivkovicc@mif.gov.me Phone: 020 / 202-167 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Once a year, in the second quarter of the previous calendar year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The Ministry of Finance and Social Welfare, in accordance with the Law on Budget and Fiscal Responsibility, has the authority to pay interest on the basis of the government debt from the funds kept in the consolidated treasury account. The performance indicator serves as an indicator of the debt cost relative to GDP. Total amount of interest in the fiscal year, from 01/01 to 31/12, is calculated based on the existing debt and the estimate of future indebtedness. Note: This performance indicator contains variables that are not in themselves under the control of the State Treasury Directorate. The trend of variable interest rates depends on market trends, while the GDP trend is influenced by a number of factors over which the State Treasury Directorate has no influence. |  |  |  |
|  | FORMULA / EQUATION Amount of interest paid / GDP X 100 |  |  |  |
| BASELINE DATA | PV (2014): 2.2% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 2.5 % | 1.9 % | 2.0 % | 2.3 % |
| DATA ON VALUES ACHIEVED | 2.3% | 2.1% | 2.2% | 2.64% |

### 2.5.2      PERFORMANCE INDICATOR 25 PASSPORT

| performance indicator | Difference between planned and achieved level of public debt |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Budget execution - Public Debt Management, Debt Analysis, Cash Management and Foreign Relations Department Reform Better public debt monitoring and reporting, definition and adoption of clear debt management procedures and debt analysis, cash management and debt repayment transactions management. |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | http://www.mf.gov.me/rubrike/drzavni-dug/ The data are published on the MoF website as part of the Public Debt Report. The Public Debt Report shows the annual debt service costs, as well as the GDP used. |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare Katarina Živković, Head of the State Treasury Directorate Katarina.zivkovicc@mif.gov.me Phone: 020 / 202-167 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Once a year, in Q2 of the previous calendar year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The Ministry of Finance and Social Welfare, in accordance with the Law on Budget and Fiscal Responsibility, prepares and publishes a report on public debt. The performance indicator serves as an indicator of the ratio between the realised level of public debt and the planned public debt for a given year. Public debt is calculated on the basis of the balance of foreign debt, internal debt, debt of state-owned companies and debt of local self-government. Note: The trend of this performance indicator is conditioned by the number of factors that are largely beyond the control of the State Treasury Directorate, such as the need to finance the budget in a given year and other factors. |  |  |  |
|  | FORMULA / EQUATION Total debt amount / planned debt amount X 100 |  |  |  |
| BASELINE DATA | PV (2014): 1.5% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 1.5% | 1.5% | 1.5% | 1.5% |
| DATA ON VALUES ACHIEVED | Public debt is 3.2% lower than planned | Public debt is 3.07% higher han planned | Realised difference in gross public debt 16.6% | Realised difference in gross public debt 16% |

# 3.    Public Internal Financial Control Development

## 3.1     Managing public finances in an efficient, economical, effective and transparent way by all spending units

### 3.1.1      PERFORMANCE INDICATOR 26 PASSPORT

| performance indicator | The percentage of ministries that formally delegated decision-making responsibilities and authorities to the line managers |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Public Internal Financial Control Development - Managing public finances in an efficient, economical, effective and transparent way by all spending units |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Annual reports on the implementation of planned activities on the establishment and development of financial management and control systems Decisions delegating powers and responsibilities to directors of management boards and general directors for defined goals |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare Nina Blečić Contact Email: nina.blecic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Once a year, during the adoption of the Consolidated Report, which is published on the website of the Government of Montenegro, after the adoption, by the end of Q2 of the current year. |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The performance indicator refers to the ministries where the directors of administrations and directors general are delegated responsibility through decisions for the defined goals and authority to manage the determined budgets for their implementation. |  |  |  |
|  | FORMULA / EQUATION Ratio between the number of ministries that delegated authorities and the total number of ministries x 100 |  |  |  |
| BASELINE DATA | PV (2014): 6.25% 2015: 6.3% 2016: 6.3% (Report: 2016: 22.22%) |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 30% | 16% | 50% | 90% |
| DATA ON VALUES ACHIEVED | 11.11% | 18% | 12% | 8.3% |

### 3.1.2      PERFORMANCE INDICATOR 27 PASSPORT

| performance indicator | Percentage of the budget users on central and local level submitting annual FMC reports |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Public Internal Financial Control Development - Managing public finances in an efficient, economical, effective and transparent way by all spending units |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Annual reports on the implementation of planned activities on the establishment and development of financial management and control systems Data can be downloaded at: www.gov.me/ResourceManager/FileDownload.aspx?rId=279138&rType=2 |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare Svetlana Karadžić Kontakt Email: svetlana.karadzic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Once a year, during the adoption of the Consolidated Report, which is published on the website of the Government of Montenegro, after the adoption, by the end of Q2 of the current year. |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The performance indicator refers to budget users at the central and local level who, in accordance with the Law on the Public Internal Financial Control System, are obliged to submit a report on the activities carried out in the entity. |  |  |  |
|  | FORMULA / EQUATION Ratio between the number of budget users at central and local level who submit annual report and the total number of users at central and local level who are obliged to submit annual report X 100 |  |  |  |
| BASELINE DATA | PV (2014): 69% 2015: 76% 2016: 76% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 75% | 80% | 90% | 95% |
| DATA ON VALUES ACHIEVED | 77% | 90% | 94% | 93% |

### 3.1.3      PERFORMANCE INDICATOR 28 PASSPORT

| performance indicator | Average number of internal auditors per unit |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Public Internal Financial Control Development - Managing public finances in an efficient, economical, effective and transparent way by all spending units |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Register of deployed internal auditors Consolidated report on the system of internal financial controls in the public sector published in Q2 of the current year for the previous calendar year |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare Miloš Baletić milos.baletic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Once a year, during the adoption of the Consolidated Report, which is published on the website of the Government of Montenegro, after the adoption by the end of Q2 of the current year. |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | By the Decree on Amendments to the Decree on the Establishment of Internal Audit in the Public Sector, 30 users of budget funds (15 at the central and 15 at the local level) are obliged to establish a special organisational unit for internal audit. Other budget users must organise a special unit for internal audit or entrust the performance of internal audit tasks to a budget user who has formed an internal audit unit. |  |  |  |
|  | FORMULA / EQUATION Average number of appointed internal auditors per unit = number of appointed internal auditors / number of established internal audit units |  |  |  |
| BASELINE DATA | PV (2014): 1.76% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 2 | 2.3 | 2.5 | 2.7 |
| DATA ON VALUES ACHIEVED | 2 | 2.21 | 2.1 | 2.1 |

### 3.1.4      PERFORMANCE INDICATOR 29 PASSPORT

| performance indicator | Percentage of appointed certified internal auditors |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Public Internal Financial Control System Development - Managing public finances in an efficient, economical, effective and transparent way by all spending units |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Register of deployed internal auditors Consolidated report on the public internal financial control system published in Q2 of the current year for the previous calendar year |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare Miloš Baletić milos.baletic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Once a year, during the adoption of the Consolidated Report, which is published on the website of the Government of Montenegro, after the adoption, by the end of Q2 of the current year. |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The Law on the Public Internal Financial Control System stipulates that in order for an internal auditor to be employed on audits, he must have passed the exam for a certified internal auditor. The internal auditor may establish employment for internal audit work without passing the exam for a certified internal auditor, provided that he passes that exam no later than one year from the day of employment, that is, from the day of assignment. |  |  |  |
|  | FORMULA / EQUATION number of certified auditors per yearnumber of appointed internal auditors per yearx100 |  |  |  |
| BASELINE DATA | PV (2014): 60% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 75% | 80% | 85% | 90% |
| DATA ON VALUES ACHIEVED | 90.90% | 94.05% | 100.00% | 93.1% |

### 3.1.5      PERFORMANCE INDICATOR 30 PASSPORT

| performance indicator | Percentage of appointed certified internal auditors who undergo CPD |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Public Internal Financial Control Development - Managing public finances in an efficient, economical, effective and transparent way by all spending units |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Continuing professional development reports |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare Miloš Baletić milos.baletic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Once a year, during the adoption of the Consolidated Report, which is published on the website of the Government of Montenegro, after the adoption, by the end of Q2 of the current year. |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | Internal auditors must continuously improve their knowledge and skills in order to contribute to their improvement by assessing the effectiveness of risk management, governance and control. |  |  |  |
|  | FORMULA / EQUATION Number of internal auditors who were assigned to audit activities throughout the year and achieved the necessary number of points for continuous professional development / Number of internal auditors |  |  |  |
| BASELINE DATA | PV (2014): 0% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 70% | 75% | 80% | 90% |
| DATA ON VALUES ACHIEVED | 74% | 83.64% | 81.36% | 80.0% |

### 3.1.6      PERFORMANCE INDICATOR 31 PASSPORT

| performance indicator | Percentage of implemented and partially implemented recommendations given by internal auditors in the previous year that were implemented by the end of the current year |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Public Internal Financial Control Development - Managing public finances in an efficient, economical, effective and transparent way by all spending units |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Annual reports of internal audit units Consolidated report on the system of public internal financial controls of the current year for the previous year. The consolidated report is published on the website of the Government of Montenegro, after its adoption, by the end of Q2 of the current year. |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare Miloš Baletić milos.baletic@mif.gov.me |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Once a year, during the adoption of the Consolidated Report, which is published on the website of the Government of Montenegro, after the adoption, by the end of Q2 of the current year. |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The percentage is calculated for all internal audit units that are obliged to submit the annual work report to the Directorate for Central Harmonisation. The percentage is calculated for all recommendations given in the previous year. |  |  |  |
|  | FORMULA / EQUATION Number of implemented or partly implemented recommendations / total number of recommendations in one calendar year X 100 |  |  |  |
| BASELINE DATA | PV (2014): 48% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 55% | 60% | 65% | 70% |
| DATA ON VALUES ACHIEVED | 73.5% | 79.16% | 84.11% | 79.4% |

# 4. Transparent financial reporting and accounting

## 4.1     Transition from the cash-based to the accrual accounting and financial reporting

### 4.1.1      PERFORMANCE INDICATOR 32 PASSPORT

| performance indicator | Public sector accountants trained for accrual accounting (based on the CIPFA methodology) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Public Internal Financial Control Development - Transition from the cash-based to the accrual accounting and financial reporting Improve the quality of the public finance management and reporting by introducing the main preconditions for key elements of accrual-based accounting |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Data from the Ministry of Finance and Social Welfare on the number of participants who attended the training |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Ministry of Finance and Social Welfare Marija Uljarević marija.popovic@mif.gov.me Phone:063202964 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | December 31 each year |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | Since 2016, the Ministry of Finance and Social Welfare has started training public sector accountants for the application of accrual accounting according to international accounting standards. The training is conducted in accordance with the CIPFA (Chartered Institute of Public Finance and Accountancy) methodology. Participants in the training are accountants in spending units of the budget of Montenegro and local self-government units. The training is conducted in cooperation with the Center for Excellence in Finance from Slovenia and the Human Resources Administration. The formula is the number of participants who only attended training in one calendar year, regardless of whether they passed the exams and successfully completed the training, because, at this stage of accounting reform, priority is given to acquainting accountants with international accounting standards. |  |  |  |
|  | FORMULA / EQUATION Number of participants who attended the training in one calendar year |  |  |  |
| BASELINE DATA | PV (2014): 0 |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 40 | 40 | 20 | 100 |
| DATA ON VALUES ACHIEVED | 40 in 2016 | 80 | 40 | 120 |

### 4.1.2      PERFORMANCE INDICATOR 33 PASSPORT

| performance indicator | Property register and double entry book-keeping system for the property implemented |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Public Internal Financial Control Development - Transition from the cash-based to the accrual accounting and financial reporting Improve the quality of the public finance management and reporting by introducing the main preconditions for key elements of accrual-based accounting |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Cadastre and State Property Administration and Assets Register System (ARS) |  |  |  |
| NAME OF DATA COLLECTION HOLDER | Cadastre and State Property Administration Email: https://kdi.gov.me/uprava Phone: +382 20 444-013 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Daily - real-time data entry (when procuring assets) |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The Property Administration in 2016-2017 developed a software and organised training for direct budget users. Users were obliged to submit the status of the property through Excel spreadsheets (templates) that were adapted to the ARS application in order to migrate them to the records. After the migration, the users are obliged to record the assets in the ARS (application for access to records) when procuring. PD data on the number of participants who attended the training and submitted the condition of the property in their ownership 195.66.166.90 |  |  |  |
|  | FORMULA / EQUATION |  |  |  |
| BASELINE DATA | PV (2014): The development of the property register has begun |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | Entered property data in the register | Training (direct and indirect budget users) and collecting information on the condition of assets | Training (indirect budget users) and migration of assets to ARS and commissioning of records | Implemented asset register and double entry accounting system |
| DATA ON VALUES ACHIEVED | 0 | 80 | 9 groups 100 public authorities 0 migration | Public authorities (99) Public services (322) DKP (39) Local government (24) Municipal authorities (196) 0 migration |

# 5. STRENGTHENING EXTERNAL AUDIT CAPACITIES

## 5.1     Improving the audit process, strengthening audit capacities and transparency in the use of public finances - State Audit Institution

### 5.1.1      PERFORMANCE INDICATOR 34 PASSPORT

| performance indicator | Level of realisation of SAI’s Annual Audit Plan |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| corresponding objective or activity | Strengthening external audit capacities - Improving the audit process, strengthening audit capacities and transparency in the use of public finances - State Audit Institution |  |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Data for monitoring performance indicators are collected at the national level. Official website of the State Audit Institution: www.dri.co.me Database: Annual Audit Plan of the SAI of Montenegro; Annual report on performed audits and activities of the SAI for the period October of the previous year - October of the current year. Audit reports published on the official website of the State Audit Institution: www.dri.co.me |  |  |  |
| NAME OF DATA COLLECTION HOLDER | State Audit Institution Zoran Jelić zoran.jelic@dri.co.me Phone: 020 / 407-407 Mihaela Popovic mihaela.popovic@dri.co.me Phone: 020 / 407-404 Marija Žugić, Department of International Relations marija.zugic@dri.co.me Phone: 020 / 407-430 |  |  |  |
| FREQUENCY OF DATA PUBLICATION | Q4 of the current calendar year. |  |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The Senate of the State Audit Institution, in accordance with Article 9 of the SAI Law, adopts the Annual Audit Plan by the end of the current year for the following year. The annual audit plan is a business secret of the Institution until all audited entities, provided for in the plan, are notified of the start of the audit. |  |  |  |
|  | FORMULA / EQUATION % = number of performed audits / number of planned audits per year X 100 |  |  |  |
| BASELINE DATA | PV (2014): 60% PV (2017): 80% |  |  |  |
| TARGET VALUE DATA | 2017 | 2018 | 2019 | 2020 |
|  | 83% | 86% | 90% | 83% |
| DATA ON VALUES ACHIEVED | 86.27% | 88.68% | 72.50% | 86.27% |

### 5.1.2 PERFORMANCE INDICATOR 35 PASSPORT

| performance indicator | Application of ISSAI-compliant methodology for financial, regularity and performance audits |  |  |  |
| --- | --- | --- | --- | --- |
| corresponding objective or activity | Strengthening external audit capacities - Improving the audit process, strengthening audit capacities and transparency in the use of public finances - State Audit Institution |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Data for monitoring performance indicators are collected at the national level. SAI source: Working documents prepared by the project team and experts engaged within the IPA project "Development and capacity building of SAI and AA". Official website of the State Audit Institution: http://www.dri.co.me/1/index.php?option=com_content&view=article&id=93&Itemid=20&lang=sr http://www.dri.co.me/1/index.php?option=com_content&view=article&id=139&Itemid=204&lang=sr |  |  |
| NAME OF DATA COLLECTION HOLDER | State Audit Institution Zoran Jelić zoran.jelic@dri.co.me Phone: 020 / 407-407 Mihaela Popovic mihaela.popovic@dri.co.me Phone: 020 / 407-404 Marija Žugić, Department of International Relations marija.zugic@dri.co.me Phone: 020 / 407-430 |  |  |
| FREQUENCY OF DATA PUBLICATION | Q4 of the current calendar year. |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | Ration between the number of adopted and implemented methodologies on performing financial audit, regularity audit and performance audit in accordance with ISSAI standards for financial audit, regularity audit and performance audit, and the number of planned methodologies. Methodology description: Audit methodology harmonised with ISSAI Level 3 - SAI has methodologies for performing financial audit, regularity audit and performance audit in accordance with ISSAI 200, 300 and 400. Audit methodology in accordance with ISSAI Level 4- SAI has methodologies (manuals, guidelines) for performing financial audit and regularity audit in accordance with ISSAI 200 and 400, ISSAI 1000-1810 and ISSAI 4000) and methodology for performance audit in accordance with ISSAI 300 and ISSAI 3000, 3100 and 3200. |  |  |
|  | FORMULA / EQUATION n/a |  |  |
| BASELINE DATA | PV (2015): Methodological Instruction for Financial and Regularity Audits compliant with ISSAI 200 and ISSAI 400, Methodological Instruction for Performance Audits compliant with ISSAI 300 and Guidelines for Audit Quality Control PV (2017): Guidelines for assessing the application of fiscal responsibility criteria; Innovated Guidelines on the methodology for performance audits in line with ISSAI 300 |  |  |
| TARGET VALUE DATA | 2018 | 2019 | 2020 |
|  | Guidelines for Auditing Annual Financial Statements of Political Entities; Guidelines for Auditing Final Budget Accounts; | n / a The activities listed in the action plan start from Q1 2019 | Manual for Financial and Regularity Audits compliant with ISSAI 4th level adopted and applied Manual for Performance Audits compliant with ISSAI 4th level upgraded and applied. Guide for Monitoring the Implementation of Recommendations from Audit Reports adopted and applied. |
| DATA ON VALUES ACHIEVED | Guidelines for Auditing Annual Financial Statements of Political Entities adopted in January 2018; Guidelines for Auditing Final Budget Accounts adopted in September 2018; | Manual for Performance Audits compliant with ISSAI 4th level adopted in December 2019 | Manual for Financial and Regularity Audits adopted in July 2020 and applied. Guidelines on the methodology of conducting performance audits in accordance with the 4th level of the ISSAI standard were adopted in December 2019 and the same began to be applied. Guidelines for drafting, monitoring and controlling the implementation of the recommendations of the State Audit Institution were adopted in June 2020 and have started to be applied. |

### 5.1.3      PERFORMANCE INDICATOR 36 PASSPORT

| performance indicator | No of trainings/seminars/ workshops for auditors delivered |  |  |  |
| --- | --- | --- | --- | --- |
| corresponding objective or activity | Strengthening external audit capacities - Improving the audit process, strengthening audit capacities and transparency in the use of public finances - State Audit Institution |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Data for monitoring performance indicators are collected at the national level. Database on trainings / seminars / workshops organised in accordance with the SAI Annual Training Plan and trainings / seminars / workshops organised through regional and international cooperation. SAI training plan Annual report on performed audits and SAI activities for the period October of the previous year - October of the current year SAI official website: www.dri.co.me |  |  |
| NAME OF DATA COLLECTION HOLDER | State Audit Institution Zoran Jelić zoran.jelic@dri.co.me Phone: 020 / 407-407 Mihaela Popovic mihaela.popovic@dri.co.me Phone: 020 / 407-404 Marija Žugić, Department of International Relations marija.zugic@dri.co.me Phone: 020 / 407-430 |  |  |
| FREQUENCY OF DATA PUBLICATION | Q4 of the current calendar year. |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The SAI Senate adopts the Annual Training Plan. In addition to trainings that are planned and implemented in accordance with the SAI Annual Training Plan, trainings are held through regional and international cooperation. |  |  |
|  | FORMULA / EQUATION Number of trainings realised in the current calendar year. |  |  |
| BASELINE DATA | PV (2014): Minimum 3 trainings organised PV (2017): 9 additional trainings organised |  |  |
| TARGET VALUE DATA | 2018 | 2019 | 2020 |
|  | Additional 6 trainings organised | Additional 7 trainings organised | Additional 10 trainings organised |
| DATA ON VALUES ACHIEVED | 13 trainings (3 internally organised and 10 at regional and international level) | 13 trainings (3 internally organised and 10 at regional and international level) | 32 trainings (22 at the domestic level and 10 at the regional and international level) |

## 5.2. Building capacities and improving audit procedure - Audit Authority

### 5.2.1      PERFORMANCE INDICATOR 37 PASSPORT

| performance indicator | No of trainings/seminars/ workshops for auditors delivered |  |  |  |
| --- | --- | --- | --- | --- |
| corresponding objective or activity | Strengthening external audit capacities - Building capacities and improving audit procedure - Audit Authority |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Internal database on completed trainings of employees of the Audit Authority |  |  |
| NAME OF DATA COLLECTION HOLDER | Audit Authority Radmila Prelević, certified auditor radmila.prelevic@revizorskotijelo.me Telephone: 067 313 199 |  |  |
| FREQUENCY OF DATA PUBLICATION | January 31 N + 1 for N year |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | A larger number of audit trainings contributes to the strengthening of the institution’s capacity and is measured by the number of conducted trainings during the calendar year per auditor. |  |  |
|  | FORMULA / EQUATION Number of audit trainings during the calendar year / number of auditors |  |  |
| BASELINE DATA | PV (2014): 3 trainings organised per auditor |  |  |
| TARGET VALUE DATA | 2018 | 2019 | 2020 |
|  | Organised a minimum of 5 audit trainings per auditor | Organised a minimum of 9 audit trainings per auditor | Organised a minimum of 7 audit trainings per auditor |
| DATA ON VALUES ACHIEVED | On average, 3 trainings were organised per auditor | Organised 11 audit trainings per auditor | Organised 9 audit trainings per auditor |

### 5.2.2      PERFORMANCE INDICATOR 38 PASSPORT

| performance indicator | Progress in implementing the Strategy and AP |  |  |  |
| --- | --- | --- | --- | --- |
| corresponding objective or activity | Strengthening external audit capacities - Building capacities and improving audit procedure - Audit Authority |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Report on the implementation of the action plan for the implementation of the Strategic Development Plan of the Audit Authority - Internal document |  |  |
| NAME OF DATA COLLECTION HOLDER | Audit Authority Radmila Prelević, Certified Auditor radmila.prelevic @ revizorskotijelo.me Phone: 067 223 252 |  |  |
| FREQUENCY OF DATA PUBLICATION | Q1 N + 1 for N year |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The success of the implementation of the activities of the action plan for the implementation of the strategy is measured in percentages and shows managerial support towards meeting the set goals. |  |  |
|  | FORMULA / EQUATION Implemented number of activities under the action plan / total number of activities under the action plan X 100 |  |  |
| BASELINE DATA | PV (2014): n/a |  |  |
| TARGET VALUE DATA | 2018 | 2019 | 2020 |
|  | n / a The activities listed in the action plan will start in 2019 | Strategic plan adopted Action plan adopted | 20% of planned activities realised |
| DATA ON VALUES ACHIEVED | n / a The activities listed in the action plan will start in 2019 | Activities have been postponed to 2020 | The strategic plan and action plan for its implementation were adopted on December 29, 2020 and refer to the period 2021-2025. |

### 5.2.3      PERFORMANCE INDICATOR 39 PASSPORT

| performance indicator | Degree of audit methodology improvement – Audit Manual |  |  |  |
| --- | --- | --- | --- | --- |
| corresponding objective or activity | Strengthening external audit capacities - Building capacities and improving audit procedure - Audit Authority |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Working reports prepared by experts engaged under the IPA project "Development and capacity building of SAI and AA" with a description of activities to improve the audit manual. |  |  |
| NAME OF DATA COLLECTION HOLDER | Audit authority Radmila Prelević, Certified Auditor radmila.prelevic @ revizorskotijelo.me Phone: 067 223 252 |  |  |
| FREQUENCY OF DATA PUBLICATION | 1x per year, depending on the dynamics of project implementation |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The degree of improvement of the audit manual is measured by the percentage of remedied deficiencies identified by the project experts. |  |  |
|  | FORMULA / EQUATION Number of Manual deficiencies eliminated / total number of Manual deficiencies x 100 |  |  |
| BASELINE DATA | PV (2014): Audit Manual has been prepared |  |  |
| TARGET VALUE DATA | 2018 | 2019 | 2020 |
|  | n / a The activities listed in the Action Plan will start in 2019 | 50% of deficiencies eliminated | 100% of deficiencies eliminated |
| DATA ON VALUES ACHIEVED | n / a The activities listed in the Action Plan will start in 2019 | 90% of deficiencies eliminated | 100% of deficiencies eliminated |

### 5.2.4      PERFORMANCE INDICATOR 40 PASSPORT

| performance indicator | Share of audits conducted by using the audit software tool |  |  |  |
| --- | --- | --- | --- | --- |
| corresponding objective or activity | Strengthening external audit capacities - Building capacities and improving audit procedure - Audit Authority |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Individual audit engagement reports - Internal documents |  |  |
| NAME OF DATA COLLECTION HOLDER | Audit authority Radmila Prelević, Certified Auditor radmila.prelevic @ revizorskotijelo.me Phone: 067 223 252 |  |  |
| FREQUENCY OF DATA PUBLICATION | Q2 of the N year for the previous year |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | The use of audit software is required for more efficient audits. The performance indicator is measured by the percentage of software used in the audit in the total number of audits conducted. |  |  |
|  | FORMULA / EQUATION Number of audits (during the calendar year) performed using audit software / Total number of audits during the calendar year X 100 |  |  |
| BASELINE DATA | PV (2014): n/a |  |  |
| TARGET VALUE DATA | 2018 | 2019 | 2020 |
|  | n / a The activities listed in the Action Plan will start in 2019 | 20% Audits conducted using software | 50% Audits conducted using software |
| DATA ON VALUES ACHIEVED | n / a The activities listed in the Action Plan will start in 2019 | 33.33% Audits conducted using software | 66.66% Audits conducted using software |

### 5.2.5      PERFORMANCE INDICATOR 41 PASSPORT

| performance indicator | Level of implementing standards to ensure audit quality |  |  |  |
| --- | --- | --- | --- | --- |
| corresponding objective or activity | Strengthening external audit capacities - Building capacities and improving audit procedure - Audit Authority |  |  |
| SOURCE OF DATA FOR MONITORING PERFORMANCE INDICATORS | Internal register of implemented quality controls |  |  |
| NAME OF DATA COLLECTION HOLDER | Audit Authority Radmila Prelević, Certified Auditor radmila.prelevic @ revizorskotijelo.me Phone: 067 223 252 |  |  |
| FREQUENCY OF DATA PUBLICATION | 1x per year |  |  |
| BRIEF DESCRIPTION OF PERFORMANCE INDICATOR AND METHODOLOGY (FORMULAS / EQUATIONS) | Guidelines for quality control ensure higher quality and reliability of audit work. It is measured as a percentage indicating the degree of application of the control guidelines. |  |  |
|  | FORMULA / EQUATION Number of audits covered by quality control / Total number of audits provided by the guidelines for quality control x 100 |  |  |
| BASELINE DATA | PV (2014): n/a |  |  |
| TARGET VALUE DATA | 2018 | 2019 | 2020 |
|  | n / a The activities listed in the Action Plan will start in 2019 | 30% | 50% |
| DATA ON VALUES ACHIEVED | n / a The activities listed in the Action Plan will start in 2019 | 75% of audits covered by quality control | 75% of audits covered by quality control |

2016-2020 Public Finance Management Reform Programme: http://www.mif.gov.me/biblioteka/strateska_dokumenta

http://www.mju.gov.me/ResourceManager/FileDownload.aspx?rId=329420&rType=2

http://www.gsv.gov.me/ResourceManager/FileDownload.aspx?rId=357599&rType=2

Conclusion No. 07-1966 of 6 July 2017 (adopted at the 32nd Session of the Government of Montenegro)

Updated version of the 2016-2020 Public Finance Management Reform Programme with the Action Plan: http://www.mf.gov.me/biblioteka/strateska_dokumenta

Performance Indicator Passports: http://www.mif.gov.me/biblioteka/strateska_dokumenta

The revised Programme covered three new areas: state aid, customs and the audit of EU funds. 2016-2020 Public Finance Management Reform Programme, website of the Ministry of Finance and Social Welfare, link to the document: http://www.mf.gov.me/biblioteka/strateska_dokumenta

In February 2018, Annual Report has been adopted, which includes the period of implementation from 1 January to 31 December 2017, based on the general overview of achieved results. It was previously adopted by the Council for Public Administration Reform, that is, the Government, and then sent to the Delegation of the European Union to Montenegro (DEU) for inspection. The 2016 Annual Report was adopted in March 2017 and can be downloaded from the website of the Ministry of Finance and Social Welfare: http://www.mf.gov.me/biblioteka/strateska_dokumenta

2016-2020 Public Finance Management Reform Programme: http://www.mif.gov.me/biblioteka/strateska_dokumenta

IPA 2014 project Support to Public Finance Management Policies in the amount of € 4,000,000.00, of which € 3,600,000.00 is the EU contribution; IPA 2014 project Implementation of Electronic Public Procurement System in the amount of € 1,650.00.00, of which € 1,500,000.00 represents the EU contribution; IPA 2014 project Support to the Tax Administration in the total amount of funding of € 1,000,000.00, of which € 900,000.00 is the EU contribution; IPA 2014 multi-beneficiary project Strengthening Economic and Public Finance Management, of which the EU contribution amounts to € 8 million; and IPA 2014 project Support to the Customs Administration in the amount of € 3,300,000.00, of which € 2,970,000.00 is the EU contribution.

Data on the Semi-Annual Report for 2019: 37% activities were fully implemented (36); 21% partly implemented (21); 42% have not been implemented (41).

Guidelines for Proposing and Selecting Financial and Regularity audits for the Annual Audit Plan were developed with the support of SIGMA, http://www.dri.co.me/1/doc/Smjernice%20za%20predlaganje%20i%20izbor%20finasijskih%20revizija%20i%20revizija%20pravilnosti%20za%20Godi%C5%A1nji%20plan%20revizija%20DRI.pdf

PEFA - Public Expenditure and Financial Accountability : http://www.mif.gov.me/ResourceManager/FileDownload.aspx?rId=395245&rType=2

Direct budget support for the implementation of the Public Administration Reform Strategy amounts to €15 mil., while national co-financing is not provided for its implementation. Of this amount, the Programme planned €12 mil. to be allocated through three tranches. The remaining € 3 mil. represent complementary technical support, to be contracted by the Delegation of the European Union to Montenegro. Therefore, the first fixed tranche in the amount of €4 mil. has been paid to Montenegro on 28 November 2018, while the first variable tranche in the amount of €2.1 million was paid in December 2019. The deadline for submitting requests for the payment of the second fixed (and also final) tranche is Q3 2021.

http://www.mif.gov.me/rubrike/Budzet_Ministarstva_finansija/

In 2020, the implementation of the capital budget, excluding the highway amounted to 180.60%, and with the included highway is 107.6%.

In accordance with the Regulation on the Organisation and Manner of Work of the Public Administration, the Tax Administration, as well as the Customs Administration, became the Revenue & Customs Administration. In order to more efficiently implement the policy in the field of revenues, the proposed changes merge the competencies of the previous Revenue Administration and the Customs Administration (April 15, 2021).

The project became effective in March 2018; The value of the project is €14 million (€ 10 million for IT and € 4 million for the business part). In the first half of 2019, the reprogramming of the project ‘Tax Administration Reform in Montenegro (RARP)’ in the amount of € 18,800 million was completed, under which EFI was included as Component 4 (total amount of € 4,800,000).

In accordance with the Regulation on the Organisation and Manner of Work of the Public Administration, the Tax Administration, as well as the Customs Administration,  became the Revenue & Customs Administration.  In order to more efficiently implement the policy in the field of revenues, the proposed changes merge the competencies of the previous Revenue Administration and the Customs Administration (April 15, 2021).

Data contained in the Public Procurement Report for 2020, prepared by the Ministry of Finance and Social Welfare in accordance with the Law, based on individual reports of contracting authorities.

Law on State Aid Control (Official Gazette of Montenegro, No. 012/18 of February 23, 2018 )

Agency for Protection of Competition is an independent body that independently performs activities determined by the Law on Protection of Competition, as well as the Law on State Aid Control.

IPA 2016 Project ‘Strengthening Administrative Capacities in the Areas of State Aid and Public Procurement’. The budget for the project is 870,000 euros.

Rulebook on Internal Organisation and Systematisation of the Ministry of Finance and Social Welfare, http://www.mif.gov.me/ministarstvo/Djelatnosti/178168/Pravilnik-o-unutrasnoj-organizacije-i-sistematizacije-Ministarstva-finansija.html

Increase in gross public debt amounted to 16.6%. If we take into account the fact that, at the end of 2019, deposits amounted to 597.13 million, the value of gross public debt, at the end of 2019, amounted to 76.5% of GDP, while the value of net public debt amounted to 64.4 % of GDP.

Increase in gross public debt amounted to 16%. If we take into account the fact that, at the end of 2020 the deposits amounted to 872.43 million, the value of gross public debt, at the end of 2020, amounted to 105.15% of GDP, while the value of net public debt amounted to 84.34% of GDP estimated for 2020.

Rulebook on the training programme and the manner of taking the exam for obtaining the certificate of public sector internal auditor (Official Gazette of Montenegro, No. 071/19 of 25 December 2019).

The trainings have so far been largely funded by donors.

The Public Sector Accounting Law, which was adopted by the Parliament of Montenegro on 22 November 2019 (Official Gazette of Montenegro, No. 066/19 of 06 December 2019).

The Law stipulates that the deadline for the adoption of bylaws is one year from the date of adoption of the Law, since the Law begins to apply on January 1, 2022.

Given that trainings begin in the middle of the year, the year of training does not coincide with a calendar year, but extends to two calendar years.

Trainings for indirect budget users (public services, local self-government and municipal branches) that started in June 2020 were interrupted due to National Coordination Body recommendations but were completed through a link to video presentations of trainings for work on the ARS web application (Asset Registry System), which were recorded so that the project of a single record of state property would not be interrupted. Due to the situation caused by COVID-19, the migration of data on real estate and movable property obtained from end users to the ARS application is planned for the first half of 2021.

The Parliament of Montenegro passed the Law on State Property, which entered into force in March 2009, which stipulates the obligation for the administrative body responsible for property affairs to establish a single register of state property, within 90 days from the date of expiration of the deadline set by the public and municipal authorities. According to these provisions, the state property register was to be operational by summer 2010.

The contract was signed on November 19, 2018, which lasted until September 2020.

Innovated 2016-2020 Public Finance Management Reform Programme, with Action Plan and Indicator Passports (June 2018). https://www.mif.gov.me/biblioteka/strateska_dokumenta

The document was adopted in 2019 and published in the Official Gazette of Montenegro, No. 068/19; It is also available on the website of the State Audit Institution - www.dri.co.me

Guidelines for proposing and selecting financial audits and regularity audits for the Annual Audit Plan were developed with the support of SIGMA

The Action Plan for the implementation of the 2020-2024 State Audit Institution Communication Strategy was developed with the support of SIGMA.

Work has begun on the development of an Action Plan for the implementation of the 2021-2025 SAI Human Resources Management Strategy with the support of SIGMA

National IPA Program, Regional and Territorial Cooperation Program as well as the Education, Employment and Social Policy Program.

Agriculture and Rural Development Program.

The manuals were approved by the Auditor General of the Audit Authority by Decision No. 109/3 2019.

Note: The degree of implementation of activities in the Action Plan is shown in such a way that the green color indicates the activity that is fully implemented (more than 80%), with their implementation planned in the future in order to further improve. Yellow colour indicates partially implemented activity (from 50%-80%), while red one indicates the activity that has not been implemented (below 50%). Also, activities that are not marked with colour have not been implemented.

Given that the Law on Final Budget Account for 2017 has not yet been adopted, the data on actual spending was taken from the SAP system at the time of drafting the Passport Performance Indicator and is not official until the adoption of the Law on Final Budget Account .

In 2020, the realisation of the capital budget, excluding the highway was 180.60%, and with the included highway was 107.6%.

Data is preliminary, while the real GDP data will be available in September 2019, for 2018 (MONSTAT quarterly GDP reports)

A calculation formula was provided and profit explained to be 95% previous profit trend. When it comes to e-returns, it could not be processed because the obligation to submit electronically began in January 2017.

Data on the fulfillment of this Performance Indicator are available in early February in the document "Report on Budget Receipts and Expenditures".

During the reporting period, the data was preliminary and stood at 2.38.

The amount of used funds indicates the budget spent by for project implementation team (CFCU is still in the process of invoices approval and will be paid in the next period ) 2020

The increase in gross public debt is 16%. If we take into account the fact that at the end of 2019 deposits amounted to 872.43 million euros, the value of gross public debt at the end of 2020 amounted to 105.15% of GDP, while the value of net public debt amounted to 84.34% GDP estimated for 2020.

Donation funded by SIGMA and IMF.

Data for 2018 are preliminary. When calculating the percentage of implementation, only recommendations for which deadline for implementation was until the end of 2018 were taken into account.

The trainings were organised in cooperation with the Human Resources Administration, and the funds were provided from the budget of Montenegro, because the implementation of the IPA project began at the end of 2018.

Funds provided as a contribution to the implementation of the Training Program for newly appointed internal auditors.

Trainings were organised in cooperation with the Human Resources Administration, and the funds were provided from the budget of Montenegro, because the implementation of the IPA project began at the end of 2018.

Trainings for indirect budget users (public services, local self-government and municipal branches) that started in June 2020 were interrupted due to recommendations of the National Coordination Body but were completed through a link to video presentations of trainings for working on the ARS web application (Asset Registry System), which were recorded so that the project of a single record of state property would not be interrupted. Due to the situation caused by the COVID-19 virus, the migration of data on real estate and movable property obtained from end users to the ARS application is planned for the first half of 2021.

Bearing in mind that the fields in the ARS application have been finalised, the funds were spent from two tranches: the first in the amount of € 14,701.50 and the second in the amount of € 19,965.00, which amounts to a total of € 34,666.50.

The Explanatory Note of the Law does not reflect all the information submitted in the request for budget funds. Comprehensive information is important when considering and negotiating budget request

Implementation of the capital budget without the inclusion of the highway - 111%, and with the inclusion of the highway - 91%

In 2020, the implementation of the capital budget, excluding the highway, was 180.60%, and with the highway included, it was 107.6%.

The data is preliminary, while the real GDP data will be available in September 2019, for 2018 (MONSTAT quarterly GDP reports).

A calculation formula was provided, and 95% income was explained to represent previous income trend. When it comes to e-returns, it could not be processed because the obligation to submit electronically began in January 2017.

Harmonisation of the tax administration in the area of administrative cooperation and mutual assistance and the Law on Income Tax (transfer pricing), by the end of Q4 2018.

Law on Amendments to the Law on Corporate Income Tax (Q4 2019);

Draft Law on Final Budget Accounts of Montenegro for 2017. 13.0 represents preliminary data until the official adoption of the Law at the Parliament (September), and until then, official data on GDP for 2017 will be available. http://www.gov.me/ResourceManager/FileDownload.aspx?rId=317590&rType=2

Data on the fulfillment of this performance indicator are available in early February in the document "Report on Budget Receipts and Expenditures"

Data contained in the Public Procurement Report for 2020, prepared by the Ministries of Finance and Social Welfare in accordance with the Law, based on individual reports of contracting authorities.

Increase in gross public debt is 16%. If we take into account the fact that at the end of 2020 deposits amounted to €872.43 million, the value of gross public debt at the end of 2020 amounted to 105.15% of GDP, while the value of net public debt amounted to 84.34% of GDP estimated for 2020.

Reports submitted to the CHU of the Ministry of Finance and Social Welfare. This performance indicator exists in the Public Administration Reform Strategy, and the results can be seen at the following link: www.gov.me/ResourceManager/FileDownload.aspx?rId=279138&rType=2

Reports submitted to the CHU of the Ministry of Finance and Social Welfare.

Number of budget users changes in accordance with the amendments to the Regulation on the organisation and manner of work of the public administration and the Budget Law for ongoing year.

The new Regulation on the Establishment of Public Sector Internal Audit ("Official Gazette of Montenegro", No. 070/19) has increased the number of units obliged to establish a special internal audit unit. For this reason, the value of this indicator decreased compared to the previous year.

The number of points is determined based on the Rulebook on the special program for professional development of public sector internal auditors ("Official Gazette of Montenegro", no. 067/19 of 12/11/2019).

Given that trainings begin in the middle of the year, the year of training does not coincide with a calendar year, but extends to two calendar years.

Entered property data in the register. Data (tables) that are submitted to the Property Directorate are processed, tested and migrated to a test version of the ARS. In the course of testing and migration of assets to a test version of the ARS we noted that the application has problems (sometimes does not allow access), of which we informed implementers, ATOS doo, Belgrade. The software assistance is undergoing and we expect fast solution to the problem. After the end of their intervention, we will do final data migration that was timely delivered, and upon migration the application will be put into operation.

Given that trainings begin in the middle of the year, the year of training does not coincide with a calendar year, but extends to two calendar years.

Trainings for indirect budget users (public services, local self-government and municipal branches) that started in June 2020 - were interrupted due to National Coordination Body recommendations, but were conducted via the video presentation of trainings on the ARS web application (Asset Registry System), which was recorded so that the project of the single record of state property would not be interrupted. Due to the situation caused by COVID-19, the migration of data on real estate and movable property obtained from end users to the ARS application is planned for the first half of 2021.

After the adoption of the said plans, the application of the said formula begins