GOVERNMENT OF MONTENEGRO

FOR CHAPTER 24 JUSTICE, FREEDOM AND SECURITY

REPORT NUMBER 3

June 2014

# Content:

Content:	2

24: Justice, Freedom and Security	3

1.	MIGRATIONS	3

2.	ASYLUM  MoI – Sandra Bugarin	42

3.	VISA POLICY  MFAEI – Dejan Vukovic	60

4.	EXTRNAL BORDERS AND SCHENGEN  MoI – Milan Paunovic	63

5.	JUDICIAL COOPERATION IN CIVIL AND CRIMINAL MATTERS	86

6.	POLICE COOPERATION AND FIGHT AGAINST ORGANISED CRIME	100

7.	FIGHT AGAINST TERRORISM  MoI – Mladen Markovic	213

8.	COOPERATION IN THE FIELD OF DRUGS  MoI – Miodrag Lakovic	230

9.	CUSTOMS COOPERATION  CA – Rade Lazovic	243

10.     COUNTERFEITING OF THE EURO  MoI – Dragan Radonjic	244

# 24: Justice, Freedom and Security

## 1.	MIGRATIONS

### 1.1.	REGULAR MIGRATIONS                   	Ministry of Interior - Abdulah Abdic

Recommendation 1 from the Screening Report – area “Migrations”

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 1.1.1. * | Establishment of the inter-ministerial working group in charge of making an overall analysis of the legal migration system, drafting amendments to relevant legislation, and monitoring the overall process of harmonisation and implementation of regulations and standards in the field of legal migration; -Preparation of the project proposal for engagement of expert support (TAIEX) with a view to preparing an all-encompassing legal migration system analysis in Montenegro; -Drafting the all-encompassing Legal Migration System Analysis in Montenegro – legislative and institutional framework, administrative capacities, and technical equipment, that should identify the problems and financial needs and recommendations for full legislative, institutional, administrative and technical harmonisation with the regulations and standards of the EU in this area, including a detailed impact assessment with respect to training needs, administrative capacities and budget required (1) 31 December 2013 [I] (2) 31 March 2014 [I] Based on the Decision of the Minister of Interior of 29 November 2013, an inter-ministerial working group was established to prepare an all-encompassing Legal Migration System Analysis in Montenegro. (3) 30 June 2014 [I] | MINISTRY OF INTERIOR Abdulah Abdic | I November 2013 (for establishment of the inter-ministerial working group and preparation of the project proposal for engagement of the expert support); December 2014 (for preparation of the Analysis) | Inter-ministerial working group established, (1) 31 December 2013 [I] Based on the Decision of the Minister of Interior of 29 November 2013, inter-ministerial working group was established. (2) 31 March 2014 [I] Based on the Decision of the Minister of Interior the inter-ministerial working group was established which, in addition to representatives of the Ministry of Interior, also included representatives of: Ministry of Justice, Ministry of Foreign Affairs and European Integration, Ministry of Finance, Ministry of Labour and Social Welfare, Employment Office, University of Montenegro and International Organisation for Migrations (IOM). (3) 30 June 2014 [I] Number of held meetings (1) 31 December 2013 [IC] One meeting of the Inter-ministerial working group was held on 29 January 2014 (2) 31 March 2014 [IC] First meeting of the working group was held on 29 January 2014. The relevant EU legislation referring to the area of illegal migrations was presented to members of the working group, in order for them to be adequately introduced to the upcoming responsibilities. (3) 30 June 2014 [IC] The second meeting of the inter-ministerial working group was held on 27 June 2014. The working group members who attended the meeting were introduced to obligations of harmonization of the national legislation with particular directives, and the Draft Road Map of harmonization of national legislation in social relations covered in areas by every particular ministry was distributed. The working group members who attended the meeting were informed that the next meeting will be held on 7 July 2014 at 11 o` clock with a view to determining the final Road Map. The invitation for the new meeting will be submitted today to the working group members who did not attend this meeting. Project proposal prepared and submitted to the European Commission, (1) 31 December 2013 [I] Project proposal requesting expert support within TAIEX in order to draft an all-encompassing Legal Migration System Analysis was prepared via the Directorate for International Cooperation of the Ministry of Interior; on 30 September 2013 the proposal was sent to the Ministry of Foreign Affairs and European Integration for further actions. 2) 31 March 2014 [I] Project proposal was prepared and submitted to the European Commission in late September. (3) 30 June 2014 [I] Project proposal was prepared and submitted to the MFAEI for further actions on 30 September 2013. Project proposal approved and expert assigned to provide expert assistance in preparation of the Analysis, (1) 31 December 2013 [I] We were informed via a letter dated 13 November 2013 that the project proposal requesting expert support (TAIEX) for preparation of an all-encompassing Legal Migration System Analysis was approved. In the period from 10 to 14 March 2014, the following experts from the Republic of Croatia will be staying in Podgorica: Irena Kalanj and Irena Maglić Radoš (2) 31 March 2014 [I] Project proposal was approved and experts were assigned to provide support in the preparation of the all-encompassing Legal Migration System Analysis The experts from the Republic of Croatia included Ms Irena Kalanj and Ms Irena Maglic Rados. As part of the efforts to implement the measure 1.1.1. which refers to the preparation of an all-encompassing Legal Migration System Analysis in Montenegro, working meetings with experts were organised in the period from 10 to 14 March 2014. On that occasion we concluded that our national legislation was not in contravention of the EU legislation, but that it was partially harmonized. (3) 30 June 2014 [I] We were informed by the letter of 13 November 2013 that the project proposal was approved by the European Commission. Legal Migration System Analysis drafted, (1) 31 December 2013 [NI] This measure is planned for end of 2014. Members of the working group have been introduced to the planned activities and the dynamics of work, as well as with the duty to take active part in the drafting of an all-encompassing analysis during the visit by experts from the Republic of Croatia. In order to provide their full contribution, they have been presented with the relevant EU legislation. (2) 31 March 2014 [NI] Preparation of Analysis is planned for the fourth quarter of 2014 (3) 30 June 2014 [PI] The Road Map for harmonisation of national legislation with relevant EU directives has been developed, and members of the working group will provide final statements on its dynamics at the meeting which is scheduled for 7 July 2014; after that, conditions will be provided for development of analysis, i.e. implementation of this measure. | The involvement and engagement of all relevant institutions during the entire process of negotiations for Chapter 24, (1) 31 December 2013 [I] ALL RELEVANT INSTITUTIONS IN MONTENEGRO HAVE THEIR REPRESENTATIVES IN THE WORKING GROUP. (3) 30 June 2014 [I] At the meeting held on 27 June 2014, absence was justified by the representative of the University of Montenegro and the International Organisation for Migrations (business trip), unlike representatives of the Ministry of Justice, the Ministry of Finance and the Ministry of Labour and Social Welfare; they received regular invitations, but did not justify their absence. Semi-annual reports on the work and activities of the inter-ministerial working group (1) 31 December 2013 [NI] WG has been working for less than six months. (3) 30 June 2014 [I] Two meetings of the inter-ministerial working group were held in the period 1 January – 30 June 2014, and the following meeting was scheduled for 7 July 2014. The working group members who attended the meeting held on 27 June 2014 received the Draft Road Map and spoken information on the date of the new meeting, whereas absent members will receive invitation for the new meeting via email, along with the minutes from today’s meeting, the Draft Road Map, as well as previously submitted directives. Expert assistance of the EC for the preparation of the all-encompassing Analysis ensured (1) 31 December 2013 [I] The visit of an expert assigned through TAIEX was organised in the period from 10 to 14 March 2014. (3) 30 June 2014 [I] In the course of the expert visit, hired experts provided useful recommendations and suggestions, which were incorporated into the Draft Road Map. Level of implementation of the defined guidelines for legislative, institutional and technical harmonisation of the national system with the regulations and standards of the European legislation (1) 31 December 2013 [NI] (3) 30 June 2014 [NI] Note: Conditions for realization of defined guidelines will be provided following adoption of the new Law on Foreigners. |

Recommendation 2 from the Screening Report– area “Migrations“

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 1.1.10. | Monitor the course of process of harmonizing and implementing newly adopted regulations in the field of illegal migrations (2) 31 March 2014 [IC] Law on Amendments to the Law on Foreigners was adopted and published (Official Gazette 61/13). The amendment referred only to the extension of the deadline in which displaced and internally displaced persons were required to file a request for permanent settlement or temporary residence. The deadline is extended until 31 December 2014. (3) 30 June 2014 [IC] | Ministry of Interior Abdulah Abdic | [IC] January 2014 – December 2018 | Semi-annual reports of the inter-ministerial working group, (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] Inter-ministerial working group was established on 29 November 2013 and the first semi-annual report will be submitted after the elapse of six months. (3) 30 June 2014 [I] The Memorandum on Cooperation was signed on 6 March 2014 between the Ministry of Interior, the Ministry of Labour and Social Welfare and UNHCR with a view to efficient implementing of the Law on Foreigners. Furthermore, operational team was established with a view to animating the displaced and internally displaced persons to submit requests for regulation of their status in Montenegro. | Expert evaluation reports on the process of harmonizing and implementing newly adopted regulations, (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [I] In compliance with the Technical-Economic Elaborate, development of the new Law on Foreigners which is currently at the proposal stage is ongoing. The European Commission provided positive opinion on the Proposal for the Law on Foreigners in this stage of law development as well. Reports of IOM representatives, (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [IC] Representative of the IOM is involved in the work of the inter – ministerial working group for development of comprehensive analysis of the legal migrations system in Montenegro; that analysis will be officially submitted to them following its completion. Reports on the problems identified in the process of harmonizing and implementing newly adopted regulations, with recommendations of the inter-ministerial working group to relevant institutions aimed at addressing the identified weaknesses (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [I] In the course of the work of the inter-ministerial working group, the need for stronger synergy of a part of its members was detected due to insufficiently expressed interest. |

### 1.2.	IRREGULAR MIGRATIONS        Ministry of Interior - Dragan Stevanovic

Recommendation 1 from the Screening Report – area “Migrations“

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 1.2.1. * | Amend the Criminal Code in accordance with the EU acquis – the Criminal Code of Montenegro needs to be amended - in terms of introducing a new criminal offence which would include items a), b), c) and partly e) of Article 9 of the Directive 2009/52/EC of 18 June 2009. (1) 31 December 2013 [I] | MINISTRY OF JUSTICE Branka Lakocevic | I September; 2013 | Establishment of a working group for drafting Amendments, (1) 31 December 2013 [I] The working group established. Proposal for Amendments drafted, (1) 31 December 2013 [I] Amendments to the Code adopted in the Parliament of Montenegro (1) 31 December 2013 [I] The Law Amending the Criminal Code, which prescribes new criminal offence – unlawful employment referred to in Article 225 a, was adopted and published in the Official Gazette of Montenegro, 40/13 of 13 August 2013. The Law entered into force on 21 August 2013. | Statistical overview of the number of criminal charges filed for the new criminal offence which would include items a), b), c) and partly e) of Article 9 of the Directive 2009/52/EC of 18 June 2009, (1) 31 December 2013 [IC] In the reporting period, no criminal charge was filed. Monthly, semi-annual and annual reports. [IC] (1) 31 December 2013 [IC] |
| 1.2.4. * | Adopt the secondary legislation which will regulate the work of the Reception Centre for Foreigners (house rules) (1) 31 December 2013 [I] | MINISTRY OF INTERIOR Abdulah Abdic | I Dec.13 | Secondary legislation adopted [I] (1) 31 December 2013 [I] The Rulebook on stay and house rules of the Reception Centre for Foreigners was adopted on 30 October 2013, published in the Official Gazette of Montenegro 50/2013. The Rulebook entered into force on 7 November 2013. |  |
| 1.2.5. | Formally put into operation the Reception Centre for Foreigners (1) 31 December 2013 [I] | MINISTRY OF INTERIOR Dragan Stevanovic | I Dec.13 | Reception Centre for Foreigners put into operation (1) 31 December 2013 [I] Technical acceptance of facilities carried out and verified by a Commission established by the Ministry of Interior. The Agreement on providing food and medical protection for migrants accommodated in the Reception Centre was signed between the Ministry of Interior and the Ministry of Justice. The Kingdom of the Netherlands donated two special vehicles for the transport of migrants. The Service for General and Auxiliary Office Tasks of the Ministry of Interior sent a letter in which it was stated that this Service would carry out all preparatory activities until 20 November 2013 in terms of maintaining hygiene and organizing the performance of these tasks, including laundry room. On 13 December 2013, the Reception Centre for Foreigners was officially opened and put into operation. |  |

Recommendation 3 from the Screening Report – area “Migrations”

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 1.2.8. * | Obtain the licence for the Reception Centre for Foreigners (1) 31 December 2013 [I] | MINISTRY OF INTERIOR Dragan Stevanovic | I July ; 2013; | Technical acceptance of the facility, (1) 31 December 2013 [I] In April 2013, technical acceptance of the Reception Centre for Foreigners was carried out. Issuing the use permits (1) 31 December 2013 [I] In April 2013, the Municipality of Danilovgrad issued use permit for the Reception Centre for Foreigners in Spuž. |  |
| 1.2.9. * | Draw up a plan of activities for providing accommodation facilities in case of a large number of irregular migrants over a short period of time. (1) 31 December 2013 [I] | MINISTRY OF INTERIOR Dragan Stevanovic | I December 2013; | Establishing the working group [R] (1) 31 December 2013 [I] The Working Group was established in September 2013. Developing plan, (1) 31 December 2013 [I] In October 2013, the Division for Foreigners, Visas and Suppression of Irregular Migrations developed a plan of activities for providing accommodation facilities in case of a large number of irregular migrants over a short period of time. Plan adopted [R] (1) 31 December 2013 [I] The plan of activities for providing accommodation facilities in case of a large number of irregular migrants over a short period of time was adopted in October 2013. |  |
| 1.2.10 * | Assessment of adequacy of capacities of the Reception Centre for Foreigners (2) 31 March 2014 [NI] (3) 30 June 2014 [PI] | Ministry of Interior Dragan Stevanovic | PI December 2014; (permanent activity at the annual level since 2014) | Hiring of expert, (2) 31 March 2014 [PI] Application was submitted for hiring of expert via TAIEX support in December 2013, through the Ministry of Foreign Affairs and European Integration of Montenegro. Feedback is awaited. (3) 30 June 2014 [PI] TAIEX Application Form for expert mission, which will be carried out in September 2014 was fulfilled and submitted to the European Commission in July 2014. Report on conducted capacity assessment (3) 30 June 2014 [?] | Measures and activities taken in compliance with prepared Assessment (3) 30 June 2014 [?] |

Recommendation 3 from the Screening Report – area “Migrations”

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 1.2.13. | Preparation and adoption of an all-encompassing plan of trainings for officers of the Reception Centre for Foreigners in order to ensure smooth operation of the Reception Centre in the following areas: counter-diversion control; establishing identity; interviewing techniques; regulations governing the work of the Reception Centre; foreign languages; carrying out repatriation; Procedure with asylum seekers. (2) 31 March 2014 [PI] (3) 30 June 2014 [I] | MINISTRY OF INTERIOR Dragan Stevanovic | I December 2014; | Preparation of all-encompassing plan of trainings (2) 31 March 2014 [I] -On 12 February 2014, the Border Police Department proposed that the topics of the trainings, provided for by this measure, should be included in the annual training programme which will be carried out at the Police Academy between 1 April 2014 and 1 April 2015 -The proposed training topics have been integrated into the framework programme for education, training and professional development at the Police Academy in Danilovgrad. (3) 30 June 2014 [I] Training plan adopted (2) 31 March 2014 [NI] (3) 30 June 2014 [I] The Framework Programme of education, vocational training and specialized advanced training for officers and state employees in the Ministry of Interior, the Police Administration and other security authorities was adopted on 30 April 2014 for the period 1 April 2014 – 1 April 2015. | Report on the number of trainings completed, (2) 31 March 2014 [?] (3) 30 June 2014 [I] Regulations governing the work of the Reception Centre for Foreigners 24 June– 8 officers of the Border Police Department – independent police inspectors for reception, accommodation and repatriation and the senior I class police officers This topic is addressed in 2 classes at the Border Police Course (25 attendees) Interviewing technique 26 June – 3 officers of the Border Police Department – independent police inspectors for reception, accommodation and repatriation and the senior I class police officers Report on the number of officers trained, (2) 31 March 2014 [?] (3) 30 June 2014 [I] Regulations governing the work of the Reception Centre for Foreigners 24 June– 8 officers of the Border Police Department – independent police inspectors for reception, accommodation and repatriation and the senior I class police officers This topic is addressed in 2 classes at the Border Police Course (25 attendees) Interviewing technique 26 June – 3 officers of the Border Police Department – independent police inspectors for reception, accommodation and repatriation and the senior I class police officers Evaluation of the success of trainings, in the context of greater efficiency and better work of officers. (2) 31 March 2014 [?] (3) 30 June 2014 [?] |
| 1.2.14 * | Study visits to the Reception Centre for Foreigners and the Reception Centre for Unaccompanied Juvenile Migrants in the EU Member States. (2) 31 March 2014 [NI] (3) 30 June 2014 [I] | Ministry of Interior Dragan Stevanovic | I December 2014; | Application for TAIEX prepared, (2) 31 March 2014 [I] In December 2013, the application was fulfilled and submitted through the Ministry of Foreign Affairs and European Integration of Montenegro for TAIEX support concerning conducting of study visits. (3) 30 June 2014 [I] Approval for study visits obtained. (2) 31 March 2014 [NI] Feedback concerning TAIEX support is expected. (3) 30 June 2014 [I] Obtained approval from TAIEX for two study visits to the Reception Centres for Foreigners located in the Federal Republic of Germany and the Netherlands. | Reports on conducted study visits. (3) 30 June 2014 [I] Report developed and submitted as regards the study visit to the Reception Centre for Foreigners in the Federal Republic of Germany - Karlsruhe, in the period 02 - 06 June 2014; four officers of the Border Police Department – Department for Foreigners, Visas and Suppression of Illegal Migrations took part in this visit. |
| 1.2.16 * | - Development and adoption of comprehensive training plan for employees in the border police, the Ministry of Labour and Social Welfare, the Ministry of Health, the Ministry of Justice and the Employment Office with a view to ensuring undisturbed implementation of regulations from areas concerning irregular migrations, which will elaborate the following aspects in more details – number of trainings, number of employees who will be involved in training, hiring of trainers– experts, through the following topics: regulations from the area of foreigners and irregular migrations; Treatment of vulnerable categories of migrants-unaccompanied juveniles, disabled persons, families, persons with war traumas etc.) Visas and visa regime; Readmission agreements; Foreign languages; Risk analysis; Procedure with asylum seekers. (2) 31 March 2014 [NI] (3) 30 June 2014 [I] | Ministry of Interior Dragan Stevanovic | I In the course of 2014[1] | Development of comprehensive training plan. (2) 31 March 2014 [PI] In March 2014, the initial note was submitted to the ministries competent for implementation of this measure, i.e. the ministries with employees, for whom the training has been planned on topics envisaged by this measure, with a view to organizing the preparatory meeting concerning development and adoption of the training plan. (3) 30 June 2014 [I] The Training Programme was developed and submitted to the Police Academy on 29 May 2014 by the Department for Foreigners, Visas and Suppression of Illegal Migrations. Training plan adopted and submitted to all relevant institutions. (2) 31 March 2014 [NI] (3) 30 June 2014 [I] Developed and adopted training programme was submitted by email to all relevant institutions on 29 June 2014, in which they are informed to designate employees who will attend the first training cycle. | Reports on the number of conducted trainings, (3) 30 June 2014 [I] Enforcement of regulations from areas concerning irregular migrations 10-11 June– Training postponed due to seasonal engagement of the border police officers This topic is addressed in 2 classes at the Border Police Course Training courses for trainers for employees of the Border Police Department in the asylum system 28-29 May – 12 police officers Exchange CEPOL – EPEP 2014 Two officers of the Border Police Department involved in the programme Aleksandar Novović and Nikola Nunić Reports on the number of trained officers, (3) 30 June 2014 [I] Enforcement of regulations from areas concerning irregular migrations 10-11 June– Training postponed due to seasonal engagement of the border police officers This topic is addressed in 2 classes at the Border Police Course Evaluation of the success of trainings, in the context of greater efficiency and better work of officers (3) 30 June 2014 [?] |
| 1.2.17. | Develop cooperation with police forces of neighbouring countries and EU Member States, as well as participate in all forms of regional police cooperation, in terms of preventing irregular migration. (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | Ministry of Interior Dragan Stevanovic | IC Continuous activity | The number of held meetings (1) 31 December 2013 [IC] During the first eleven months of 2013, 146 meetings were held at national, regional and local level. Participation in the second working meeting of representatives of the services competent for implementation of agreements on readmission, held in Sarajevo – Bosnia and Herzegovina on 15 May 2013. Participation in the regional conference in Belgrade on good EU practices in relation to migration profile, attended by 18 EU Member States and countries of the Western Balkans. Participation in the regional conference held in Sarajevo in relation to asylum and good practices of the states in the region and EU Member States. Participation in the regional conference of representatives of security services in relation to good practices of the European Union regarding asylum status, held in Sarajevo – Bosnia and Herzegovina, on 15 and 16 May 2013, organised within TAIEX and the Ministry of Security of Bosnia and Herzegovina, and MARRI. Study visits to French border police organised by the Embassy of France in Belgrade, held in the period from 29 May to 1 June 2013 in Nice – France. Participation in the DCAF meeting held in the period from 27 to 30 August 2013 in Sarajevo – Bosnia and Herzegovina, in relation to the improvement of legal norms of the work of border forces of the Western Balkan region, in the area of the fight against irregular migrations, more efficient implementation of readmission and organization of joint flights in the upcoming period. Visit to federal and state police of the Federal Republic of Germany. Participation in the seminar on asylum and migration titled: „Good practice in the EU“ held in Metkovići, organised by the Ministry of Interior of the Republic of Croatia, as well in the bilateral meeting with the Head of the State Border Administration of the Republic of Croatia. Participation in the seminar on the fight against trafficking in human beings in Ankara – Turkey, within the framework of Individual Partnership Cooperation Programme (IPCP). Participation in the DCAF meeting held in Ohrid in relation to risk analysis and statistical data concerning irregular migrations. Participation in the seminar titled “Suppression of trafficking in human beings – exchange of experiences” held in Podgorica, organised by the Government Office for the Fight Against Trafficking in Human Beings, UNDP and the Ministry of Interior of Croatia. During 2013, officers of the Border Police participated in two joint operations with countries of the region, organised by DCAF. (2) 31 March 2014 [IC] In the first quarter of 2014 the following activities were completed: • Participation in the meeting, organized by DCAF, of the working group for legal reform in the area of illegal migration and readmission on the theme of “Preparation of Draft Agreement on organization of joint flights for repatriation of illegal migrants, Draft Agreement on early warning and risk analysis “Border Centre”, as well as Draft Protocol on implementation of the agreement on joint flights”, which was held on 29-31 January 2014 in Bijeljina, Bosnia and Herzegovina • -A meeting of the joint committee for monitoring the implementation of the Agreement on Readmission between Montenegro and Albania was held in February 2014. • - A meeting of the joint committee for monitoring the implementation of the Agreement on Readmission between Montenegro and Kosovo was held in February 2014. - A meeting with a delegation of Italy in relation to the signing of the Protocol on Implementation of the Readmission Agreement was held in February 2014. (3) 30 June 2014 [IC] The following was carried out in the second quarter of 2014:  Meeting with members of the Border Police of Kosovo at the local level was held on 17 May 2014 at the Border Crossing Point Kulina.  In April, in the period 08 April - 12 April 2014, one officer from the Department participated in the training held in Valbadon – the Republic of Croatia, on the topic `` Human Trafficking“ organized by the US Embassy in Podgorica.  In April, in the period 08 April – 12 April 2014, one officer from the Department participated in the course at the International Institute for Humanitarian Law in Sanremo – Italy, which was organized by the Institute, UNHCR, and the Ministry of Foreign Affairs of Norway and Switzerland.  On 13 May, two representatives of the Department for Foreigners, Visas and Suppression of Illegal Migrations participated in the meeting with representatives of the Regional Cooperation Council in Podgorica.  In May, in the period 26 – 28 May, one officer from the Department for Foreigners, Visas and Suppression of Illegal Migrations participated in the meeting with representatives of the Regional Cooperation Council in Zagreb.  In the period 02-06 June, the Delegation of the Ministry of Interior of Montenegro – the Police Administration ( 4 officers from the Department for Foreigners, Visas and Suppression of Illegal Migrations)took part in the study visit to the Ministry of Interior and the Ministry of Integration of Baden-Wurttemberg in the Federal Republic of Germany, with special emphasis on the visit to the Reception Centre for Foreigners in Karlsruhe and expert meeting dedicated to presentation on the best practices in implementation and enforcement of Directive on common standards and procedures in Member States for returning illegally staying third-country nationals (2008/115/EC). | Reports (semi-annual and annual) on the number of joint patrols, joint operations, and achieved results. (1) 31 December 2013 [IC] Semi-annual report as well as report for 11 months of 2013 on the number of joint patrols with neighbouring countries was made (746 on land and 128 joint patrols on water). Report was made on joint operations in 2013 (2 – two), organised by DCAF, as well as on the results achieved. (2) 31 March 2014 [IC] From 1 December 2013 until the end do first quarter 2014, in accordance with the Agreement and the Protocol, joint patrols were carried out together with border police departments of the following countries: - with the Republic of Albania - 52 patrols; - with the Republic of Serbia - 77 patrols on land; - with Bosnia and Herzegovina - 80 patrols on land. - tighter control of the state border in cooperation with international security forces in Kosovo - 12 synchronised patrols; (3) 30 June 2014 [IC] Joint patrols with border police of neighbouring countries were carried out in the reporting period on the grounds of the Agreement and the Protocol: - with the Republic of Albania - 49 patrols. - with the Republic of Serbia - 78 land patrols. - with Bosnia and Herzegovina - 86 land patrols. - control of the state border strengthened in cooperation with Kosovo – 14 synchronized patrols. - Joint patrols on the Adriatic Sea with the Republic of Croatia on Prevlaka – 1 joint patrol. |
| 1.2.18. | Cooperation with FRONTEX on the implementation of the Working Arrangement (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30.VI 2014 [IC] | POLICE ADMINISTRATION | IC Continuous activity | Number of activities carried out with FRONTEX [RK] (1) 31 December 2013 [IC] Participation in the annual conference on risk analysis in the states of the Western Balkan, held in Skoplje – Macedonia, on 15 May 2013. In the period from 2 to 13 September 2013, an officer of the Border Police participated in the specialized training organised by FRONTEX titled „Detection of forged documents” in the Netherlands. On 2 and 3 October 2013, participation in the conference of partner academies and national training coordinators in Warsaw – Poland. Monthly reports in relation to the drafting of risk analysis in the states of the Western Balkans. Three activities with FRONTEX were carried out in 2013. During 2013, 11 reports on irregular migrations in the area of Montenegro were submitted to the Unit for drafting risk analysis for the states of the Western Balkans (WB RAN). During the implementation of the programme “Fight against trafficking in human beings” of the European Agency for the Management of Operational Cooperation at the External Borders of the Member States of the European Union– FRONTEX, two advisors from the Office for the fight against trafficking in human beings completed the training and gained certificates as national trainers for the training of border police in the fight against trafficking in human beings. The training was held in Gaeta, Italy, in the period from 16 to 20 September 2013 and the following sessions were delivered: trafficking in human beings as a violation of human rights – legal framework; three phases of trafficking in human beings, vulnerable groups, vulnerability; identification of potential victims of trafficking and traffickers; transfer to the second line; mental health – access to victims; learning principles of the adults; interviewing –„7 steps“ model; case studies – interviewing victims; designing course titled trafficking in human beings for the border police. (2) 31 March 2014 [IC] Participation in the 21st International Border Police Conference, which was held in Warsaw, Poland, on 25-26 November 2013, addressing the issues of common interest for border management and exchange of experiences in the area of border security. Participation in a workshop on assessment of the interoperability programme for the joint syllabus of the basic training for border police, held in Ljubljana, Slovenia, in the period from 10 to 14 February 2014. Participation in the training for future English Language instructors, referring to the work of border police officers at airport border crossings, which was held in Bratislava, Slovakia, from 24 to 28 February 2014. There are plans for the certified officer to organize and carry out a training course in English Language for the Border Police. One officer completed the European Course for Dog Handlers and received a certificate in general handling of dogs (obedience, detection of human scent, tracking humans and use of force)” in accordance with Frontex standards on training dogs at the state border. The final, fifth, module and testing was organized in Sibiu, Romania, in the period from 10 to 23 March 2014. Participation in the Operational Heads of Airports Conference, which was held in Warsaw, Poland, from 4 to 7 March. An initiative was introduced and our officers and those of the Office for Fight against Trafficking in Human Beings met with representatives of OESC to discuss the provision of support and help in the implementation of the Frontex project “Training border police in fight against trafficking in human beings”. Monthly reporting in relation to the preparation of risk analysis for countries in the Western Balkans. (3) 30 June 2014 [IC] -Presence of lecturers from the Police Academy, in the period 25-28 March 2014, in Warsaw -Poland, on the training of FRONTEX, in compliance with the mobility project for lecturers in line with the joint curriculum and programme for the basic training of the border police in EU countries. - Participation in the meeting of experts of the Network for Risk Analysis of the countries in the Western Balkans, which was held on 02 April 2014 in Warsaw - Poland, - Presence of lecturers from the Police Academy in the period 05-16 May in the Slovak Republic, on the training of FRONTEX in compliance with the joint curriculum and programme for the basic training of the border police in EU countries. - Training conducted and completed for 119 officers of the border police on the topic ``Training of the border police for the fight against trafficking in human beings`` according to the FRONTEX project. - Monthly reporting as regards development of the risk analysis for countries of the Western Balkans | Reports on the number of employees participating in joint operations (1) 31 December 2013 [IC] In the reporting period, there were no joint operations organised by FRONTEX. (2) 31 March 2014 [?] (3) 30 June 2014 [IC] In the reporting period, there were no joint operations organised by FRONTEX. Reports on the number of working meetings, (1) 31 December 2013 [IC] During 2013, two working meetings organised by FRONTEX were held, in which border police officers participated. (2) 31 March 2014 [?] (3) 30 June 2014 [IC] - Participation of officers of the Border Police Department in the meeting of experts of the Network for Risk analysis for countries of the Western Balkans, which was held on 2 April 2014 in Warsaw - Poland, Reports on the exchange of information (1) 31 December 2013 [IC] During 2013, 11 monthly reports on movement of irregular migrations on the territory of Montenegro were submitted to FRONTEX. (2) 31 March 2014 [IC] In the reporting period, 3 monthly reports on movement of irregular migrations on the territory of Montenegro. (3) 30 June 2014 [IC] In the reporting period, 3 monthly reports on movement of irregular migrations on the territory of Montenegro. |

Recommendation 4 from the Screening report – area “Migrations“

### 1.3.	READMISSION OF IRREGULAR MIGRANTS                  Ministry of Interior	 - Dragan Dasic

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 1.3.1. | Efficient and effective implementation of the Agreement on Readmission between Montenegro and European Community regarding readmission of persons without residence permits. 1) 31 December 2013 [IC] (2) 31 March 2014 [IC] Ministry of Interior received a total of 54 requests for admission of 120 persons from EU Member States. Thirty-two requests for admission of 72 persons were granted, 16 requests for admission of 37 persons were denied, while 6 requests admission of 11 persons are being processed. (3) 30 June 2014 [IC] | MINISTRY OF INTERIOR Dragan Dasic | IC Continuous/ Permanent activity | Number of requests received for readmission of own citizens divided upon (1) 31 December 2013 [I] In the period from 1 January to 19 December 2013, a total of 108 requests for reception of 222 persons were received from EU Member States. Note: these data refer to the period from 1 January to 15 December 2013. (2) 31 March 2014 [IC] In the period from 1 January to 31 March 2014, the Ministry of Interior received from EU Member states a total of 32 readmission requests for Montenegrin citizens, which referred to 72 persons. (3) 30 June 2014 [I] In the period 1 January – 30 June 2014, the Ministry of Interior received from EU Member states a total of 39 readmission requests which referred to 87 persons. - EU Member States, (1) 31 December 2013 [I] 1. Germany - 69 requests for 149 persons; 2. Sweden - 17 requests for 36 persons; 3. Luxembourg- 8 requests for 16 persons; 4. Switzerland - 5 requests for 12 persons; 5. Austria - 2 requests for 2 persons; 6. the Netherlands - 1 request for 1 person; 7. Denmark – 2 requests for 2 persons; 8. Belgium - 1 request for 1 person; 9. France - 1 request for 1 person; 10. Finland - 1 request for 1 person; 11. Slovenia 1 request for 1 person. (2) 31 March 2014 [IC] 1.Germany - 19 requests for 49 persons; 2. Sweden 4 requests for 12 persons; 3. Poland 1 request for 1 person; 4. Luxembourg 4 requests for 6 persons; 5. Spain 3 requests for 3 persons; 6. Denmark 1 request for one person. (3) 30 June 2014 [I] 1. Germany - 23 requests for 54 persons, 2. Sweden - 5 requests for 10 persons, 3. Luxembourg - 5 requests for 17 persons, 4. Belgium - 1 request for 1 person, 5. Denmark - 2 requests for 2 persons, 6. Poland - 1 request for 1 person, 7. Spain -2 requests for 2 persons. -Number of positive answers (1) 31 December 2013 [I] In response to requests for readmission of own citizens, positive answers were received i.e. 108 requests were granted for admission of 222 persons (2) 31 March 2014 [IC] All the requests for admission of Montenegrin citizens were granted, i.e. 32 requests for admission of 72 persons submitted by relevant authorities of EU Member States were granted. (3) 30 June 2014 [I] All requests that referred to reception of Montenegrin citizens in the period 1 January – 30 June 2014 obtained positive answers, i.e. positive answers were submitted to the EU Member States for 39 requests for reception of 87 persons. -Number of negative answers, (1) 31 December 2013 [I] There were no negative replies to readmission requests of own citizens. (2) 31 March 2014 [IC] In the period from 1 January to 31 March 2014, there were no negative replies to requests for admission of own, i.e. Montenegrin, citizens. (3) 30 June 2014 [I] In the period 1 January – 30 June 2014 there were no negative replies to requests for reception of own citizens. -Number of written notifications on completed transfers, (1) 31 December 2013 [I] A total of 21 notifications for transfers were submitted. (2) 31 March 2014 [IC] In the period from 1 January to 31 March 2014, the Ministry of Interior received a total of six (6) written notifications from EU Member States on transfer of persons. (3) 30 June 2014 [I] In the period 1 January – 30 June 2014, the Ministry of Interior received in total nine (9) written notifications from the EU Member States on transfer of total 23 persons. Number of persons transferred (1) 31 December 2013 [I] 2) 31 March 2014 [IC] In the period from 1 January to 31 March 2014, EU Member States submitted notifications for six persons who were to be transferred. (3) 30 June 2014 [I] In the period 1 January – 30 June 2014, we were informed by the Police Administration that in total 13 persons were transferred to Montenegro. Number of requests received for readmission of citizens of third countries categorised as follows: (1) 31 December 2013 [I] A total of 58 requests were received for admission of 111 persons from third countries or without citizenship. (2) 31 March 2014 [IC] In the period from 1 January to 31 March 2014, the Ministry of Interior received from EU Member States a total of 17 requests for admission of persons from third countries or persons without citizenship, which referred to a total of 38 persons. (3) 30 June 2014 [I] In the period 1 January – 30 June 2014, the Ministry of Interior received from the EU Member States a total of 27 requests for admission of persons from third countries or persons without citizenship, which referred to a total of 71 persons. -Member state of EU, (1) 31 December 2013 [I] 1. Germany - 50 requests for 91 persons; 2. Sweden - 3 requests for admission of 8 persons; 3. Luxembourg - 3 requests for admission of 6 persons; 4. Switzerland - 2 requests for 6 persons. (2) 31 March 2014 [IC] 1. Germany - 15 requests for 36 persons, 2. Sweden - 1 request for 1 person, 3. Luxembourg - 1 request for 1 person. (3) 30.VI 2014 [I] 1. Germany - 28 requests for 70 persons, 2. Spain - 1 request for 1 person. -Number of positive answers, (1) 31 December 2013 [I] Positive replies were received to 8 requests for admission of 20 persons. (2) 31 March 2014 [IC] In the period from 1 January to 31 March 2014, 1 request for admission of 1 person who was not a Montenegrin citizen was granted. (3) 30 June 2014 [I] In the period 1 January -30 June 2014, the Ministry of Interior provided positive answer for 2 requests for admission of 2 persons who are not Montenegrin citizens. -Number of negative answers, (1) 31 December 2013 [I] Negative reply was given to 50 requests for admission of 91 persons. (2) 31 March 2014 [IC] In the period from 1 January to 31 March 2014, EU Member States received from the Ministry of Interior 16 negative replies referring to 37 persons. (3) 30 June 2014 [I] In the period 1 January – 30 June 2014, the EU Member States received from the Ministry of Interior a total of 25 negative replies referring to 68 persons. -Number of written notifications on completed transfers, (1) 31 December 2013 [I] During this period no written notification on transfer of citizens of third countries or persons without citizenship was submitted. (2) 31 March 2014 [IC] In the period from 1 January to 31 March 2014, the Ministry of Interior did not receive any written notification on transfer of citizens of third countries or persons without citizenship. (3) 30 June 2014 [I] In the period 1 January – 30 June 2014, the Ministry of Interior received from the EU Member States one (1) written notification on transfer of two (2) persons, who are not Montenegrin citizens. Number of transferred persons, (1) 31 December 2013 [I] During this period, there were no transferred persons who are foreign citizens or citizens without citizenship. (2) 31 March 2014 [IC] In the period from 1 January to 31 March 2014, there were no transfers of persons from EU Member States to Montenegro. (3) 30 June 2014 [I] In the period 1 January-30 June 2014, the Ministry of Interior did not obtain the information that there were transfers of foreign citizens or persons without citizenship. - Number of received/granted/denied requests for transit, - (1) 31 December 2013 [I] In the period from 1 January to 23 December 2013, transit for two persons from Slovenia to Kosovo was approved. (2) 31 March 2014 [IC] According to the records of the Police Administration, no requests for transit were received from EU Member States in the period from 1 January to 31 March 2014. (3) 30 June 2014 [I] In the period 1 January – 30 June 2014, according to the records of the Police Administration, no requests for transit were received from EU Member States. Number of accelerated border procedures, (1) 31 December 2013 [I] (2) 31 March 2014 [IC] (3) 30 June 2014 [I] Number of persons from vulnerable groups who are readmitted in country (e.g. minors and persons with special needs) (1) 31 December 2013 [I] (2) 31 March 2014 [IC] In the period from 1 January to 31 March 2014, no persons from the category of vulnerable persons were subject to readmission (3) 30 June 2014 [I] In the period 1 January – 30 June 2014, no persons from the category of vulnerable persons were subject to readmission. |  |
| 1.3.2 * | Conclusion of the implementation protocols with other EU Member States at the request of any party, on the grounds of Article 19 of the Agreement between the European Community and the Republic of Montenegro on the readmission of persons residing without authorization (1) 31 December 2013 [PI] (2) 31 March 2014 [PI] Protocol between the Government of Montenegro and the Government of the Republic of Italy on implementation of the Agreement between Montenegro and the European Community on readmission (returning and admission) of persons residing without authorization, in completely aligned in the course of negotiations which were conducted in Podgorica on 27 and 28 February 2014. Negotiations with the following countries were initiated by the Act 03 number: 050/13-79095/2 of 24 March 2014: Spain, Poland, Cyprus, Romania and Portugal. (3) 30 June 2014 [PI] Signing of this protocol was initiated by the Act 03 number: 373/14-9520/3 of 4 April 2014, through the Directorate for International Cooperation and European Integration of the Ministry of Interior. By 26 May 2014, response to the proposed initiative was not submitted. | Ministry of Interior Dragan Dasic | PI Second half; 2017; | Initiative for conducting negotiations launched, (1) 31 December 2013 [PI] The initiative was launched on 26 November 2013 through the MFAEI, Initiative for starting negotiations and conclusion of the protocol with the following countries: Finland, Hungary, Greece, Denmark, France and Sweden. By 13 December 2013, we received no response as regards the launched initiative. (2) 31 March 2014 [PI] We received response from the competent authorities of Finland and Sweden on the previously launched initiative of 26 November 2013. In the response which was submitted to us on 5 March 2014, competent authorities of Finland and Sweden indicate that for now they do not assent to conducting negotiations for the purpose of harmonization of the implementation protocol. We did not receive the response to launched initiative from other states until 31 March (Hungary, Greece, France and Denmark). We initiated conducting of negotiations with the following countries by the Act 03 number: 050/13-79095/2 of 24 March 2014: Spain, Poland, Cyprus, Romania and Portugal. Competent authorities of the Republic of Italy initiated negotiations for the purpose of harmonization of the implementation protocol by the note number: 4517/DGIT VII/deS/21670 of 30 January 2014. (3) 30 June 2014 [PI] Conducting of negotiations with the following countries was initiated by the Act 03 number: 050/13-79095/2 of 24 March 2014, through the Directorate for International Cooperation and European Integration of the Ministry of Interior: Poland, Spain, Cyprus, Romania and Portugal. By 30 June 2014, we received no response to submitted initiative. Initiative accepted and texts of proposals for the protocol exchanged, (1) 31 December 2013 [NI] By 13 December 2013, we received no response to our initiative. (2) 31 March 2014 [PI] Initiative of competent authorities of the Republic of Italy was accepted by the Act 03 number: 050/14-9592/1 of 24 February 2014 as regards negotiations for harmonization of the text of the Protocol between Montenegro and the Republic of Italy on implementation of the Agreement on Readmission (returning and admission) of persons residing without authorization. (3) 30 June 2014 [PI] In the period 1 January – 30 June 2014 the initiative of the competent authorities of the Republic of Italy was accepted and negotiations were conducted (on 27 and 28 February 2014); in the course of these negotiations, the text of the implementation protocol on readmission with the Republic of Italy was harmonized. Furthermore, the competent authorities of Hungary accepted our initiative for conducting negotiations of November 2013 and proposed that the negotiations should be conducted in the first working week of July 2014. By the Act 03-264/14-28002/2 of 10 June 2014, by mediation of the MFAEI, we proposed to the competent authorities of Hungary that the negotiations should be conducted on 3 and 4 July 2014 in Podgorica. By 30 June 2014, we received no response to this act. The deadline for conducting negotiations agreed, (1) 31 December 2013 [NI] (2) 31 March 2014 [PI] Negotiations between the delegation of the Government of Montenegro and the Government of the Republic of Italy were conducted on 27 and 28 February 2014 in Podgorica. (3) 30 June 2014 [PI] Considering the fact that the competent authorities of Hungary accepted our initiative for conducting negotiations in Podgorica and proposed that they should be conducted in the course of the first working week of July, on which we agreed and proposed 3 and 4 July 2014, we think that this deadline has been agreed, unless some technical problems or misunderstandings in diplomatic communication occur. Text of the protocol harmonised and signed, (1) 31 December 2013 [NI] (2) 31 March 2014 [PI] The text of the Protocol between the Government of Montenegro and the Government of the Republic of Italy was completely harmonised and signed by heads of delegations, in the course of negotiations which were conducted on 27 and 28 February 2014 in Podgorica. (3) 30 June 2014 [PI] The text of the Protocol on Readmission between the Government of Montenegro and the Government of the Republic of Italy has been harmonized and signed in the period 1 January – 30 June 2014. Protocol signed, (1) 31 December 2013 [NI] (2) 31 March 2014 [PI] At the session held on 19 March 2014, the Government of Montenegro provided the consent for the text of the Protocol between the Government of Montenegro and the Government of the Republic of Italy on implementation of the Agreement between the European Community and Montenegro on the readmission of persons residing without authorization and authorized the Minister of Interior to sign it. (3) 30 June 2014 [PI] The signing of the Protocol between the Government of Montenegro and the Government of Italy was initiated by the Act 03 number: 373/14-9520/3 of 4 April 2014, through the Directorate for International Cooperation and European Integration of the Ministry of Interior. By 30 June 2014, we received no response to submitted initiative. Entry of the Protocol into force (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] The Protocol will enter into force after signing and completion of internal procedures by both Montenegro and the Republic of Italy. (3) 30 June 2014 [PI] In the period 1 January-30 June 2014, the Announcement was passed for entry into force of the Protocol on Readmission between Montenegro and the Republic of Estonia (Official Gazette of Montenegro-International Treaties 6/14), of 11 June 2014, stating that the Protocol which was signed in New York on 24 September 2013 entered into force on 2 May 2014. | Statistical indicators on the number of persons subject to readmission, (1) 31 December 2013 [PI] The measure is partially implemented due to the fact that we implement the Agreement between the Republic of Montenegro and the European Union with the EU Member States with which we did not conclude the readmission protocols, for example Sweden. (2) 31 March 2014 [NI] We will be able to provide statistical data on the number of persons subject to readmission after the beginning of implementation of the protocol. For now, this area is regulated by the Agreement between Montenegro and the European Community of the readmission (returning and admission) of persons residing without authorization. (3) 30 June 2014 [PI] The measure is partially implemented due to the fact that we implement the Readmission Agreement between the Republic of Montenegro and the European Union with the EU Member States with which we did not conclude the readmission protocols, for example Hungary. Reports of the expert assessment on implementation of the readmission agreement and protocol, (1) 31 December 2013 [NI] (2) 31 March 2014 [I] The European Commission did not have comments for the first Report on implementation of the readmission agreement and protocol. (3) 30 June 2014 [PI] The European Commission did not have comments for the first Report on implementation of the readmission agreement and protocol. |

Recommendation 5 from the Screening report - Migrations

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 1.3.3. | Adopt the Law on Ratification of the Agreement and the Implementing Protocol with the Republic of Serbia and the Law on Ratification of the Agreement with the Republic of Turkey. (1) 31 December 2013 [I] | MINISTRY OF INTERIOR Dragan Dasic | I December; 2013; | Proposals for the Law on Ratification of the Agreement with the Republic of Serbia and the Republic of Turkey adopted (1) 31 December 2013 [I] Pursuant to the Conclusion No. 1258/3 of 13 June 2013, the Government of Montenegro adopted the Proposal for the Law on the Ratification of the Agreement with the Republic of Serbia. Pursuant to the Conclusion No. 1259/3 of 13 June 2013, the Government of Montenegro adopted the Proposal for the Law on the Ratification of the Agreement with the Republic of Turkey. The Laws on the Ratification of the Agreement with the Republic of Serbia and the Republic of Turkey adopted, (1) 31 December 2013 [I] The Law on the Ratification of the Agreement on readmission (return and admission) of persons, whose entrance or stay is illegal, between the Government of Montenegro and the Government of the Republic of Serbia, was published together with the Implementing Protocol in the Official Gazette of Montenegro – International treaties, 08/13 of 22 October 2013. In the above mentioned Official Gazette, the Law on the Ratification of the Agreement on Readmission with the Republic of Turkey was also published. Entry into force of the Laws on Ratification of the Agreements with the Republic of Serbia and the Republic of Turkey, (1) 31 December 2013 [I] The laws entered into force on 31 October 2013. | Number of persons subject to readmission (1) 31 December 2013 [NI] The laws ratifying these agreements entered into force, but the Agreements have not yet entered into force which depends on the authorities in the Republic of Serbia and the Republic of Turkey. |
| 1.3.4. | Initiating and conducting negotiations related to concluding the Agreement on Readmission with Iceland. (1) 31 December 2013 [PI] (2) 31 March 2014 [PI] (3) 30 June 2014 [PI] The initiative for conducting negotiations with a view to harmonizing the Agreement on Readmission was submitted to the Republic of Iceland in February 2012, October 2013 and March 2014. By 26 May 2014, we received no response as regards the submitted initiatives. | MINISTRY OF INTERIOR Dragan Dasic | PI December; 2014; (Competent Montenegrin bodies will initiate the negotiations for the signing of the Agreement in the third quarter of 2013). | Initiative for negotiations launched, (1) 31 December 2013 [I] The Initiative for conducting negotiations and concluding agreement was sent to the Republic of Iceland through the Ministry of Foreign Affairs and European Integration on 31 September 2013. By 26 December 2013, we received no reply in relation to the initiative. (2) 31 March 2014 [I] Through the Act 03 No. 050/13-71715/3 of 25 March 2014 submitted via the Directorate for International Cooperation and European Integration of the Ministry of Interior, the initiative was presented to the Republic of Iceland initiative, along with a proposal to conduct negotiations in Podgorica with a view to coordinating the text of the Agreement. Along with this initiative, the competent authorities of Iceland were also presented with a Draft Agreement prepared by the Directorate for Foreigners, Migration and Readmission. Through the Act 03 No. 050/13-71715 of 25 March 2014, submitted via the Directorate for International Cooperation and European Integration of the Ministry of Interior, the initiative was submitted again. Note: In February 2012, October 2013 and March 2014, the Republic of Iceland was presented with an initiative to conduct negotiations in order to coordinate the text of the Agreement on Readmission. By 31 March 2014 no reply was received in relation to the aforesaid initiatives. (3) 30 June 2014 [I] Through the Act 03 No. 050/13-71715/3 of 25 March 2014, submitted via the Directorate for International Cooperation and European Integration of the Ministry of Interior, the initiative was submitted to the Republic of Iceland with the proposal for conducting negotiations with a view to final harmonizing of the text of the Agreement on Readmission. The Draft Agreement was submitted along with the initiative. By 30 June we received no response to the submitted initiative. Initiative accepted and drafts of Proposals for Agreement exchanged, (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] We have received no response in relation to our initiatives of February 2012 and October 2013. (3) 30 June 2014 [NI] Note: Since 30 June 2014 we received no response to the submitted initiative. Dates for conducting negotiations agreed, (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] Date for negotiations has not been agreed. (3) 30 June 2014 [NI] Note: The date for conducting negotiations was not agreed since we still did not receive the response to the submitted initiative. Text of the Agreement agreed and initialled, (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] Text of the Agreement has not been agreed and initialled. (3) 30 June 2014 [NI] Note: Text of the Agreement has not been agreed Initiative for signing of the Agreement launched, (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] Initiative for signing of the Agreement has not been launched, since it has not been agreed. (3) 30 June 2014 [NI] Note: Text of the Agreement has not been agreed. Initiative accepted and date for signing the Agreement agreed, (1) 31 December 2013 [NI] (2) 31March 2014 [NI] Date for signing of the Agreement has not been agreed as it has neither been finalised nor approved by the Government of Montenegro. (3) 30 June 2014 [NI] The Agreement signed, (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] Agreement has not been signed, because it has not been finalised. (3) 30 June 2014 [NI] Note: Text of the Agreement has not been agreed. Proposal for the Law on Ratification of the Agreement adopted, (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] Proposal for the Law on Ratification of the Agreement has not been adopted, because it has neither been finalized, nor signed. (3) 30 June 2014 [NI] Note: The Agreement has not been signed. The Law on Ratification of the Agreement adopted in the Parliament (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] The Law on Ratification of the Agreement has not been adopted, because it has neither been finalised nor signed. (3) 30 June 2014 [NI] Note: The Agreement has not been signed. | Number of persons who are subject to readmission (1) 31 December 2013 [NI] Agreement has not been signed, which is why there are no persons subject to readmission. (2) 31 March 2014 [NI] Agreement has not been signed, which is why there are no persons subject to readmission. (3) 30 June 2014 [NI] Note: The Agreement on Readmission with the Republic of Iceland has not been signed; therefore, there are no persons subject to readmission between Montenegro and the Republic of Iceland. |
| 1.3.5. | Continuation of negotiations in order to conclude the Agreement and the Implementing Protocol with the Russian Federation. (1) 31 December 2013 [PI] (2) 31 March 2014 [PI] (3) 30 June 2014 [PI] By the Conclusion: 08-1029/3 of 8 May 2014, the Government of Montenegro adopted the Information on negotiations between the delegation of the Government of Montenegro and the delegation of the Government of the Russian Federation on the conclusion of the Agreement on Readmission, accepted the text of the Agreement with the Protocol and authorized the Minister of Interior to sign it. Signing of the Agreement and the Protocol was initiated by the Act 03 number: 261/14-3021/5 of 14 May 2014, through the Directorate for International Cooperation and European Integration of the Ministry of Interior. By 26 May 2014, we received no response to the proposed initiative. | MINISTRY OF INTERIOR Dragan Dasic | PI December ; 2014; | The first round of negotiations held in March 2013, (1) 31 December 2013 [I] The first round of negotiations was held on 5 October 2013. The text of the Agreement was largely agreed. (2) 31 March 2014 [?] No further reporting required (3) 30 June 2014 [I] Continuation of negotiations initiated , (1) 31 December 2013 [PI] The initiative proposed by the competent authorities of the Russian Federation for conducting the second round of the negotiations was accepted via the Directorate for International Cooperation of the Ministry of Interior. By 26 December 2013 the date for conducting the negotiations was not defined. (2) 31 March 2014 [I] The competent authorities of the Russian Federation proposed, through the Ministry of Foreign Affairs and European Integration, that the second round of negotiations be held in Moscow on 12 and 13 March 2014. (3) 30 June 2014 [I] The competent authorities of the Russian Federation initiated conducting of the second round of negotiations for 12 and 13 March 2014. The date for conducting the second round of the negotiations agreed, (1) 31 December 2013 [NI] Date for the second round of negotiations has not been agreed. (2) 31 March 2014 [I] The initiative proposed by the competent authorities of the Russian Federation was accepted through the letter of the Ministry of Interior No. 03-261/14-3021/2 of 24 January 2014. (3) 30 June 2014 [I] The initiative of the competent authorities of the Russian Federation was accepted and the negotiations were conducted on 12 and 13 March 2014 in Moscow. Text of the Agreement and Implementing Protocol agreed and initialled, (1) 31 December 2013 [NI] (2) 31 March 2014 [I] During the negotiations in Moscow, the text of the Agreement between the Government of Montenegro and the Government of the Russian Federation on readmission (return and admission) of persons residing without authorization and the text of the Protocol for its implementation was fully agreed. After the completion of negotiations, heads of delegations signed the Minutes on the negotiations stating the fact that the texts of the Agreement and the Protocol were fully agreed upon. (3) 30 June 2014 [I] Initiative launched for signing the Agreement and Implementing Protocol, (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] The signing procedure will be initiated after the Government of Montenegro approves the texts of the Agreement and the Protocol and authorizes the Minister of Interior to sign them. (3) 30 June 2014 [I] The signing of the Agreement and the Protocol was initiated by the Act 03 number: 261/14-3021/5 of 14 May 2014. By 30 June 2014 we received no response to the proposed initiative. Initiative accepted and date agreed for signing of the Agreement and Implementing Protocol, (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] After the Government of Montenegro approves the texts of the Agreement and the Protocol and authorises the Minister of Interior to sign them, a date for the signing will be proposed. (3) 30 June 2014 [NI] Agreement and Implementing Protocol signed, (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] After the Government of Montenegro approves the texts of the Agreement and the Protocol and authorises the Minister of Interior to sign them, the signing of the Agreement and the Protocol will be initiated. (3) 30 June 2014 [NI] Note: The initiative has been submitted to the competent authorities of the Russian Federation Proposal for the Law on Ratification of the Agreement adopted, (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] This procedure will follow after the signing of the Agreement and the Protocol. (3) 30 June 2014 [NI] Note: The Proposal for the Law on Ratification of the Agreement has not been adopted since the Agreement has not been signed. The Law on Ratification of the Agreement adopted in the Parliament (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] This procedure will follow after the signing of the Agreement and the Protocol. (3) 30 June 2014 [NI] | Number of persons who are subject to readmission, (1) 31 December 2013 [NI] Since the Agreement on Readmission has not been signed, there are no persons subject to readmission. (2) 31 March 2014 [NI] References to persons subject to readmission can only be made after the Agreement and the Protocol enter into force. (3) 30 June 2014 [NI] Note: Considering the fact that the Agreement on Readmission between Montenegro and the Russian Federation has not been signed, there are no persons subject to readmission between these two states. |

OBJECTIVE: Adopt new strategy of reintegration of persons returned on the basis of the Agreement on Readmission, with the Action Plan for its implementation

## 2.	ASYLUM                Ministry of Interior	 - Sandra Bugarin

Recommendation 1 from the Screening Report – ``Asylum“

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 2.1. | Establish an inter-ministerial working group for the drafting of the new Law on Asylum Prepare an analysis of the impact of the new Law on administrative and technical capacities of the competent authorities engaged in the asylum system (2) 31 March 2014 [I] (3) 30 June 2014 [I] | Ministry of Interior Sandra Bugarin | I April ; 2014; September; 2014 | Working group established and started to work (2) 31 March 2014 [I] By the Decision of the Minister of Interior 01 No. 050/14-9502/2 of 5 March 2014, an inter-ministerial working group was established to draft the new Law on Asylum, secondary legislation for implementation of the law and prepare an analysis of the impact of the new Law on administrative and technical capacities of the competent authorities involved in the asylum system. Members of the inter-ministerial working group for the drafting of the new Law on Asylum include representatives of the Ministry of Interior, Ministry of Labour and Social Welfare, Ministry of Justice, Ministry of Education, Ministry of Health, Ministry of Finance, Ministry of Foreign Affairs and European Integration, Ministry for Human and Minority Rights, University of Montenegro, UNHCR and NGO Legal Centre and NGO CEDEM. (3) 30 June 2014 [I] By the Decision of the Minister of Interior 01 No. 050/14-9502/2 of 5 March 2014, an inter-ministerial working group was established to draft the new Law on Asylum, secondary legislation for implementation of the law and prepare an analysis of the impact of the new Law on administrative and technical capacities of the competent authorities involved in the asylum system. Members of the inter-ministerial working group for the drafting of the new Law on Asylum include representatives of the Ministry of Interior, Ministry of Labour and Social Welfare, Ministry of Justice, Ministry of Education, Ministry of Health, Ministry of Finance, Ministry of Foreign Affairs and European Integration, Ministry for Human and Minority Rights, University of Montenegro, UNHCR and NGO Legal Centre and NGO CEDEM. Analysis completed (2) 31 March 2014 [?] (3) 30 June 2014 [?] | Ensuring participation and engagement of all relevant institutions in the process of harmonising legislation (2) 31 March 2014 [I] Members of the inter-ministerial working group for the drafting of the new Law on Asylum include representatives of the Ministry of Interior, Ministry of Labour and Social Welfare, Ministry of Justice, ministry of Education, Ministry of Health, Ministry of Finance, Ministry of Foreign Affairs and European Integration, Ministry for Human and Minority Rights, University of Montenegro, UNHCR and NGO Legal Centre and NGO CEDEM. (3) 30 June 2014 [I] Members of the inter-ministerial working group for the drafting of the new Law on Asylum include representatives of the Ministry of Interior, Ministry of Labour and Social Welfare, Ministry of Justice, ministry of Education, Ministry of Health, Ministry of Finance, Ministry of Foreign Affairs and European Integration, Ministry for Human and Minority Rights, University of Montenegro, UNHCR and NGO Legal Centre and NGO CEDEM. The inter-ministerial working group had their first meeting on 25 March, when modalities for future activities were identified and personal duties of every individual member specified, in compliance with competences of authorities that delegated them. The second meeting of a part of the inter-ministerial working group was held on 20 June with a view to specifying obligations of certain members in the process of development of the Analysis of Impact of the new Law on Asylum to administrative and technical capacities of the competent authorities involved in the asylum system. |
| 2.6 * | Educate the trainers for the training of civil servants and police officers of the border police in the asylum system (3) 30 June 2014 [I] | Ministry of Interior Sandra Bugarin | I Second quarter; 2014 | Trainers educated (3) 30 June 2014 [I] Trainers for training of civil servants and police officers of the border police in the asylum system have attended three sets of trainings at the Police Academy. The training was conducted by representatives of UNHCR and the Directorate for Asylum in the period 28 – 29 May 2014, 10 – 11 June 2014 and 23 – 24 June 2014. | The list of educated trainers developed. (3) 30 June 2014 [I] Thirty trainers of the Border Police were educated on the following topics: national legislation in the area of asylum, European legislation and international standards in the work with asylum seekers, with special emphasis on vulnerable groups. Training course of trainers for the border police officers in the asylum system 28-29 May– 10 attendees 10-11 June– 10 police officers 23-24 June– 10 attendees Number of conducted trainings and number of civil servants and police officers who will be educated by trainers. (3) 30 June 2014 [IC] Educated trainers will share the knowledge they obtained with colleagues from the Border Police, in the course of everyday work in case they have the contact with asylum seekers. Training course of trainers for the border police officers in the asylum system 28-29 May – 10 attendees 10-11 June – 10 police officers 23-24 June – 10 attendees |
| 2.7. | Train the state, border and other police officers in the asylum system, as required, with regard to recognising asylum seekers, establishing the origin of asylum seekers, analysis of reasons for seeking asylum, translation and interpretation, as well as monitoring voluntary returns, with special reference to vulnerable groups such as: unaccompanied minors, women under risk, victims of violence, non-refoulement, international standards and rights of refugees. (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | POLICE ACADEMY | IC Continuously | The number of delivered trainings, [RK] (1) 31 December 2013 [IC] 1 training In cooperation with the EU Delegation in Podgorica, the Directorate for Asylum organized an expert visit with the support of TAIEX for the training of officers engaged in the asylum system regarding: procedures at the border, recognising bona fides refugees, vulnerable groups, non –refoulement, standards for the reception of the asylum seekers. The visit was carried out in the period from 7 to 11 October 2013. (2) 31 March 2014 [IC] From 17 to 21 March 2014, 10 police officers at the Border Police completed the training organized with the support of TAIEX regarding: “recognizing asylum seekers”, “identifying the country of origin”, “analysis of reasons for seeking asylum” “monitoring voluntary returns”,” special reference to vulnerable groups”... In the period from 7 to 11 April 2014, 10 police officers at the Border Police completed the training organized with the support of TAIEX regarding: “recognizing asylum seekers”, “identifying the country of origin”, “analysis of reasons for seeking asylum” “monitoring voluntary returns”,” special reference to vulnerable groups”... (3) 30 June 2014 [IC] In cooperation with the EU Delegation in Podgorica, the Directorate for Asylum organized the expert visit with the help of TAIEX for training of officers involved in the asylum system, on the topic: procedures at the border, recognizing bona fides refugee, vulnerable groups, non -refoulement, standards for the reception of the asylum seekers. The visit took place in the period 02-06 June 2014. At the Border Police Course, the topic titled Asylum System is addressed in 7 classes (Police Academy). The number of civil servants trained (1) 31 December 2013 [IC] Five civil servants and 20 border police officers were trained in relation to: procedures at the border, recognizing bona fides refugees, vulnerable groups, non – refoulement, standards for the reception of the asylum seekers. (2) 31 March 2014 [IC] From 17 to 21 March 2014, 10 police officers at the Border Police completed the training organized with the support of TAIEX. From 7 to 11 April, 10 police officers at the Border Police completed the training organized with the support of TAIEX. (3) 30 June 2014 [IC] Five civil servants and ten border police officers were trained on the following topics: procedures at the border, recognizing bona fides refugee, vulnerable groups, non -refoulement, standards for the reception of the asylum seekers. |  |

Recommendation 2 from the Screening Report– area “Asylum”

Recommendation 3 from the Screening Report– area “Asylum”

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 2.15. | Strengthen the administrative capacities of the Directorate for Asylum. Strengthen the administrative capacities of the Asylum Directorate through its reorganisation and increase in the number of civil servants and work efficiency. Establishment of the mechanisms for the translation needs with countries in the region and increase the number of interpreters for the needs of Directorate for Asylum. (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] The bylaw on job description of the Directorate for Asylum provides for 6 positions, with 5 positions occupied, while a vacancy notice for the one remaining position was published through the Human Resources Administration on 24 February 2014. (3) 30 June 2014 [IC] | MINISTRY OF INTERIOR Sandra Bugarin | IC December 2013; fourth quarter; 2016 | Out of 6 envisaged civil servant positions in the Asylum Directorate, 4 are currently occupied, while the remaining two will be occupied within the set deadline (1) 31 December 2013 [PI] 1 position filled. With a view to implementing the above mentioned activity at the Asylum Directorate, one position for civil servant was filled, an independent advisor I –administrator of proceedings. Currently, according to the existing Rulebook on internal organization and job description, one position remained vacant – independent advisor III, which is to be filled after the completion of a hiring procedure for a civil servant. In accordance with the Rulebook on internal organization and job description, the Directorate for Asylum has 6 positions, 5 of which have been filled (the fifth position was filled in July 2013), while the sixth position will be filled after the completion of a hiring procedure for a civil servant. Considering the complexity of procedures for hiring a civil servant, it is impossible to specify the exact time when this vacancy will be filled. (2) 31 March 2014 [PI] The bylaw on job description of the Directorate for Asylum provides for 6 positions, with 5 positions occupied, while a vacancy notice for the one remaining position was published through the Human Resources Administration on 24 February 2014. (3) 30 June 2014 [PI] Following publication of the vacancy notice through the Human Resources Administration on 24 February 2014, testing for the applicants was conducted on 19 May 2014. Administrative capacities of the Asylum Directorate strengthened, number of civil servants and interpreters increased, technical conditions met for establishing translation mechanisms with the countries in the region and reorganisation carried out by establishing special Divisions (1) 31 December 2013 [NI] Note: Planned by December 2016 (3) 30 June 2014 [?] Division for procedures (receiving requests, conducting procedures) (1) 31 December 2013 [NI] Note: Planned by December 2016 (3) 30 June 2014 [?] Division for searching information on countries of origin of asylum seekers, connecting and electronic updating with relevant information sources regarding countries of origin of asylum seekers (1) 31 December 2013 [NI] Note: Planned by December 2016 (3) 30 June 2014 [?] Division – Dublin Unit (1) 31 December 2013 [NR] Note: Planned by December 2016 (3) 30 June 2014 [?] | Statistical indicators on the number of requests submitted/solved; resolved within the legally set deadline, the number of backlog cases; (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] From 1 January to 1 April 2014, the Directorate for Asylum received 118 requests for asylum, including 104 from men and 14 from women. Out of this number, 70 conclusions were adopted to terminate proceedings, 3 decisions to deny request and 45 requests are being processed. In this period, additional protection was approved for two persons who filed requests for asylum in late 2013. (3) 30 June 2014 [IC] In the period 1 January – 17 June 2014, the Directorate for Asylum received 394 requests for asylum - 340 from men and 54 from women. Out of that number, one positive decision was adopted (refugee status), 336 conclusions on termination of the procedure, 6 decisions on denial of the request and 51 requests are being processed. In this period, additional protection was approved for two persons who filed the request for asylum in late 2013. Practice of the Asylum Directorate in the implementation of the new Law on Asylum, complimentary to the EU practice, to be confirmed through expert reports (1) 31 December 2013 [NI] (3) 30 June 2014 [?] |
| 2.16. | Establish the mechanism of permanent monitoring in order to improve asylum procedures. (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | MINISTRY OF INTERIOR Sandra Bugarin | IC Continuously | The number of monitored interviews, the number of monitored decisions, gap analysis Over 600 statements and decisions for the asylum seekers. (1) 31 December 2013 [I] In the period July – August 2013, representatives of UNHCR were present during taking of statements from 12 asylum seekers (all notifications and decisions were also submitted to them). Due to a small number of employees in the UNHCR Office in Podgorica, it was agreed that, in the future, they will get involved and monitor the cases of persons from war-torn areas, as well as cases of especially vulnerable groups, such as minors, women, and victims. Representatives of UNHCR analysed 580 asylum applications in Montenegro for the period from 1 September to 15 October 2013; decisions were not analysed because in that period no decision was made on the merits. However, decisions on suspension of procedure were made. Considering 20 applications UNHCR, in cooperation with NGO Legal Centre, visited the centre for collective accommodation of the asylum seekers, where only four asylum seekers were found. Later, those four persons did not come to scheduled interviews. Representatives of UNHCR analysed 85 asylum applications in Montenegro for the period from 15 October to 16 December 2013; 34 applications were considered to be grounded asylum applications. In this regard, in cooperation with NGO Legal Centre, they continued to engage in those cases. Yes, this was a control of the decisions made by the Directorate for Asylum. More than 600 statements and decisions were analyzed in this reporting period. Legal Centre is a nongovernmental organization, i.e. an executive partner of UNHCR which deals with providing free legal aid to asylum seekers. UNHCR is monitoring the activities and decisions of the Directorate for Asylum as part of its regular mandate and in accordance with the provisions of the Law on Asylum, and not as a result of a special project. (2) 31 March 2014 [IC] Representatives of UNHCR were present when 3 asylum seekers made their statements (all the documents and decisions were presented to them for cases when they were not presented). (3) 30 June 2014 [IC] For the period January – June 2014, representatives of UNHCR were present during taking of statements from 7 asylum seekers. All the documents and decisions were submitted to them for cases of asylum seekers who did not appear on the scheduled interview or who left Montenegro in the course of the proceeding. Reports on completion of monitoring (semi-annual reports) (1) 31 December 2013 [IC] Drafting semi-annual report on completion of monitoring (period from 1 July to 1 January 2013) is an ongoing activity, which will be completed by the end of January 2014. UNHCR produced a semi-annual monitoring report for the period from 1 July to 31 January 2013, which was submitted to The ministry of Interior and Ministry of Foreign Affairs and European Integration. (2) 31 March 2014 [IC] In late January 2014, UNHCR produced a monitoring report on the work of the Directorate for Asylum. The report was submitted to the Ministry of Interior and Ministry of Foreign Affairs and European Integration. (3) 30 June 2014 [?] | Asylum procedures quality improved and best practices identified (1) 31 December 2013 [RK] (2) 31 March 2014 [RK] Through the expert support of TAIEX, the Directorate for Asylum became better acquainted with European practices for asylum granting procedures, which will be implemented through the adoption of the new Law on Asylum. (3) 30 June 2014 [IC] Through the expert support of TAIEX, the Directorate for Asylum became better acquainted with European practices for asylum granting procedures, which will be implemented through the adoption of the new Law on Asylum. |
| 2.17. | Train staff of the Asylum Directorate and the State Commission for Resolving Asylum-Related Complaints, focusing on identification of countries of origin of asylum seekers, reasons for seeking asylum, translation and interpretation, as well as with regard to supervision of voluntary departures and EURODAC, with a special emphasis on vulnerable groups such as: unaccompanied minors, women under risk, victims of violence, non-refoulement, international standards and the rights of refugees. (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | MINISTRY OF INTERIOR Sandra Bugarin | IC Continuously | Staff of the Asylum Directorate and State Commission for Resolving Asylum-Related Complaints additionally trained (1) 31 December 2013 [IC] Five officers of the Asylum Directorate trained. The Asylum Directorate, in cooperation with EU Delegation in Podgorica, organized expert visit through support of TAIEX for training of officers engaged in the asylum system. The visit was carried out in the period from 7 to 11 October 2013. Five officers of the Asylum Directorate completed training in the following areas: safe country of origin, safe third country, first state of asylum, inadmissible applications and retrieval and cancellation of refugee status as additional protection, acts of persecution, and actors of persecution, vulnerable groups and non-refoulement. Representatives of UNHCR in Montenegro presented the paper “International Protection Considerations with regard to people fleeing the Syrian Arab Republic, Update II”; the training was held on 18 November 2013 for five officers from the Asylum Directorate. Representatives from UNHCR in Montenegro presented paper “Beyond proof, credibility assessment in EU asylum system”, published in May 2013 in Brussels. The training was held on 20 November 2013 for five officers of the Asylum Directorate. 2) 31 March 2014 [IC] From 17 to 21 March 2014, 5 officers of the Directorate for Asylum and 5 officers of the State Commission were trained in the following areas: “identifying the country of origin”,, “analysis of reasons for seeking asylum”, "EURODAC and DABLIN", "vulnerable groups", "non-refoulement", "rights of refugees in EU legislation ". From 7 to 11 April 2014, with the support of TAIEX, 5 officers of the Directorate for Asylum were trained in the following areas: “identifying the country of origin”,, “analysis of reasons for seeking asylum”, "EURODAC and DABLIN", "vulnerable groups", "non-refoulement", "rights of refugees in EU legislation ". (3) 30 June 2014 [IC] In the period 02-06 June 2014, with the support of TAIEX, 5 officers of the Directorate for Asylum were trained in the following areas: “identifying the country of origin”,, “analysis of reasons for seeking asylum”, "EURODAC and DABLIN", "vulnerable groups", "non-refoulement", "rights of refugees in EU legislation ". |  |
| 2.18. | Strengthen the cooperation with the countries in the region as regards monitoring mixed migrations and asylum system, by initiating meetings and taking part in regional initiatives. (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | MINISTRY OF INTERIOR Sandra Bugarin | IC Continuous activity | The number of held bilateral and multilateral meetings, (1) 31 December 2013 [IC] 1 meeting On 10 and 11 December, in cooperation with IOM and UNHCR, a round table was held in Vienna in relation to: “Development of overall regional access to protection of refugees and international migrations in the Western Balkans”. This round table represented the continuation of activities organized by IOM and UNHCR in relation to the Regional initiative for the development of overall regional access to international migrations and protection of refugees in the Western Balkans and with the aim to build the capacities of the countries of the Western Balkans to introduce introducing a more efficient migration policy. Regional round table in Vienna: The round table was co-organised by UNHCR and IOM, with participants from Croatia, Bosnia and Herzegovina, Serbia, Kosovo, Montenegro, Albania and Macedonia. Representatives of the European Commission and MARRI also participated in the round table. No conclusions were adopted at the round table, but an agreement was reached for UNHCR and IOM to produce a regional plan, based on the discussion among participants, with a set of short-term, mid-term and long-term measures that need to be introduced at the national and regional level in order for the countries of the region to be able to address more effectively the phenomenon of mixed migrations. The regional plan is being finalized and it is expected to be presented to participating countries during February. (2) 31 March 2014 [IC] There were no activities in this area in the reporting period. (3) 30 June 2014 [IC] There were no activities in this area in the reporting period. The number of adopted recommendations, (1) 31 December 2013 [?] (2) 31 March 2014 [RK] There were no activities in this area in the reporting period. (3) 30 June 2014 [?] Reports on the implementation of recommendations adopted in regional conferences (1) 31 December 2013 [?] (2) 31 March 2014 [IC] There were no activities in this area in the reporting period. (3) 30 June 2014 [PI] There were no activities in this area in the reporting period. | Better quality of monitoring mixed migrations and asylum system in the region, to be confirmed through expert reports. (1) 31 December 2013 [?] (2) 31 March 2014 [RK] There were no activities in this area in the reporting period. (3) 30 June 2014 [IC] There were no activities in this area in the reporting period. |

Recommendation 4 from the Screening Report– area “Asylum”

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 2.19. * | Centre for Asylum Seekers put into operation with the capacity of 65 beds, with the possibility of increasing the capacity to 100 beds in case of a need. (1) 31 December 2013 [I] Measure is being monitored by EU and UNHCR. (2) 31 March 2014 [IC] The Centre admitted asylum seekers on 20 February 2014. It accommodated 14 persons who previously stayed in alternative accommodation facilities in Konik and Vrela Ribnicka-Podgorica. In addition, the person who filed asylum requests in Montenegro in the reporting period was also accommodated at the Centre. Since the date of their transfer to the Centre, there have been no asylum seekers in alternative accommodation facilities. Persons seeking asylum are provided with 3 meals and medical care at the Centre. (3) 30 June 2014 [IC] | MINISTRY OF LABOUR AND SOCIAL WELFARE Zeljko Sofranac | IC Dec.13 | Centre for asylum seekers put into function (1) 31 December 2013 [I] Centre was opened on 3 February 2014 (2) 31 March 2014 [IC] The Centre admitted asylum seekers on 20 February 2014. It accommodated 14 persons who previously stayed in alternative accommodation facilities in Konik and Vrela Ribnicka-Podgorica. In addition, the person who filed asylum requests in Montenegro in the reporting period was also accommodated at the Centre. Since the date of their transfer to the Centre, there have been no asylum seekers in alternative accommodation facilities. Persons seeking asylum are provided with 3 meals and medical care at the Centre. (3) 30 June 2014 [I] | Conditions created for accommodation of asylum seekers in the Centre [DR] (1) 31 December 2013 [I] Centre was opened on 3 February 2014 (2) 31 March 2014 [IC] It accommodated 14 persons who previously stayed in alternative accommodation facilities in Konik and Vrela Ribnicka-Podgorica. In addition, the person who filed asylum requests in Montenegro in the reporting period was also accommodated at the Centre. Since the date of their transfer to the Centre, there have been no asylum seekers in alternative accommodation facilities. Persons seeking asylum are provided with 3 meals and medical care at the Centre. (3) 30 June 2014 [IC] The Conclusion of the Ministry of Finance of 16 June 2014 prescribes the duty for the Ministry of Labour and Social Welfare to consider the possibility of increase of the existing accommodation capacities in cooperation with the Ministry of Finance. The number of asylum seekers, persons with approved protection and vulnerable groups for which care was provided (1) 31 December 2013 [IC] 3472 asylum seekers were accommodated in 2013 There were no persons under protection Number of vulnerable groups: - a total of 51 minors *up to one year of age (babies), six persons *between one and eighteen years of age, 45 persons -unaccompanied minors, four persons -unaccompanied women, 191 persons -pregnant women, one of whom was unaccompanied -two breastfeeding women All the aforesaid members of vulnerable groups were accommodated in the period June-December 2013, except three unaccompanied female persons (2) 31 March 2014 [IC] In this period, two persons were accommodated who were approved additional protection (3) 30 June 2014 [IC] 332 persons - 63 members of vulnerable groups (52 unaccompanied women and 11 juveniles) were accommodated in the period 31 March 2014 – 30 June 2014. |
| 2.20. | Secure additional accommodation capacities for asylum seekers in alternative facilities (lease of alternative private facilities for 150 persons). (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | MINISTRY OF LABOUR AND SOCIAL WELFARE Zeljko Sofranac | IC Continuous activity | Additional accommodation in alternative facilities secured (1) 31 December 2013 [IC] Alternative accommodation was provided through lease of residential facilities. Due to a greater number of asylum seekers than expected, 250 places were secured. Alternative accommodation facilities are located in Konik, in Podgorica. (2) 31 March 2014 [IC] If necessary alternative accommodation capacities will be secured. (3) 30 June 2014 [IC] On 16 June 2014, the Ministry of Finance informed the Ministry of Labour and Social Welfare that it can provide alternative accommodation for persons from the asylum system, following complete use of accommodation capacities or in case of sudden inflow of a large number of asylum seekers. | Provided conditions for reception of asylum seekers, (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] There were no activities in this reporting period. (3) 30 June 2014 [IC] There was no need for alternative accommodation. The number of asylum seekers, persons with approved protection and vulnerable groups for which care was provided (1) 31 December 2013 [IC] 3472 asylum seekers were accommodated in 2013 There were no persons under protection Number of vulnerable groups: - a total of 51 minors *up to one year of age (babies), six persons *between one and eighteen years of age, 45 persons -unaccompanied minors, four persons -unaccompanied women, 191 persons -pregnant women, one of whom was unaccompanied -two breastfeeding women All the aforesaid members of vulnerable groups were accommodated in the period June-December 2013, except three unaccompanied female persons. (2) 31 March 2014 [IC] There were no activities in this reporting period. (3) 30 June 2014 [IC] There was no need for alternative accommodation. |
| 2.21. | Establish the mechanisms of permanent monitoring in relation to occupancy and evaluation of adequacy of capacities of the Centre for Asylum Seekers with support of UNHCR, with special focus on vulnerable groups and the preparation of analysis for defining additional accommodation needs. (1) 31 December 2013 [NI] Report can be prepared only after 6 months on 30 June 2014 because the Action Plan for Chapter 24 provides that the implementation of this measure should start after the Centre is put into operation (3 February 2014) (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | MINISTRY OF LABOUR AND SOCIAL WELFARE Zeljko Sofranac | IC Continuous activity [4]; | Analysis of the state, report on conducted monitoring (semi-annual reports); Adapting the existing capacities on the basis of current monitoring (1) 31 December 2013 [NI] Mechanisms of permanent monitoring in relation to occupancy and evaluation of adequacy of capacities of the Centre for Asylum Seekers with support of UNHCR, with a special focus on vulnerable groups, will be established after the Centre is put into operation. (2) 31 March 2014 [IC] Mechanisms of permanent monitoring of occupancy and evaluation of adequacy of capacities of the Centre for Asylum Seekers with the support of UNHCR, with special focus on vulnerable groups, was established after the Centre was put into operation, and regular weekly monitoring was performed accordingly (3) 30 June 2014 [IC] UNHCR performs the monitoring continuously on the grounds of direct insight and 15-day report developed by the Centre for Asylum Seekers Monitoring. Since 31 March 2014 UNHCR received five reports. | Improved quality of reception conditions for asylum seekers on the basis of real needs (1) 31 December 2013 [NI] (2) 31 March 2014 [IC] Improved quality of reception conditions for asylum seekers. (3) 30 June 2014 [IC] The following is being provided: - Separate accommodation of men, families and vulnerable groups (unaccompanied women, unaccompanied juveniles etc.) -Appropriate health care within the Centre. Since the opening of the Centre, there were 20 primary health care examinations and 71 examinations at the higher level; there is 24-hour duty of medical technicians, along with visits of the doctor, on the grounds of the signed Protocol on Cooperation with the Public Health Institution in Danilovgrad -Three meals, with the possibility of adjustment to health needs of users; -Help provided in clothes and footwear; - Transportation of asylum seekers with a view to obtaining health care and interviewing in the Ministry of Interior (monthly tickets for public transport, as well as official vehicle when necessary) -Manual on rights and obligations of the asylum seekers, flyers for legal aid to beneficiaries and house rules in several languages -Interpretation from English, French and Arabian languages in the course of the interview with social worker and psychologist, in the course of health examinations and when necessary; Interpreters are provided by UNHCR -Use of Internet, Skype and cable TV with 60 channels (80% are foreign programs). |
| 2.23. | Provide reception conditions adequate to the needs of vulnerable groups (e.g. unaccompanied minors, single mothers, victims of violence) (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | MINISTRY OF LABOUR AND SOCIAL WELFARE Zeljko Sofranac | IC Continuous activity | Provided reception conditions adequate to the needs of vulnerable groups (1) 31 December 2013 [I] For these groups we provide adequate conditions according to possibilities and on the basis of the previous social anamnesis of their needs, particularly referring to accommodation, food, medical protection etc. Needs assessment is currently being made in cooperation with UNHCR and NGO HELP. Adequate assistance was provided for 234 women, 47 minors in the company of one or both parents and 4 unaccompanied minors. ______________________________________ Where are these solutions located?? The documentation about the help provided is kept at the Administration for the Care of Refugees Are these figures for the period June-December 2013?? Yes, from June to December, except for five female persons, three of whom were unaccompanied and two accompanied What has happened to these 4 unaccompanied minors? Are them still under the Montenegrin system? Please describe The four minors mentioned were accommodated: -one person on 5 and 6 June 2013 -one person from 12 to 17 June 2013 - one person from 31 July 2013 to 20 August 2013 -one person from 20 September 2013 to 4 October 2013 These persons voluntarily left the accommodation facilities without prior notice We are unaware if these four minors are still in the Montenegrin system. (2) 31 March 2014 [IC] Conditions created for vulnerable groups: premises (separate premises), human resources (medical, welfare workers, psychologist, pre-school teacher, pedagogue…), food (3) 30 June 2014 [IC] Conditions in the Centre for Asylum Seekers are adjusted to vulnerable groups in the following manner: -separate accommodation: bedrooms, toilets, living rooms and kitchenettes; -Additional care (psycho-social and pedagogical) is provided by employees of the Centre for Asylum Seekers; -nutrition adjusted to juveniles. | Better protection of vulnerable groups and easier integration (1) 31 December 2013 [RK] Members of vulnerable groups are provided with special accommodation Pregnant and breastfeeding women and minors between one and seven years of age are provided with three meals, including one cooked and one fruit meal Minors under one year of age are provided with adequate food for their age, as well as adequate means of hygiene (disposable diapers, ear buds, body cream, etc.) When necessary, minors between one and three years of age are provided with disposable diapers Like other asylum seekers, these persons also have access to medical protection in public health institutions at all levels and they are provided with medications as required. _______________________________ Evidence for the aforesaid is kept at the Administration for the Care of Refugees (2) 31 March 2014 [RK] The facilities and capacities of the Centre for Asylum Seeker are adequate to the need of vulnerable groups. (The Centre currently accommodates four women who have adequate treatment and separate accommodation). |
| 2.24 | Training of civil servants and employees for more efficient work in the area of reception conditions with special emphasis to vulnerable groups, (for example, unaccompanied juveniles, women at risk, victims of violence) (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | Ministry of Labour and Social Welfare Zeljko Sofranac | IC January – December 2014; and; January-December 2016 | Employees of the Centre for Asylum Seekers additionally educated (2) 31 March 2014 [IC] The expert visit with support of TAIEX took place in the period 17-21 March 2014. The training was attended by 10 employees of the Centre on the following topics: Conditions for reception of vulnerable groups, minimum standards for reception of asylum seekers etc. The expert visit with support of TAIEX took place in the period 07-11 April 2014. The training was attended by 10 employees of the Centre on the following topics: Conditions for reception of vulnerable groups, minimum standards for reception of asylum seekers etc. (3) 30 June 2014 [IC] The training of employees of the Centre for Asylum Seekers, within which the visit of EU expert took place as well, was conducted in the period 2 -3 June 2014. | Greater efficiency in care and increased quality of work (number of trained civil servants and employees) (2) 31 March 2014 [IC] The quality of work of employees of the Centre for Asylum Seekers was increased after the training. (3) 30 June 2014 [IC] In the period 2 – 3 June 2014, 10 employees of the Centre for Asylum Seekers were trained. |

Recommendation 5 from the Screening Report– area “Asylum”

## 3.	VISA POLICY            Ministry of Foreign Affairs and European Integration - Dejan Vukovic

Recommendation 1 from the Screening Report– area ``Visa policy“

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 3.1. * | Prepare the analysis of financial, administrative, legal and procedural measures, as well as the necessary infrastructure for implementation of the EU visa policy, with a view to preparing for the Schengen Action Plan Adopt the Schengen Action Plan, which will inter alia cover the following: EU visa Regulation 539/2001, capacities for reception of confidential information on security details of travel documents, visa forms and their application in practice several months prior to accession, the EU Visa Code, Visa Information System and connection with diplomatic and consular representative offices of Montenegro, as well as finding alternative for consular representation of Montenegro abroad using the EU Member States. Note: More details provided in the section 4 – External borders and Schengen (3) 30 June 2014 [IC] | Ministry of Foreign Affairs and European Integration Dejan Vukovic | IC May 2014; December 2015; | Analysis prepared (1) 31 December 2013 [NI] (3) 30 June 2014 [I] Developed Analysis of financial, administrative, legal and procedural measures, as well as the necessary infrastructure for implementation of the EU visa policy, with a view to preparing for the Schengen Action Plan. The mentioned Analysis was submitted to the European Commission before the prescribed deadline. Schengen Action Plan adopted (3) 30 June 2014 [NI] Note: Envisaged for the fourth quarter of 2015. |  |

Recommendation 1 from the Screening Report– area ``Visa policy“

Recommendation 5 from the Screening Report– area “Asylum”

| Br. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 3.3. | Issue visas at the border crossing points only in exceptional cases, if it is required for humanitarian, personal or professional reasons – in these cases, visas will be issued with a previous notification and after checks were carried out. (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | POLICE ADMINISTRATION Dragan Stevanovic | IC Ongoing | Strict observance of regulation (1) 31 December 2013 [I] Visas at borders were issued in accordance with Article 22 of the Law on Foreigners of Montenegro. (2) 31 March 2014 [IC] Regulations strictly observed (3) 30 June 2014 [IC] Regulations strictly observed | Number of issued visas at the border crossing points; (1) 31 December 2013 [IC] A total of 14 visas were issued at border crossing points in the period from 1 January to 30 November 2013. Out of this number, 12 visas were type B, issued to sailors, while 2 visas were type C. (2) 31 March 2014 [IC] There were no visas issued in border crossings in the period from 1 January 2014 and 25 March 2014. (3) 30 June 2014 [IC] Only 10 visas have been issued at the border crossing points in the period 25 March – 10 June 2014 (3 type C and 7 type B to sailors) Number of received notifications and completed checks; (1) 31 December 2013 [?] In the period from 1 January to 30 November, 14 notifications for issuing visas at borders were received and 14 checks were carried out. (2) 31 March 2014 [IC] No notifications were receive and therefore no checks were carried out. (3) 30 June 2014 [IC] In the period 25 March – 10 June, 17 notifications for issuing visas at the borders were received and 17 checks were carried out. |
| 3.4. | Inform ship agents, who submit requests for issuing visas to sailors, to send these requests to competent diplomatic missions and consular posts because visas cannot be issued at the border crossing points but in exceptional cases. (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | POLICE ADMINISTRATION Dragan Stevanovic | IC Ongoing | Continuous and improved informing of ship agents. (1) 31 December 2013 [IC] Ship agents are directed towards diplomatic missions and consular posts of Montenegro, i.e. to foreign diplomatic missions and consular posts which represent Montenegro in issuing visas, which resulted in great reduction of issued visas to sailors at border crossing points. Because during 2012, 71 visas of type B were issued to sailors. (2) 31 March 2014 [IC] Ship agents are referred to diplomatic and consular offices of Montenegro, or foreign diplomatic and consular offices that represent Montenegro in the processes of issuing visas (3) 30 June 2014 [IC] | Number of issued visas type “B” to sailors (1) 31 December 2013 [IC] During period from 1 January to 30 November 2013, 12 visas of type B were issued to sailors. (2) 31 March 2014 [IC] No visas of type "B" were issued in the reporting period. (3) 30 June 2014 [IC] In the reporting period, 7 visas of type B were issued to sailors |

## 4.	EXTERNAL BORDERS AND SCHENGEN                  Ministry of Interior	 - Milan Paunovic

Recommendation 1, 2 and 4 from the Screening Report– area “External borders and Schengen” (recommendation relating to Schengen Action Plan)

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 4.1. * | 1. Development of comprehensive analysis of needs concerning legal, technical, human resources and infrastructural requirements and their expenses for the purpose of harmonization with relevant parts of the Schengen acquis by the accession to the EU, as well as for the purpose of the accession to Schengen Establishment of the inter-ministerial working team for development of the Schengen Action Plan (3) 30 June 2014 [PI] | Ministry of Interior Natasa Starovlah Knezevic | PI May 2014; May 2015; | 1. EU experts hired and analysis developed (3) 30 June 2014 [PI] The Working Group has been established and tasked with development of the need assessment analysis for the purpose of harmonization with the relevant parts of the Schengen acquis by the accession to the EU, as well as for the purpose of the accession to Schengen; work will be performed on the grounds of this analysis together with the EU experts who will be selected for the Twinning Project: Support to adoption of the acquis from the area of Schengen, development of the need analysis concerning legal, technical, human resources and infrastructural requirements and their expenses. Evaluation is ongoing for the selection of the EU partner for the Twinning Project: Support to adoption of the acquis from the area of Schengen; the selection of partner is expected by the end of June 2014. Inter-Ministerial Team for development of the Schengen Action Plan established; (3) 30 June 2014 [PI] The Inter-Ministerial Working Team has been established for development of the need assessment analysis for the purpose of harmonization with the relevant parts of the Schengen acquis by the accession to the European Union, as well as for the purpose of the accession to Schengen. Project fiche completed for development of the Schengen Action Plan. The European Commission approved the Project fiche under the Twinning project and allocated the funds in the amount of EUR 1 million, which will include development of comprehensive analysis as well. 2. Subgroups within the Inter-Ministerial Team Group established; (3) 30 June 2014 [NI] Note: Subgroup within the Inter-Ministerial Team has not been established Goals and tasks of the Inter-Ministerial Team and subgroups defined; (3) 30 June 2014 [NI] | Plan established for short-term and long-term measures and activities in the process of the accession of Montenegro to the EU, in the surveillance of the external borders in compliance with the Schengen acquis in terms of more efficient border management, future external EU borders (3) 30 June 2014 [I] Inter-Ministerial Working Team established, Procedure ongoing for the selection of expert through the Twinning Project |

Recommendations 3 and 5 from the Screening Report – area “External borders and Schengen” (recommendations related to the integrated border management)

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 4.6. | Draft reports on the Implementation of the Integrated Border Management Strategy 2013-2016, until the adoption of the new Strategy, in accordance with the EU’s IBM concept (1) 31 December 2013 [I] (2) 31 March 2014 [I] | MINISTRY OF INTERIOR Milan Paunovic | I 1. Continuously until the adoption of new strategy and Action plan at the beginning of 2014; | Annual reports on implementation of action plans drafted, (1) 31 December 2013 [I] The Government of Montenegro reconsidered and adopted Information on Implementation of Integrated Border Management Strategy for the period 2013-2016 at the session held on 26 December 2013. (2) 31 March 2014 [I] The Government of Montenegro adopted the Report on Implementation of the Integrated Border Management Strategy for 2013 at the session of 26 December 2013. (3) 30 June 2014 [I] The Government of Montenegro reconsidered and adopted Information on Implementation of Integrated Border Management Strategy for the period 2013-2016 at the session held on 26 December 2013. Annual action plans for implementation of the Integrated Border Management Strategy 2013-2016 drafted, in accordance with the vital interests of Montenegro, changes within the European Union and the European Commission’s guidelines with regard to the EU’s Schengen IBM concept (1) 31 December 2013 [I] The Government of Montenegro reconsidered and adopted Information on Implementation of Integrated Border Management Strategy for the period 2013-2016 at the session held on 26 December 2013. (2) 31 March 2014 [?] (3) 30 June 2014 [?] | Annual reports on implementation of the Integrated Border Management Strategy, (1) 31 December 2013 [I] The Government of Montenegro reconsidered and adopted Information on implementation of Integrated Border Management Strategy for the period 2013-2016 at the session held on 26 December 2013. (2) 31 March 2014 [?] (3) 30 June 2014 [I] Level of implementation of measures and activities and achieved results (1) 31 December 2013 [?] (2) 31 March 2014 [?] (3) 30 June 2014 [?] |
| 4.7. | 1. Establish a working group for the development of the Integrated Border Management Strategy 2014-2018. Engage EU experts for support in the development of the Strategy. Adopt an innovated Integrated Border Management Strategy 2014-2018 in accordance with the concept IBM EU. (1) 31 December 2013 [PI] (2) 31 March 2014 [I] (3) 30 June 2014 [I] | MINISTRY OF INTERIOR Milan Paunovic | I 1. September 2013; 2. Until December 2013; 3. March 2014 | 1. Established WG for Strategy development (1) 31 December 2013 [I] Innovated Integrated Border Management Strategy 2014-2018 will be prepared by the Commission for demarcation and establishment of the state border, determination of border crossing points, establishment of the regime of border traffic with neighbouring countries and implementation of the Strategy for Integrated Border Management, formed by the Decision of the Ministry of Interior 01 No. 051/13-8362/1 of 11 March 2013, pursuant to Article 4 paragraph 1 of the Law on State Border (Official Gazette of Montenegro 72/09) and Decisions of the Government of Montenegro, No. 06-424/3 of 7 March 2013. (2) 31 March2014 [I] Innovated Integrated Border Management Strategy 2014-2018 will be prepared by the Commission for demarcation and establishment of the state border, determination of border crossing points, establishment of the regime of border traffic with neighbouring countries and implementation of the Strategy for Integrated Border Management, formed by the Decision of the Ministry of Interior 01 No. 051/13-8362/1 of 11 March 2013, pursuant to Article 4 paragraph 1 of the Law on State Border (Official Gazette of Montenegro 72/09) and Decisions of the Government of Montenegro, No. 06-424/3 of 7 March 2013. (3) 30 June 2014 [I] 2. EU expert engaged for support in the development of the Strategy (1) 31 December 2013 [I] TAIEX application form for expert support for the drafting of the Strategy completed. Application accepted and expert assigned. We expect the expert to arrive by the end of January 2014. (2) 31 March 2014 [I] TAIEX application form for expert support for the drafting of the Strategy completed. Application accepted and expert assigned. (3) 30 June 2014 [I] The TAIEX expert visited Montenegro in the period 21-25 January 2014 and provided support in development of the Integrated Border Management Strategy for the period 2014-2018 and the Framework Action Plan for implementation of the Integrated Border Management Strategy for the period 2014-2018. 3. Innovated Integrated Border Management Strategy 2014-2018 adopted (1) 31 December 2013 [NI] (2) 31 March 2014 [I] At the session of 27 March 2014, the Government of Montenegro adopted the Integrated Border Management Strategy for the period 2014-2018 and the Framework Action Plan for implementation of the Strategy for the period 2014-2018. The Strategy and the Framework Action Plan were submitted to the European Commission for opinion on 28 February 2014. The European Commission’s opinion on the aforesaid documents was received from on 13 march 2014 along with positive comments and certain suggestions that have been incorporated in the Strategy for the period 2014-2018 and the Framework AP for implementation of the Strategy for the period 2014-2018. The Action Plan for implementation of the Strategy for 2014 will be submitted, after translation, to the EC for opinion and afterwards to the Government of Montenegro for adoption. (3) 30 June 2014 [I] Action Plan for implementation of the Integrated Border Management Strategy for 2014 was submitted to the European Commission for opinion on 15 April 2014. On 8 May 2014, the European Commission provided positive opinion for the Action Plan for IBM for 2014. Following that, the AP was submitted to the Government for adoption. At the session held on 29 May 2014, the Government of Montenegro adopted the Action Plan for implementation of the IBM Strategy for 2014. OSCE Mission will finance printing of the Strategy and the Action Plan. Materials will be submitted to internal organizational units of the Ministry of Interior and other state authorities competent for implementation of measures. The analysis of the recent realization of the Action Plan for implementation of the IBM Strategy by the end of 2014 will be carried out at the meeting of the Border Commission of the Ministry, at the beginning of July 2014. (Action Plan provides for total 117 activities). At the meeting of the Commission, dilemmas will be removed one more time as regards the area of competences and persons responsible for implementation of particular measures. |  |

Recommendation 6 and 7 from the Screening Report– area “External borders and Schengen” (recommendation relating to cooperation with neighbouring countries)

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 4.8. | In addition to those already signed, sign the protocols on joint patrols with the remaining neighbouring countries (the Republic of Croatia and the Republic of Kosovo) and define contact points. Recommend signing of a protocol on establishing operational cooperation with the FRONTEX at the EU external border with the Republic of Croatia, member state as of 1 July 2013, with a view to fully implementing the EU Regulations No 2007/2004/EC and No 1168/2011/EC and Prepare a plan for the future operational cooperation with the FRONTEX at the EU external borders. (1) 31 December 2013 [PI] (2) 31 March 2014 [PI] (3) 30 June 2014 [IC] | POLICE ADMINISTRATION Vukoman Zarkovic | IC 1. December 2013; 2. ; December; 2014; 3 continuously, in accordance with the FRONTEX policy and position | Protocols on establishing cross-border operational cooperation signed with all neighbouring countries and operational police cooperation established at the EU external borders (1) 31 December 2013 [NI] The Draft Protocol on joint patrols was submitted to the Republic of Croatia. After harmonization of the Agreement on police cooperation between the Government of Montenegro and the Government of the Republic of Kosovo, the Montenegrin side will propose to Kosovo the Draft Protocol on joint patrols. Taking into consideration that on 18 June 2009 the Working agreement on establishment of operative cooperation between Police Directorate of Montenegro and FONTEX was signed, it is necessary to consult the European Commission if Montenegro is obliged, before its accession to the EU, to sign the Agreement on establishment of operative cooperation with FRONTEX at the external borders of EU with the Republic of Croatia, in accordance with the EU Regulations No 2007/2004/EC and No 1168/2011/EC. (2) 31 March 2014 [PI] The Draft Protocol on joint patrols was presented to the Republic of Croatia on 14 February 2013. We received no reply in relation to the initiative to organize a meeting in order to finalise this Protocol. On 26 March 2014, the following agreements were signed with the Republic of Kosovo: 1.Agreement between the Government of Montenegro and the Government of the Republic of Kosovo on police cooperation; 2.Protocol between the Ministry of Interior of Montenegro and Ministry of Interior of the Republic of Kosovo on joint patrols at state border, 3.Protocol between the Ministry of Interior of Montenegro and the Ministry of Interior of the Republic of Kosovo on holding regular meetings between border police forces at all management levels. 4. Agreement between the Government of Montenegro and the Government of the Republic of Kosovo on the opening of the joint border crossings for international road transport of passengers Kotlovi-Kuciste, on the road Murino-Cakor-Pec; 5.Protocol between the Ministry of Interior of Montenegro and the Ministry of Interior of the Republic of Kosovo on procedures for joint border controls and payment of expenses incurred in the operation of joint the border Kotlovi-Kuciste; 6. Agreement between the Government of Montenegro and the Government of the Republic of Kosovo on the opening of international road border crossing Kula-Savine Vode, on the road Rozaje-Kula-Pec; 7. Agreement between the Government of Montenegro and the Government of the Republic of Kosovo on regulating border traffic regime; On the basis of the information obtained from the chairperson of the Working Group for Chapter 24 “Justice, Freedom and Security” it was noted that Montenegro was not required to sign the Agreement on establishment of operative cooperation with FRONTEX at the external borders of EU, in accordance with the EU Regulations No 2007/2004/EC and No 1168/2011/EC. (3) 30 June 2014 [IC] The Draft Protocol on Joint Patrols was submitted to the Republic of Croatia on 14 February 2013. We received no response as regards the initiative for organisation of the meeting with a view to harmonising this Protocol. On 6 March 2014, the initiative was submitted for conducting negotiations with the Ministry of Interior of the Republic of Croatia on harmonisation of the Protocol on organising the joint patrols along the state border and the Protocol on organising meetings at the national, regional and local level between representatives of the border services. The Protocol between the Ministry of Interior of Montenegro and the Ministry of Interior of the Republic of Kosovo on joint patrols at the state border was signed in Pristina on 26 March 2014. Preparations for joint training are underway in order to start the implementation of this Protocol. By the Act of the Ministry of Interior: 050/14-24132/2 of 15 May 2014, through diplomatic channels, the letter was submitted to the Minister of Interior of the Republic of Kosovo, initiating the establishment of the Joint Expert Commission for implementation of agreements which were signed in the course of the official visit of the Minister of Interior of Montenegro to Pristina. Composition of Montenegrin expert commission for implementation of the agreement and the protocol has been determined. It was proposed that the first meeting of the Commission should be held in the course of June 2014, in which the issues important for implementation of signed agreement should be considered. It is necessary to adopt decisions on publication of signed agreements, with a view to completing internal legal procedures necessary for its entry into force. In this regard, inter-ministerial consultations will be conducted as regards the competences for realisation of this obligation. As the future member of the EU and the Schengen area, Montenegro develops the concept of the EU IBM, with the Member States and relevant agencies and bodies of the EU, inter alia, with a view to improving of cooperation with FRONTEX. The Framework AP for implementation of the IBM Strategy 2014-2018 provides for activities until and following the accession to the EU. Conclusion of the Agreement on Operational Cooperation with FRONTEX has been planned as well following accession of Montenegro to the EU. Until then, in cooperation with FRONTEX, Montenegro will apply the existing working arrangement, which was signed between the Police Administration and FRONTEX in 2008. That cooperation refers to participation as an observer in particular joint actions carried out at the external and internal EU borders, participation in various meeting and trainings where experiences and news from the area of border control duties are exchanged, as well as through exchange of data and information upon assessment and the request of FRONTEX. | Concrete results in the implementation of protocols, prevented illegal crossings of the state border and other forms of cross-border crime; (1) 31 December 2013 [?] (2) 31 March 2014 [?] (3) 30 June 2014 [PI] By the Act of the Ministry of Interior of 15 May 2014, through diplomatic channels, the letter was submitted to the Minister of Interior of the Republic of Kosovo initiating the establishment of the Joint Expert Commission for implementation of agreements which were signed in the course of the official visit of the Minister of Interior of Montenegro to Pristina. Composition of Montenegrin expert commission for implementation of the agreement and the protocol has been determined. Established operational cross-border police cooperation at the Montenegrin border and at the EU external borders (1) 31 December 2013 [?] (2) 31 March 2014 [?] (3) 30 June 2014 [PI] By its accession to the EU, in cooperation with FRONTEX, Montenegro will use the existing signed working arrangement, which was signed between the Police Administration and FRONTEX in 2008. Conclusion of the Agreement on Operational Cooperation with FRONTEX has been planned following accession of Montenegro to the EU. |
| 4.9. | Fully align the existing agreement with Bosnia and Herzegovina on border crossing points for border traffic with the EU Regulation No 1931/2006, and conclude agreements on defining the border traffic regime with the remaining neighbouring countries in accordance with the EU acquis. (1) 31 December 2013 [PI] (2) 31 March 2014 [IC] (3) 30 June 2014 [PI] | POLICE ADMINISTRATION Milan Paunovic | PI Permanent task until the conclusion of all agreements | The existing agreements aligned, and the agreements on defining the border traffic regime concluded with the remaining neighbouring countries in accordance with the EU acquis (1) 31 December 2013 [NI] The Agreement on border traffic has not been agreed with the Republic of Croatia due to the insistence of the Croatian side that on the date of signing of this Agreement, the application of particular articles should be terminated, which would derogate from the Protocol between the Government of the Federal Republic of Yugoslavia and the Government of the Republic of Croatia on temporary regime along the south border between two countries, dated 10 December 2002. Additionally, it should be taken into account that this Protocol is valid until the conclusion of the Agreement on border, and the Agreement on border traffic does not refer to maritime area between Montenegro and the Republic of Croatia in accordance with the Regulation (EC) No 1931/2006. Based on the Act of the Ministry of Interior 01 No. 011/13-33446/2 dated 21 June 2013, the initiative for organizing a meeting with the competent institution of Bosnia and Herzegovina, in relation to amendments to the Agreement on border crossing points for border traffic between the Government of Montenegro and the Council of Ministers of Bosnia and Herzegovina, was sent. Amendments to this Agreement will define crossing of joint state border outside the opened border crossing points under the conditions of border regime, at particular crossing locations i.e. control points, upon appropriate approval, in order to enable the population residing in the border area to cross border and for their everyday purposes, especially after closing 44 side roads between two countries. Based on the letter of the Ministry of Interior 01 no. 282 /13- 22443/1 dated 26 April 2013, the initiative for conducting negotiations with the Ministry of Interior of the Republic of Kosovo in order to prepare the Agreement on opening border crossing points for international traffic and regulating regime of border traffic was sent. In order to conduct negotiations with the Ministry of Interior of the Republic of Kosovo in relation to “ Preparation of the Proposal for the Agreement between two countries and dynamics of preparation, building border crossing point between Murino-Čakor-Peja , reconstruction and opening of this road”, the following documents were submitted to Kosovo representatives via diplomatic channels: -Draft Agreement on opening international road border crossing point Kula (Montenegro) – Savine vode (The Republic of Kosovo), between the Government of Montenegro and the Government of the Republic of Kosovo, on the road Rožaje – Kula – Peja; - Draft Agreement on opening joint border crossing point Kotlovi (Montenegro) – Kučište (the Republic of Kosovo) for international, seasonal, passenger traffic, between the Government of Montenegro and the Government of Kosovo, on the road Murino-Čakor-Pec; - Draft Agreement between the Government of Montenegro and the Government of Kosovo on regulating regime of border traffic. Taking into consideration that agreements on border crossing points have not been agreed and concluded yet and since the Ministers of Interior of Montenegro and the Republic of Kosovo concluded, at a meeting held on 8 April 2013 in Podgorica, that “work of line commissions of two countries should be continued as soon as possible in order to prepare the proposed agreements”, the above mentioned initiative was sent. -It is expected that the Kosovo side will accept initiative for continuation of negotiations related to harmonization and preparation for signing these agreements. Based on the letter of the Ministry of Interior 01 No. 1328/4 dated 17 September 2013, the initiative for continuation of negotiations between the Commission of the Montenegrin Ministry of Interior and Commission of the Ministry of Interior of the Republic of Serbia was sent, in order to finally agree, prepare and conclude the Agreement between the Government of Montenegro and the Government of the Republic of Serbia on border crossing points for road and railway international and border traffic. At the second session the Commissions of Montenegro and the Republic of Serbia dated 22 September 2011 in Podgorica, agreements on border crossing points Dobrakovo – Gostun, Ranče – Jabuka, Dračenovac – Špiljani, Bijelo Polje- Prijepolje and Agreement on regulating regime of border traffic were agreed in principle. Agreements on border crossing points Vuča – Godovo and Čemerno – Granica were not agreed. At the previous meeting, an issue related to phyto-sanitary control at border crossing points Ranče – Jabuka and Dračenovac – Špiljani, was not agreed, according to principle of reciprocity. Taking into consideration that agreement between the Administration for Inspection Affairs of Montenegro and the Plant Protection Directorate and the Veterinary Directorate of the Republic of Serbia on the establishment of inspection control at border crossing point Ranče – Jabuka in November 2011 and at border crossing points Dračenovac – Špiljani dated 4 September 2013, conditions have been met to finally agree on these agreements. It is expected that the Serbian side will accept the initiative for continuation of negotiations related to preparation for signing all seven agreements on border crossing points and border traffic. It is necessary to conclude the Protocol on joint border controls and costs of the work of joint border crossing point Zatrijebačka Cijevna – Grabon with the Republic of Albania, in accordance with the signed Agreement on opening of this joint border crossing point (we expect to agree and sign this Protocol in January 2014). This activity is carried out within the Strategic project IPA Cross-Border Cooperation Programme Montenegro – the Republic of Albania, which implies construction of joint border crossing point Zatrijebačka Cijevna – Grabon in order to implement the idea of connecting Podgorica and Plav through the territory of Albania, reconstruction of BCP Božaj (removal of the “bottleneck”), demarcation of border line at Skadar Lake between Montenegro and the Republic of Albania and road construction of Zatrijebačka Cijevna- Grabon, in the amount of EUR 3,600,000.00. -Also, in the first quarter of 2014, the Proposal for Agreement on opening of the border crossing point for international railway traffic – Tuzi – Bajza will be prepared. (2) 31 March 2014 [IC] On 24 March 2014, the fourth, repeated, request was sent for continuation of negotiations with the competent authorities of Bosnia and Herzegovina in relation to amendments to the Agreement on border crossings for border traffic between the Government of Montenegro and the Council of Ministers of Bosnia and Herzegovina. The Agreement on border traffic has not been agreed with the Republic of Croatia due to the insistence of the Croatian side that on the date of signing of this Agreement, the application of particular articles should be terminated, which would derogate from the Protocol between the Government of the Federal Republic of Yugoslavia and the Government of the Republic of Croatia on temporary regime along the south border between two countries, dated 10 December 2002, which would otherwise remain applicable until the conclusion of the Agreement on border. Based on the Act of the Ministry of Interior 01 No. 1328/4 dated 17 September 2013, the initiative for continuation of negotiations between the Commission of the Montenegrin Ministry of Interior and the Commission of the Ministry of Interior of the Republic of Serbia was sent, in order to finally agree, prepare and conclude the Agreement between the Government of Montenegro and the Government of the Republic of Serbia on border crossing points for road and railway international and border traffic. In terms of cooperation with the Republic of Albania, we note that the Albanian side demands additional harmonization or the previously harmonized Protocol between the Ministry of Interior of Montenegro and the Ministry of Interior of the Republic of Albania on the conduct of joint border controls and payment of costs of work at the joint border crossing point Zatrijebačka Cijevna – Grabon | The border traffic regime with the neighbouring countries established in accordance with the adopted rules for border traffic at the EU external borders; (1) 31 December 2013 [NI] The Agreement on border traffic has not been agreed with the Republic of Croatia due to the insistence of the Croatian side that on the date of signing of this Agreement, the application of particular articles should be terminated, which would derogate from the Protocol between the Government of the Federal Republic of Yugoslavia and the Government of the Republic of Croatia on temporary regime along the south border between two countries, dated 10 December 2002. Additionally, it should be taken into account that this Protocol is valid until the conclusion of the Agreement on border, and the Agreement on border traffic does not refer to maritime area between Montenegro and the Republic of Croatia in accordance with the Regulation (EC) No 1931/2006. Based on the letter of the Ministry of Interior 01 No. 011/13-33446/2 dated 21 June 2013, the initiative for organizing a meeting with the competent institution of Bosnia and Herzegovina, in relation to amendments to the Agreement on border crossing points for border traffic between the Government of Montenegro and the Council of Ministers of Bosnia and Herzegovina, was sent. Amendments to this Agreement will define crossing of joint state border outside the opened border crossing points under the conditions of border regime, at particular crossing locations i.e. control points, upon appropriate approval, in order to enable the population residing in the border area to cross border and for their everyday purposes, especially after closing 44 side roads between two countries. Based on the letter of the Ministry of Interior 01 no. 282 /13- 22443/1 dated 26 April 2013, the initiative for conducting negotiations with the Ministry of Interior of the Republic of Kosovo in order to prepare the Agreement on opening border crossing points for international traffic and regulating regime of border traffic was sent. In order to conduct negotiations with the Ministry of Interior of the Republic of Kosovo in relation to “ Preparation of the Proposal for the Agreement between two countries and dynamics of preparation, building border crossing point between Murino-Čakor-Peja , reconstruction and opening of this road”, the following documents were submitted to Kosovo representatives via diplomatic channels: -Draft Agreement on opening international road border crossing point Kula (Montenegro) – Savine vode (The Republic of Kosovo), between the Government of Montenegro and the Government of the Republic of Kosovo, on the road Rožaje – Kula – Peja; - Draft Agreement on opening joint border crossing point Kotlovi (Montenegro) – Kučište (the Republic of Kosovo) for international, seasonal, passenger traffic, between the Government of Montenegro and the Government of Kosovo, on the road Murino-Čakor-Pec; - Draft Agreement between the Government of Montenegro and the Government of Kosovo on regulating regime of border traffic. Taking into consideration that agreements on border crossing points have not been agreed and concluded yet and since the Ministers of Interior of Montenegro and the Republic of Kosovo concluded, at a meeting held on 8 April 2013 in Podgorica, that “work of line commissions of two countries should be continued as soon as possible in order to prepare the proposed agreements”, the above mentioned initiative was sent. -It is expected that the Kosovo side will accept initiative for continuation of negotiations related to harmonization and preparation for signing these agreements. Based on the letter of the Ministry of Interior 01 No. 1328/4 dated 17 September 2013, the initiative for continuation of negotiations between the Commission of the Montenegrin Ministry of Interior and Commission of the Ministry of Interior of the Republic of Serbia was sent, in order to finally agree, prepare and conclude the Agreement between the Government of Montenegro and the Government of the Republic of Serbia on border crossing points for road and railway international and border traffic. At the second session the Commissions of Montenegro and the Republic of Serbia dated 22 September 2011 in Podgorica, agreements on border crossing points Dobrakovo – Gostun, Ranče – Jabuka, Dračenovac – Špiljani, Bijelo Polje- Prijepolje and Agreement on regulating regime of border traffic were agreed in principle. Agreements on border crossing points Vuča – Godovo and Čemerno – Granica were not agreed. At the previous meeting, an issue related to phyto-sanitary control at border crossing points Ranče – Jabuka and Dračenovac – Špiljani, was not agreed, according to principle of reciprocity. Taking into consideration that agreement between the Administration for Inspection Affairs of Montenegro and the Plant Protection Directorate and the Veterinary Directorate of the Republic of Serbia on the establishment of inspection control at border crossing point Ranče – Jabuka in November 2011 and at border crossing points Dračenovac – Špiljani dated 4 September 2013, conditions have been met to finally agree on these agreements. It is expected that the Serbian side will accept the initiative for continuation of negotiations related to preparation for signing all seven agreements on border crossing points and border traffic. It is necessary to conclude the Protocol on joint border controls and costs of the work of joint border crossing point Zatrijebačka Cijevna – Grabon with the Republic of Albania, in accordance with the signed Agreement on opening of this joint border crossing point (we expect to agree and sign this Protocol in January 2014). This activity is carried out within the Strategic project IPA Cross-Border Cooperation Programme Montenegro – the Republic of Albania, which implies construction of joint border crossing point Zatrijebačka Cijevna – Grabon in order to implement the idea of connecting Podgorica and Plav through the territory of Albania, reconstruction of BCP Božaj (removal of the “bottleneck”), demarcation of border line at Skadar Lake between Montenegro and the Republic of Albania and road construction of Zatrijebačka Cijevna- Grabon, in the amount of EUR 3,600,000.00. -Also, in the first quarter of 2014, the Proposal for Agreement on opening of the border crossing point for international railway traffic – Tuzi – Bajza will be prepared. (2) 31 March 2014 [?] (3) 30 June 2014 [PI] The fifth urgent letter was submitted on 5 May 2014 with a view to continuing activities for development of amendments to the Agreement on the Border Crossing Points for the border traffic between Montenegro and Bosnia and Herzegovina. We have no response to the submitted initiative. By the Act of the Ministry of Interior of 17 September 2013, the fourth urgent letter was submitted for continuation of negotiations between the Commission of the Ministry of Interior of Montenegro and the Commission of the Ministry of Interior of the Republic of Serbia with a view to final harmonizing and preparation for conclusion of the Agreement between the Government of Montenegro and the Government of the Republic of Serbia on the border crossing points in road and railway international and border traffic. We have no response to the submitted initiative. The Agreement on border traffic has not been agreed with the Republic of Croatia due to the insistence of the Croatian side that on the date of signing of this Agreement, the application of particular articles should be terminated, which would derogate from the Protocol between the Government of the Federal Republic of Yugoslavia and the Government of the Republic of Croatia on temporary regime along the south border between two countries, dated 10 December 2002, which would otherwise remain applicable until the conclusion of the Agreement on border. The Agreement between the Government of Montenegro and the Government of the Republic of Kosovo on regulation of the border traffic regime was signed on 26 March 2014 in Pristina. At the session held on 5 June 2014, the Government of Montenegro accepted the Proposal for the Protocol between the Ministry of Interior of Montenegro and the Ministry of Interior of the Republic of Albania on realization of the joint border control and payment of costs arising from the work at the Joint Border Crossing Point Zatrijebačka Cijevna-Grabon, with the Proposal for the Protocol which was submitted by the Ministry of Interior. Effects of implementation of the signed agreements (1) 31 December 2013 [?] (2) 31 March 2014 [?] (3) 30 June 2014 [PI] - As regards the effects of implementation of the agreement, the establishment of the Joint Expert Commission of the Ministry of Interior of Montenegro and the Ministry of Interior of the Republic of Kosovo for implementation of signed agreements was initiated through diplomatic channels. - Composition of Montenegrin expert commission for implementation of the agreement and the protocol has been determined. - It was proposed that the first meeting of the Joint Expert Commission should be held in the course of June 2014 with a view to considering the issues important for implementation of signed agreements (the proposed meeting was not held). - It is necessary to adopt decisions on publication of signed agreements with a view to completing internal legal procedures required for its entry into force. |
| 4.10. | 1. Enhance the protection of external borders through operational cooperation with the neighbouring countries in preventing the illegal crossings of the state border by alternative roads: Demolish 22 side roads suitable for illegal crossing of the state border between Montenegro and Bosnia and Herzegovina, in accordance with the Agreement on defining border crossings between Montenegro and BIH and drafted joint Study of Montenegro and Bosnia and Herzegovina on demolishing side roads suitable for illegal border crossings (44 roads suitable for illegal border crossings are defined, 22 demolished by each side). Initiate the establishment of mixed working teams for the development of the study for demolishing roads with the Republic of Kosovo, Republic of Albania and Republic of Serbia. Demolish side roads with: - The Republic of Kosovo - The Republic of Albania 3.3 The Republic of Serbia Implement increased patrol activities and increase the number of control points along the state border, as well as use the technical means for border crossing surveillance. (1) 31 December 2013 [PI] (2) 31 March 2014 [IC] (3) 30 June 2014 [PI] | POLICE ADMINISTRATION Vukoman Zarkovic | PI May 2014; Since July 2013; 3.1. December 2014; July 2015; 3.3.December 2015; 4. Continuous activity | 1. 22 roads demolished by Montenegro (1) 31 December 2013 [NI] The procedure for tender announcement for the selection of contractors for demolishing side roads appropriate for illegal crossing of state border between Montenegro and Bosnia and Herzegovina is ongoing. It is expected to carry out selection of contractors during 2014. (2) 31 March 2014 [NI] The procedure for tender announcement for the selection of contractors for demolishing side roads appropriate for illegal crossing of state border between Montenegro and Bosnia and Herzegovina is ongoing. It is expected to carry out selection of contractors during 2014. In the Act No. 011 /13-33446/3 of 24 March 2014, the fourth request was sent for continuation of negotiations with the competent authorities of Bosnia and Herzegovina in relation to amendments to the Agreement on border crossings for border traffic between the Government of Montenegro and the Council of Ministers of Bosnia and Herzegovina, along with the resolution of the regime of border traffic and closure of roads suitable for illegal crossings of the state border. A mixed expert group of Montenegro and Bosnia and Herzegovina drafted an annex to the Study on demolition of side roads. (3) 30 June 2014 [PI] On 24 April 2014, the urgent letter was submitted for continuation of negotiations with the competent authorities of Bosnia and Herzegovina as regards amendments to the Agreement on the Border Crossing Points for the Border Traffic between the Government of Montenegro and the Council of Ministers of Bosnia and Herzegovina for border traffic, along with resolution of the border traffic regime and closure of roads suitable for illegal crossing of the state border, in compliance with the Proposal of the Border Commission of Montenegro of 9 October 2013 and position of the State Commission for the Integrated Border Management of Bosnia and Herzegovina of September2013, when support was provided for urgent conducting of the meeting with the Border Commission of the Ministry of Interior of Montenegro. The first announced tender for the selection of contractor was not successful, due to the fact that no one applied for it. The procedure for announcement of the second tender is ongoing for the selection of contractor for demolition of side roads suitable for illegal crossing of the state border between Montenegro and Bosnia and Herzegovina. We expect that the contractor will be selected and the work will be carried out by the end of the first half of 2014. 2. Established inter-ministerial working teams (1) 31 December 2013 [NI] Through the letter of the Ministry of Interior No. 282/13 -62713/2 dated 30 September 2013, an initiative was sent via diplomatic channels in relation to establishment of joint working groups with the Republic of Kosovo, the Republic of Albania and the Republic of Serbia for drafting of the Study on demolition of side roads suitable for illegal border crossings and establishing the dynamics of closing these roads with these neighbouring countries in order to prevent illegal crossing of the state border outside BCP and contribute to suppression of illegal migrations and other forms of cross-border crime. We expect that initiative will be accepted and that the activities related to suppression of illegal crossings of the state border will be implemented. (2) 31 March 2014 [NI] On 7 March 2014, requests were repeated to neighbouring countries for establishment of joint groups for drafting of the studies and establishing the dynamics for closure of side roads. (3) 30 June 2014 [PI] The initiative was submitted on 06 March 2014 for establishment of mixed working groups for development of elaborate for closure of side roads suitable for illegal crossing of the state border and demolition of these roads with the neighbouring states Bosnia and Herzegovina, the Republic of Kosovo, the Republic of Albania and the Republic of Serbia. Through the Act of the MFAEI 09/16-821/8 of 23 April 2014, the Ministry of Interior of Montenegro received the Letter of the Ministry of Foreign Affairs of the Republic of Albania 4740/1 of 14 April 2014, which confirms that Albanian side is ready for establishment of the Joint Working Group for development of elaborate for closure of side roads suitable for illegal crossing of the state border and for their demolition. The Department determined the composition of the Working Group for fulfilment of this obligation. We were informed by the Embassy of the Republic of Albania in Montenegro through diplomatic channels on 29 May 2014 that Albanian side accepted the proposal for conducting of the meeting of the joint expert groups for development of elaborate for closure of side roads between two countries on 3 June 2014. The meeting of the joint expert groups of Montenegro and the Republic of Albania for development of elaborate for closure of side roads suitable for illegal crossing of the state border and their demolition was held in Shkoder on 3 June. They determined the content of the Elaborate and defined obligation for the heads at the local level along the entire state border to visit locations together by the end of June 2014 and carry out photographing and GPS positioning. The full commitment to successful organization and implementation of joint activities at the state border was expressed at the meeting. The next meeting was scheduled for the beginning of July 2014. 3. Demolished side roads with Republics of Kosovo, Albania and Serbia (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [PI] Montenegro takes steps with a view to closing alternative roads with neighbouring states. In December 2013, the Annex was developed for the elaborate of Montenegro and Bosnia and Herzegovina on demolition of side roads suitable for illegal crossing of the state border (44 roads suitable for crossing of the state border were defined, each side will demolish 22) with the proposal for the border traffic at the crossing points. The content of the elaborate, as well as the obligation for the heads at the local level along the entire state border to visit locations together by the end of June 2014 and carry out photographing and GPS positioning were determined at the meeting of the joint expert groups of Montenegro and the Republic of Albania for development of the Elaborate for closure of side roads suitable for illegal crossing of the state border and for their demolition, which was held in Shkoder on 3 June 2014. 4.Undertaken activities (1) 31 December 2013 [I] In accordance with the risk analysis, the Border Police supervises green and blue border. During this year, organizational units of the Border Police at regional level were additionally equipped with a mobile set for electronic supervision of the state border CCTV type ``SMARDEC” (9 base stations and 28 detectors) (2) 31 March 2014 [?] (3) 30 June 2014 [IC] In accordance with the risk analysis, the Border Police supervises green and blue border. During this year, organizational units of the Border Police at regional level were additionally equipped with a mobile set for electronic supervision of the state border CCTV type ``SMARDEC” (9 base stations and 28 detectors). Through the use of this technology, in addition to prevention, significant results are achieved in detection and prevention of the cross-border crime. Three thermo vision cameras and fifteen CCTV cameras (their installation is being prepared) were delivered through donation via EXBS Programme of USA. Procurement of installation equipment is awaited, as well as material required for putting these sensors into operation. Locations for installation were defined and people were trained for use of this equipment. The new equipment was installed in the period 10 January – 1 June 2014 at the following border crossing points in Montenegro: Border Crossing Point Božaj ( 1 computer and 1 optical reader); Airport Podgorica (3 computers); Airport Tivat ( two computers and two optical readers); Border Crossing Point Vraćenovići ( one computer and one optical reader); Border Crossing Point Dračenovac ( one computer and two optical readers) The Centre for Electronic Surveillance of the State Border in Bar was designated, and it will develop into the National Coordination Centre, in compliance with EUROSUR. Certain activities have been planned for technical improvement of this Centre with a view to connecting with neighbours. In the first four months of 2014, joint patrols were carried out with the following countries: 105 with the Republic of Serbia, 65 with the Republic of Albania and 102 with Bosnia and Herzegovina. | Decrease in the number of illegal border crossings (1) 31 December 2013 [?] (2) 31 March 2014 [?] (3) 30 June 2014 [PI] Increased efficiency in detection of cases of illegal crossing of the state border, reduced number of illegal crossings and number of criminal offences related to the area of cross-border traffic. |

Recommendation 8 from the Screening Report– area “External borders and Schengen”

| No. | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 4.11. | 1. Prepare a joint plan of measures for prevention and suppression of corruption at border crossings by all institutions involved [7] 2. Implementation of the plan and establishment of a monitoring mechanism, including annual reporting on results (2) 31 March 2014 [PI] | POLICE ADMINISTRATION Slavko Vojinovic | I 1. January; 2014; annually from January 2015 | 1. Plan developed (2) 31 March 2014 [PI] A draft joint plan of measures for prevention and suppression of corruption at border crossings was prepared and will be signed by the Ministry of Interior-Police Administration, Customs Administration and the Administration for Inspection Affairs. There are plans to hire a TAIEX expert for the period April/May, for the purpose of providing expert support for the preparation of the final version of the Plan. (3) 30 June 2014 [I] The Joint Plan of measures for prevention and repression of corruption at the border was signed on 4 April 2014 between the Ministry of Interior, the Police Administration, the Customs Administration and the Administration for Inspection Affairs. TAIEX expert from Poland visited Montenegro in the period 12-16 May, with a view to providing critical opinion on the adopted Joint Plan of measures for prevention and repression of corruption at the border. On 3 July 2014, through the Directorate for International Cooperation and European Integration, we received evaluation report of TAIEX expert (Event Nr.56505, stating inter alia that a certain progress has been achieved in this area. 2. Annual report produced (2) 31 March 2014 [?] (3) 30 June 2014 [?] | Reduced corruption at border crossings, more efficient handling of complaints (2) 31 March 2014 [?] (3) 30 June 2014 [I] Successful implementation of the plan and establishment of monitoring mechanisms, including annual reporting on results. Improved normative framework with a view to improving the work of institutions at the border crossing points and their suppression of corruption. Improved administrative, technical and material capacities of institutions at the border crossing points for suppression of corruption. Intense implementation of preventive measures and control mechanisms for prevention of corruption in institutions at the border crossing points. Permanent specialization of staff for the fight against corruption at the border crossing points. Reduced corruption and more efficient acting upon complaints. Defined concrete forms of mutual cooperation between the Police Administration, the Customs Administration and the Administration for Inspection Affairs in repression of corruption at the border. Improved fight against corruption and other criminal activities at the border, particularly smuggling. Provided joint and coordinated acting of the border services as regards prevention and repression of corruption at the border in compliance with the EU best practice. |

## 5.	JUDICIAL COOPERATION IN CIVIL AND CRIMINAL MATTERS

### 5.1.	JUDICIAL COOPERATION IN CIVIL AND COMMERICAL MATTERS          	MINISTRY OF JUSTICE	 - Lidija Masanovic

Recommendation 1 from the Screening Report – area “Judicial cooperation in civil and commercial matters“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 5.1.1. * | Submit the text of the Proposal for and/or the Law on Private International Law in English, with the attached Table of Concordance, to the EC – DG Justice, in order to assess the degree of conformity with relevant conventions (Brussels I and II, Rome I and II and Lugano). (1) 31 December 2013 [I] (2) 31 March 2014 [I] | MINISTRY OF JUSTICE Svetlana Rajkovic | I Oct 2013 | Text of the Law submitted to the European Commission (1) 31 December 2013 [I] The text of the Law was translated and submitted to the EC on 25 November 2013 through the Ministry of Foreign Affairs and European Integration. (2) 31 March 2014 [I] | Assessment of compliance of the Law on Private International Law submitted by the EC, with the recommendations for further improvement of national legislation (1) 31 December 2013 [I] Assessment of compliance with table of concordance was translated and submitted to the EC. |
| 5.1.2 * | § Prepare the analysis of the national civil, procedural and enforceable legislation with a view to evaluating the degree of compliance with the acquis. The analysis will contain the separate impact analysis for transposition of the relevant EU regulations into Montenegrin legislation in terms of assessment of the current and required administrative, budgetary, human resources and educational capacities and needs based on the number of cases, efficiency of procedure and the existing structure of employees. The Analysis will include the following Regulations: Regulation (EC) No 1393/2007 of the European Parliament and of the Council of 13 November 2007 on the service in the Member States of judicial and extrajudicial documents in civil or commercial matters Council Regulation (EC) No 1206/2001 of 28 May 2001 on cooperation between the courts of the Member States in the taking of evidence in civil or commercial matters Regulation (EC) No 805/2004 of the European Parliament and of the Council of 21 April 2004 creating a European Enforcement Order for uncontested claims Regulation (EC) No 1896/2006 of the European Parliament and of the Council of 12 December 2006 creating a European order for payment procedure Regulation (EC) No 861/2007 of the European Parliament and of the Council of 11 July 2007 establishing a European Small Claims Procedure Council Regulation (EU) No 1259/2010 of 20 December 2010 implementing enhanced cooperation in the area of the law applicable to divorce and legal separation Council Regulation (EC) No 4/2009 of 18 December 2008 on jurisdiction, applicable law, recognition and enforcement of decisions and cooperation in matters relating to maintenance obligations Amended Council Regulation (EC) No 2201/2003 of 27 November 2003 concerning jurisdiction and the recognition and enforcement of judgments in matrimonial matters and the matters of parental responsibility, repealing Regulation (EC) No 1347/2000 (3) 30 June 2014 [IC] | Ministry of Justice Tijana Badnjar | IC January– December 2014 | Prepared Analysis of the degree of compliance with proposals for amendments to legislation for the purpose of full harmonization and recommendations for strengthening of human resource capacities of the competent authorities. (3) 30 June 2014 [IC] With the help of EUROL Project, the Ministry of Justice hired the expert Aude Fiorini, lecturer at the University of Dundee, United Kingdom, to develop the analysis which will include the assessment of compliance of the national civil and enforceable procedure with relevant EU regulations. |  |
| 5.1.11. * | Conclude the Agreement on Cooperation between the Ministry of Justice, the Judicial Training Centre, and the faculties of law, aimed at the implementation of training programmes in the field of private international law and EU law. (1) 31 December 2013 [I] | MINISTRY OF JUSTICE Svetlana Rajkovic | I Sep 2013 | The Agreement, defining forms of cooperation through single training programme, concluded (1) 31 December 2013 [I] The Agreement on Cooperation among the Ministry of Justice, Judicial Training Centre, and Faculty of Law of the Montenegrin University was signed on 4 December 2013. |  |
| 5.1.12. * | Prepare the general education programme for judges and prosecutors and representatives of legislative and executive branch of power. The programme will contain the following: - trainings on international private law and EU law following the Lisbon Treaty and obligation of harmonisation - Law on International Private Law, relations with international private law, practical implications for implementation, - theme trainings for employees of ministries and judges on provisions defined by EU conventions and decrees: Regulation 44/2001 (Brussels I) on jurisdiction and the recognition and enforcement of judgments, case law; Council Regulation (EC) 1397/2007, Council Regulation (EC) 1348/2000 on the service in the Member States of judicial and extrajudicial documents in civil or commercial matters, connection with the Hague Convention of 1965, case law; Regulation 1206/2001 on cooperation between the courts of the Member States in the taking of evidence in civil or commercial matters, facilitated communication, use of video links, case law; Regulation (EC) 1896/2006 creating a European order for payment procedure, case law; Regulation (EC) 805/2004 creating a European Enforcement Order for uncontested claims and Regulation 1869/2005 replacing the Annexes to Regulation (EC) No 805/2004, case law; 2007 Lugano Convention on jurisdiction and the recognition and enforcement of judgments in civil and commercial matters; Regulation 2201/2003 (Brussels II bis) concerning jurisdiction and the recognition and enforcement of judgments in matrimonial matters and the matters of parental responsibility, case law; Regulation (EC) 4/2009 on jurisdiction, applicable law, recognition and enforcement of decisions and cooperation in matters relating to maintenance obligations European Contract Law: Regulation 593/2008 on the law applicable to contractual obligations (Rome I), Regulation 864/2007 on the law applicable to non-contractual obligations (Rome II), case law (1) 31 December 2013 [I] (2) 31 March 2014 [I] | MINISTRY OF JUSTICE Svetlana Rajkovic | I December 2013 | Education programme prepared (1) 31 December 2013 [I] The Education programme was prepared on 20 December 2013 and submitted to the Programme board for continuous education and the Coordination board of the Centre for reconsideration. (2) 31 March 2014 [I] The Education programme was approved by the Programme board for continuous education and the Coordination Board of the Centre for reconsideration. cluster included in the Work Programme of Human Resources Administration and Judicial Training Centre (1) 31 December 2013 [PI] The Training programme was prepared and submitted to the Programme board for continuous education and the Coordination board of the Centre for reconsideration and approval. (2) 31 March 2014 [I] The Programme board for continuous education and the Coordination Board of the Centre for reconsideration approved the Training program. |  |
| 5.1.13. | Implement a training programme for judges and prosecutors and representatives of legislative and executive power according to defined programme (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | JUDICIAL TRAINING CENTRE Maja Milosevic | IC Since January 2014 continuously | Number and type of organized trainings (2) 31 March 2014 [IC] Two seminars were organised on "National legislation in operation of mutual assistance and international cooperation in civil and commercial matters" for judges and prosecutors from the northern region (4 and 5 March 2014) and judges and prosecutors from the central and southern region (6 and 7 March 2014). (3) 30 June 2014 [IC] In the reporting period 1 January – 30 June 2014, five training courses were carried out in compliance with the Training Programme for judges and prosecutors on international legal assistance and international cooperation in civil and commercial matters (four two-day courses and 1 one-day course), in cooperation between the Judicial Training Centre of Montenegro, the Ministry of Justice of Montenegro, OSCE Mission in Montenegro and UNDP Montenegro; financial support for this programme was provided by the British Embassy in Podgorica. - Two seminars were held in March on the topic “National legislation in the function of providing international legal assistance and international cooperation in civil and commercial matters “for judges from the northern region (4 and 5 March 2014) and judges of the central and southern region (6 and 7 March 2014) -Two seminars were held in April on the topic ''International legal assistance and international cooperation in civil and commercial matters– multilateral and bilateral treaties’ for judges of the northern region (22 and 23 April 2014) and judges of the central and southern region (24 and 25 April 2014) - The seminar was held in May on the topic “Overview of the acquis in the area of international judicial cooperation in civil matters'', (27 May 2014) which was attended by judges from all three regions. Number and structure of participants (2) 31 March 2014 [IC] 20 representatives of courts and 20 representatives of prosecutors’ offices attended the seminars. (3) 30 June 2014 [IC] The seminars organized within the Training Programme for judges and prosecutors on international private law and international cooperation in civil and commercial matters were attended by the same group, i.e. judges from civil and commercial departments from the central, southern and northern region of Montenegro – 53 attendees in total Press clipping (2) 31 March 2014 [?] (3) 30 June 2014 [?} Materials published on the website of the ministries (2) 31 March 2014 [?] (3) 30 June 2014 [?} Questionnaires of participants (2) 31 March 2014 [IC] Seminar participants filled out evaluation forms and evaluated seminar with the highest grade (5) (3) 30 June 2014 [IC] At the end of the seminar, participants were asked to fill out evaluation forms. At the seminar held on: - 4 and 5 March 2014, evaluation forms were filed out by 18 participants and the final grade for the success of the seminar was 4,7 (grades from 1 to 5) -6 and 7 March 2014., evaluation forms were filed out by 13 participants and the final grade for the success of the seminar was 5 (grades from 1 to 5) - 22 and 23 April 2014, evaluation forms were filed out by 20 participants and the final grade for the success of the seminar was 4,65 (grades from 1 to 5) -24 and 25 April 2014, evaluation forms were filed out by 14 participants and the final grade for the success of the seminar was 4,42 (grades from 1 to 5) - 27 May 2014, evaluation forms were filed out by 18 participants and the final grade for the success of the seminar was 4,5 (grades from 1 to 5) | The administrative capacities of the judicial authorities and executive authorities promoted and trained to effectively apply regulations from the field of private international law and EU law (2) 31 March 2014 [?] (3) 30 June 2014 [?} |

Recommendation 2 from the Screening Report – area “Judicial cooperation in civil and criminal matters“

### 5.2.	JUDICIAL COOPERATION IN CRIMINAL MATTERS	MINISTRY OF JUSTICE	 - Svetlana Rajkovic

Recommendation 1 from the Screening Report – area „Judicial cooperation in criminal matters“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 5.2.1. * | Submit the consolidated text of the Law on International Legal Assistance in Criminal Matters, with the attached Table of Concordance, to the EC – DG Justice. (1) 31 December 2013 [I] | MINISTRY OF JUSTICE Svetlana Rajkovic | I Sep 2013 | Text of the Law submitted to the European Commission (1) 31 December 2013 [I] Text of the Law and Table of Conformity submitted to the European Commission on 25 November 2013 | Submitted assessment grade of compliance of the Law on International Legal Assistance in Criminal Matters by the EC along with recommendations for further improvements in the national legislation (1) 31 December 2013 [PI] Assessment grade of compliance of the Law on International Legal Assistance in Criminal Matters submitted to the EC, for opinion. |
| 5.2.2 * | Prepare the analysis of the existing national legislation for the purpose of assessment of the degree of compliance with the acquis. The Analysis will contain the separate impact analysis for transposition of the relevant EU regulations into Montenegrin legislation in terms of assessment of the existing and required administrative, budgetary, human resources and educational capacities and needs of the Ministry of Justice, competent courts and prosecutor`s offices, based on the number of cases, efficiency of procedure and the existing structure of employees. (3) 30 June 2014 [IC] | Ministry of Justice Svetlana Rajkovic | IC June - December 2014 | Prepared Analysis of the degree of compliance with proposals for amendments to legislation for the purpose of full harmonization and recommendations for strengthening of human resource capacities of the competent authorities. (3) 30 June 2014 [IC] The working group for development of the analysis has been established and the national expert has been selected. The working group includes representatives of the Ministry of Justice, the Judicial Council and the national expert. Foreign expert has been selected. TAIEX application for the engagement of the foreign expert has been prepared. |  |

Recommendation 2 from the Screening Report – area “Judicial cooperation in criminal matters“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 5.2.9. | Organize regular meetings of representatives of the ministries of justice with which Montenegro has signed a bilateral agreement on international legal assistance in criminal matters, on the implementation of bilateral agreements that provide direct cooperation of the courts. (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | MINISTRY OF JUSTICE Svetlana Rajkovic | IC Since January 2014 at least once a year | Number of held regional meetings (2) 31 March 2014 [IC] The first meeting of representatives of the Ministry of Justice of Montenegro with representatives of the Ministry of Justice of the Republic of Serbia, regarding the implementation of bilateral agreements on mutual legal assistance in criminal matters, was held on 5 - 7 February 2014. (3) 30 June 2014 [IC] The second regional meeting was held between representatives of the Ministries of Justice of the countries in the region. The meeting was attended by the Assistant Minister of Justice of the Republic of Croatia, the Assistant Minister of Justice of Bosnia and Herzegovina, the Head of the Department for International Legal Assistance in Criminal Matters in Serbia, the Head in charge of international legal assistance in the FYR of Macedonia and the Head in charge of international legal assistance in Slovenia. The meeting was held on 26 May 2014 in Podgorica. | Increased number of cases in which the direct cooperation between courts was established, (2) 31 March 2014 [?] (3) 30 June 2014 [?] Promoted the quality of the implementation of bilateral agreements (2) 31 March 2014 [?] (3) 30 June 2014 [?] |
| 5.2.10 * | Organize the regional conferences as regards enforcement of provisions of bilateral treaties providing for direct cooperation between courts (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | Judicial Training Centre Maja Milosevic | IC Since January 2014 at least once a year | Number of regional conferences held (2) 31 March 2014 [IC] Regional seminar was organized in Ulcinj on 27 and 28 March 2014, on the topic: ''International legal assistance and fight against trans-national organized crime and other forms of the cross-border crime'' – experiences of Montenegro, Albania and USA. This gathering was attended by representatives of the Ministry of Justice, the police, INTERPOL office, judges and prosecutors from Montenegro and the Republic of Albania, as well as experts from USA. (3) 30 June 2014 [IC] Regional seminar was organized in Ulcinj on 27 and 28 March 2014, on the topic: ''International legal assistance and fight against trans-national organized crime and other forms of the cross-border crime'' – experiences of Montenegro, Albania and USA. This gathering was attended by representatives of the Ministry of Justice, the police, INTERPOL office, judges and prosecutors from Montenegro and the Republic of Albania, as well as experts from USA. | Increased number of cases in which direct cooperation between courts was established (3) 30 June 2014 [?] Improved quality of implementation of bilateral treaties (3) 30 June 2014 [?] |

Recommendation 3 from the Screening Report – area “Judicial cooperation in criminal matters“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 5.2.11. * | Prepare the plan of education for judges and prosecutors, Ministry of Justice and officers of Police Administration on positive regulations from the area of international legal assistance in criminal matters, which includes trainings on provisions of ILACM, as well as provisions of multilateral and bilateral agreements from the area of ILACM. Theme trainings for employees of ministries and judges concerning provisions defined by the following EU conventions and decrees: - European Convention on mutual provision of legal assistance in criminal matters, with accompanying protocols, - European Convention on extradition with accompanying protocol, - Convention on transfer of convicted persons, - European Convention on transfer of procedure, - Convention on simplified procedure of extradition between EU states, - Framework Decision 2002/584/JHA on European Arrest Warrant and procedure of transfer between Member States - Convention from 2000 on mutual assistance in criminal matters between EU Member States, along with the Protocol. (1) 31 December 2013 [I] | MINISTRY OF JUSTICE Svetlana Rajkovic | I December 2013 | Education programme prepared (1) 31 December 2013 [I] The education programme was prepared on 20 December 2013 and submitted to the Programme board for continuous education and to the Coordination board of the Centre for reconsideration. (2) 31 March 2014 [I] The Programme board for continuous education and Coordination board of the Centre for reconsideration approved the education programme. cluster included in the programme of work of the Human Resources Administration and Judicial Training Centre, as well as Police Academy (1) 31 December 2013 [PI] The training programme was prepared and submitted to the Programme board for continuous education and Coordination board of the Centre for reconsideration and approval. (2) 31 March 2014 [I] The Programme board for continuous education and the Coordination Board of the Centre for reconsideration approved the education programme. |  |
| 5.2.12. | Conduct trainings on the basis of prepared plan (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | JUDICIAL TRAINING CENTRE Maja Milosevic | IC Since January 2014 | Number and type of organized trainings (2) 31 March 2014 [IC] In accordance with implementation of the Education programme of judges and prosecutors, two seminars on "International legal assistance and international cooperation in criminal matters as part of international and European law” were organised on 25 – 26 February and 27 – 28 February 2014 in Budva. The first seminar was dedicated to the judges and prosecutors from northern part of Montenegro, and the second one to judges and prosecutors from the central and southern part of Montenegro. (3) 30 June 2014 [IC] The Judicial Training Centre, the Ministry of Justice of Montenegro and UNDP Office in Montenegro organized five education courses under the Programme for education of judges and prosecutors on international legal assistance in criminal matters (4 two-day courses and 1 one-day course) - The seminar was organized on 25 – 26 February 2014, for judges and prosecutors of the northern region and on 27 - 28 February 2014, for judges and prosecutors of the central and southern region on the topic: ``International legal assistance and international cooperation in criminal matters as a part of the international and the European law” - The seminar was organized on 14 and 15 April 2014, for judges and prosecutors of the northern region and on 16 and 17 April 2014, for judges and prosecutors of the central and southern region on the topic: ''International treaties of Montenegro as a base for international legal assistance in criminal matters”. - The seminar for judges and prosecutors from all three regions was organized on 27 May 2014 on the topic ``Overview of the acquis in the area of international judicial cooperation in criminal matters”. Number and structure of participants (2) 31 March 2014 [IC] First seminar was dedicated to the judges and prosecutors from northern part of Montenegro, and the second one to judges and prosecutors from the central and southern part of Montenegro. 22 participants, representatives of prosecutors’ office and courts, attended each seminar. (3) 30 June 2014 [IC] Seminars organized under the Training Programme for judges and prosecutors on international cooperation in criminal matters were attended by the same participants, i.e. judges and prosecutors from the central, southern and northern region of Montenegro – 45 participants in total Press clipping (2) 31 March 2014 [?] (3) 30 June 2014 [?] Materials published on the website of the Ministry (2) 31 March 2014 [?] (3) 30 June 2014 [?] Questionnaires of participants (2) 31 March 2014 [IC] Seminar participants filled out evaluation forms and evaluated seminar with the highest grade (5). (3) 30 June 2014 [IC] At the end of the seminar, participants were asked to fill out evaluation forms. At the seminar held on: - 25 and 26 February 2014, evaluation forms were filed out by 19 participants and the final grade for the success of the seminar was 4,9 (grades from 1 to 5) -27 and 28 February 2014, evaluation forms were filed out by 14 participants and the final grade for the success of the seminar was 4,7 (grades from 1 to 5) - 14 and 15 April 2014, evaluation forms were filed out by 15 participants and the final grade for the success of the seminar was 4,6 (grades from 1 to 5) - 16 and 17 April 2014, evaluation forms were filed out by 10 participants and the final grade for the success of the seminar was 4,7 (grades from 1 to 5) - 27 May 2014, evaluation forms were filed out by 20 participants and the final grade for the success of the seminar was 4,75 (grades from 1 to 5) | The administrative capacity of the judicial bodies, Ministry of Justice and Police Administration promoted and trained to effectively implement the international agreements and national regulations in the field of judicial cooperation and legal assistance in criminal matters (2) 31 March 2014 [?] (3) 30 June 2014 [?] |

Recommendation 4 from the Screening Report – area “Judicial cooperation in criminal matters“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 5.2.13. | Organize expert visiting of representatives of EUROJUST to relevant institutions (2) 31 March 2014 [IC] Report on a study visit of EUROJUST’s experts, organized on 7-8 October 2013, was received on 8 January 2014. During the visit, the EUROJUST's experts met with representatives of the Ministry of Justice, Supreme Public Prosecutor’s Office, and Agency for the Protection of Personal Data and the Free Access to Information and Ministry of Interior. The report provided specific recommendations that need to be fulfilled prior to signing the Agreement with EUROJUST. | MINISTRY OF JUSTICE Svetlana Rajkovic | IC During 2014; depending on EUROJUST’s requirements | Organized experts visit (2) 31 March 2014 [IC] In order to fulfil all recommendations from the Report of the expert visit to EUROJUST, specific activities were conducted: Representative of the Agency for the protection of personal data, as well as national expert on the protection of personal data from the Ministry of Interior, began with visits to all prosecutors' offices and conducting the trainings on-site. These trainings represent educational workshops, regarding the introduction of standards for the protection of personal data and the implementation of the new Law on protection of personal data. At the suggestion of EUROJUST, the preparation of the Rules of Procedure of the prosecution office that will include procedures for the handling of personal data is ongoing. The Rules of Procedure will be sent to EUROJUST for comments. With the support of IPA 2010 Regional Programme, Strengthening the Prosecutors' Network in the fight against corruption and organized crime, a regional seminar on "Data protection during investigation and prosecution of criminal activities”, was organized on 14 and 15 March 2014, at which the speakers were Malci Gabrijelcic and Diana Alonso Blas, EUROJUST experts. At the initiative of Montenegro, topics of the seminar included the protection of personal data, and a lecturer in this area from Montenegro was accepted. Harmonization of the text of the Protocol on Cooperation between the Agency for the protection of personal data and Supreme Public Prosecutor's Office is ongoing in order to define close cooperation forms between the two bodies. Required information submitted (2) 31 March 2014 [IC] | Based on the evaluation of conformity of national legislation and reports of the expert mission, the further necessary steps aimed at signing the agreement defined (2) 31 March 2014 [?] |

## 6.	POLICE COOPERATION AND FIGHT AGAINST ORGANISED CRIME

### 6.1.	POLICE COOPERATION	MINISTRY OF INTERIOR	 - Dejan Djurovic

Recommendation 1 from the Screening Report– area “Police cooperation“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.1.1. | 1. Hire the EU experts for the purpose of drafting: Analysis of the state of play in terms of application of standards of personal data protection standards and data confidentiality (legislative, organizational, IT, staff and procedural analysis), Proposal of measures for drafting procedures, organisation of trainings and procurement of the missing equipment (computer, safety equipment, computer programs) for implementation of standards in the field of personal data protection. (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] (3) 30 June 2014 [NI] The beginning of the Twinning project for development of the AP for Schengen is anticipated for implementation of the mentioned measure; selection of the country that will be the partner in this project has been planned for June 2014. | POLICE ADMINISTRATION Natasa Starovlah Knezevic | NI December 2013; February 2014 | Experts engaged. Analysis completed (1) 31. December 2013 [NI] In July 2013, project was proposed to the EU (planned activity 3.1) for Twinning which will be carried out with the financial support of the EU (in the amount of EUR 1.100.000). Project includes Inter alia engagement of experts in order to draft situation analysis in terms of personal data protection. The opinion of the EU in relation to proposed project is expected. (2) 31 March 2014 [NI] Experts will be engaged through Twinning project, after which information on the application of standards and protection of personal data (legislative, organizational, personnel, IT) will be prepared through the analysis of the situation In July 2013, project was proposed to the EU (planned activity 3.1) for Twinning which will be carried out with the financial support of the EU (in the amount of EUR 1.100.000). Project includes inter alia engagement of experts in order to draft situation analysis in terms of personal data protection. The project was approved by the EU and beginning of implementation is expected by the end of the second quarter of 2014. Note: The project was approved by the EU. Beginning of its implementation is expected by the end of the second quarter of 2014. (3) 30 June 2014 [NI] The beginning of the Twinning project for development of the AP for Schengen is anticipated for implementation of the mentioned measure; selection of the country that will be the partner in this project has been planned for June 2014. Note: The beginning of the Twinning project for development of the AP for Schengen is anticipated for implementation of the mentioned measure; selection of the country that will be the partner in this project has been planned for June 2014. Proposal of measures for the improvement of the protection of personal data and confidentiality of data was prepared[8] (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] Proposed measure will be part of the analysis made ​​by experts, after the beginning of the implementation of the Twinning project. (3) 30 June 2014 [NI] Proposed measures will be the integral part of the analysis developed by experts, after the beginning of implementation of the Twinning project Note: Proposed measures will be the integral part of the analysis developed by experts, after the beginning of implementation of the Twinning project |  |
| 6.1.2. | 1. Fulfil personal data protection standards on the basis of analysis done: drafting rulebooks on the form and contents of personal data records, according to the Law on Internal Affairs, amending procedures for handling personal data [9] drafting the Personal Data Protection Plan upgrading of computer programs for electronic records of personal data, and application of IT security standards [10] Organisation of continuous trainings for Police Administration staff regarding personal data protection. (1) 31 December 2013 [PI] (2) 31 March 2014 [PI] According to the Personal Data Protection Plan the following was carried out: - Instructions on security of a computer system of the Ministry of Interior were adopted; - Instructions on method of determining the need for procurement and testing of procurement of computer equipment were adopted; - Instructions on Access and access control to system of Ministry of Interior were adopted; - Rulebook on the form, content and manner of keeping records of collected, processed and used data and international data exchange (Official Gazette 41/13) was adopted; - Instructions on use of data from the records of the Ministry of Interior by the Police Administration were adopted; - Instructions on inactivation of police data were adopted; Final processing of application solutions; implemented application solutions in order to access work applications using digital certificates (implementation starts from 15 January 2014) and logging action to be based on the certificates. (3) 30 June 2014 [PI] | POLICE ADMINISTRATION Zora Cizmovic | PI 1. September 2013; October 2013; October 2013; November 2013; September 2013 – IV quarter of 2017, continuously, at least once a year | 1. Rulebooks on the form and contents of personal data records drafted, which are kept according to the Law on Internal Affairs (1) 31 December 2013 [I] Rulebooks on the form and contents of personal data records, kept in accordance with the Law on Internal Affairs, were drafted. (2) 31 March 2014 [I] Rulebooks on the form and contents of personal data records, kept in accordance with the Law on Internal Affairs, were drafted. (3) 30 June 2014 [I] The Rulebook on the form and content of personal data records was developed, in compliance with the Law on Internal Affairs. Procedures for handling personal data developed (input, updating and deletion of personal data) (1) 31 December 2013 [NI] According to the Plan for Personal Data Protection, the following activities were carried out: - Instructions on computer system security of the Ministry of Interior were adopted; - Instructions on the manner of establishing the needs for procurement and checking procurement of computer equipment were adopted; - Instructions on access and access control to the system of the Ministry of Interior were adopted; - Regulation on form, contents and manner of keeping records on collected, processed and used data and international data exchange were adopted (Official Gazette of Montenegro 41/13); - Instructions on use of data from the records of the Ministry of Interior by Police Administration were adopted; - Instructions on inactivation of police data were adopted. (2) 31 March 2014 [PI] (3) 30 June 2014 [NI] Note: The beginning of the Twinning project for development of the AP for Schengen is anticipated for implementation of amended procedures for personal data handling; selection of the country that will be the partner in this project has been planned for June 2014. Plan of Personal Data Protection drafted (1) 31 December 2013 [I] According to the Plan for Personal Data Protection, the following activities were carried out: - Instructions on computer system security of the Ministry of Interior were adopted; - Instructions on the manner of establishing the needs for procurement and checking procurement of computer equipment were adopted; - Instructions on access and access control to the system of the Ministry of Interior were adopted; - Regulation on form, contents and manner of keeping records on collected, processed and used data and international data exchange were adopted (Official Gazette of Montenegro 41/13); - Instructions on use of data from the records of the Ministry of Interior by Police Administration were adopted; - Instructions on inactivation of police data were adopted. (2) 31 March 2014 [?] (3) 30 June 2014 [NI] Note: The beginning of the Twinning project for development of the AP for Schengen is anticipated for development of the Plan for Personal Data Protection; selection of the country that will be the partner in this project has been planned for June 2014. Application solutions for the electronic management of all personal databases, as well as for automatically alert/deletion of personal data kept in electronic databases, upon the expiry of the legal deadline for data storage in database, were drafted (1) 31 December 2013 [I] Final processing of application solutions; implemented application solutions in order to access work applications using digital certificates (implementation starts from 15 January 2014) and logging action to be based on the certificates. (2) 31 March 2014 [?] (3) 30 June 2014 [I] Application solutions were finally processed for electronic records of personal data and application of IT safety standards. Plan of continuous training of employees of the Police Administration was made – Programme of the Police Academy was drafted. (1) 31 December 2013 [NI] The activities related to preparation of training plan of police officers in terms of personal data protection are ongoing. (2) 31 March 2014 [NI] The activities related to preparation of training plan of police officers in terms of personal data protection are ongoing. (3) 30 June 2014 [I] Under the Training Plan for international police cooperation, which was submitted to the Police Academy for insight, trainings for officers of the Department as regards personal data protection will be carried out at the Police Academy in Danilovgrad in the fourth quarter of 2014. Two officers from the Department for International Police Cooperation attended the training on the topic ``International police cooperation and personal data protection“, which was held in Zagreb. | 1. Number of information kept in personal data records (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [?] Number of deleted/updated information pursuant to the application of personal data protection standards, number of controls conducted concerning the confidentiality and protection of personal data, number of applications for examination/complaints of persons whose data are being processed, and number of rejected complaints/applications for examination (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [?] Number of information/personal data stored in electronic form into applications for storage of personal data; number of information exchanged via Europol, which are stored into national databases via applications (1) 31 December 2013 [NI] (2) 31 March 2014 [PI] During period from 1 January to 31 March 2014, information was exchanged with Europol. All information stored in an electronic database. Note: Pursuant to the fact that Montenegro has not signed an operating agreement with Europol, which allows the exchange of personal data, all information exchanged with Europol included no personal data. (3) 30 June 2014 [?] Number of unclassified and classified information exchanged with Europol (number of information containing personal data), number of information stored into Europol's AWF, number of joint police operations with Europol (1) 31 December 2013 [NI] (2) 31 March 2014 [PI] During the reporting period, 28 unclassified and 2 classified pieces of information were exchanged with Europol. Given that the Operating Agreement on Cooperation has not yet been signed, Montenegro did not have direct information exchange with Europol, which was used for AWF. (3) 30 June 2014 [?] |
| 6.1.3. | · Fulfil security standards defined by: Europol Instructions for network security-System Specific Security Requirements Europol Security Manual Europol Guidance for Security. (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] (3) 30 June 2014 [I] | POLICE ADMINISTRATION Dejan Djurovic | NI Nov 2013 | Standards fulfilled – drafted analysis of fulfilment of recommendations defined by Europol’s documents in relation to standard procedures applied in Montenegro (1) 31 December 2013 [NI] In July 2013, the project was proposed to the EU (planned activity 3.1) for Twinning which will be carried out with the financial support of the EU (in the amount of EUR 1.100.000). The project inter alia includes engagement of experts in order to draft situation analysis in terms of personal data protection. The EU approved the project. Its implementation will be carried out during 2014. Within preparation for signing the Agreement on operative cooperation with Europol, in order to exchange classified data, during 2014 Memorandum of Understanding will be signed. It will define necessary standards in accordance with the Europol Security Manual. (2) 31 March 2014 [PI] In July 2013, the project was proposed to the EU (planned activity 3.1) for Twinning which will be carried out with the financial support of the EU (in the amount of EUR 1.100.000). The project inter alia includes engagement of experts in order to draft situation analysis in terms of personal data protection. The EU approved the project. Its implementation will be carried out during 2014. Within preparation for signing the Agreement on operative cooperation with Europol, in order to exchange classified data, during 2014 Memorandum of Understanding will be signed. It will define necessary standards in accordance with the Europol Security Manual. Draft analysis of security is made in accordance with the EUROPOL's documentation. (3) 30 June 2014 [I] The analysis of fulfilment of security standards defined by instructions of EUROPOL was developed with the support of UNDP. |  |
| 6.1.4 * | Signing of the Operational Agreement on Cooperation with EUROPOL (with a view to exchanging of personal data).[11] (2) 31 March 2014 [NI] Signing of the Operational Agreement with EUROPOL is expected at the end of 2014 The procedure before the competent EUROPOL bodies is underway. (3) 30 June 2014 [PI] | POLICE ADMINISTRATION Ivan Ivanisevic | PI Until December 2014 | Operational Agreement on Cooperation signed Ratified in the Parliament of Montenegro and entered into force (2) 31 March 2014 [PI] The Draft Operational Agreement with EUROPOL was developed in December 2013 and endorsed by the Government of Montenegro. The Draft Agreement was endorsed by the EU Management Board and submitted to the Joint Supervisory Body (JSB), from which consideration and adoption of this draft in April 2014 are expected Note: Dynamics of signing of the Operational Agreement is now under the exclusive jurisdiction of EUROPOL, considering the fact that Montenegro fulfilled all obligations concerning preconditions for signing of the agreement (3) 30 June 2014 [PI] The Draft Operational Agreement with EUROPOL was developed in December 2013 and endorsed by the Government of Montenegro. The Draft agreement was endorsed by all competent authorities of the EU; therefore, formal invitation from EUROPOL for signing of the agreement is now anticipated | Number of unclassified and classified information exchanged with EUROPOL, number of information kept in analytical working files of EUROPOL (AWF), number of joint police operations with EUROPOL as a result of information exchanged via AWF (1) 31 December 2013 [IC] In the course of 2013, 172 communications were exchanged with EUROPOL (via Siena-e), out of that number there were 167 unclassified information (Basic Protection Level), and 5 information labelled as RESTRICTED. All information that were exchanged has strategic character (did not contain personal data) due to the fact that the Operational Agreement on Cooperation has not been signed yet. Montenegro still does not participate in AWF due to the same reason (2) 31 March 2014 [IC] (3) 30 June 2014 [?] |
| 6.1.6 * | 1. Accession and active participation of Montenegro in the Analytical Working Files (AWF) of EUROPOL [12] Designation – appointment of the contact point who will act as the national coordinator for AWF (1) 31 December 2013 [NI] Accession to AWF of EUROPOL is not possible until the Operational Agreement with EUROPOL is signed (2) 31 March 2014 [NI] The mentioned activity will be carried out only after signing of the Operational Agreement with EUROPOL, which has been planned for December 2014. It is necessary to launch the initiative for development of the analysis of needs for membership into the AWF and form the request for accession after that The optimal deadline is the beginning of 2015. (3) 30 June 2014 [NI] The mentioned measure will be implemented only after signing of the Operational Agreement with EUROPOL, which has been planned for December 2014. Therefore, the optimal deadline for implementation of the mentioned measure is January 2015. | POLICE ADMINISTRATION Dejan Djurovic | NI 1. January 2014, continuously[13]; January 2014 | 1. Montenegro participates in AWF of EUROPOL concerning South-Eastern Europe (through submission, analysis and use of information from AWF,)[14] (2) 31 March 2014 [NI] (3) 30 June 2014 [NI] Note: The mentioned measure will be implemented only after signing of the Operational Agreement with EUROPOL, which has been planned for December 2014. Therefore, the optimal deadline for implementation of the mentioned measure is January 2015. National coordinator for AWF designated – appointed (2) 31 March 2014 [NI] (3) 30 June 2014 [NI] Note: The mentioned measure will be implemented only after signing of the Operational Agreement with EUROPOL, which has been planned for December 2014. Therefore, the optimal deadline for implementation of the mentioned measure is January 2015. | Number of information entered into the analytical working files of EUROPOL (AWF); number of exchanged information concerning particular working files, number of criminal reports – prosecuted persons and criminal organizations, on the grounds of information received from the analytical working files (2) 31 March 2014 [NI] (3) 30 June 2014 [?] |
| 6.1.7. | Submission of information on new identified psychoactive substances via Siena link to Europol (1) 31 December 2013 [IC] Procedure for the submission of information for Europol concerning identified new psychoactive substances was agreed with the Department for Fight against Drugs Smuggling, in order to be forwarded via Sienna link to Europol. The new forms of psychoactive substances have not been identified in Montenegro so far. (2) 31 March 2014 [IC] The above mentioned activity is being carried out continuously. Notification on submitting information on new psychoactive substances has been sent to the Department for Fight against Drugs Smuggling and Forensic Centre. There are no new psychoactive substances in Montenegro, if any, the above-mentioned organizational units of the Police Administration will inform us and Europol will be promptly informed via Siena link. (3) 30 June 2014 [IC] | POLICE ADMINISTRATION Dejan Djurovic | IC January 2014, Continuously[15] | Number of submitted information in relation to number of identified new psychoactive substances[16] (1) 31 December 2013 [IC] The new forms of psychoactive substances were not identified, so information was not submitted. (2) 31 March 2014 [?] (3) 30 June 2014 [IC] The new forms of psychoactive substances were not identified, so information was not submitted. |  |
| 6.1.8. | 1. Establish a secure electronic communication network [17] for mutual access to data bases [18] and exchange of information between law enforcement agencies [19], including Public Prosecution Office [20], by: drafting analysis with proposal of measures, in relation to the existing infrastructure and possibilities for access to data bases, Implementing measures for enabling access to data bases and exchange of information. (1) 31 December 2013 [PI] The process of drafting situation analysis, in order to produce proposal of measures, is ongoing. In order to implement this measure, the working group for drafting the situation analysis and proposal of measures was established. Expert support is provided by Croatia, as assistance in drafting the document, through cooperation with UNDP. In this regard, two experts gave recommendations in relation to fulfilment of obligations. Recommendations refer to IT, organizational and procedural aspect. Selection of optimal model for institutional networking is ongoing. (2) 31 March 2014 [PI] A working group for the implementation of the above-mentioned measure was established. Meetings of the working group were held and databases of other law enforcement institutions were presented, which are important and require approach within the exercise of regular operations for the Police Administration, Ministry of Interior. In order to assist in the preparation of the analysis, experts from the Republic of Croatia (UNDP), after visiting the Department of International Police Cooperation, Department of IT communications in December 2013, made ​​an analysis of the existing infrastructure and possibility to access the data for the purpose of establishing protected communications network for mutual data access and exchange of information among law enforcement services, including the State Prosecutor's Office. Based on this analysis, as well as situation analysis, the Working Group for the measure 6.1.8 prepared its analysis of opportunities and ways of networking the institutions for the purpose of exchange of information and future mutual access to data in databases. Formal confirmation of this analysis by all included bodies is expected. In order to secure the establishment of electronic communications by the Ministry of Interior, ​​the terms of reference and specifications of needs were made for the UNDP for the implementation of an intranet for the Ministry of Interior, which will be used as the basis for communication among bodies. (3) 30 June 2014 [IC] | POLICE ADMINISTRATION Natasa Starovlah Knezevic | IC 1. October 2013; I quarter of 2015 | Special programme made which enables access to databases (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [IC] Analysis developed and aligned with the proposed measures, as regards the existing infrastructure and the possibility for access to databases, and exchange of information between authorities. Note: As regards the indicators, there is no indicator related to development of analysis, therefore, the development of analysis has been placed into this indicator. All indicators refer to realization envisaged for the first quarter of 2015. Networking of databases of all relevant bodies with Prosecution Office carried out (1) 31. December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [NI] Improved existing technical conditions for access to databases in competent bodies (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [NI] Delivered trainings on use of databases (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [NI] Enabled access to databases (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [NI] - Report on work of Public Prosecution Office for fight against organised crime, corruption, terrorism and war crimes (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [NI] - Report of the European Commission (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [NI] - Report of MONEYVAL (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [NI] | Established better and more efficient inter-institutional cooperation (number of exchanged information, number of accesses to databases, number of investigations for which network was used in order to access databases and exchange information). (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30 June 2014 [?] |

Recommendation 2 from the Screening Report– area “Police cooperation“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.1.11. | 1. Analysis of the current situation with regard to the necessary resources for effective international police cooperation: equipment (computer and communications equipment) human resources (needs analysis to increase the number of employees, training needs analysis) analysis of needs for additional financial resources in accordance with identified needs[24] 2. Implementation of activities based on the completed needs analysis: procurement of equipment[25] recruitment of missing personnel[26] training of officers (1) 31 December 2013 [PI] Within the implementation of these measures, with funding from the International Organization for Migration (IOM), the expert team of Slovenian police carried out an evaluation of the situation in the Department of International Police Cooperation. The situation analysis was conducted in terms of human resources, organizational structure, implementation of the EU standards in international police cooperation, defining procedures for international police cooperation. According to this analysis, recommendations are made ​​regarding the future development of the Department, missing personnel (especially in terms of establishing the functioning according to the 24/7 principle and in terms of future expansion of the Schengen area of action - SIRENE Bureau). Also, as part of the regular activities of the evaluation of the situation regarding the application of international standards, the Department of International Police Cooperation visited the Interpol’s Evaluation Team. Based on the analysis of situation, it made ​​recommendations in the area of recruitment of necessary personnel (in terms of establishing the work based on 24/7 principle and filling the vacancy job positions for translators), as well as in terms of procurement of missing IT equipment (in terms of establishing a server room, setting AFIS unit - workstation within the Department). Within the assessment of fulfilment of security standards, team of the Directorate for Data Secrecy made ​​recommendations regarding the establishment of server room in order to adequately keep electronically stored classified secret data in accordance with the EU and NATO standards. According to the analysis of the current situation in terms of electronic data security, the Department of Information Technology and Department of International Police Cooperation made the project for establishing server room, worth EUR 65,000, which will be implemented during 2014. The above-mentioned departments are periodically carrying out the analysis of needs for procurement of computer equipment. In accordance with this, plan of the procurement of equipment is defined. Plan for upgrading the existing IT equipment in the Department of International Police Cooperation was made in the amount of cca. EUR 40,000, which is transformed into the project for external financing. As part of implementation of training plan and implementation of standards for international police cooperation, the Twinning project was made, approved by the EU, which will be financed from the EU budget in the amount of EUR 1.1 million and implemented in the period 2014-2015. (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | POLICE ADMINISTRATION Natasa Starovlah Knezevic | IC January 2014, continuously [27] | Analysis made. The necessary funding defined. Equipment purchased for the department, which was defined necessary by the analysis, equipment put into operation (1) 31 December 2013 [PI] Analysis made. The necessary funding defined. The missing equipment was not procured. Note: These activities are carried out periodically, according to the identified needs. The recent analysis was conducted in February 2014 (2) 31 March 2014 [IC] Slovenian experts made an analysis of the state of the equipment in light of future five years period of development and submitted it to the IT Department. Make a request for the procurement of equipment together with SIT. The analysis of needs to increase the number of employees was made. (3) 30 June 2014 [R] The analysis of the current situation as regards the resources required for efficient international police cooperation has been developed with the support of Slovenian experts. The request for procurement of equipment has been developed together with SIT. Realization of activities on the grounds of conducted analysis of needs is underway. Recruited staff, conducted trainings, in accordance with the needs analysis (1) 31 December 2013 [NI] Training plan and trainings will be implemented in the framework of the Twinning project funded by the EC, which is expected to start in the second quarter of 2014. Note: The delay in implementation is due to delay of the Twining project. (2) 31 March 2014 [?] (3) 30 June 2014 [?] |  |
| 6.1.12 * | Amending the Decree on police representatives with a view to the following: introducing the possibility for police representatives to represent the EU interests in third countries Amending the procedures for selection of police representatives with a view to defining authorizations of the police director to conduct the procedure for selection and propose the candidate for police representative Defining authorizations of the police for provision of guidelines for work to police representatives (3) 30 June 2014 [I] | POLICE ADMINISTRATION Hermin Sabotic | I June 14 | Decree amended as regards enabling of police representatives to represent the EU interests in third countries [28] (3) 30 June 2014 [I] Pursuant to Article 121 paragraph 5 of the Law on Internal Affairs, at the session held on 26 June 2014, the Government of Montenegro passed the DECREE AMENDING THE DECREE ON CONDITIONS AND METHOD OF SELECTION OF POLICE REPRESENTATIVE WHO ARE TRANSFERRED TO WORK ABROAD. | Number of information exchanged with the liaison officer for the needs of other EU Member States, number of police operations initiated by the liaison officer, for the needs of other EU Member States[29] (1) 31 December 2013 [NI] This activity will be possible only after the accession of Montenegro to the EU (3) 30 June 2014 [?] |
| 6.1.15. * | 1. Expansion of Interpol’s services – establishment of the FIND system and its integration into the existing police databases [32] Input of all lost/stolen/invalid travel documents into Interpol's SLTD database Develop procedures to use the FIND system Establishment of a system for checking passengers on cruise ships and ships used for pleasure voyages (Interpol's batch searches) Expansion of the FIND system to the private sector. (1) 31 December 2013 [I] (3) 30 June 2014 [I] | POLICE ADMINISTRATION Natasa Starovlah Knezevic | I September 2013; 2013, continuously [33]; September 2013; I quarter of 2015; March 2014; | 1. FIND system implemented (1) 31 December 2013 [I] FIND system was put into operation on 1 December 2013 at all border crossing points in Montenegro (3) 30 June 2014 [I] FIND system was put into operation on 1 December 2013 at all border crossing points in Montenegro Equipment which lacked procured – put into operation (1) 31 December 2013 [?] (3) 30 June 2014 [?] The necessary computer programs developed (1) 31 December 2013 [I] Computer program of FIND system developed, and interconnected with application Border in order to check persons/documents/vehicles at BCPs. (3) 30 June 2014 [I] Computer program of FIND system developed, and interconnected with application Border in order to check persons/documents/vehicles at BCPs Automatic input of all invalid documents into Interpol’s SLTD database[34] (1) 31 December 2013 [I] All lost/stolen/invalid documents are timely entered into Interpol’s SLTD database. (3) 30 June 2014 [I] All lost/stolen/invalid documents are timely entered into Interpol’s SLTD database. Procedure for the use of the FIND system drafted (1) 31 December 2013 [I] Procedure for the use of Interpol’s databases through FIND system was drafted. (3) 30 June 2014 [I] Procedures for the use of FIND system have been developed. System for checking passengers on cruise ships and ships established; number of checks carried out at border crossing points (1) 31 December 2013 [?] (3) 30 June 2014 [?] FIND system connected to the private sector for the purpose of checking documents and vehicles. (1) 31 December 2013 [I] Within the framework of Interpol project I-Checkit, Montenegro as a pilot country expanded FIND system to private sector (in the first phase to the tourist companies – hotels). FIND expands in accordance with agreements signed with representatives of hotel facilities on a voluntary basis i.e. if private companies recognize interest in the partnership with Interpol. (3) 30 June 2014 [?] | Number of persons/vehicles/documents entered into Interpol's database, number of checks of persons/vehicles/documents, number of hits, number of wanted persons located, number of searched vehicles located (1) 31 December 2013 [I] Within the period 1-18 December statistical data are: 1. Total number of checks through FIND: a. Persons 214.774 b. 214.774 c. Vehicles 81.345 2. Number of persons entered into FIND – 41 3. Number of persons found by means of FIND - 1 4. Number of vehicles entered into Interpol data base - 4 5. Number of hits - 1 vehicle per FIND 6. Number of hits for documents per FIND - 2 (3) 30 June 2014 [I] The following statistical data are provided for the period 1 January-1 May 2014: 1. Total number of checks through FIND: a. Persons – 2,940.785 b. Vehicles – 1,062.889 c. Travel documents– 3,040.138 2. Number of persons entered into FIND – 69 3. Number of persons found by means of FIND - 17 4. Number of vehicles entered into Interpol database - 41 5. Number of hits - 41 vehicles per FIND 6. Number of hits for documents per FIND - 18 |
| 6.1.17. | 1. Establish the duty 24/7 service needed for international police cooperation Fill in positions laid down by the job classification act [36] Draft instructions for the work of the 24/7 duty service as a part of the Manual for International Police Cooperation.[37] (1) 31 December 2013 [PI] (2) 31 March 2014 [PI] (3) 30 June 2014 [I] | POLICE ADMINISTRATION Milan Tomic | I 1. December 2013; December 2013 | 1. Positions laid down by the job classification act filled in; work of international police cooperation organized according to the 24/7 principle (1) 31 December 2013 [PI] Implementation of activity is ongoing. Four out of five vacancies are occupied. The process for occupying 1 remaining vacancy is also ongoing. After this, duty 24/7 service will be established. (2) 31 March 2014 [PI] Implementation of activity is ongoing. Four out of five vacancies are occupied. The process for occupying 1 remaining vacancy is also ongoing. After this, duty 24/7 service will be established. (3) 30 June 2014 [I] Instructions for the work of 24/7 service drafted (1) 31 December 2013 [PI] Activities related to drafting Manual for international police cooperation are ongoing. Draft Manual has been made. (2) 31 March 2014 [PI] Activities related to drafting Manual for international police cooperation are ongoing. Draft Manual has been made. (3) 30 June 2014 [I] The instruction for the work of duty 24/7 service has been developed as a part of the Manual for international police cooperation. | Number of officers engaged in the work of the duty service for international police cooperation, number of information exchanged outside standard working hours, number of cases acted upon outside standard working hours (1) 31 December 2013 [I] Number of duty officers – for now, 3 operators and one inspector on standby duty Number of processed messages in relation to cases outside standard working hours (period 01 July-18 December) – 3730 (2) 31 March 2014 [?] (3) 30 June 2014 [?] |
| 6.1.18. | Training of officers in the field of international police cooperation in connection with the following: Use of Interpol's databases Use of Europol's databases Introduction of new systems of data exchange (I-Link, Siena, SIS, Prüm) Standards for the protection of personal data and confidentiality of data Work with the Europol's AWFs Access to the Schengen Information System Implementation of target pursuit and extradition of persons Foreign languages (1) 31 December 2013 [IC] In cooperation with the Interpol, in November 2013, training in using Interpol's databases was held at the Police Academy, within the I-checkit project. As part of the Department of International Police Cooperation, officials of the Department, who have been certified as Europol trainers for Siena, ending with December 2013, trained five officers of the Department to use Europol's Sienna applications. Within the Department, from existing resources, trainings for foreign (English) language started. (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | POLICE ACADEMY | IC January 2014, continuously [38] | Training plan defined (2) 31.III 2014 [PI] Activities for developing a training plan for needs of staff of the Department of International Police Cooperation are ongoing. Greater part of the training will be implemented through Twinning for making the Schengen Action Plan and through TAIEX, when visit of Slovenian experts in the period 2-6 June 2014 is planned. Furthermore, arrangement with the Police Academy regarding training plan that is related to standards for the protection of personal data and confidentiality of data is ongoing. Local experts will be engaged for this type of trainings. Communication with the General Secretariat of INTERPOL about trainings related to usage of INTERPOL's databases is ongoing. Training related to the implementation of target pursuit and extradition of persons will be implemented in cooperation with colleagues from Germany, after their visit to the Department of International Police Cooperation. (3) 30 June 2014 [IC] The mentioned measure is implemented continuously. Two officers of the Department for International Police Cooperation attended the training on the topic ``International police cooperation and personal data protection“, which was held in Zagreb. Three officers of the Department are participating in the study visit to EUROPOL, within which they will become familiar with the work and the functioning of EUROPOL, as well as the use of EUROPOL databases and the work with the analytical working files. The visit to the Federal Republic of Germany will be carried out at the beginning of July with a view to training on the topic Conducting targeted search and extradition of persons. Training of officers in the segment of introduction of new systems for data exchange (I-link, Siena, SIS, Prüm) and access to the Schengen Information System will be conducted under the Twinning project for Schengen. Training related to the use of INTERPOL databases will be conducted in agreement with the Secretariat General of INTERPOL. All officers of the Department attended the training on the topic Enforcement of the Law on Data Secrecy, which was held in the Human Resources Administration and organized by the Directorate for Data Secrecy. Organized trainings at national and international level (2) 31 March 2014 [?] (3) 30 June 2014 [IC] The mentioned measure is implemented continuously. Two officers of the Department for International Police Cooperation attended the training on the topic ``International police cooperation and personal data protection“, which was held in Zagreb. Three officers of the Department are participating in the study visit to EUROPOL, within which they will become familiar with the work and the functioning of EUROPOL, as well as the use of EUROPOL databases and the work with the analytical working files. The visit to the Federal Republic of Germany will be carried out at the beginning of July with a view to training on the topic Conducting targeted search and extradition of persons. Training of officers in the segment of introduction of new systems for data exchange (I-link, Siena, SIS, Prüm) and access to the Schengen Information System will be conducted under the Twinning project for Schengen. Training related to the use of INTERPOL databases will be conducted in agreement with the Secretariat General of INTERPOL. All officers of the Department attended the training on the topic Enforcement of the Law on Data Secrecy, which was held in the Human Resources Administration and organized by the Directorate for Data Secrecy. Police Academy: Practical actions in the area of international police cooperation INTERPOL/EUROPOL 9 June - 12 officers of the Border Police Department 10 June - 12 officers of the Border Police Department 11 June - 10 officers of the Criminal Investigation Police Department 12 June - 6 officers of the Criminal Investigation Police Department Training for foreign languages which has been planned for May was postponed for September 2014 due to the absence of the lecturer. Activity of CEPOL webinar : ``Financial crime” (15/2014) – 20 May “Sexual exploitation of children through Internet: international cooperation in online investigations” (11/2014) 2 June “Europol” (26/2014) – 25 April Conducted classical trainings and e-learning (2) 31 March 2014 [?] (3) 30 June 2014 [?] Number of implemented trainings in relation to number of planned trainings (2) 31 March 2014 [?] (3) 30 June 2014 [?] Number of trained employees in relation to total number of employees specified for training – periodical setting of employees (2) 31 March 2014 [?] (3) 30 June 2014 [?] | Number of exchanged information through Interpol, Europol and the Schengen, number of data entered into Interpol, Europol and the Schengen database, number of hits in databases of Interpol, Europol and the Schengen, number of persons deprived of their liberty on the basis of conducted target (2) 31 March 2014 [?] (3) 30 June 2014 [?] |

Recommendation 3 from the Screening Report– area “Police cooperation“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.1.19. * | 1. Establishment of the National Contact Point for football games Training of officers of the NCP for international cooperation (training for foreign languages) Information of the Council of the EU on establishment of the NCP (3) 30 June 2014 [IC] | POLICE ADMINISTRATION | IC December 2014; January 2014 – II half of 2019,; Following the accession to the EU; | 1. National Contact Point established [39] (3) 30 June 2014 [I] The National Contact Point has been designated Number of trainings, number of officers in the NCP who speak foreign language, in comparison with the total number of officers in the NCP (3) 30 June 2014 [PI] Police Academy: Activity of CEPOL- webinar: ``Pan-European Safety” (27/2014) – 22 May Trainings have been agreed with the Police Academy and will be conducted from September 2014. Information on established NCP submitted to the Secretariat General of the Council of the EU (3) 30 June 2014 [?] | Number of information exchanged between the National Contact Point and the NCPs of other countries of the EU; number of organized joint activities related to football games (3) 30 June 2014 [?] |
| 6.1.20. * | 1. Establishment of the National Contact Point (NCP) for protection of public figures Training of officers of the NCP for international cooperation (training for foreign languages) Information of the Council of the EU on establishment of the NCP (3) 30 June 2014 [IC] | POLICE ADMINISTRATION | IC 1. December 2014; January 2014 – second half of 2019, ; December 2014 | 1. National Contact Point established [40] (3) 30 June 2014 [I] The National Contact Point has been designated Number of trainings, number of officers in the NCP who speak foreign language, in comparison with the total number of officers in the NCP (3) 30 June 2014 [PI] Trainings have been agreed with the Police Academy and will be conducted from September 2014. Information on established NCP submitted to the Secretariat General of the Council of the EU (3) 30 June 2014 [?] | Number of information exchanged between the National Contact Point and the NCPs of other countries of the EU; number of organized joint activities related to protection of guarded persons (3) 30 June 2014 [?] |

Application of Prüm Decision

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.1.25. | 1. Establishment of a working group for the implementation of the Prüm Decision, hiring experts, with the aim of: [44] Analysis of the situation regarding the existence of a database of DNA, fingerprints and vehicles and possibility to exchange these data within the Prüm: Existence of the AFIS system Existence of the CODIS system Analysis of the information system in terms of adaptability to meet the obligations of Prüm Decision Implementation of the recommendations of the analysis: Procurement of equipment, AFIS, CODIS Conducting trainings for the use of CODIS and AFIS system development of application solutions, establishment of secure communication links, defining the procedures Defining points of contact for the exchange of DNA and fingerprints data Conducting training for national contact point Defining the point of contact for the exchange of additional information after HIT in the databases of DNA or fingerprints abroad Defining the point of contact for the exchange of information on the owners of motor vehicles Conducting training for national contact point Defining the points of contact for cooperation within the Prüm Decision by other articles of the Decision of Council Conducting training for national contact point Drafting a legal act (Decree) for the implementation of decisions of the Council of the EU Making the Statement on compliance with commitments from Article 36(2) of the Council Decision 2008/615/JHA [45] Sending the Statement of registry entries on DNA, fingerprints and owners of motor vehicles [46]Sending the statement of national points of contact - sending through the General Secretariat of the Council[47] Evaluation of the implementation of the recommendations Implementation of the recommendations of the Evaluation report (2) 31 March 2014 [IC] (3) 30 June 2014 [IC] | POLICE ADMINISTRATION Dejan Djurovic | IC March 2014; March 2014; December 2014; first quarter of 2015; first quarter of 2015; first quarter of 2015; first quarter of 2015; first half of 2017; After accession to the EU; After accession to the EU; After accession to the EU; second quarter of 2015, continuously (quarterly); third quarter of 2015; | 1. Working Group established; EU expert hired: (2) 31 March 2014 [PI] Working Group for the implementation of these measures was established. The Working Group held its first meeting and made mini analysis, i.e. each member of the WG prepared an analysis of the situation from his/her field of work in relation to the Prüm Decision, with a particular focus on legislation, bylaws, organizational structure, human resources, trainings required for the use of CODIS, etc., with the aim to facilitate the functioning and exchange of information of Forensic Centre with other organizational units of the Police Administration and Ministry of Interior, and in the future with other law enforcement agencies, both locally and abroad. Mini analysis will be submitted to experts from Croatia and Slovenia who will, through TAIEX, visit the Police Administration in the period 7-11 April 2014. Based on our proposal and mini analysis, experts will make an evaluation and introduce proposal of measures for the implementation of Prüm Decision. (3) 30 June 2014 [I] The Working Group for implementation of Prüm Decision was established by the decision of the Minister of Interior 01/3 number 050/14-2879/3, of 23 January 2014. Experts from the Republic of Croatia and Slovenia were hired for development of the Prüm analysis, which has been completed. Analysis of situation completed - report with recommendations made (2) 31 March 2014 [?] (3) 30 June 2014 [I] The analysis of situation was developed on the grounds of recommendations provided by hired experts from Slovenia and Croatia. Three meetings of the Working Group were held, and the Report with conclusions was developed in the final meeting. The analysis of situation related to the existence of database for DNA, fingerprints and motor vehicles as well as the possibility of exchange of these data within Prum – the existence of AFIS system and CODIS system, as well as the analysis of information system as regards adaptability for fulfilment of obligations from Prüm decision have been developed; experts from Slovenia and Croatia provided assistance in development of the analysis. Analysis of situation completed - report with recommendations made (2) 31 March 2014 [?] (3) 30 June 2014 [I] The analysis of situation was developed on the grounds of recommendations provided by hired experts from Slovenia and Croatia. Three meetings of the Working Group were held, and the Report with conclusions was developed in the final meeting. The analysis of situation related to the existence of database for DNA, fingerprints and motor vehicles as well as the possibility of exchange of these data within Prum – the existence of AFIS system and CODIS system, as well as the analysis of information system as regards adaptability for fulfilment of obligations from Prüm decision have been developed; experts from Slovenia and Croatia provided assistance in development of the analysis. Implemented recommendations from the analysis (the CODIS was procured and put into operation; number of trainings to use the CODIS system; established an effective AFIS system; number of trainings to use AFIS system) (2) 31 March 2014 [?] (3) 30 June 2014 [PI] CODIS software was procured through donation of the FBI and trainings for its use were conducted, whereas obtaining of the model for procurement of AFIS is underway. Defined contact points for DNA and fingerprints (2) 31 March 2014 [?] (3) 30 June 2014 [?] Number of conducted trainings for National Contact Point (2) 31 March 2014 [?] (3) 30 June 2014 [?] Defined contact points for the exchange of additional information on hits for the DNA and fingerprints (2) 31 March 2014 [?] (3) 30 June 2014 [?] Defined contact point for the exchange of information on the owners of motor vehicles, number of conducted trainings for national contact point (2) 31 March 2014 [?] (3) 30 June 2014 [?] Defined contact point for information exchange related to other articles of the Prüm Decision, number of conducted trainings for national contact point (2) 31 March 2014 [?] (3) 30 June 2014 [?] Drafted legal act (Decree) for the implementation of the Decision of the Council of the EU (2) 31 March 2014 [?] (3) 30 June 2014 [?] Submitted statements on the fulfilment of obligations and database registration, and national contact points (2) 31 March 2014 [?] (3) 30 June 2014 [?] Statement on established registry of DNA, fingerprints and owners of motor vehicles, sent to the Competent Authority of the EU (2) 31 March 2014 [?] (3) 30 June 2014 [?] Statement of established contact points sent to the General Secretariat of the Council of the EU (2) 31 March 2014 [?] (3) 30 June 2014 [?] Performed periodic evaluations of fulfilling the obligations of the recommendations - making additional recommendations (2) 31 March 2014 [?] (3) 30 June 2014 [?] Recommendations from the evaluation reports completed - activities by additional recommendations carried out (2) 31 March 2014 [?] (3) 30 June 2014 [?] | Number of checks of databases of DNA and DKT (through AFIS and CODIS), number of hits, number of persons whose identity was determined, number of exchanged additional information after a positive matches in databases of DNA and DKT, number of persons processed on the basis of identity determining (2) 31 March 2014 [?] (3) 30 June 2014 [?] |

Obligations assumed at bilateral screening

| No. | Measure / Activity | Competent body | Deadline Status | Indicator of result | Indicator of impact |
| --- | --- | --- | --- | --- | --- |
| 6.1.29. * | 1. Development of „Case Management“ application (Application for case management, for overall international operative police cooperation) Binding of application in a single criminal intelligence system [57] Defining of the form of request within international police cooperation – integration in Case management application Analysis, drafting of the plan and connecting all police units through single electronic secure network (INTRANET) for the purpose of enabling exchange of data up to the level “Confidential”[58] Training of employees who will work on the Case Management application (3) 30/06/2014 [PI] | Police Administration Natasa Starovlah Knezevic | PI 1. July 2014; first quarter of 2015; December 2014; first quarter of 2015; March 2014 | 1. Developed application for case implementation management (Case Management application)[59] (3) 30/06/2014 [I] Developed Case Management application and it is up and running. Application bound to the criminal intelligence system for the purpose of storing data. (3) 30/06/2014 [NI] Note: Activities on binding application to the criminal intelligence system are ongoing. The binding will be possible upon establishment of Intranet Form of request defined[60] (3) 30/06/2014 [I] Integration into the Case Management application was carried out – forms of request within international police cooperation were defined. Established Intranet – exchange of information at the level of the Ministry of Interior via electronic secure gateway (3) 30/06/2014 [PI] Analysis of INTRANET was conducted. Plan of trainings created. Number of organized trainings, number of employees who underwent training (3) 30/06/2014 [I] Organized trainings for employees who work on the Case Management application. | Number of cases entered into the Case Management application, number of entered information, number of information/cases that were transferred from the application to the criminal intelligence system (Infostream), number of information exchanged via INTRANET, number of queries in available bases (3) 30/06/2014 [PI] Number of entered/exchanged information for the period January-June 2014 – 14,654 Number of cases entered into the Case Management application for the period January – June 2014 – 4,649 |

### 6.2.	FIGHT AGAINST ORGANISED CRIME                    	MINISTRY OF INTERIOR	 - Sasa Milic

Recommendation 1 from the Screening Report– area “Fight against organized crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.2. * | Make report on necessity to amend the Criminal Procedure Code, especially in the part referring to: - Allocation of ex officio defence attorney according to the order from the list of Bar Chamber; - more precise determination of legally invalid evidence, in terms of recalling certain articles of CPC; - procedure of implementing decision on temporary seizure, as well as the right of third persons acting in good faith in relation to temporarily seized property; - provisions which regulate measures of secret surveillance regarding: subjects which order measures of secret surveillance, scope of measures of secret surveillance, criminal offence for which measures of secret surveillance can be applied, persons upon whom measures of secret surveillance can be applied and duration of those measures; - provisions which regulate rejection of criminal charge and control of rejection; - provisions which regulate authorisations and actions of police in preliminary investigation; and it will be especially reconsidered prescribing possibility for police to hear a suspect upon the approval of the Public Prosecutor without the consent of the suspect, along with deadlines for police for depriving persons of freedom, as well as need to make decisions by police; - deadline for the Public Prosecutor to make decision on holding a person, as well as to prescribe deadline for lodging a complaint against decision on holding; to especially reconsider necessity to amend the holding period for certain criminal offences (organised crime and corruption); - provisions on offering evidence in investigation with a view to prescribing obligation for the Public Prosecutor to make decision against which complaint can be lodged; - Provisions which regulate control of indictment with a view to functional competence for indictment approval. Note: the same measure is defined by the Action Plan for negotiating chapter 23 in terms of Repressive actions against corruption (RECOMMENDATION 2.2.2, measure 2.2.2.1) (1) 31 December 2013 [I] | MINISTRY OF JUSTICE Duska Velimirovic | I June 2013 | Report made on scope of necessary amendments to CPC and decision made on period when concrete amendments to CPC shall be carried out. (1) 31 December 2013 [I] The Government of Montenegro adopted Report on necessity to amend the Criminal Procedure Code on 27 June 2013. |  |

Recommendation 2 from the Screening Report – area “Fight against organised crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.5. * | Make a comprehensive analysis of the organisational structure, capacities and competences of state authorities and administration bodies in the fight against organised crime and corruption, that will include: overview of legislative framework for fight against corruption and organised crime (Criminal Code, Criminal Procedure Code, Law on Internal Affairs, Customs Law, etc); organisational structure and functional content of the public prosecution office, police, Customs Administration, Tax Administration, etc.; a special section on seizure of material gain , with particular emphasis put on practical issues when identifying property for extended seizure, exchange of information and competences of the Public Property Administration in respect of management and redemption of the temporarily seized property; a special section on the structure and competences of the special investigative team and its relations towards other bodies; existing relevant databases for the efficient implementation of the CPC and identification of technical barriers in terms of access to databases of the Tax Administration, Customs Administration, Police Administration, Ministry of Interior, Public Property Administration, Central Depositary Agency, Harbour Master’s Office, Securities Commission, Central Register of Commercial Entities, and reassessment of the role of the current special investigative team; comparative model of Croatia and Slovenia; and proposal of conclusions for overcoming existing legislative and institutional limitations Note: the same measure is provided for in Action Plan for Chapter 23, Repressive Actions, measure 2.2.1.1 (1) 31 December 2013 [I] | MINISTRY OF INTERIOR Milos Vukcevic | I October 2013 | Analysis made with recommendations for amending legislative and institutional framework for fight against corruption in accordance with the Government’s Work Programme - priority activities point 56 (1) 31 December 2013 [I] At the session held on 14 November 2013, the Government adopted the Analysis of the organisational structure, capacities and competences of state authorities and administration bodies in the fight against organised crime and corruption, with recommendations for improvement of legislative and institutional framework. |  |
| 6.2.6. | Adopt a plan of implementation of conclusions from the previous analysis with concrete measures that need to be implemented, competent authorities and deadlines for implementation of measures, especially: - laws that need to be amended, and particularly the Criminal Code, Criminal Procedure Code, Law on Internal Affairs, Customs Law, etc.; - changes that need to be made in organisational structure; - improvement of the procedure for seizure of material gain and functioning of the Public Property Administration; - define the future role of the investigative team; - establish unique database and enable exchange of information between relevant authorities; - adopt the best solutions from the comparative experience. Note: the same measure is provided for in Action Plan for Chapter 23, part 2.2. Repressive Actions, measure 2.2.1.2 (1) 31 December 2013 [NI] (2) 31 March 2014 [I] (3) 30/06/2014 [I] | MINISTRY OF INTERIOR Milos Vukcevic | I December 2013 | Plan of implementation of conclusions from the analysis adopted (1) 31 December 2013 [NI] Note: Plan of implementation of conclusions is expected to be drafted in January 2014. (2) 31 March 2014 [I] At the session held on 13 February 2014, the Government of Montenegro adopted a Plan of implementation of the conclusions of the Analysis of organizational structure, capacity and authorizations of state authorities and administration bodies in combating organized crime and corruption, with concrete measures to be implemented, the competent authorities and deadlines. (3) 30/06/2014 [I] At the session held on 13 February 2014, the Government of Montenegro adopted a Plan of implementation of the conclusions of the Analysis of organizational structure, capacity and authorizations of state authorities and administration bodies in the fight against organized crime and corruption, with concrete measures to be implemented, the competent authorities and deadlines. |  |
| 6.2.9. * | Establish special information system within the Department for Suppression of Corruption, Organised Crime, Terrorism and War Crimes which will be used for establishment of database and secure communication channel with the court, police and other authorities in charge of law enforcement, and which will provide the access for the Public Prosecutor`s Office and the special investigating team to databases required for efficient conducting of financial investigations, as well as electronic exchange of data and information. Note: The same measure is foreseen in Chapter 23, part 2.2 Repressive activities against corruption (3) 30/06/2014 [NI] The Working Group which was formed by the Vice-President of the Government for political system, internal and foreign policy, in line with the Analysis of the organizational structure, capacities and authorities of the state bodies and administration bodies in combating organized crime and corruption, prepared a detailed Analysis with the proposal for the solution for formation of the information system. Namely, the Working Group was divided into two sub-groups. The task of the first sub-group was to prepare the project of reconstruction of SKS in the building of the Supreme Public Prosecutor's Office, as well as to further improve the Lan network. The task of the second group was to form an internal BUS application for the needs of secure communication with other state bodies | SUPREME PUBLIC PROSECUTOR’S OFFICE Djurdjina Ivanovic | NI June 2014; September 2014 | Established special information system and secure channel for exchange of information (3) 30/06/2014 [?] Databases linked between the prosecution and databases of the Ministry of Interior, Tax Administration, Police Administration, Central Register of Business Entities, Harbourmaster's Offices, Customs Administration, Central Depository Agency, Commission (3) 30/06/2014 [?] Add the Property Administration, i.e. future authority which will be in charge of return of seized property (3) 30/06/2014 [?] | Established better and more efficient inter-institutional cooperation (3) 30/06/2014 [?] -Report on the work of the Public Prosecutor's Office for fight against organized crime, corruption, terrorism and war crimes (3) 30/06/2014 [?] -Report of the European Commission (3) 30/06/2014 [?] -Report of MONEYVAL (3) 30/06/2014 [?] |
| 6.2.10. | Expand premises of the Department for suppression of corruption, organised crime, terrorism and war crimes Note: The same measure is provided for in Chapter 23, section 2.2 Repressive Action against Corruption (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] (3) 30/06/2014 [NI] In conversations with the Vice-President of the Government for political system, internal and foreign policy and the Minister of Justice, it was agreed to consider a possibility for expanding the premises of the Department for Suppression of Organized Crime, Corruption, Terrorism and War Crimes through eviction of the Misdemeanour Council from their working area which is located in the same building as the premises of the Department. | SUPREME PUBLIC PROSECUTOR’S OFFICE Radmila Cukovic | NI December 2013 | Expanded spatial capacities (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] Activities aimed at finding suitable premises are ongoing, which are related to the formation of the Special Prosecutor's Office as a separate prosecution. (3) 30/06/2014 [?] | Conditions provided for better work of the Prosecution Office (1) 31 December 2013 [NI] Note: On 17 December 2012, the Supreme Public Prosecutor’s Office sent to the Public Property Administration request for providing necessary office premises for the needs of the Department for suppression of corruption, organised crime, terrorism and war crimes. It requested to have been provided with appropriate premises in order to adequately solve the issue of expanding premises in the Department. The negotiations between the Ministry of Finance and the Capital Podgorica for providing adequate premises are ongoing. (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.11. | Strengthen human resources capacities of the Department for suppression of corruption, organised crime, terrorism and war crimes by employing two expert assistants and two IT experts. Note: The same measure is provided for in Chapter 23, section 2.2 Repressive Action against Corruption (1) 31 December 2013 [PI] (2) 31 March 2014 [PI] (3) 30/06/2014 [PI] | SUPREME PUBLIC PROSECUTOR’S OFFICE Radmila Cukovic | PI September 2013-March 2014 | Strengthened human resources capacities by employing two expert assistants and two IT experts (1) 31 December 2013 [PI] The Department for fight against corruption, organized crime, terrorism and war crimes employed 1 professional economist, on 22 October 2013. Note: In January 2014, it is planned to announce vacancy position for the purpose of employment of two IT experts. (2) 31 March 2014 [PI] The Department for fight against corruption, organized crime, terrorism and war crimes employed 2 professional economists. Internal announcement for employment of two IT experts was launched within the state authority for which no one applied. It is planned to launch internal announcement within state authorities. (3) 30/06/2014 [PI] The Supreme Public Prosecutor's Office sent a request to the Human Resources Administration for filling the position of employee in the IT sector. |  |
| 6.2.12. | Strengthen the administrative capacity of the Special Prosecutor's Office through the formation of a multidisciplinary team of expert assistants and accountants, experts in the field of money laundering, banking experts, experts in international banking transactions, tax experts Note: The same measures is provided for in Chapter 23, section 2.2 Repressive Actions against Corruption (2) 31 March 2014 [NI] Implementation of the measures depends on the adoption of the Law on special prosecutor's office and the provision of premises for the Special Prosecutor's Office. (3) 30/06/2014 [NI] On 19 February 2014, through signing of an Agreement between representatives of the Supreme Public Prosecutor's Office, Police Administration, Tax Administration, Administration for Prevention of Money Laundering and Terrorism Financing and the Customs Administration, a Joint Investigation Team was formed in the Department for Suppression of Corruption, Organized Crime, Terrorism and War Crimes. The work of the Joint Investigation Team is coordinated by the special prosecutor or a deputy that he authorises. The Law on Special Public Prosecutor's Office, which is planned to be adopted in the fourth quarter of this year, will reconsider functioning of this team, which now functions as a multidisciplinary team, i.e. its composition and manner of functioning as a permanent or ad hoc team will be reconsidered depending on concrete cases and the degree of their complexity. | SUPREME PUBLIC PROSECUTOR’S OFFICE Radmila Cukovic | NI March 2014 | Multidisciplinary team established (2) 31 March 2014 [?] (3) 30/06/2014 [NI] |  |
| 6.2.13. | Analysis of material and technical needs of the Department for Fight against Organized Crime and Corruption, Department for the Prevention of Crime and Department for Combating Economic Crime (2) 31 March 2014 [I] (3) 30/06/2014 [I] | POLICE ADMINISTRATION Sasa Milic | I March 2014 | Analysis prepared (2) 31 March 2014 [I] During February 2014, analysis of material and technical needs of the Department for Fight against Organized Crime and Corruption, Department for the Prevention of Crime and Department for Combating Economic Crime was prepared. It was drafted on the basis of current equipment condition of these units. (3) 30/06/2014 [I] During February 2014, analysis of material and technical needs of the Department for Fight against Organized Crime and Corruption, Department for the Prevention of Crime and Department for Combating Economic Crime was prepared. It was drafted on the basis of current equipment condition of these units. | Initiated planned procurements (2) 31 March 2014 [?] (3) 30/06/2014 [NI] Note: Process for launching planned procurement by the analysis was started. |
| 6.2.17. | Amendments to the Rulebook on Internal Organization and Job Classification of the Ministry of Interior, with the objectives of: reorganization, determination of responsibilities and centralization of lines of work of economic crime defining the jurisdiction of the Department for Combating Economic Crime and Department for Fight against Organized Crime and Corruption in the implementation of financial investigations [65] (2) 31 March 2014 [PI] (3) 30/06/2014 [PI] | POLICE ADMINISTRATION Milos Vukcevic | PI February 2014; December 2014 | Decision on the establishment of a working group whose member will be a representative of line of economic crime (2) 31 March 2014 [I] By the Decision of Minister, the Subgroup (special working group) was established within the Working Group for Amendments to the Rulebook on Internal Organization and Job Classification that is primarily responsible for the implementation of these measures. Member of the group is also Head of Department for Economic Crime. Minister and Director of the Police Administration gave their consent for conducting the centralization of lines of work of the economic crime. The Working Group held the meeting and established guidelines for future work. (3) 30/06/2014 [I] Adopted Amendments to the Rulebook on Internal Organization and Job Classification of the Ministry of the Interior (2) 31 March 2014 [?] (3) 30/06/2014 [PI] Several meetings of the working sub-group were held. Proposal of the Rulebook was drafted. | Number of initiated investigations (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.18. | According to the recommendations of experts, through changes in organization and job classification within the Crime Police Sector, specialized organizational units shall be formed in the following areas: financial investigations; high-tech crime; trafficking in human beings and terrorism.[66] (2) 31 March 2014 [PI] (3) 30/06/2014 [PI] | POLICE ADMINISTRATION Milos Vukcevic | PI February 2014; April 2014; May 2014; December 2014; March 2015 | Working Group established (2) 31 March 2014 [I] By the Decision of Minister, the Subgroup (special working group) was established within the Working group for Amendments to Rulebook on Internal Organization and Job Classification that is primarily responsible for the implementation of these measures. The Working Group held the meeting and established guidelines for future work. (3) 30/06/2014 [I] Estimation of the required number of employees made (2) 31 March 2014 [?] (3) 30/06/2014 [I] Assessment of the required number of employees for all 4 groups made. Group for suppression of terrorism - 3 employees Group for suppression of trafficking in human beings - 3 employees; Group for suppression of high-tech crime - 3 employees; Group for financial investigations - 5 employees; Total for 4 groups: 14 employees; Proposal of Rulebook drafted (2) 31 March 2014 [?] (3) 30/06/2014 [I] Draft rulebook for all 4 groups drafted. Adopted Amendments to the Rulebook on Internal Organization and Job Classification (2) 31 March 2014 [?] (3) 30/06/2014 [?] Filling Vacant Positions (2) 31 March 2014 [?] (3) 30/06/2014 [?] | Number of initiated investigations (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.20. | Strengthening the staff capacities and organizing educational programs home and abroad (courses, trainings, seminars, study visits) within the scope of the lines of work of economic crime with a special focus on corruption, money laundering, financial investigations, counterfeiting of money (euro), misuse and falsification of credit cards, computer data security, copyright and intellectual property[68] (2) 31 March 2014 [IC] (3) 30/06/2014 [IC] | POLICE ADMINISTRATION Dragan Radonjic | IC January 2014 - December 2018 | Number of completed trainings on annual basis (2) 31 March 2014 [IC] In the first quarter of 2014, employees of the line for combating economic crime attended: - training on Prevention of Money Laundering in Montenegro and best practices around the world organized by MANS and supported by the EU, which was attended by two employees of the Department for Combating Economic Crimes; - Course on financial investigations organized by the British Embassy, which was attended by five employees of the Department for Combating Economic Crimes; - Training on Fight against corruption in the police force organized by the French Embassy in Podgorica, which was attended by five employees of the Department for Combating Economic Crimes; - National Strategy for Combating Money Laundering and Terrorism Financing organized by TAIEX, OSCE and Administration for Prevention Money laundering and Terrorism Financing, which was attended by one employee of the Department for Combating Economic Crimes. The British Embassy, ICITAP i.e. U.S. Embassy, Police Administration and Police Academy organized a course on "Financial investigations" in the period from 10 to 14 March 2014 at the Police Academy in Danilovgrad. The aim of the course was to point out the importance of international financial investigations in the field of fight against organized crime to participants, with the aim of preventing and fighting crime and catching offenders. Course was attended by 18 participants-5 participants from the State Prosecutor's Office of Montenegro, 8 employees of the Police Administration who work on combating economic and organized crime, 1 participant from the Tax Administration and 4 participants from the State Prosecutor's Office of the Republic of Albania. Lecturers on the course were: Miroslav Milenovic, expert in forensic accounting and financial investigations from the Republic of Serbia; Tristram Hicks, expert in financial investigations from Great Britain; Rod Stokes, expert in financial investigations from Great Britain and Artur Zoto, expert in financial investigations from Great Britain. No training was held on other topics in period 1 January 2014 to 1 April 2014 at the Police Academy. Within the plan for 2014, a course on the topic of financial investigation is planned to be organized in December 2014. Also in 2014, three more trainings are planned to be held for border police officers (75 participants) who are trained by Frontex programme where they will learn about Financial investigations and corruption, 4 hours per each topic. (3) 30/06/2014 [IC] In the first half of 2014, employees of the line for combating economic crime attended: - training on Prevention of Money Laundering in Montenegro and best practices around the world organized by MANS and supported by the EU, which was attended by two employees of the Department for Combating Economic Crimes; - Course on financial investigations organized by the British Embassy, which was attended by five employees of the Department for Combating Economic Crimes; - Training on Fight against corruption in the police force organized by the French Embassy in Podgorica, which was attended by five employees of the Department for Combating Economic Crimes; - National Strategy for Combating Money Laundering and Terrorism Financing organized by TAIEX, OSCE and Administration for Prevention Money laundering and Terrorism Financing, which was attended by one employee of the Department for Combating Economic Crimes. -’’XI South-East Conference’’-fight against counterfeiting of Euro organized by OLAF and the Central Bank of Montenegro which was attended by 2 employees of the Department for Combating Economic Crimes. To summarise, in the reporting period, employees of the Department for Combating Economic Crimes took part in 5 trainings which were attended by 15 employees. Police Academy: Activity of CEPOL: ”Organized crime links” (18/2014) Representatives of the Police Academy attended the seminar:”High-tech crime – experience of the USA and countries of the region“, held on 10-11 04 in Budva Number of trained employees on an annual basis in relation to total number of employees dealing with economic crime (2) 31/03/2014 [IC] In the first quarter of 2014, employees of the line for combating economic crime attended: - training on Prevention of Money Laundering in Montenegro and best practices around the world organized by MANS and supported by the EU, which was attended by two employees of Department for Combating Economic Crimes; - Course on financial investigations organized by the British Embassy, which was attended by five employees of OZSPK; - Training on Fight against corruption in the police force organized by the French Embassy in Podgorica, which was attended by five employees of Department for Combating Economic Crimes; - National Strategy for Combating Money Laundering and Terrorism Financing organized by TAIEX, OSCE and the USPFNT CG, which was attended by one employee of Department for Combating Economic Crimes. The British Embassy, ICITAP i.e. U.S. Embassy, Police Administration and Police Academy organized a course on "Financial investigations" in the period from 10 to 14 March 2014 at the Police Academy in Danilovgrad. The aim of the course was to point out the importance of international financial investigations in the field of fight against organized crime to participants, with the aim of preventing and fighting crime and catching offenders. Course was attended by 18 participants-5 participants from the State Prosecutor's Office of Montenegro, 8 employees of the Police Administration who work on combating economic and organized crime, 1 participant from the Tax Administration and 4 participants from the State Prosecutor's Office of the Republic of Albania. Lecturers on the course were: Miroslav Milenovic, expert in forensic accounting and financial investigations from the Republic of Serbia; Tristram Hicks, expert in financial investigations from Great Britain; Rod Stokes, expert in financial investigations from Great Britain and Artur Zoto, expert in financial investigations from Great Britain. No training was held on other topics in period 1 January 2014 to 1 April 2014 at the Police Academy. Within the plan for 2014, a course on the topic of financial investigation is planned to be organized in December 2014. Also in 2014, three more trainings are planned to be held for border police officers (75 participants) who are trained by Frontex programme where they will learn about Financial investigations and corruption in duration of 4 school classes. (3) 30/06/2014 [IC] In the first half of 2014, employees of the line for combating economic crime attended: - training on Prevention of Money Laundering in Montenegro and best practices around the world organized by MANS and supported by the EU, which was attended by two employees of the Department for Combating Economic Crimes; - Course on financial investigations organized by the British Embassy, which was attended by five employees of the Department for Combating Economic Crimes; - Training on Fight against corruption in the police force organized by the French Embassy in Podgorica, which was attended by five employees of the Department for Combating Economic Crimes; - National Strategy for Combating Money Laundering and Terrorism Financing organized by TAIEX, OSCE and Administration for Prevention Money laundering and Terrorism Financing, which was attended by one employee of the Department for Combating Economic Crimes. -’’XI South-East Conference’’-fight against counterfeiting of Euro organized by OLAF and the Central Bank of Montenegro which was attended by 2 employees of the Department for Combating Economic Crimes. To summarise, in the reporting period, employees of the Department for Combating Economic Crimes took part in 5 trainings which were attended by 15 employees. | Number of initiated investigations (2) 31 March 2014 [?] (3) 30/06/2014 [?] Report on the results of work in this area (2) 31 March 2014 [?] (3) 30/06/2014 [?] |

Recommendation 3 from the Screening Report – area „Fight against organised crime“	 - Danijela Milicevic

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.21. | Analyse and amend Montenegrin legislation in accordance with recommendations of the Financial Action Task Force. (1) 31 December 2013 [PI] (2) 31 March 2014 [PI] (3) 30/06/2014 [PI] | ADMINISTRATION FOR PREVENTION OF MONEY LAUNDERING AND TERRORISM FINANCING Kristina Bacovic | PI December 2013 | Amendments to relevant laws and secondary legislation (Criminal Code, Law on Prevention of Money Laundering and Terrorism Financing) (1) 31 December 2013 [PI] Implementation is ongoing. The Working group drafted Proposal for the new Law on Prevention of Money Laundering and Terrorism Financing which is mainly harmonised with the recommendation of the FATF. Adoption of the Proposal for the Law on Prevention of Money Laundering and Terrorism Financing by the Government of Montenegro is expected until the end of 2013. Its adoption in the Parliament is expected in the first quarter of 2014. The Proposal for the Law is sent to the EC to provide its expert opinion on the level of harmonization of the Proposal for the Law with the appropriate international standards. In July 2013, the Parliament of Montenegro adopted the Law Amending the Criminal Code that entered into force on 21 August 2013. In addition, amendments were carried out in accordance with recommendations of Committee of Council of Europe – MONEYVAL regarding harmonisation with FATF recommendations. (2) 31 March 2014 [PI] In accordance with the recommendations of the FATF and the Draft of IV Directive of the EP and the Council on the prevention of the use of the financial system for the purpose of money laundering and terrorism financing, a working group was established for drafting the new Law on the Prevention of Money Laundering and Terrorism Financing. It consisted of representatives of the following institutions: Administration for Prevention of Money Laundering and Terrorism Financing, Ministry of Finance, Insurance Supervision Agency, Parliament of Montenegro, Tax Administration, Supreme Public Prosecutor’s Office, Ministry of Justice, Administration for Games of Chances, Police Administration, Securities Commission, Agency for Electronic Communications and Postal Services, Bar Association of Montenegro, Notary Chamber of Montenegro. The EC gave an opinion on the Draft of Law before it entered into the parliamentary procedure. At the session of the Government held on 27 February 2014, the Draft Law was discussed and few technical suggestions for modification were given. After that, the Draft law was adopted at the session of the Government held on 06 March 2014 and submitted to further parliamentary procedure for adoption. The Proposal of Law is expected to be adopted during the regular spring sitting of the Parliament. The new law includes numerous solutions from the FATF Recommendations, in accordance with the framework of Montenegrin legislation. (3) 30/06/2014 [PI] The Proposal of the new Law on Prevention of Money Laundering and Terrorism Financing is in the Parliamentary procedure and it is expected to be adopted by the end of 2014. Montenegrin legislation harmonised with the FATF recommendations (1) 31 December 2013 [PI] Implementation is ongoing. The Working group drafted Proposal for the new Law on Prevention of Money Laundering and Terrorism Financing which is mainly harmonised with the recommendation of the FATF. Adoption of the Proposal for the Law on Prevention of Money Laundering and Terrorism Financing by the Government of Montenegro is expected until the end of 2013. Its adoption in the Parliament is expected in the first quarter of 2014. The Proposal for the Law is sent to the EC to provide its expert opinion on the level of harmonization of the Proposal for the Law with the appropriate international standards. In July 2013, the Parliament of Montenegro adopted the Law Amending the Criminal Code that entered into force on 21 August 2013. In addition, amendments were carried out in accordance with recommendations of Committee of Council of Europe – MONEYVAL regarding harmonisation with FATF recommendations. (2) 31 March 2014 [PI] In accordance with the recommendations of the FATF and the Draft of IV Directive of the EP and the Council on the prevention of the use of the financial system for the purpose of money laundering and terrorist financing, a working group was established for drafting the new Law on the Prevention of Money Laundering and Terrorism Financing. It consisted of representatives of the following institutions: Administration for Prevention of Money Laundering and Terrorism Financing, Ministry of Finance, Insurance Supervision Agency, Parliament of Montenegro, Tax Administration, Supreme Public Prosecutor’s Office, Ministry of Justice, Administration for Games of Chances, Police Administration, Securities Commission, Agency for Electronic Communications and Postal Services, Bar Association of Montenegro, Notary Chamber of Montenegro. The EC gave an opinion on the Draft of law before it entered into the parliamentary procedure. At the session of the Government held on 27 February 2014, Draft law was discussed and few technical suggestions for modification were given. After that, Draft law was adopted at the session of the Government held on 06 March 2014 and submitted to further parliamentary procedure for adoption. The Proposal of Law is expected to be adopted during regular spring sitting of the Parliament. The new law includes numerous solutions from the FATF Recommendations, in accordance with the framework of Montenegrin legislation. (3) 30/06/2014 [PI] The Proposal of the new Law on Prevention of Money Laundering and Terrorism Financing is in the Parliamentary procedure and it is expected to be adopted by the end of 2014. | Legislative framework harmonised with the FATF recommendations provides a wider scope of application of relevant laws in regulated sector (1) 31 December 2013 [PI] In July 2013, the Parliament of Montenegro adopted the Law Amending the Criminal Code that entered into force on 21 August 2013. In addition, amendments were carried out in accordance with recommendations of the Committee of Council of Europe – MONEYVAL concerning harmonisation with FATF recommendations. (2) 31 March 2014 [PI] In accordance with the recommendations of the FATF and the Draft of IV Directive of the EP and the Council on the prevention of the use of the financial system for the purpose of money laundering and terrorism financing, a working group was established for drafting a new Law on the Prevention of Money Laundering and Terrorism Financing. It consisted of representatives of the following institutions: Administration for Prevention of Money Laundering and Terrorism Financing, Ministry of Finance, Insurance Supervision Agency, Parliament of Montenegro, Tax Administration, Supreme Public Prosecutor’s Office, Ministry of Justice, Administration for Games of Chances, Police Administration, Securities Commission, Agency for Electronic Communications and Postal Services, Bar Association of Montenegro, Notary Chamber of Montenegro. The EC gave an opinion on the Draft of Law before it entered into the parliamentary procedure. At the session of the Government held on 27 February 2014, the Draft Law was discussed and few technical suggestions for modification were given. After that, the Draft law was adopted at the session of the Government held on 06 March 2014 and submitted to further parliamentary procedure for adoption. The Proposal of Law is expected to be adopted during the regular spring sitting of the Parliament. The new law includes numerous solutions from the FATF Recommendations, in accordance with the framework of Montenegrin legislation. (3) 30/06/2014 [PI] The Proposal of the new Law on Prevention of Money Laundering and Terrorism Financing is in the Parliamentary procedure and it is expected to be adopted by the end of 2014. |
| 6.2.22. | Organizing training in the field of implementation of the new FATF recommendations for officers of the institutions involved in the SPN/FT system, and for taxpayers. (1) 31 December 2013 [PI] The Human Resources Administration in cooperation with relevant institutions shall take actions and measures in connection with the development of Trainings Plan, identifying the target groups and speakers for the implementation of trainings. (2) 31 March 2014 [NI] (3) 30/06/2014 [NI] The Human Resources Administration, in accordance with the recommendation, prepared and sent application for TAIEX support for implementation of the measure; however, as there was no feedback regarding the sent application, the measure has not been implemented. | HUMAN RESOURCES ADMINISTRATION Jadranka Djurkovic | NI January –September 2014 | Training plan for regulated sector drafted (1) 31 December 2013 [PI] Meeting with representatives of relevant institutions was held and measures were undertaken in order to develop Training plan. (2) 31 March 2014 [PI] The Human Resources Administration in cooperation with the representative of the Directorate for Prevention of Money Laundering and Terrorism Financing filled out and forwarded to TAIEX an application which provides the following: 1) Development of training programs and plans for the implementation of the FATF recommendations (April 2014); 2) Training for representatives of Montenegrin institutions involved in the system for prevention of money laundering and terrorism financing (May 2014), 3) Training for other taxpayers (banks, insurance companies, etc.) involved in the system for prevention of money laundering and terrorism financing (September 2014). (3) 30/06/2014 [NI] Note: Developed draft Training Programme for the regulated sector, but, due to the reason named in the note, it has not been finalised. Completed trainings in relation to the harmonization and amendments to relevant legal acts (1) 31 December 2013 [PI] Adoption of Amendments to the Law on Prevention of Money Laundering and Terrorism Financing is expected at the end of March this year, after which implementation of trainings for the staff of institutions involved in the system of prevention of money laundering and terrorism financing, as well as for other taxpayers according to the law, will begin. (2) 31 March 2014 [?] (3) 30/06/2014 [NI] | Number of organized trainings and number of participants (1) 31 December 2013 [NI] The training will be implemented following the adoption of Amendments to the Law on the prevention of money laundering and terrorism financing, which is in the process of harmonization with the new FATF recommendations. (2) 31 March 2014 [?] (3) 30/06/2014 [NI] Number of trained trainers (1) 31 December 2013 [NI] Training for trainers will be organized after adoption of the Amendments to the Law on the prevention of money laundering and terrorism financing. (2) 31 March 2014 [?] (3) 30/06/2014 [NI] |

Recommendation 4 from the Screening Report– area “Fight against organised crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.24. | Increase and use of sanctions for failure to comply with the legislation and reporting obligations; (2) 31 March 2014 [PI] (3) 30/06/2014 [PI] | ADMINISTRATION FOR PREVENTION OF MONEY LAUNDERING AND TERRORISM FINANCING Kristina Bacovic | PI January - September 2014 | Amendments to the legal provisions relating to the increase in the amount of sanctions for failure to comply with the legislation and reporting obligations made (2) 31 March 2014 [PI] Draft of the new Law on the Prevention of Money Laundering and Terrorism Financing in part Penalties, Articles 99, 100, 101, 102 and 103 prescribed increase of almost all amounts of fines, compared to the existing legislation, for all offenses in terms of the Law on the Prevention of Money Laundering and Terrorism Financing. Criminal provisions are determined in accordance with the Law on Misdemeanours. (3) 30/06/2014 [PI] This measure has been partially implemented with drafting of the new Law on the Prevention of Money Laundering and Terrorism Financing. The Government of Montenegro adopted this proposal of the new Law on the Prevention of Money Laundering and Terrorism Financing on 6 March 2014 and sent it to the Parliamentary procedure. The new Law on the Prevention of Money Laundering and Terrorism Financing is expected to be adopted by the end of 2014. Amounts of fines for all misdemeanours within the meaning of the Law on the Prevention of Money Laundering and Terrorism Financing have been increased in penalty clauses of the new Law on the Prevention of Money Laundering and Terrorism Financing in comparison to the current legal solution. In addition, these penalty clauses have been defined in accordance with the Law on Misdemeanours. Also, in relation to this measure, trainings are planned to be organised for supervisory bodies defined by the Law on the Prevention of Money Laundering and Terrorism Financing. These trainings will be organized with TAIEX support. Wider control plan of taxpayers drafted -controlled sector (2) 31 March 2014 [?] (3) 30/06/2014 [NI] Note: This measure is directly related to passing of the new Law on the Prevention of Money Laundering and Terrorism Financing and its implementation will start upon adoption of this Law. This Law is in the Parliamentary procedure and it is expected to be adopted by the end of 2014. Increased number of sanctions imposed for failure to comply with the law (2) 31 March 2014 [?] (3) 30/06/2014 [NI] Note: This measure is directly related to passing of the new Law on the Prevention of Money Laundering and Terrorism Financing and its implementation will start upon adoption of this Law. This Law is in the Parliamentary procedure and it is expected to be adopted by the end of 2014. | Increase and use of sanctions for failure to comply with the legislation and reporting obligations; (2) 31 March 2014 [?] (3) 30/06/2014 [NI] Note: This measure is directly related to passing of the new Law on the Prevention of Money Laundering and Terrorism Financing and its implementation will start upon adoption of this Law. This Law is in the Parliamentary procedure and it is expected to be adopted by the end of 2014. |

Recommendation 5 from the Screening Report– area “Fight against organised crime“

Recommendation 6 from the Screening Report– area “Fight against organised crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.26. | Sign a Protocol on Cooperation of the Ministry of Interior - Police Administration and Supreme Public Prosecutor’s Office, whereby cooperation in the pre-trial and criminal procedures will be regulated. Note: The same measure is provided for in the Action Plan for Chapter 23, 2.2.4.1 (1) 31 December 2013 [NI] Draft of the Protocol has been made. Its preparation is in final phase and it is expected to be signed in the upcoming period. (2) 31 March 2014 [I] (3) 30/06/2014 [I] | SUPREME PUBLIC PROSECUTOR’S OFFICE Veselin Vuckovic | I Ongoing | Protocol signed (1) 31 December 2013 [IC] (2) 31 March 2014 [I] The Agreement on cooperation of the State Prosecutor's Office and Ministry of Interior – Police Administration was signed on 9 April 2014. It elaborates the role of police and prosecutors in carrying out the operations in investigation and criminal proceedings. (3) 30/06/2014 [I] The Agreement on cooperation of the Public Prosecutor's Office and Ministry of Interior – Police Administration was signed on 9 April 2014. It elaborates the role of police and prosecutors in carrying out the operations in investigation and criminal proceedings. | Elaborated roles of police and prosecutors in conducting actions in investigation related to corruption and other criminal offences (1) 31 December 2013 [IC] (2) 31 March 2014 [?] (3) 30/06/2014 [I] The Agreement elaborates on the role of police in relation to all criminal offences, thus also including corruptive. |
| 6.2.27. | Signing of the Agreement between the state authorities of Montenegro and authorities of other countries such as the Tax Administration, Customs Administration, Harbour Master’s Office, on the exchange of information necessary for data collection in the pre-trial and criminal proceedings Note: The same measures is provided for in Action Plan 23 under section 2.2.4.2 (2) 31 March 2014 [NI] (3) 30/06/2014 [IC] This measure is contentious. The Customs Administration of Montenegro cooperates with customs services of the European Union Member States on the basis of Article 99 of the Stabilisation and Association Agreement between the European Communities and their Member States of the one part and the Republic of Montenegro, of the other part (Official Gazette of Montenegro 7/07), i.e. on the basis of Protocol 6 to the Agreement (Mutual administrative assistance in customs matters). The Customs Administration signed 27 bilateral agreements on customs cooperation and mutual assistance in customs matters, out of which 12 were with customs services of EU Member States. The Memorandum of Understanding was signed with the Customs Agency of Italy on exchange of information between the customs houses of Bar and Bari. Agreements on electronic exchange of data were signed with the customs services of Serbia, Bosnia and Herzegovina, Kosovo and Albania – Regional project SEED. The Customs Administration is part of the ILECUs project (International Law Enforcement Coordination Units), created with a view to faster exchange of information on cross-border crime for Western Balkans countries: Albania, Bosnia and Herzegovina, Croatia, Serbia, Montenegro and FYR Macedonia. As regards Agreements related to collection of evidence in pre-trial and criminal proceedings, the Customs Administration does not have the necessary legal authority to conduct evidence collecting procedures in accordance with the Criminal Procedure Code, and therefore it may not sign agreements with customs managements of other countries which oblige it to do so. Since the lack of authority of the Customs Administration in this area has been recognised through reports of EU expert missions, the Action Plan for Chapter 24: Justice, freedom and security – Sub-Area Customs Cooperation foresees passing of the new Law on Customs Service which will prescribe all required authorities of customs officers for initiating evidence collecting procedures in pre-trial and criminal proceedings, in accordance with the Criminal Procedure Code, customs and other regulations. Drafting of the new Law on Customs Service is ongoing. The Customs Administration sent an initiative to the Ministry of Justice aimed at recognizing, through amendments to the Criminal Procedure Code, while respecting the requirements of the Naples II Convention and best practices of the EU countries, the necessity of strengthening the authority of customs officers for initiating evidence collecting procedures as regards criminal offences in the area of customs and acting upon the order of the public prosecutor in accordance with this law. | POLICE ACADEMY Rade Simonovic | IC January 2014 and further | Agreements concluded (2) 31 March 2014 [?] (3) 30/06/2014 [IC] The Customs Administration of Montenegro cooperates with customs services of the European Union Member States on the basis of Article 99 of the Stabilisation and Association Agreement between the European Communities and their Member States of the one part and the Republic of Montenegro, of the other part (Official Gazette of Montenegro 7/07), i.e. on the basis of Protocol 6 to the Agreement (Mutual administrative assistance in customs matters). The Customs Administration signed 27 bilateral agreements on customs cooperation and mutual assistance in customs matters, out of which 12 were with customs services of EU Member States. The Memorandum of Understanding was signed with the Customs Agency of Italy on exchange of information between the customs houses of Bar and Bari. Agreements on electronic exchange of data were signed with the customs services of Serbia, Bosnia and Herzegovina, Kosovo and Albania – Regional project SEED. As regards Agreements related to collection of evidence in pre-trial and criminal proceedings, the Customs Administration does not have the necessary legal authority to conduct evidence collecting procedures in accordance with the Criminal Procedure Code, and therefore it may not sign agreements with customs managements of other countries which oblige it to do that. In the area of tax policy, the Agreement on cooperation was signed between Member States of the B6 Group in the area of tax administration on mutual cooperation of 6 former republics of Yugoslavia, except for FYR Macedonia. | Established the possibility of the exchange of information between authorities of different countries (2) 31 March 2014 [?] (3) 30/06/2014 [IC] The Customs Administration of Montenegro cooperates with customs services of the European Union Member States on the basis of Article 99 of the Stabilisation and Association Agreement between the European Communities and their Member States of the one part and the Republic of Montenegro, of the other part (Official Gazette of Montenegro 7/07), i.e. on the basis of Protocol 6 to the Agreement (Mutual administrative assistance in customs matters). The Customs Administration signed 27 bilateral agreements on customs cooperation and mutual assistance in customs matters, out of which 12 were with customs services of EU Member States. The Memorandum of Understanding was signed with the Customs Agency of Italy on exchange of information between the customs houses of Bar and Bari. Agreements on electronic exchange of data were signed with the customs services of Serbia, Bosnia and Herzegovina, Kosovo and Albania – Regional project SEED. For now, the information is exchanged at the request and they are related to data and clarification of laws in the area of taxes. -Annual Work Report (2) 31 March 2014 [?] (3) 30/06/2014 [?] -EC Progress Report (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.28. * | Prepare an analysis of the organizational structure, capacity and authorization of state authorities and administrative bodies in the fight against corruption and organized crime. Note: The same measures is provided for in Action Plan 24 under section 6.2.5 and Action Plan 23 under section 2.2.1.1 (1) 31 December 2013 [I] At the session held on 14 November 2013, the Government adopted the analysis of the organizational structure, capacity and authorization of state authorities and administrative bodies in the fight against corruption and organized crime, with recommendations for improvement of the legislative and institutional framework. |  | I | No indicators |  |
| 6.2.29. | Adopt a Plan of implementation of conclusions from the previous analysis Note: The same measure is provided for in the Action Plan for Chapter 24, 6.2.6, and in the Action Plan for Chapter 23, 2.2.1.2 (1) 31 December 2013 [NI] Drafting Plan of implementation of conclusions is expected in January 2014. (2) 31 March 2014 [I] At the session held on 13 February 2014, the Government of Montenegro adopted a Plan of implementation of the conclusions of the Analysis of organizational structure, capacity and authorization of state authorities and administrative bodies in the fight against corruption and organized crime, with concrete measures to be implemented, competent authorities and deadlines. | MINISTRY OF INTERIOR Milos Vukcevic | I | No indicators |  |
| 6.2.31. | According to the recommendations of experts, secure communications channels for the exchange of electronic mail and information [69] (Info-ex, Secure Mailing Service [70]) among the Police, Special Prosecutor's Office and High Court shall be established. Connection with other law enforcement authorities shall be provided through measure 6.1.8. (2) 31 March 2014 [PI] (3) 30/06/2014 [I] | MINISTRY OF INTERIOR Natasa Starovlah Knezevic | I March 2014; September; 2014; I quarter of 2015; I quarter of 2015; II quarter of 2015; | Prepared analysis of technical needs (2) 31 March 2014 [I] Drafted needs analysis (3) 30/06/2014 [I] Analysis of technical needs has been prepared. Drafted Terms of reference (2) 31 March 2014 [I] Drafted Terms of reference The Terms of reference was submitted to the UNDP which has to implement tender procedure based on donations of the Norwegian Government. (3) 30/06/2014 [?] Equipment procured (2) 31 March 2014 [?] (3) 30/06/2014 [?] Completed installation of communication systems (2) 31 March 2014 [?] (3) 30/06/2014 [?] Implemented trainings on equipment and assigned access rights (2) 31 March 2014 [?] (3) 30/06/2014 [?] | Number of electronic messages exchanged between related authorities on an annual basis (2) 31 March 2014 [?] (3) 30/06/2014 [?] |

Recommendation 8 from the Screening Report– area „Fight against organised crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.32. | Strengthening the capacity of human resources through the increased number of jobs for civil servants for the implementation of secret surveillance measures (SSM) [71] (2) 31 March 2014 [PI] (3) 30/06/2014 [PI] | POLICE ADMINISTRATION Milan Tomic | PI February 2014; April 2014; May 2014; December; 2014; March 2015; May 2015; | Working group established (2) 31 March 2014 [I] In March 2014, Minister of Interior established a working group for capacity building of human resources for the implementation of secret surveillance measures. (3) 30/06/2014 [I] In March 2014, Minister of Interior established a working group for capacity building of human resources for the implementation of secret surveillance measures. Made evaluation of necessity to increase the number of employees for SSM (2) 31 March 2014 [?] (3) 30/06/2014 [I] In April 2014, Evaluation of necessity to increase the number of employees for SSM was made. The document is classified as “LIMITE”. Drafted Proposal of Rulebook (2) 31 March 2014 [?] (3) 30/06/2014 [PI] Aligned with the measure 6.2.45. (ILP), so as to draft both proposals simultaneously, as it is the same organizational unit (Special Verification Unit). The deadline for the same indicator in measure 6.2.45 is September 2014. Adopted Amendments to the Rulebook on Internal Organization and Job Classification (2) 31 March 2014 [?] (3) 30/06/2014 [?] Increased number of employees for the implementation of SSM, through relocation of police officers (2) 31 March 2014 [?] (3) 30/06/2014 [?] Civil servants who meet the requirements employed for an indefinite period of time (2) 31 March 2014 [?] (3) 30/06/2014 [?] | The capacities of the Special Verification Unit enable conducting at least four field operations simultaneously (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.33. | Definition and organization of specialized trainings in the country and abroad for trainers and officials for secret surveillance measures and research and development in the areas of: monitoring of telecommunications and Internet operating technique and observation newly-adopted instructions (2) 31 March 2014 [IC] (3) 30/06/2014 [IC] | POLICE ADMINISTRATION Natasa Starovlah Knezevic | IC March 2014; from April 2014 to April 2016; | Prepared curriculum for trainings (including time and content) (2) 31 March 2014 [I] Prepared Training plan for SSM. Completed trainings for February and March 2014. (3) 30/06/2014 [I]  In March 2014, Plan of basic and specialized training for the area of SSM was prepared. All trainings in the area of SSM which are organized in the Police Academy are aligned with the Work Programme of the Academy for the period until April 2015. Number of organised trainings (courses, seminars, workshops, study visits) (2) 31 March 2014 [IC] February 2014 = 1 March 2014 = 1 (3) 30/06/2014 [IC] In the period January – June 2014, the following results were achieved: 9 trainings were organized (courses, seminars, workshops, working visits) with 3 self trainers and 73 trained employees Number of self-trainers (2) 31 March 2014 [IC] February 2014 = 3 (3) 30/06/2014 [IC] In the period January – June 2014, the following results were achieved: 9 trainings were organized (courses, seminars, workshops, working visits) with 3 self trainers and 73 trained employees | Number of trained employees (2) 31 March 2014 [IC] February 2014 = 14 Mart 2014 = 5 (3) 30/06/2014 [IC] In the period January – June 2014, the following results were achieved: 9 trainings were organized (courses, seminars, workshops, working visits) with 3 self trainers and 73 trained employees |
| 6.2.34. | Establish working group and develop: 1. Analysis on situation and needs for material and technical assets in the Special Verification Unit, 2. Analysis of information system for the needs of Special Verification Unit (1) 31 December 2013 [PI] (2) 31 March 2014 [PI] | MINISTRY OF INTERIOR Natasa Starovlah Knezevic | I October; 2013; March; 2014 ; | Working group established (1) 31 December 2013 [I] Based on the Decision made by the Minister No 01-113/13-69476/1 dated 17 October 2013, the Working group for drafting Analysis on situation and needs for material and technical assets in the Special Verification Unit was established. (2) 31 March 2014 [I] Based on the Decision made by the Minister No 113/13-69476/1 dated 17 October 2013, the Working group was formed, consisted of: Natasa Starovlah-Knezevic, president, Ranko Vojinovic, member, Darko Simonovic, member, Nikola Rogosic, member, Ivan Jokic, member, Srdjan Markovic, member, and Bojan Miranovic, member. (3) 30/06/2014 [I] With the decision of the Minister br.01-113/13-69476/1 of 17 October 2013, a working group was formed for drafting analysis of situation and needs for material and technical resources in the Special Verification Unit. 1. Analysis of situation and needs with recommendations prepared (1) 31 December 2013 [NI] Note: Due date for implementation has not passed. Implementation due date is 31 March 2014. (2) 31 March 2014 [PI] Analysis of the current situation of technical resources of the Special Verification Unit was completed. An overview of needs for equipping the Special Verification Unit by special purposes equipment was made. The confirmation of EU experts in terms of the necessary equipment for special purpose is expected. The visit of EU experts, through TAIEX, was scheduled for 22 to 25 April 2014. Note: According to the plan, experts were supposed to be in Podgorica from 10 to 14 March 2014, however, the mission is delayed for a period 22-25 April 2014. (3) 30/06/2014 [I] Expert mission happened in the period 22.04 -25.04.2014. After that, drafting of the analysis of the situation was completed and recommendations were given with the dynamics of implementation and evaluated financial needs. 2. Analysis of IS with recommendations prepared (1) 31 December 2013 [NI] Note: Due date for implementation has not passed. Implementation due date is 31 March 2014. (2) 31 March 2014 [I] An analysis of the current situation of IT equipment of Special Verification Unit was made. The review of needs for hardware and software was done. (3) 30/06/2014 [I] | Initiated planned procurements (1) 31 December 2013 [NI] Note: Due date for implementation has not passed. (2) 31 March 2014 [?] (3) 30/06/2014 [I] Plan of procurement drafted and evaluation of financial resources done for the next four years. Procedure initiated for procurement of software and equipment envisaged for 2014. |
| 6.2.35. | Equipping the Special Verification Unit with material and technical means in accordance with the EU standards, on the basis of the previous analysis (IT and special purpose equipment for conducting investigations and surveillance, audio, video and GPS devices, improving the system of secret surveillance of telecommunications and Internet, vehicles and material and technical resources, etc.). In accordance with the recommendations of the experts, the mechanisms of electronic recording and external control of the implementation of secret surveillance measures within the system for monitoring telecommunications shall be improved. (2) 31 March 2014 [NI] These measures will be implemented only after the implementation of measures 2.6.34. (3) 30/06/2014 [IC] | MINISTRY OF INTERIOR Natasa Starovlah Knezevic | IC March 2014; from March 2014; to September 2018; | Equipment procured (2) 31 March 2014 [?] (3) 30/06/2014 [IC] June 2014: The system for secure exchange of data with the use of USB media was procured. Completed equipment installation (2) 31 March 2014 [?] (3) 30/06/2014 [?] |  |
| 6.2.36. | Procurement and equipping of premises and vehicles for permanent and mobile command centre for secret surveillance measures (2) 31 March 2014 [NI] Measure will be implemented in II/III quarter. (3) 30/06/2014 [PI] | MINISTRY OF INTERIOR Zoran Asanovic | PI February 2014; June 2014; October 2014; December; 2014; | Analysis prepared (2) 31 March 2014 [?] (3) 30/06/2014 [I]  In February 2014, Analysis for procurement and equipping of premises and vehicles for permanent and mobile command centre for secret surveillance measures was prepared with detailed specifications. The document was classified as”Confidential”. Procurement completed (2) 31 March 2014 [?] (3) 30/06/2014 [PI] On 10 June 2014, the Minister of Interior passed the Decision on initiation of the procedure of confidential procurement and Decision on appointment of the commission for procurement. Completed equipment installation (2) 31 March 2014 [?] (3) 30/06/2014 [?] Permanent and mobile command centre for SSM operational (2) 31 March 2014 [?] (3) 30/06/2014 [?] | Command and control of planning and implementation of SSM is centralized (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.37. * | Passing of the Manual on application of secret surveillance measures, which should particularly elaborate on: Introduction of safety mechanism through the obligation of drafting (in the preparation phase): operative-tactical analytical assessment and Risk analysis (for object of surveillance and officers conducting SSM). (3) 30/06/2014 [I] | Ministry of Interior Milos Vukcevic | I June 2014; second quarter of 2015; fourth quarter of 2015; | Working group formed (3) 30/06/2014 [I] On 3 June 2014, the Minister of Interior formed the working group. The working group will continuously conduct activities until 30 June 2015. Proposals for guidelines drafted (3) 30/06/2014 [I] Proposals for guidelines drafted. Draft Manual developed. Manual adopted (3) 30/06/2014 [PI] Draft Manual defined. | There are standard operative procedures for preparation and implementation of SSM (including safety mechanisms) (3) 30/06/2014 [?] |
| 6.2.38. * | Passing of the Manual on the use of resources for special operative needs (in accordance with Article 122 of the Law on Internal Affairs) (3) 30/06/2014 [I] | Ministry of Interior Milos Vukcevic | I June 2014; second quarter of 2015; fourth quarter of 2015; | Working group formed (3) 30/06/2014 [I] On 3 June 2014, the Minister of Interior formed the working group. The working group will continuously conduct activities until 30 June 2015. Proposals drafted (3) 30/06/2014 [I] Proposal for the Manual drafted. Manual adopted (3) 30/06/2014 [?] | There are standard operative procedures for financing the preparation and implementation of SSM (3) 30/06/2014 [?] |
| 6.2.39. * | Defining and organising professional trainings in country and abroad for trainers and civil servants for investigation of undercover investigators (3) 30/06/2014 [IC] | Police Administration Aleksandar Radovic | IC March 2014; until third quarter of 2015; third quarter of 2017; | Curriculum for trainings (including time and content) (3) 30/06/2014 [I] Plan of Trainings for 2014 was made in the Unit for Undercover Investigators. For the implementation of this plan, one training remains which is planned for October 2014 and it would essentially make full use of the adopted plan. Planning of trainings for 2015 is not possible at this moment due to type of trainings and the manner in which they are implemented and planned (they are implemented in cooperation with foreign partners and also depend on the decisions on trainings of foreign partners). Number of completed organized trainings (courses, seminars, workshops, study visits) (3) 30/06/2014 [IC] The course on the topic of hiring of undercover investigators was organized in the period 27-31 January 2014 in the organization of the ICITAP in the Police Academy in Danilovgrad. The course was attended by a total of 16 trainees, out of whom two were judges and three were prosecutors. Three officers completed 15-day training for undercover investigators, two in Slovenia and one in Croatia. In cooperation with the Great Britain police, a regional training for undercover investigators was organized in the period 17-28 March. Number of participants – 18 from 6 countries. A regional conference of prosecutors/investigative judges and heads of units for undercover investigators was organized on 24-28 March 2014 in Budva, also in co-organization of the Great Britain police. Number of self trainers in relation to planned trainings (3) 30/06/2014 [?] | Capacities for undercover investigators enable conducting of at least two simultaneous operations in Montenegro and one abroad (3) 30/06/2014 [?] |
| 6.2.40. | Establish a working group and develop: An analysis on situation and needs for material and technical assets in the Unit for UC. (1) 31 December 2013 [PI] (2) 31 March 2014 [I] (3) 30/06/2014 [I] | MINISTRY OF INTERIOR Aleksandar Radovic | I October; 2013; February; 2014; | Working group established (1) 31 December 2013 [I] Based on the Decision made by the Minister of Interior no. 01-113/13-59405/2 dated 03 October 2013, the Working group for drafting Analysis on situation and needs for material and technical assets in the Unit for Undercover investigators was established. (2) 31/03/2014 [?] (3) 30/06/2014 [I] Based on the Decision made by the Minister of Interior no. 01-113/13-59405/2 dated 03 October 2013, the Working group for drafting Analysis on situation and needs for material and technical assets in the Unit for Undercover investigators was established. Prepared analysis on situation and needs with recommendations (1) 31 December 2013 [PI] Note: Due date for implementation has not passed. Implementation due date is 31 March 2014. (2) 31 March 2014 [I] The analysis on situation and needs for material and technical assets in the Unit for undercover investigators was adopted. (3) 30/06/2014 [I] The analysis on situation and needs for material and technical assets in the Unit for undercover investigators was adopted. | Initiated planned procurements (1) 31 December 2013 [NI] Note: Due date for implementation has not passed. (2) 31 March 2014 [?] (3) 30/06/2014 [NI] Note: The deadline for implementation is September 2014. The items for procurement of specific equipment are currently being considered (in AP indicator of result named as Number of sets for collection of evidence and protection) and procurement of computers and accompanying equipment. The item of secured undercover vehicles is not in the consideration phase and it will probably not be implemented until September 2014. |
| 6.2.42. | Adoption of the Instructions on the method and procedure of selection, training, appointment, engagement and manner of work of undercover investigators. (2) 31 March 2014 [PI] (3) 30/06/2014 [I] | MINISTRY OF INTERIOR Milos Vukcevic | I March 2014; June 2014; October 2014 | Working group established (2) 31 March 2014 [I] Working group established (3) 30/06/2014 [I] Proposals made (2) 31 March 2014 [PI] Draft of the instructions was defined. (3) 30/06/2014 [I] Proposal for the Instruction defined. Instructions adopted (2) 31 March 2014 [?] (3) 30/06/2014 [?] | There are standard operating procedures (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.43. | Adoption of Instructions on financial operations and funds for special operational needs of the Unit of undercover investigators (2) 31 March 2014 [PI] (3) 30/06/2014 [PI] | MINISTRY OF INTERIOR Milos Vukcevic | PI March 2014; June 2014; October 2014 | Working group established (2) 31 March 2014 [I] Working group established (3) 30/06/2014 [I] Working group was established and it drafted Proposal for the Instructions – Decision number 01-050/14-3754/1 of 23 January 2014. Proposals made (2) 31/03/2014 [PI] (3) 30/06/2014 [I] Proposal has been drafted. Instructions adopted (2) 31 March 2014 [?] (3) 30/06/2014 [?] | There are standard operating procedures (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.44. * | Adoption of Instructions for the procedure of development, method of keeping and destroying undercover documents.[72] (3) 30/06/2014 [I] | Ministry of Interior Aleksandar Radovic | I March 2014; June 2014; October 2014 | Working group established (2) 31/03/2014 [PI] Working group established (3) 30/06/2014 [I] Working group established. Proposals drafted (3) 30/06/2014 [I] The working group drafted proposal for the Instructions. Instructions adopted (3) 30/06/2014 [?] | There are standard operative procedures (3) 30/06/2014 [?] |
| 6.2.45. | Harmonize the organizational structure of the Police Administration with a model "Management conducted by intelligence-led policing" - ILP (2) 31 March 2014 [PI] (3) 30/06/2014 [PI] | POLICE ADMINISTRATION Milos Vukcevic | PI February 2014; April 2014; May 2014; September 2014; December 2014; I quarter of 2015; III quarter of 2015; IV quarter of 2015 | Working group established (2) 31 March 2014 [I] Based on the Decision made by Minister, the Working group whose members are inter alia two foreign experts (IPA and OSCE) was established. (3) 30/06/2014 [I] On 18 February 2014, a working group was established. Made a decision on the organizational separation of intelligence and investigative operations at the Ministry of Interior - Police Administration (2) 31 March 2014 [I] Decision on the organizational separation of intelligence and investigative operations was made, as well as to concentrate in one organisational structure the following tasks: collection, processing, analysing and distribution of intelligence data and information. (3) 30/06/2014 [I] In April 2014, at the proposal of the working group and with the consent of the Director of the Police Administration, the Minister of Interior approved: organizational separation of intelligence and investigative operations in the Ministry of Interior – Police Administration and concentration of tasks of collection, processing, analysis and distribution of intelligence data in one organizational structure. Made a decision to concentrate in one organisational structure the following tasks: collecting, processing, analysing and distributing the intelligence data and information (2) 31 March 2014 [?] (3) 30/06/2014 [I] In April 2014, at the request of the working group and with the consent of the Director of the Police Administration, the Minister of Interior approved: organizational separation of intelligence and investigative operations in the Ministry of Interior – Police Administration and concentration of tasks of collection, processing, analysis and distribution of intelligence data in one organizational structure. Drafted Proposal of Rulebook (2) 31 March 2014 [?] (3) 30/06/2014 [PI] In May 2014, data and proposals from the field were collected and in the course of May and June alignment was done of required police professions in headquarters and on the field for the needs of preparation of draft proposal for the Rulebook (with the deadline until September). The alignment is simultaneously done for the measure 6.2.32. Adopted Amendments to the Rulebook on Internal Organization and Job Classification in Police Administration (2) 31 March 2014 [?] (3) 30/06/2014 [?] Founded Unit for criminal and intelligence activities at the central level in the Police Administration (2) 31 March 2014 [?] (3) 30/06/2014 [?] Founded special units for criminal and intelligence activities in all regions of Montenegro (2) 31 March 2014 [?] (3) 30/06/2014 [?] Completed harmonisation process with ILP (2) 31 March 2014 [?] (3) 30/06/2014 [?] | Capacities of Unit for criminal and intelligence activities (central level) allow the implementation of six simultaneous long-term projects on reporting (2) 31 March 2014 [?] (3) 30/06/2014 [?] Capacities of Unit for criminal and intelligence activities (regional level) allow the implementation of two simultaneous intelligence researches (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.46. * | Make amendments to: Manual for ILP and Instructions on work with operative links (3) 30/06/2014 [IC] | Police Administration Milan Tomic | IC April ; 2014; second quarter of 2015; fourth quarter of 2015 | Working group established (3) 30/06/2014 [I] On 8 June 2014, the Minister of Interior established the working group. Draft proposal for the Manual for ILP completed (3) 30/06/2014 [IC] The working group will continuously conduct activities until 30 June 2015. Amendments to the Manual for ILP adopted and aligned the Instructions on work with operative links (3) 30/06/2014 [?] |  |
| 6.2.48. | Develop a national intelligence model of prioritization, management and allocation of tasks in the field of opposition to serious and organized crime based on SOCTA analysis, according to the Conclusion of the Council of the EU, No 3043 of 09 October 2010. (2) 31 March 2014 [IC] (3) 30/06/2014 [PI] | MINISTRY OF INTERIOR Hermin Sabotic | PI April 2014; October 2014; I quarter of 2015; | Founded National (2) 31 March 2014 [PI] Draft of the Decision on founding National Interagency Strategic Steering Group was made (3) 30/06/2014 [PI] Drafted Proposal of the Decision on founding National Interagency Strategic Steering Group and National Interagency Operative Steering Group, as working bodies for combating serious and organised crime. Proposal for the decision on founding of these two steering groups was submitted with the accompanying material to the Minister for the signature and further forwarding to the Government. After the Minister approves proposal for the decisions, the material will be discussed at the session of the Government. National Interagency Strategic Steering Group and National Interagency Operative Steering Group are expected to be founded by mid-July of this year at the latest. Founded National Interagency Operative Steering Group (2) 31 March 2014 [?] (3) 30/06/2014 [?] Adopted methodologies for annual and multi-year planning to combat serious and organized crime (2) 31 March 2014 [?] (3) 30/06/2014 [?] | Number of meetings of interagency groups (2) 31 March 2014 [?] (3) 30/06/2014 [?] Drafted first MASP (multiannual strategic plan) – (YES/NO indicator) (2) 31 March 2014 [?] (3) 30/06/2014 [?] Drafted OAP (operating annual plan) – (YES/NO indicator) (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.49. | Definition and organization of basic and specialized trainings in the country and abroad for managers, employees and trainers involved in the implementation of the ILP model in a strategic and operational level in the following areas: administration and management of the ILP model preparation of strategic and operational analysis criminal Intelligence Jobs training on new equipment and software (connection with measures 6.2.35, 36 and 37) (2) 31 March 2014 [PI] (3) 30/06/2014 [IC] | POLICE ADMINISTRATION Nikola Rogosic | IC February 2014; from April 2014 to April 2016; | Prepared curriculum for training (including time and content) (2) 31 March 2014 [?] (3) 30/06/2014 [I] In February 2014, the Plan for basic and specialized trainings for the area of ILP was prepared. All trainings in the area of ILP which are organized in the Police Academy are aligned with the Work Programme of the academy for the period until April 2015. Number of organized trainings (courses, seminars, workshops, study visits) (2) 31 March 2014 [I] Number of organized trainings in March: 3. Number of trained employees: 37. (3) 30/06/2014 [IC] Number of organized trainings: February 2014 = 1 March 2014 = 3 April 2014 = 2 May 2014 = 2 Number of trained employees: February 2014 = 15 March 2014 = 37 April 2014 = 44 May 2014 = 25 Police Academy: Self-assessment of quality of work in the police organization using the CAF model, application and adherence to the Action Plan 04.02. - 17 officers of the border police department Intelligence work and DESK function 17. – 19.02. – 15 officers of the General police jurisdiction department Management and decision-making in ILP process 20.03. – 20 officers of the Police Administration Training for criminal-operative work and Desk function 14.-16.04. – 15 trainees Training for the use of handheld GPS device of the type GARMIN Rino 650 14.04. 15 officers of the border police department Training for the use of the SMARTDEC system and use of the new operative server 15.04. – 15 trainees (officers working on tasks of electronic surveillance of national border) 16.04.-15 trainees (officers working on tasks of electronic surveillance of national border) In the course of the border police, the topic of training on technical devices is discussed through 4 lessons Number of self-trainers (2) 31 March 2014 [I] Number of self-trainers: 5 (3) 30/06/2014 [I] Number of self-trainers: 5 | Increased number of operational reports composed in accordance with the ILP within the Crime Police Sector by 10% until the end of 2016. (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.50. | Establish working group and develop: an analysis on situation and needs for IT equipment at local level in police (1) 31 December 2013 [PI] (2) 31 March 2014 [I] (3) 30/06/2014 [I] | MINISTRY OF INTERIOR Natasa Starovlah Knezevic | I October 2013; March 2014 ; | Working group established (1) 31 December 2013 [I] Based on the Decision made by the Minister of Interior no. 01-113/13-69476/1 dated 17 October 2013, the Working group for drafting Analysis on situation and needs for IT equipment at local level in police was established. (2) 31 March 2014 [I] The Working group was established in October 2013. (3) 30/06/2014 [I] Prepared analysis on situation and needs with recommendations (1) 31 December 2013 [NI] Note: Due date for implementation has not passed. Implementation due date is 31 March 2014. (2) 31 March 2014 [I] Analysis on situation and needs for IT equipment at local level in police for the implementation of ILP was prepared. (3) 30/06/2014 [I] | Initiated planned procurements (1) 31 December 2013 [NI] Note: Due date for implementation has not passed. (3) 30/06/2014 [?] |
| 6.2.52. | Establish a working group and develop: An analysis on needs for “Entity management” software in police. (1) 31 December 2013 [PI] (2) 31 March 2014 [I] (3) 30/06/2014 [I] | MINISTRY OF INTERIOR Natasa Starovlah Knezevic | I October 2013; February 2014; | Working group established (1) 31 December 2013 [I] Based on the Decision made by the Minister of Interior no. 01-113/13-69476/2 dated 17 October 2013, the Working group for drafting Analysis on needs for Entity Management System software in police was established. (2) 31 March 2014 [I] Based on the Decision No 113/13-69476/1 dated 17 October 2013, the Working group was established, consisted of: Natasa Starovlah-Knezevic, president, Darko Simonovic, member, Dejan Djurovic, member, Nikola Rogosic, member, Ivan Jokic, member, and Snezana Vujovic, member. (3) 30/06/2014 [I] Prepared Analysis on needs with recommendations (1) 31 December 2013 [NI] Note: Due date for implementation has not passed. Implementation due date is 31 March 2014. (2) 31 March 2014 [I] Conducted analysis that includes: overview of the current situation needs analysis and manner of their implementation assessment of the required software and their estimated values Gantt chart of activities (3) 30/06/2014 [I] | Initiated planned procurements (1) 31 December 2013 [NI] Note: Due date for implementation has not passed. (2) 31 March 2014 [I] The procedure for procurement of software solutions was initiated. (3) 30/06/2014 [?] |
| 6.2.53. * | Development/procurement/installation of software for implementation of ILP model in police in accordance with findings of the analysis: „Entity management“ (3) 30/06/2014 [NI] Development of tender documentation for procurement of software is ongoing in accordance with the analysis of needs conducted within the measure 6.2.52 | Ministry of Interior Natasa Starovlah Knezevic | NI From June 2014 ; until June 2015; | “Entity Management” system implemented in the computer system of the police (3) 30/06/2014 [?] | Number of entities entered into the system (3) 30/06/2014 [?] |

Recommendation 8 from the Screening Report– area ”Fight against organised crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.56. | Amend the Law on Witness Protection, inclusion of the category of witness collaborator in line with recommendations of experts, redefining of the term close person, number of members and composition of the Commission for Application of the Protection Program etc. It is also needed to define, in accordance with the Law on Witness Protection Article 47, the budget of the Unit for Witness Protection. (1) 31 December 2013 [PI] (2) 31 March 2014 [PI] (3) 30/06/2014 [PI] | MINISTRY OF JUSTICE Merima Bakovic | PI December 2013; April 2014; September 2014 | Proposal for the Law on Witness Protection determined (1) 31 December 2013 [PI] The Proposal for the Law on Witness Protection was adopted at the session of the Government of Montenegro held on 26 December 2013 (2) 31 March 2014 [I] At the session held on 3 March 2014, the Committee on Political System, Judiciary and Administration of the Parliament of Montenegro unanimously adopted Proposal of the Law Amending the Law on Witness Protection. The Proposal will be submitted to the Parliament for adoption. (3) 30/06/2014 [I] At the session held on 3 March 2014, the Committee on Political System, Judiciary and Administration of the Parliament of Montenegro unanimously adopted Proposal of the Law Amending the Law on Witness Protection. The Proposal will be submitted to the Parliament for adoption. Law Amending the Law on Witness Protection adopted (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30/06/2014 [NI] Note: At the session held on 5 May 2014, the Legislative Committee discussed and expressed positive opinion about this proposal of the Law; Parliamentary voting of the proposal of the law is pending. At the session held on 19 June 2014, the Government of Montenegro discussed the Amendment (submitted by the Positive Montenegro) to the Proposal of the Law amending the Law on Witness Protection, and with the explanation informed the Parliament of Montenegro that it does not accept the proposed amendment. Therefore, the proposal of the law is returned to repeated Parliamentary voting and will be on the agenda at the session of the Parliament scheduled for 8 July 2014 (After discussion of the Proposal of the Law by the competent Parliamentary committees, the Report was submitted to the Parliament along with the recommendation for adoption of the Law). Means for enforcement of the Law to be defined in the special proportion in relation to the Ministry of Interior (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30/06/2014 [?] | The Law and bylaws harmonised with operational needs (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30/06/2014 [?] Results of the implementation of the Law (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.57. | Work on training concept/ Organise and implement specialised trainings at all levels, improve management of protection measures in implementation of the Protection Program in all segments and in the procedure of application of urgent measures. (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30/06/2014 [IC] | OFFICE FOR FIGHT AGAINST TRAFFICKING IN HUMAN BEINGS | IC From March 2013 to IV quarter of 2015; | Number of successfully completed specialised trainings (1) 31 December 2013 [IC] Three trainings completed. In cooperation with the agency of the Government of Republic of the Northern Ireland, NI-CO from Belfast, within the regional project WINPRO II “Cooperation in criminal justice: Witness Protection in the Fight against Organised Crime and Corruption” in which Serbia, Croatia, Bosnia and Herzegovina, Macedonia, Albania, Kosovo and Montenegro participate, financed by the IPA 2012 Multi-beneficiary Programme, three specialized trainings for the Unit for witness protection were delivered: -«Train the trainers» as regional training organized by WINPRO II project team, held in Croatia. - «Basic course for witness protection» as regional training organized by WINPRO II project team, held in Montenegro. - «Close protection» as regional training organized by WINPRO II project team, held in Bosnia and Herzegovina. (2) 31 March 2014 [IC] In January: 1 workshop, 1 officer and 1 officer of the Bureau of Human Resources and Legal Affairs In February: 1 specialist training, 2 trained officers. In March: • one workshop on "Human Resources Management in the Witness Protection", held in Skopje, which was attended by an officer of Unit for Witness Protection, an officer of the Bureau of Human Resources and Legal Affairs, and an officer of the Department for Strategic development and normative activities; • one joint specialized training on "Close Protection", held in Bar, where three officers of the Unit, four officers of the Department for Protection of Persons and five officers of the Special Verification Unit were trained; • one regional conference on "Balkan network in the Witness Protection" held in Mostar. It was attended by two officers of the Unit, as well as representatives of six countries (Bosnia and Herzegovina, Croatia, Kosovo, Serbia, Macedonia, Albania). The themes of the conference were "Operational procedures and possibilities of the Unit for Witness Protection in case of crossing the state border and transit of protected persons" and "Procedures and possibilities of the Units for protection during temporary relocation of protected persons with the list of costs and exchange of operational information." (3) 30/06/2014 [IC] In January: 1 workshop, 1 officer and 1 officer of the Bureau of Human Resources and Legal Affairs In February: 1 specialist training, 2 trained officers. In March: • one workshop on "Human Resources Management in the Witness Protection", held in Skopje, which was attended by one officer of Unit for Witness Protection, one officer of the Bureau of Human Resources and Legal Affairs, and one officer of the Department for Strategic development and normative activities; • one joint specialized training on "Close Protection", held in Bar, where three officers of the Unit, four officers of the Department for Protection of Persons and five officers of the Special Verification Unit were trained; • one regional conference on "Balkan network in the Witness Protection" held in Mostar. It was attended by two officers of the Unit, as well as representatives of six countries (Bosnia and Herzegovina, Croatia, Kosovo, Serbia, Macedonia, Albania). The themes of the conference were "Operational procedures and possibilities of the Unit for Witness Protection in case of crossing the state border and transit of protected persons" and "Procedures and possibilities of the Units for protection during temporary relocation of protected persons with the list of costs and exchange of operational information." • one international conference «Europol network conference on witness protection », held in Rome, in the organization of Europol, which was attended by the head of the Unit and which was attended by representatives of 57 countries, as well as representatives of Eulex, ICC, ICTY, EC, UNODC and NI-CO (April) • one regional meeting on the topic “Implementation of the project Winpro II and human resources management “, which was held in Tirana and which was attended by two members of the Witness Protection Unit, as well as representatives of police, courts and prosecutions from seven countries: Serbia, Albania, Kosovo, FYR Macedonia, Croatia, B&H and Montenegro (April) • one specialized training on the topic of “Operative planning” held in Podgorica, where four officers of the Witness Protection Unit were trained (April) • one regional training on the topic of “Education of educators”, held in Bar and it was attended by one officer of the Witness Protection Unit and one officer of the Ministry of Justice – Institution for Enforcement of Criminal Sanctions (May) • one joint specialized training on the topic of “Medical skills”, held in Bar, where four officers of the Witness Protection Unit and four officers of the Special Verification Unit were trained (May) In June: •one joint conference of «Salzburg forum» and «Balkan network on witness protection 05.06.-06.06.2014 in Valbandon, Republic of Croatia. The conference was attended by two officers of the Witness Protection Unit of Montenegro, as well as representatives of the services for witness protection from: Bosnia and Herzegovina, FYR Macedonia, Slovenia, Austria, Bulgaria, Czech Republic, Hungary, Poland, Romania, Slovak Republic, Slovenia, Croatia, Latvia and Estonia. •one joint specialized training on the topic «Counter surveillance and anti-surveillance» held in Budva from 09 06 until 13 06 2014, where three members of the Witness Protection Unit and 5 officers of the Special Verification Unit were trained. • one advanced joint specialized training «Close protection» held in Budva from 16 06 until 20 06 2014, where three members of the Witness Protection Unit and six officers of the Special Verification Unit were trained. • one study visit to the Republic of Northern Ireland, in the period 23-27 06 2014, Belfast, R.N.Ireland. The reason and purpose of this visit was introduction and visit to the prison system with a view to presenting practical solutions concerning justice associates and witnesses serving sentence within the prison system (special prison units). One member of the Unit took part in the visit, and the delegation consisted of the Assistant Director for criminal police department and Head of the Witness Protection Unit, Director and two more representatives of the Institution for the Enforcement of Criminal Sanctions and the Ministry of Justice. • one two-day workshop on the topic of «Witness protection in fight against organized crime and corruption », in Podgorica on 26-27 06 2014 with a view to advancing experience as regards international and national legislation on witness protection, application of non-procedural and procedural protection measures, as well as steps applied on undertaking them. The workshop was attended by one member of the Unit. | The fulfilment of the plan provided by the project (1) 31 December 2013 [IC] In accordance with the plan provided for the project, three trainings were organized during 2013. In cooperation with the agency of the Government of Republic of the Northern Ireland, NI-CO from Belfast, within the regional project WINPRO II “Cooperation in criminal justice: Witness Protection in the Fight against Organised Crime and Corruption” in which Serbia, Croatia, Bosnia and Herzegovina, Macedonia, Albania, Kosovo and Montenegro participate, financed by the IPA 2012 Multi-beneficiary Programme, three specialized trainings for the Unit for witness protection were delivered: -«Train the trainers» as regional training organized by WINPRO II project team, held in Croatia. - «Basic course for witness protection» as regional training organized by WINPRO II project team, held in Montenegro. - «Close protection» as regional training organized by WINPRO II project team, held in Bosnia and Herzegovina. (2) 31 March 2014 [?] WINPRO II (1) 31/12/2013 [IC] In cooperation with the agency of the Government of Republic of the Northern Ireland, NI-CO from Belfast, within the regional project WINPRO II “Cooperation in criminal justice: Witness Protection in the Fight against Organised Crime and Corruption” in which Serbia, Croatia, Bosnia and Herzegovina, Macedonia, Albania, Kosovo and Montenegro participate, financed by the IPA 2012 Multi-beneficiary Programme, three specialized trainings for the Unit for witness protection were delivered: -«Train the trainers» as regional training organized by WINPRO II project team, held in Croatia. - «Basic course for witness protection» as regional training organized by WINPRO II project team, held in Montenegro. - «Close protection» as regional training organized by WINPRO II project team, held in Bosnia and Herzegovina. (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.58. | Equipping the Witness Protection Unit, communication means and equipment to testify via video link (video conference), procurement of special armoured vehicles for the Unit’s needs in accordance with experts' recommendations. (2) 31 March 2014 [PI] (3) 30/06/2014 [I] | MINISTRY OF INTERIOR | I March 2014; III quarter of 2015; IV quarter of 2015 | Needs analysis (2) 31 March 2014 [I] Needs analysis was drafted on 28 February 2014 for operational and tactical equipping of the Unit for Witness Protection with identified needs – Criminal Police Sector. (3) 30/06/2014 [I] Needs analysis was drafted on 28 February 2014 for operational and tactical equipping of the Unit for Witness Protection with identified needs – Criminal Police Sector. Procured one video conferencing (2) 31 March 2014 [?] (3) 30/06/2014 [?] Number of procured vehicles (2) 31 March 2014 [?] (3) 30/06/2014 [?] | Ratio (%) (2) 31 March 2014 [?] (3) 30/06/2014 [?] Spent funds (2) 31 March 2014 [?] (3) 30/06/2014 [?] necessary funds determined by analysis (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.59. | Analysis of needs and matching the number of employees of the Unit for Witness Protection with defined needs. (2) 31 March 2014 [PI] (3) 30/06/2014 [I] | MINISTRY OF INTERIOR | I March; 2014; June; 2014; December; 2014; I quarter of 2015 | Needs analysis (2) 31/03/2014 [I] An analysis of the needs and aligning the number of officers of the Unit for Witness Protection with the identified needs was drafted on 28 February 2014. It was agreed with the Criminal Police Sector. (3) 30/06/2014 [I] An analysis of the needs and aligning the number of officers of the Unit for Witness Protection with the identified needs was drafted on 28 February 2014. It was agreed with the Criminal Police Sector. The Analysis of the needs and aligning the number of officers of the Unit for Witness Protection was drafted. The analysis, as a proposal of the Unit for Witness Protection, was agreed on at the level of the Criminal Police Sector and approved by the deputy director for the criminal police sector and in the same text sent as a proposal for job descriptions, so that the Working Group for drafting of the Rulebook on internal organization and job descriptions would have a detailed explanation. Proposal of the job classification drafted (2) 31 March 2014 [?] (3) 30/06/2014 [I] Proposal of the job descriptions was drafted. Adoption of the Rulebook (2) 31 March 2014 [?] (3) 30/06/2014 [?] Filling vacant positions of the Unit (2) 31 March 2014 [?] (3) 30/06/2014 [?] |  |

Recommendation 9 from the Screening Report– area „Fight against organised crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.60. * | Within the analysis of organisational structure, capacities and powers of state authorities and state administration bodies in the fight against organised crime and corruption, current situation relating to the procedure of confiscation of property gain, its custody and management will be specially analysed and a model for improvement will be proposed. Note: The same measure is provided for in Chapter 23, section 2.2 Repressive Action against Corruption. (1) 31 December 2013 [I] | MINISTRY OF INTERIOR Milos Vukcevic | I October 2013 | Drafted analysis presenting current situation in cases where property gain was confiscated, its continued custody and management by the Public Property Administration, with detected obstacles and deficiencies in application of this instrument and recommendations for improvement (1) 31 December 2013 [I] At the session held on 14 November 2013, the Government adopted Analysis of organisational structure, capacities and powers of state authorities and state administration bodies in the fight against organised crime and corruption, with recommendations for improvement of legislative and institutional framework. |  |
| 6.2.63. * | Develop internal operating procedures of the Public Property Administration Note: The same measure is provided for in Chapter 23, section 2.2 Repressive action against corruption. (1) 31 December 2013 [I] | PUBLIC PROPERTY ADMINISTRATION | I December 2013 | Developed operating procedures, Specified criteria for management of various types of property (1) 31 December 2013 [I] The Public Property Administration in August 2013 adopted Rulebook on application of the Law on custody of temporarily and permanently seized assets. |  |
| 6.2.64. * | Establish an electronic register of seized assets which will contain the following: number of the decision; name of the court or authority responsible for conducting misdemeanour proceedings, type and estimated value of seized assets and information about the person from whom the assets were seized Note: The same measures is provided for in Chapter 23, section 2.2 Repressive action against corruption (1) 31 December 2013 [I] | PUBLIC PROPERTY ADMINISTRATION | I December 2013 | Established system of recording seized assets (1) 31 December 2013 [I] The Public Property Administration drafted the Project of Information System for management of recording seized assets. In order to implement necessary functions, the following processes have been provided: opening records, recording the following data: number of decision or body competent for management of procedure, type and estimated value of assets and persons from whom assets were seized, recording changes and entering new items in codebook. Digital register of seized assets was established in September 2013. |  |
| 6.2.65. | Report regularly on custody and management of seized assets. Note: The same measures is provided for in Chapter 23, section 2.2 Repressive action against corruption (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30/06/2014 [IC] | PUBLIC PROPERTY ADMINISTRATION | IC Semi-annually | Semi-annual reports of the Public Property Administration drafted and published on the website (1) 31 December 2013 [IC] The report for the period June – December 2013 is available at web page of the Public Property Administration. (2) 31 March 2014 [IC] The report for the period June – December 2013 is available at web page of the Public Property Administration. The next report is expected in July. (3) 30/06/2014 [IC] | Number of cases and value of permanently confiscated property (1) 31 December 2013 [?] (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.66. | Adopt a training plan and conduct trainings for officers of the Public Property Administration in the area of custody and management of seized assets. Note: The same measure is provided for in Chapter 23, section 2.2 Repressive Action against Corruption (1) 31 December 2013 [I] (2) 31 March 2014 [IC] (3) 30/06/2014 [I] | HUMAN RESOURCES ADMINISTRATION Jadranka Djurkovic | I December 2013 and continuously | Adopted training plan (1) 31 December 2013 [PI] These trainings are part of joint activities of the Human Resources Administration and Judicial Training Centre, intended for representatives of judiciary, prosecutor’s organization, Police Administration as well as employees from the Public Property Administration and part of annual training programme of the Judicial Training centre and Human Resources Administration. (2) 31 March 2014 [PI] The Human Resources Administration prepares Training Plan and Programme for officers of the Public Property Administration in the area of care and management of seized assets after which two trainings will be carried out. (3) 30/06/2014 [I] Training plan and programme defined. Number of delivered trainings (1) 31 December 2013 [I] During 2013, four trainings were carried out related to this topic. Training titled “Financial investigation and seizure of property – experiences of the Republic of Croatia and the Great Britain” was held in the period 21-22 March 2013. 18 officers attended the training; two of them were representatives of the Public Property Administration. Training titled “Financial investigation and seizure of property“was held on 2 and 3 July 2013. 26 representatives attended the training; out of this number two were from the Public Property Administration. Training titled “Financial investigation and seizure of property – experiences from the Republic of Slovakia “was held on 10 October 2013. 31 representatives attended the training; out of this number three were from the Public Property Administration. OSCE in Montenegro organised for the officers from the Public Property Administration two day training on 14 and 15 November 2013, titled “Management of temporarily and permanently seized property (issue and manner of solving the issue). (2) 31 March 2014 [?] (3) 30/06/2014 [I] Training on the topic "Management of temporarily and permanently seized property – issue and manner of solving the issue – experiences of the Republic of Croatia” held on 29-30 April 2014. Training on the topic “Financial investigation and seizure of property" held on 19-20 May 2014 in the organization of the Human Resources Administration, CENPF and OSCE. One more training on the same topic is planned for 30 June-1 July 2014 in the organization of the Human Resources Administration, CENPF, Embassy of the USA and OSCE. Number and structure of participants (1) 31 December 2013 [I] Training titled “Financial investigation and seizure of property – experiences of the Republic of Croatia and the Great Britain” was held in the period 21-22 March 2013. 18 officers attended the training; two of them were representatives of the Public Property Administration. Training titled “Financial investigation and seizure of property“was held on 2 and 3 July 2013. 26 representatives attended the training; out of this number two were from the Public Property Administration. Training titled “Financial investigation and seizure of property –experiences from the Republic of Slovakia“was held on 10 October 2013. 31 representatives attended the training; out of this number three were from the Public Property Administration. OSCE in Montenegro organised for the officers from the Public Property Administration two day training on 14 and 15 November 2013, titled “Management of temporarily and permanently seized property (issue and manner of solving the issue). (2) 31 March 2014 [?] (3) 30/06/2014 [I] Training on the topic "Management of temporarily and permanently seized property – issue and manner of solving the issue – experiences of the Republic of Croatia” which was held on 29-30 April 2014 was attended by 8 employees of the Public Property Administration and 3 employees of the Ministry of Justice. Training on the topic “Financial investigation and seizure of property" held on 19-20 May 2014 was attended by 17 participants, including: 7 representatives of the Prosecution, 6 representatives of the judiciary, 2 representatives of the Police Administration, 1 representative of the Public Property Administration and 1 representative of the Administration for the Prevention of Money Laundering. |  |
| 6.2.67. | Train employees of the Police Administration, public prosecutors and judges on financial investigations, detection and freezing of criminal assets in accordance with the annual training program. Note: The same measure is provided for in Chapter 23, section 2.2 Repressive Action against Corruption (2) 31/03/2014 [IC] During the reporting period from 1 January to 31 March 2014, there were no activities on this topic, because these activities are planned for the upcoming period (May 2014 and further) (3) 30/06/2014 [IC] | JUDICIAL TRAINING CENTRE Maja Milosevic | IC During 2014 | Number and structure of participants (2) 31 March 2014 [?] (3) 30/06/2014 [IC] Two seminars organised (May and June 2014) attended by a total of 47 attendees out of whom: 17 representatives of the Prosecution, 16 representatives of the judiciary, 7 representatives of the Police Administration, 7 representatives of public administration Number of organised trainings (2) 31 March 2014 [?] (3) 30/06/2014 [IC] Two seminars organized: - 19 and 20 May 2014 – the Judicial Training Centre of Montenegro, in cooperation with the OSCE – Mission to Montenegro and the Human Resources Administration, organized the seminar on the topic “Financial investigation and seizure of property”. - 30 June and 1 July 2014– the Judicial Training Centre of Montenegro, in cooperation with the USA Embassy in Podgorica, OSCE Mission to Montenegro and the Human Resources Administration of Montenegro, organized the seminar on the topic:”Best financial practice in conducting financial investigations and seizure of property: new approaches and inter-institutional cooperation”. |  |

Recommendation 10 from the Screening Report– area „Fight against organised crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.70. | Implement the Strategy for Fight against Trafficking in Human Beings for the period 2012-2018 and the accompanying Action [74] (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30/06/2014 [IC] | OFFICE FOR FIGHT AGAINST TRAFFICKING IN HUMAN BEINGS Zoran Ulama | IC Semi-annually; II half of 2018 | Report on implementation of the Strategy for Fight against Trafficking in Human Beings for the period 2012-2018 and the accompanying Action Plan (2012-2013) (1) 31 December 2013 [I] On its 45th session held on 28 November 2013, the Government adopted Report on implementation of the Strategy for Fight against Trafficking in Human Beings and Action plan for the period from 1 January to 30 June 2013, prepared by the Working group for monitoring implementation of the National strategy for the fight against trafficking in human beings. (2) 31 March 2014 [I] On 15 January 2014, the Government's Office for Fight against Trafficking in Human Beings published the second repeated public call for non-governmental organizations to propose a candidate for a member of the Working group for Monitoring the Implementation of the National Strategy for Fight against Trafficking in Human Beings. Two NGOs applied on the second repeated public call. List of candidates proposed for member of the Working group is published on the web site of the General Secretariat of the Government of Montenegro – Office for Fight against Trafficking in Human Beings on 27 January 2014. Decision on the selection of members of the Working group was made and published on the web site of the Office on 3 February 2014. At 55th session of the Government of Montenegro, which was held on February 13 2014, the Report on the implementation of strategies to fight against trafficking in human beings and Action Plan for the period July-December 2013 were adopted. Action Plan for implementation of the strategy to fight against trafficking in human beings for period 2012 - 2013 defined 85 measures, while implementation of 67 measures was monitored during the reporting period. Two measures were implemented, while 53 measures are being implemented continuously or if necessary. Simultaneously, 3 measures were partially implemented while 9 measures were not implemented. The Working Group for Monitoring the Implementation of the National Strategy to fight against trafficking in human beings held a set of meetings in order to produce a reasonable Action Plan for the implementation of the strategy for 2014. Process of public consultations with civil society was also carried out. The proposal of the Action Plan was sent to the Government for consideration and it is expected to be adopted at the session that will be held next week. (3) 30/06/2014 [I] The Report on the degree of implementation of the Strategy for fight against trafficking in human beings for the period October 2013 – June 2014. The National Strategy for fight against trafficking in human beings consists of five parts: prevention, efficient criminal prosecution, protection of victims, coordination and partnership and international cooperation. The Government of Montenegro systematically supervises the activities concerning the fight against trafficking in human beings through monitoring carried out by the Working Group for monitoring the implementation of the Strategy for fight against trafficking in human beings and individual action plans. In the first quarter of 2014, a representative of NGO was included in the work of the Working Group on the basis of a public call. The Working Group for monitoring the implementation of the National Strategy for fight against trafficking in human beings held several meetings (regular on 30 January 2014, extraordinary on 3 March 2014 and thematic meeting on 29 April). Under the chapter Prevention – in the respective period the following activities have been implemented: on the occasion of the Day of the Faculty of Law, a one-hour lecture was organized at this faculty for third-year students on Fight against trafficking in human beings. During the Red Cross Week, from 8-15 May, fight against trafficking in human beings was discussed in 6 schools in Podgorica. Within the project ”Monitoring the situation of children returned from EU Member States” organized by the NGO Montenegrin Women's Lobby in cooperation with the Hungarian organization Terre des hommes, assistance and support was provided for 20 children with families who were returned from EU Member States. The assistance implied direct psychosocial support, material support, informative educational workshops on the issue of trafficking and its consequences. These activities were implemented in five municipalities of Montenegro (Podgorica, Berane, Rozaje, Bijelo Polje, Budva). Prevention programme was implemented with girls, younger girls and their mothers through direct individual conversations of general practitioners and gynaecologists on the risks affecting their health in general, and in particular reproductive health after early marriage. The workshops also tackled Roma custom law, early marriages and arranged marriages with minors, where special emphasis was put on possible consequences of this type of marriage which can be materialised through various forms of violence or trafficking in Roma girls. Apart from the workshops, these topics were also discussed in individual conversations in camps Konik I and II. Prevention and education campaign was also carried out for youth and children of RAE population at risk, concerning possible consequences of addiction and panhandling that can lead young boys to the world of crime, panhandling, addiction, and put young girls at risk of becoming victims of trafficking, prostitution and arranged marriages. Also organized was the round table titled “Together in prevention and protection” with representatives of institutions, ministries, international and domestic NGOs on the possibilities of finding the best solutions for the issue of panhandling, early marriages and arranged marriages of Roma girls and youth in general. A number of informative-education workshops were organized with vulnerable categories of population at risk of becoming victims of trafficking in human beings (children without parental care from the centre “Ljubovic”and children from the Roma refugee camp “Konik I”). Under this project, also created was the publication “Stop Child Trafficking”. Under the chapter Education – in the respective period, the following activities were implemented: Head of the Office for Fight against Trafficking in Human Beings Zoran Ulama and advisor in the Office attended the training on the topic of “Fight against human trafficking” which was organized by the General Staff of the Republic of Turkey in the Training Centre of the Partnership for Peace in Ankara, in the period from 7-11 October 2013. A significant part of the course focused on NATO policy in suppression of trafficking in human beings. 29-30 October – In the organization of the Government's Office for Fight against Trafficking in Human Beings, United Nations Development Programme (UNDP) in Montenegro and Croatia and the Centre of Excellence of the Ministry of Foreign and European Affairs of the Republic of Croatia, on 29-30 October 2013, a two-day seminar was held on the topic of “Suppression of trafficking in human beings in the procedure of accession to the EU – exchange of experiences”. 26-27 November – the Government's Office for Fight against Trafficking in Human Beings, in cooperation with the Ministry of Interior – Police Administration and the United Nations Office on Drugs and Crime from Vienna, organized a seminar on the topic of “Criminal justice response to trafficking in human beings in Montenegro”. Representatives of police authorities (7 officers), prosecution (1) and judiciary (2) of Montenegro took part in the seminar. 12-13 December- the Government's Office for Fight against Trafficking in Human Beings, in cooperation with the USA Embassy in Montenegro and the Judicial Training Centre, organized a regional seminar on the topic “Prosecuting the cases of trafficking in human beings – cooperation between the police and prosecution – experiences of the countries in South East Europe”. A special emphasis was put on exchange of experiences in conducting investigations concerning the criminal offence of trafficking in human beings, with focus on cooperation of representatives of police and prosecution, as well as on taking statements from victims of human trafficking. Employees of the Ministry of Health held a meeting with representatives of the Emergency Medical Service aimed at introducing indicators for early identification of potential victims of human trafficking and procedures of further referral with particular attention to the Agreement on mutual cooperation in the area of fight against trafficking in human beings. * 5 health workers employed in the Emergency Medical Service. Representatives of the Office for Fight against Trafficking in Human Beings who are also certified national trainers by the FRONTEX for training of border police on the topic of suppression of trafficking in human beings, in cooperation with the Police Administration – Border Police Department, and with the support of the OSCE Mission to Montenegro, started the first phase of organizing trainings at the end of May 2014. In that respect, so far a total of 6 trainings have been organized including: 19 May in Podgorica, 20 May in Bar, 29 May in Nikšić, 30 May in Pljevlja, 3 June in Bijelo Polje and 4 June in Rožaje. Each of these trainings was attended by 15 border police officers. Through several modules, the participants got familiar with the issue itself, manners and methods of identification of victims and potential victims of human trafficking, techniques of interviewing victims, as well as with the institutional and legislative mechanisms in the fight against human trafficking. Due to particular vulnerability of children as regards trafficking in human beings, within each module, trafficking of children was treated as a separate unit. The final trainings within the first phase are planned for 10 and 12 June in Ulcinj and Herceg Novi. The next three phases will be implemented during October – November 2014, April – May 2015 and October – November 2015 and all Montenegrin police officers will be trained in the course of them. 20 officers of the criminal police were nominated and they will attend training at the Police Academy in Danilovgrad at the end of June of this year on the topic – identification of victims – where international experts will be the lecturers. In the period 10-11 March 2014, a study visit to Zagreb was organized by the UNDP, to the institutions dealing with the issue of human trafficking in Croatia, which was attended by one employee of the Department. In the period 24-25 March, a regional workshop was held in Pristina on the topic of Fight against organized crime and the upcoming challenges in the organization of TAIEX and Europol, and it was attended by two employees of the Department. In the period from 6-14 April 2014, a regional workshop was held in Valbandon – Pula in the organization of ICITAP on the topic of Trafficking in human beings, it was attended by two employees. On 7 May 2014, a regional workshop was held in Skopje in the organization of IOM, on the topic of “Situation in the region of Western Balkan in the field of fight against trafficking in human beings”, it was attended by one employees of the Police Administration and one employee of the office for fight against trafficking in human beings. In the period from 13-14 May 2014, a regional workshop was held in Sarajevo, in the organization of TAIEX, on the topic of “Fight against trafficking of children”, which was attended by one employee of the Police Administration, Special Prosecutor for organized crime, corruption and war crimes, one social worker and two representatives of the office for fight against trafficking in human beings. Within the chapter Efficient criminal prosecution – in the respective period, the following activities have been implemented: In accordance with the action “trafficking”, the activities were significantly stepped up at the local levels, related to identification of potential victims of human trafficking, facilities and persons of interest, etc. The Working Group of the Ministry of Interior – Police Administration was established and it conducts activities on development of the model of a newly formed unit for fight against trafficking in human beings. Completion of activities and establishment of the unit is planned for the second half of this year. Within the chapter Protection – in the respective period, the following activities were implemented: The Government of Montenegro continued to allocate required funds for the functioning of the Shelter for victims of human trafficking from the budget funds of the Office for Fight against Trafficking in Human Beings. These funds are intended for financing of expenditure required for meeting the basic needs of victims of human trafficking, as well as for providing medical, legal, psychological and other types of assistance. Also, these funds are used for paying earnings for five activists of the NGO Montenegrin Women's Lobby who are employed in the Shelter and costs of lease and other overhead expenses for the facility where the Shelter for victims of human trafficking is located. At the same time, the Office for Fight against Trafficking in Human Beings uses these funds to finance the SOS hotline for victims of human trafficking which is available 24/7 to all persons who find themselves in the need of calling or getting informed on the issue of human trafficking. Since January, approximately EUR 7,500 was allocated from the budget of the Office for Fight against Trafficking in Human Beings for the abovementioned needs. In the period from 2 to 4 June, a TAIEX expert paid an official visit to the Shelter. The goal of the visit was drafting of an analysis on functioning of the Shelter of victims of human trafficking and giving recommendations for building human resources and technical capacities with a view to achieving alignment with EU standards in this area. One representative of the Ministry of Justice and Deputy Special Prosecutor for organized crime, corruption and war crimes took part at the regional workshop on the efficient protection of victims and witnesses of human trafficking in criminal proceedings in South East Europe on 29-30 April 2014, Sarajevo, Bosnia and Herzegovina. Within the chapter Coordination and partnership – following activities were implemented in the respective period: The Government of Montenegro systematically supervises the activities as regards the fight against human trafficking through monitoring carried out by the Office for Fight against Trafficking in Human Beings, the main task of which is to coordinate the implementation of the national policy in this regard, as well as through the work of the Working Group for monitoring the implementation of the Strategy for Fight against Trafficking in Human Beings and individual action plans. In the first quarter of 2014, one representative of NGO was included in the work of the Working Group on the basis of a public call. The Working Group for monitoring the implementation of the National Strategy for Fight against Trafficking in Human Beings held several meetings (regular on 30 January 2014, extraordinary on 3 March 2014 and a thematic meeting on 29 April). On 29 April 2014, a thematic meeting of this body was held in extended composition (attended by principals of elementary and secondary schools in Podgorica, representatives of the centres for social work and representatives of the police) with a view to paying additional attention to solving the issue of forced arranged marriages among RAE population. On the 45th session held on 28 November 2013, the Government adopted the Report on Implementation of the Strategy for the Fight against Trafficking in Human Beings and Action Plan for the period 1 January – 30 June 2013, which was prepared by the Working Group for monitoring the implementation of the National Strategy for Fight against Trafficking in Human Beings. On the 55th session of the Government of Montenegro held on 13 February 2014, the Report on implementation of the strategy for fight against trafficking in human beings and the action plan for the period July-December 2013 was adopted. The Action Plan for implementation of the strategy for fight against trafficking in human beings for 2012-2013 defined a total of 85 measures, and in the reporting period implementation of 67 measures was monitored. Two measures were implemented, while 53 measures were implemented either continuously or when needed. At the same time, 3 measures were partially implemented, while 9 measures remained unimplemented. On the session held on 10 April 2014, the Government of Montenegro adopted the Action Plan for implementation of the Strategy for 2014. The Action Plan is a result of a 4-month work of the Working Group for monitoring implementation of the National Strategy for Fight against Trafficking in Human Beings, in the course of which several joint meetings were held and a procedure of public consultations with the civil sector was carried out as well. Within the chapter International cooperation – following activities were implemented in the respective period: 8-9 October – Advisor in the Government's Office for Fight against Trafficking in Human Beings took part at the conference “Combating Trafficking in Human Beings in South Eastern Europe – for a better protection of children” which was held in Kishinev, Moldova on 8-9 October 2013. The conference was dedicated to strengthening joint efforts in the fight against trafficking of children and in the fight against criminal networks, while reviewing the special dimensions of the problem, such as the integrated manner of approach to the issue of effective protection of children victim, as well as the existing and new approaches in finding persons responsible for trafficking (uncovering networks, criminal prosecution, international cooperation). 30-31 October, Vienna, Austria – Head of the Office for Fight against Trafficking in Human Beings, Deputy Special Prosecutor for organized crime, corruption and war crimes and advisor in the Office, at the invitation of the OSCE, took part in the work of the seminar on the topic of Strengthening cooperation among countries of origin, transit and destination in combating irregular migration and related transnational organized crimes”. Countries of the Western Balkan, as well as Turkey, Ukraine, Greece, Norway, France, Poland and representatives on international organizations IOM, UNODC, ICMPD, as well as representatives of the EU agency FRONTEX took part in the work of the seminar. General trends of irregular migrations, smuggling of migrants and human trafficking with roots from conflict and post-conflict countries from Afghanistan, through eastern Mediterranean to Central and Western Europe were all discussed at the seminar. 21-22 November – Head of the Office for Fight against Trafficking in Human Beings/National Coordinator took part in the work of a regional conference dedicated to the issues of human trafficking and prostitution, which was organized by the Swedish institute in cooperation with the Swedish Embassy and NGO Domino: “Swedish and Balkan experience”. The conference was held in Zagreb, Croatia on 21-22 November. 5 and 6 December – Head of the Office and the national coordinator in the fight against trafficking in human beings, at the invitation of the National Committee for Combating Trafficking in Human Beings of the Republic of Moldova, paid a visit to Kishinev on 5 and 6 December of this year where he took part in the work of the conference “Strengthening criminal justice response to trafficking in persons in South Eastern Europe – Combating abuse of the Internet and strengthening cross-border intelligence sharing”, which the National Committee organized in cooperation with the United Nations Office on Drugs and Crime (UNODC). At the end of January and in February of this year, the Head of the Office for Fight against Trafficking in Human Beings and the National Coordinator for fight against trafficking in human beings met with foreign diplomatic representatives in Montenegro, Ambassadors of Turkey, Austria, Germany, Czech Republic, France and Italy, on which occasion he highlighted strong commitment of the Government of Montenegro to face these serious issues which represent one of the most serious ways of violating fundamental human rights and in that respect he presented overall efforts that Montenegro is making in the fight against trafficking in human beings, at the normative and institutional level, and gaining support for implementation of planned activities. On 25 April 2014, the national coordinators of Kosovo and Montenegro signed the Protocol on Cooperation in combating trafficking in human beings with a view to improving identification, notification, referral, cooperation in criminal proceedings and voluntary return of victims and potential victims of human trafficking. Contact persons were appointed for monitoring the implementation of the Protocol by the Ministry of Interior – Police Administration 2 employees, the Ministry of Labour and Social Welfare, the Administration for Inspection Affairs, Supreme Public Prosecutor's Office and the Office for Fight against Trafficking in Human Beings. Appointment of contact persons for drafting protocol on cooperation in the fight against trafficking in human beings with Albania and with Serbia (representing institutions (Supreme Public Prosecutor's Office, the Office for Fight against Trafficking in Human Beings, the Ministry of Interior, Police Administration, the Ministry of Labour and Social Welfare, the Administration for Inspection Affairs). First meeting of the teams of the two countries in charge of drafting of the Protocol on cooperation was held. STATISTICS- 01.10.2013-06.06.2014. PA- 1 criminal charge: - On 20 March 2014, officers of the Safety Department Ulcinj brought one criminal charge against K.A. born on 14 July 1968 in Bar, with permanent residence in Ulcinj, national of Montenegro. M.I., national of B &H, housewife, was identified as an injured party – victim. The victim was given all necessary assistance and protection in the Shelter of the Government, upon which, at a personal request, she was returned to B & H where the competent bodies assumed the task of caring for her. – Officers of the Police Administration – Criminal Police Sector – Department for Fight against Organized Crime and Corruption, according to the action “trafficking”, undertake measures and actions of cooperation with the Security Centre and the Safety Department, as well as with the Border Police Sector, which results in more efficient operative activities. Also present is the constant cooperation with NCB Interpol Podgorica as regards exchange of information and actions in accordance with the submitted requests. Prosecution- 1 appeal and 1 indictment: -Against the judgment K br. 6/13, finding J.V. guilty of the criminal offence of trafficking in human beings under Article 444 paragraph 6 of the Criminal Code, the High Public Prosecutor's Office lodged an appeal on 10 February 2014; - The Basic Public Prosecutor's Office in Ulcinj brought an indictment KT. br.56/14 on 24.03.2014 against K.A. for the criminal offence of trafficking in human beings under Article 444 paragraph 1 of the Criminal Code. Courts: 2 judgments reached and 1 case discussed by the panel: 1. Case K. br.6/13 – against one person Criminal proceedings against J.V., national of the FYR Macedonia and Montenegro. Judgment of the High Court in Podgorica K.br.6/13 announced on 18.11.2013, expedited on 28.01.2014, J.V. was found guilty and was sentenced to a 3 (three) years and 6 (six) month prison sentence for the criminal offence under Article 444 paragraph 6 of the Criminal Code of Montenegro. Against this judgment of the High Court, the Supreme Public Prosecutor's Office lodged an appeal on 10 02 2014, and the defender of the convicted party on 11 02 2014. The documents of the case of the High Court in Podgorica K.br.6/13 were submitted on 24 February 2014 to the Appellate Court of Montenegro for the purpose of making decision upon lodged appeals. The second-degree (appellate) procedure is ongoing. The case was discussed by the panel on 14 April 2014 and the decision of the Appellate Court of Montenegro is currently being written. 2. Case K.br.19/12 (earlier K. br 286/10) - Judgment of the High Court in Podgorica K.br.19/12 final and enforceable on 4 11 2013, finding six persons guilty for the criminal offence of trafficking in human beings, 1 injured party, Roma with the origin from Kosovo, case initiated in 2010. 3. Case Ks.br. 2/12 - "Aphrodite" – Judgment of the High Court in Podgorica Ks.br.2/12, final and enforceable on 16 12 2013, finding seven defendants guilty for committing the criminal offence of criminal association under Article 401 paragraph 1 of the Criminal Code and mediation in prostitution referred to in Article 210 paragraph 1 of the Criminal Code, two defendants for committing the continued criminal offence of mediation in prostitution under Article 210 paragraph 1 in conjunction with Article 49 of the Criminal Code and sentenced to imprisonment. The same judgment acquitted three persons accused of committing a criminal offence of trafficking in human beings under Article 444 paragraph 2 in conjunction with paragraph 1 of the Criminal Code, three persons accused of a criminal offence of trafficking in human beings under Article 444 paragraph 6 in conjunction with paragraph 1 in conjunction with Article 23 of the Criminal Code, and three persons accused of a criminal offence of abuse of official position under Article 416 paragraph 1 of the Criminal Code. -1 victim of human trafficking, with origins from B & H. She stayed in the Government's Shelter for victims of human trafficking in the period from 19 March 2014 until 30 April 2014, when, at her personal request, she was returned to Bosnia and Herzegovina, in cooperation between the Office for Fight against Trafficking in Human Beings, the Ministry of Interior of Montenegro and the Ministry of Interior of Bosnia and Herzegovina. Evaluation of the Strategy for Fight against Trafficking in Human Beings for the period 2012-2018 (1) 31 December 2013 [IC] Reports on the implementation of measures from the Action Plans for the implementation of the Strategy for Fight against Trafficking in Human Beings for the period 2012-2018 are being continuously monitored. (2) 31 March 2014 [?] (3) 30/06/2014 [IC] | Report of State Department and other relevant subjects on trafficking in human beings worldwide (1) 31 December 2013 [I] The Trafficking in Persons (TIP) Report of the State Department (published each year in June), classified Montenegro in Group II of countries, in the ranks of those countries that are making significant efforts to prevent trafficking. (2) 31 March 2014 [?] (3) 30/06/2014 [?] Increased number of identified victims of trafficking; (1) 31 December 2013 [PI] According to statistics from 1 January to 1 December 2013, there were no criminal charges for criminal offence of trafficking in human beings under Article 444 of the Criminal Code, but series of measures and actions were conducted in order to verify the operational cognition, as well as processing the requests of other institutions. Note: The competent public prosecutor's office has filed charges against one person for criminal offence of trafficking in human beings (criminal charges from 2012, 7 potential victims of trafficking-4 from Montenegro, 2 from Macedonia and 1 from Bosnia and Herzegovina, sex: female, out of whom 2 are minor (from Montenegro)). It also has appealed to the judgment of the Superior Court, by which persons from the Aphrodite case were purged of charges in relation to criminal offence of trafficking in human beings. (2) 31 March 2014 [?] (3) 30/06/2014 [?] |

Recommendation 10 from the Screening Report – area “Fight against organised crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.71. | The Training Program for judges and prosecutors shall include training of judges and prosecutors in relation to the new legislation for the criminal offence of trafficking in human beings, with a particular focus on the specifics of taking statements from victims. (2) 31 March 2014 [PI] Regional conference on trafficking in human beings will be organized in Montenegro, in the second half of May 2014 where special emphasis will be placed on the development of a regional curriculum for the fight against trafficking in human beings. (3) 30/06/2014 [IC] | JUDICIAL TRAINING CENTRE Maja Milosevic | IC I quarter of 2014; Annually | Drafted Training programme (2) 31 March 2014 [I] (3) 30/06/2014 [I] Drafted Training programme Number of delivered trainings in accordance with adopted Training programme (2) 31 March 2014 [IC] The last training was organized in December 2013, and trainings for 2014 are planned for the upcoming period. (3) 30/06/2014 [IC] Two education activities implemented: - 27 - 29 May 2014 – The Judicial Training Centre of Montenegro, in cooperation with UNODC, organized the Regional Conference on developing the regional curriculum on trafficking in persons for criminal justice professionals of South Eastern Europe, with a view to developing the Regional curriculum on trafficking in persons, methodologies and material for training. At the same time, this gathering represented training for trainers. - 24-25 June 2014. - Belgrade, a regional training titled:''Regional pilot training on trafficking in persons for criminal justice professionals of South Eastern Europe”, in the organization of UNODC and the Judicial Academy of the Republic of Serbia. | Number of trained judges and prosecutors in relation to the new legislation for the criminal offence of trafficking in human beings, with special reference to the specifics of taking evidence from victims (2) 31 March 2014 [?] (3) 30/06/2014 [IC] Two deputy basic public prosecutors and one judge of the High Court in Podgorica |
| 6.2.72. | Train officers of the Police Administration (Crime Investigation Police Department, general police, border police) on methods of early identification of potential victims of human trafficking and their treatment as well as on specificity of taking testimonies from potential victims of human trafficking. (1) 31 December 2013 [NI] (2) 31/03/2014 [IC] (3) 30/06/2014 [IC] | POLICE ACADEMY | IC Annually | Number of organised trainings (1) 31 December 2013 [NI] Note: During this year, trainings were not organised because Annual training programme of Police Academy did not include these trainings. We emphasise that Training programme was developed for the period April 2013 – April 2014 and the Ministry of Interior – Police Administration did not express the need for this type of training. Due to this fact, it was not included in the Annual training programme of Police Academy unlike previous years when several trainings were delivered in relation to this topic. (2) 31 March 2014 [IC] In the framework of the regional project of the United Nations Development Programme in Montenegro and Croatia "Regional Advisors - exchange of experience in the field of EU accession", the representatives of Montenegrin institutions (police, prosecutors and the Office for Fight against Trafficking in Human Beings) participated in a study visit to the institutions responsible for issues of fight against trafficking in human beings of the Republic of Croatia (Office for Human Rights and Rights of National Minorities, Ministry of Interior, Supreme State Prosecutor's Office, Ministry of Social Policy and Youth and NGOs). ** Five officers of the Police Administration will attend the workshop which will be held on 24-25 March 2014 in Pristina (Kosovo) organized by TAIEX and Europol, which will be dedicated to the issues of human trafficking, drug trafficking and intelligence-led policing. *** Representatives of the Office for Fight against Trafficking in Human Beings, who possess Frontex certificates of national trainers for training border police in the fight against human trafficking, agreed upon the plan and dynamics of implementation of trainings for representatives of border police by Frontex program with representatives of the Police Administration - Border Police Sector. This will be supported by the OSCE Mission in Montenegro. It is planned to implement trainings in four cycles and to train employees at all border crossings. This year 2 training cycles will be organized. First cycle of trainings is planned to start at the end of April. (3) 30/06/2014 [IC] Trainings of police representatives related to fight against trafficking in human beings in the period from 1 January to 30 June 2014. Representatives of the Office for Fight against Trafficking in Human Beings who are also certified national trainers by FRONTEX for training of the border police on the topic of suppression of trafficking in human beings, in cooperation with the Police Administration – Border Police Sector, and with the support of the OSCE Mission to Montenegro, started the first phase of organizing trainings at the end of May 2014. In that respect, so far 6 trainings have been organized, including: - 19 May in Podgorica, - 20 May in Bar, - 29 May in Nikšić, - 30 May in Pljevlja, - 3 June in Bijelo Polje and - 4 June in Rožaje, - 10 June Ulcinj - 12 June Herceg Novi Each of these trainings was attended by 15 border police officers. Through several modules, the participants got familiar with the issue itself, manners and methods of identification of victims and potential victims of human trafficking, techniques of interviewing victims, as well as with the institutional and legislative mechanisms in the fight against human trafficking. Due to particular vulnerability of children as regards trafficking in human beings, within each module, trafficking of children was treated as a separate unit. The next three phases will be implemented during October – November 2014, April – May 2015 and October – November 2015 and all Montenegrin police officers will be trained in the course of them. In the period 10-11 March 2014, a study visit to Zagreb was organized by the UNDP, to the institutions dealing with the issue of human trafficking in Croatia, which was attended by one employee of the Department. In the period 24-25 March, a regional workshop was held in Priština on the topic of Fight against organized crime and the upcoming challenges in the organization of TAIEX and Europol, and it was attended by two employees of the Department. In the period from 6-14 April 2014, a regional workshop was held in Valbandon – Pula in the organization of ICITAP on the topic of Trafficking in human beings, it was attended by two employees. On 7 May 2014, a regional workshop was held in Skopje in the organization of IOM, on the topic of “Situation in the region of Western Balkan in the field of fight against trafficking in human beings”, it was attended by one employees of the Police Administration and one employee of the office for fight against trafficking in human beings. In the period from 13-14 May 2014, a regional workshop was held in Sarajevo, in the organization of TAIEX, on the topic of “Fight against trafficking of children”, which was attended by one employee of the Police Administration, Special Prosecutor for organized crime, corruption and war crimes, one social worker and two representatives of the office for fight against trafficking in human beings. In the period from 23 to 27 June, seven employees of the Police Administration and two employees of the Office for Fight against Trafficking in Human Beings attended the training on the topic “Specific methods of interviewing victims of human trafficking, with particular focus on children”, with experts of the French police as lecturers. In the period 26-27 June, a training was organized at the Police Academy on the topic „Trafficking in persons” for 9 employees of the Police Administration and 1 of the Police Academy. A training plan was made and two more trainings on this topic are planned after September. | Number of officers who have successfully completed a training program (1) 31 December 2013 [NI] Note: Trainings were not organized this year, because it was not planned by annual training program of the Police Academy. Please note that the training program is made for the period April 2013 - April 2014, and this year the Ministry of Interior - Police Administration has not demonstrated the need for this type of training. Therefore, trainings were not included in the annual program of the Police Academy, unlike previous years, when higher number of trainings on this topic was realized. (2) 31 March 2014 [IC] * 1 officer of the Police Administration, the Department for Combating Organized Crime participated in the study visit, 1 representative of the prosecutor's office and 2 representatives of the Office for Fight against Trafficking in Human Beings ** Representatives of the Police Administration who will attend the workshops will be: 2 officers of the Department for Combating Organized Crime, 2 officers from the Department for fight against drug smuggling and 1 officials from the Directorate for international police cooperation. (3) 30/06/2014 [IC] In the period 26-27 June, a training will be organized at the Police Academy on the topic „Trafficking in persons” for 20 employees of the Border police department. A training plan was made and two more trainings on this topic are planned after September. |
| 6.2.73. | Implement trainings for inspectors on labour and safety, employees of health care institutions, centres for social work, NGOs on methods for early identification of potential victims and victims of trafficking and their referral (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30/06/2014 [IC] | OFFICE FOR FIGHT AGAINST TRAFFICKING IN HUMAN BEINGS Zoran Ulama | IC Annually | Number of organized trainings (1) 31 December 2013 [IC] Five trainings were organised in 2013. * The Office for Fight against Trafficking in Human Beings, in cooperation with the American NGO "Fair Girls" and NGO "Montenegrin female lobby" organized in May this year two one-day trainings, intended for social and health workers, representatives of the Police Administration and local authorities from the southern and central region on: "Strengthening the capacity of law enforcement authorities to identify trafficking victims of Romani population." The same training was organized in July for representatives of the aforementioned institutions from the northern region of Montenegro. **Labour and safety inspectors, Tourism Inspection and NGOs participated in the work of international workshop titled:"The fight against seasonal sexual exploitation" organized by the Office for Fight against Trafficking in Human Beings at the end of April 2013, with the support of TAIEX. *** Chief Labour Inspector participated in the seminar titled: »Fight against trafficking in human beings in the process of accession to the EU - exchange of experiences«, organised in Podgorica by the Government’s Office for the Fight against Trafficking in Human Beings, UNDP and Croatian Ministry of Interior. (2) 31 March 2014 [IC] During the reporting period, officials of the Ministry of Health held a meeting with representatives of the Ambulance Service aimed at introducing indicators for early identification of potential victims of trafficking and procedures of further referral with special reference to the Agreement on mutual cooperation in the fight against trafficking in human beings. (3) 30/06/2014 [IC] Employees of the Ministry of Health held a meeting with representatives of the Emergency Medical Service aimed at introducing indicators for early identification of potential victims of human trafficking and procedures of further referral with particular attention to the Agreement on mutual cooperation in the area of fight against trafficking in human beings. Number of attendees - 5 health workers employed in the Emergency Medical Service. | Number of participants per institutions/organizations that have successfully completed training (1) 31 December 2013 [IC] *A total of 22 officials of the Centres for Social Work, 16 employees of the health centres, 9 employees of the Ambulance Service, 18 representatives of the Police Administration, 9 employees of local governments, 4 representatives of the NGO sector and 2 officials of the Office successfully attended the training. ** 1 labour inspector and 1 tourist inspector and 3 representatives of NGOs *** 1 labour inspector (2) 31 March 2014 [IC] 5 health workers – employed at the Ambulance Service (3) 30/06/2014 [IC] Employees of the Ministry of Health held a meeting with representatives of the Emergency Medical Service aimed at introducing indicators for early identification of potential victims of human trafficking and procedures of further referral with particular attention to the Agreement on mutual cooperation in the area of fight against trafficking in human beings. Number of attendees - 5 health workers employed in the Emergency Medical Service. |

Recommendation 10 from the Screening Report– area “Fight against organised crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.74. * | - Amend the Criminal Code in terms of: - defining the term of a victim of trafficking in human beings; - introduction of “slavery and related actions” as a form of exploitation caused by the criminal offence of trafficking in human beings ; - making the acceptance of intended exploitation by a victim of trafficking in human beings irrelevant; - extension of the scope of Article 445 in order to cover children under the age of 18. (1) 31 December 2013 [I] | MINISTRY OF JUSTICE Branka Lakocevic | I September; 2013; | Amendments to the Criminal Code adopted (1) 31 December 2013 [I] The Law Amending the Criminal Code was adopted and published in the Official Gazette of Montenegro 40/13 dated 13 August 2013. The Criminal Code entered into force on 21 August 2013. | Number of criminal offences; (1) 31 December 2013 [NI] According to statistics from 1 January to 1 December 2013, there were no criminal charges for criminal offence of trafficking in human beings under Article 444 of the Criminal Code, but series of measures and actions were conducted in order to verify the operational cognition, as well as processing the requests of other institutions. Number of convicted persons for criminal offence of trafficking in human beings (1) 31 December 2013 [I] 13 persons were convicted for criminal offence of trafficking in human beings Note: In the period 1 January – 1 December 2013 competent courts passed two judgments as follows: - the judgment of the High Court dated to 21 July, second instance judgment pronouncing six persons guilty of criminal offence of trafficking in human beings, 1 person aggrieved, Roma woman originating from Kosovo, case initiated in 2010; – judgment of the High Court dated to 18 June, pronouncing seven defendants guilty for committing the crime of criminal association under Article 401, paragraph 1 of the Criminal Code and mediation in prostitution under Article 210, paragraph 1 of the Criminal Code; two defendants for committing the continued criminal offence of mediation in prostitution under Article 210 paragraph 1 in connection with Article 49 of the Criminal Code and sentenced them to prison. The same judgment released three defendants from the charges for committing the criminal offence of trafficking in human beings under Article 444 paragraph 2 in connection with paragraph 1 of the Criminal Code; three defendants from the charges for committing criminal offence of trafficking in human beings under Article 444 paragraph 6 in connection with paragraph 1 in connection with Article 23 of the Criminal Code; and three defendants from the charges for committing criminal offence of abuse of official position under Article 416 paragraph 1 of the Criminal Code. |
| 6.2.76. | Adopt the Law on Compensation of Damage to Victims of Serious Criminal Offences with a view to establishing a national system for compensation of damage available to victims of trafficking in human beings. (1) 31 December 2013 [NI] (2) 31 March 2014 [NI] (3) 30/06/2014 [PI] | MINISTRY OF JUSTICE Merima Bakovic | PI July; 2013; December 2013 | Proposal of the Law determined (1) 31 December 2013 [NI] Note: The reason for delay was the fact that the Council of the European Union has in the meantime adopted the Directive on minimum standards for victims of criminal offences in EU. It is necessary to harmonize Proposal of Law with that Directive. (2) 31 March 2014 [NI] The reason for delay was the fact that the Council of the European Union has in the meantime adopted the Directive on minimum standards for victims of criminal offences in EU. It is necessary to harmonize Proposal of Law with that Directive. (3) 30/06/2014 [I] The working group drafted a Proposal of the Law on Compensation of Damages for Victims of Criminal Acts of Violence and it is in the Governmental procedure. The proposal is expected to be defined by the Government at the session on 10 July 2014. Law on Compensation of Damage to Victims of Serious Criminal Offences adopted (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30/06/2014 [NI] The working group drafted a Proposal of the Law on Compensation of Damages for Victims of Criminal Acts of Violence and it is in the Governmental procedure. The proposal is expected to be defined by the Government at the session on 10 July 2014. Note: The working group drafted a Proposal of the Law on Compensation of Damages for Victims of Criminal Acts of Violence and it is in the Governmental procedure. The proposal is expected to be defined by the Government at the session on 10 July 2014. | Number of victims of trafficking who have acquired the right to compensation on this basis (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30/06/2014 [?] |

Recommendation 10 from the Screening Report – area „Fight against organised crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.78. | Ensure unhindered functioning of the Shelter for Victims of Human Trafficking. (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30/06/2014 [IC] | OFFICE FOR FIGHT AGAINST TRAFFICKING IN HUMAN BEINGS Zoran Ulama | IC Annually | Providing fees for the people working with the victims in the Shelter, (1) 31 December 2013 [IC] In order to pay fees to the female activists of NGO who provide protection to protégés in the Shelter for victims of THB, it was allocated EUR 16.500 in the period from 1 January to 1 December 2013. Note: The Government of Montenegro allocates from the budget of the Office for the fight against THB necessary money assets for functioning of the Shelter for victims of THB. These assets are intended for financing expenditure necessary to meet basic living needs of victims of THB, as well as to provide medical, legal, psychological and other forms of assistance. Also, these assets are used to pay earnings for five female activists of NGO »Montenegrin female lobby« employed in the Shelter as well as costs for rent and other costs related to facility where the Shelter for victims of THB is located. At the same time, the Office for the fight against trafficking in human beings finances from these assets SOS hotline for victims of THB which is available 24h to all persons who need to call or want to inform themselves about the problem of THB. Since January 2013 to 1 November 2013, the budget of Office for the fight against trafficking in human beings allocated for the above mentioned needs cca. EUR 23.000. (2) 31/03/2014 [IC] The Government of Montenegro continued to allocate from the budget of the Office for the fight against THB necessary money assets for functioning of the Shelter for victims of THB These assets are intended for financing expenditure necessary to meet basic living needs of victims of THB, as well as to provide medical, legal, psychological and other forms of assistance. Also, these assets are used to pay earnings for five female activists of NGO »Montenegrin female lobby« employed in the Shelter as well as costs for rent and other costs related to facility where the Shelter for victims of THB is located. At the same time, the Office for the fight against trafficking in human beings finances from these assets SOS hotline for victims of THB which is available 24h to all persons who need to call or want to inform themselves about the problem of THB. Since January, the budget of Office for the fight against trafficking in human beings allocated for the above mentioned needs cca. EUR 7.500 (3) 30/06/2014 [IC] Covering overhead expenses and the rent expenses for the Shelter, (1) 31 December 2013 [IC] In the period from January 2013 to 1 December 2013, the Office for the fight against trafficking in human beings allocated for the above mentioned needs cca. EUR 9.800. (2) 31 March 2014 [IC] The Government of Montenegro continued to allocate from the budget of the Office for the fight against THB necessary money assets for functioning of the Shelter for victims of THB These assets are intended for financing expenditure necessary to meet basic living needs of victims of THB, as well as to provide medical, legal, psychological and other forms of assistance. Also, these assets are used to pay earnings for five female activists of NGO »Montenegrin female lobby« employed in the Shelter as well as costs for rent and other costs related to facility where the Shelter for victims of THB is located. At the same time, the Office for the fight against trafficking in human beings finances from these assets SOS hotline for victims of THB which is available 24h to all persons who need to call or want to inform themselves about the problem of THB. Since January, the budget of Office for the fight against trafficking in human beings allocated for the above mentioned needs cca. EUR 7.500 (3) 30/06/2014 [IC] Procurement of the required funds for the basic needs of protégés of the Shelter (1) 31 December 2013 [PI] All basic conditions for recovery of the protégés were provided during their stay in the Shelter. (2) 31 March 2014 [IC] The Government of Montenegro continued to allocate from the budget of the Office for the fight against THB necessary money assets for functioning of the Shelter for victims of THB. These assets are intended for financing expenditure necessary to meet basic living needs of victims of THB, as well as to provide medical, legal, psychological and other forms of assistance. Also, these assets are used to pay earnings for five female activists of NGO »Montenegrin female lobby« employed in the Shelter as well as costs for rent and other costs related to facility where the Shelter for victims of THB is located. At the same time, the Office for the fight against trafficking in human beings finances from these assets SOS hotline for victims of THB which is available 24h to all persons who need to call or want to inform themselves about the problem of THB. Since January, the budget of Office for the fight against trafficking in human beings allocated for the above mentioned needs cca. EUR 7.500. (3) 30/06/2014 [IC] | Number of protégés of the Shelter who were provided assistance and accommodation; (1) 31 December 2013 [I] During 2013, 2 protégés stayed at Shelter for victims of THB. (2) 31 March 2014 [?] (3) 30/06/2014 [?] Provided work continuity of Shelter for victims of trafficking in human beings; (1) 31 December 2013 [I] Necessary money assets were allocated for work of employees and stay of protégés in the Shelter during 2013. (2) 31 March 2014 [?] (3) 30/06/2014 [?] |
| 6.2.79. * | Engagement of EU experts with a view to drafting analysis of the functioning of the Shelter for victims of human trafficking and giving recommendations for building the human resources ant technical capacities of the shelter for the purpose of achieving alignment with EU standards in this area (3) 30/06/2014 [PI] | OFFICE FOR FIGHT AGAINST TRAFFICKING IN HUMAN BEINGS Zoran Ulama | PI Second quarter of 2014; | Engaged an expert, (3) 30/06/2014 [I] In the period from 2 to 4 June, a TAIEX expert paid an official visit to Montenegrin institutions and the Shelter. A total of 10 meetings were held, including with representatives of the Office for Fight against Trafficking in Human Beings, the Supreme Public Prosecutor, the Supreme Court, the Ministry of Health, the Ministry of Labour and Social Welfare, the centre for social work, the Ministry of Interior, the Police Administration, representatives of the Shelter for Victims of Human Trafficking, as well with representatives of all non-governmental organizations which directly or indirectly deal with the issues of fight against trafficking in human beings. The goal of the visit was drafting of an analysis on the functioning of the Shelter for Victims of Human Trafficking and giving recommendations for building the human resources and technical capacities of the shelter for the purpose of achieving alignment with EU standards in this area. By the end of June, we expect a written elaborate by the expert, which will form the basis for activities on technical and staff advancement of the Shelter for Victims of Human Trafficking. Drafted analysis on the functioning of the Shelter for Victim of Human Trafficking and given recommendations for building the human resources and technical capacities of the shelter for the purpose of achieving alignment with EU standards in this area (3) 30/06/2014 [PI] In the period from 2 to 4 June, a TAIEX expert paid an official visit to Montenegrin institutions and the Shelter. A total of 10 meetings were held, including with representatives of the Office for Fight against Trafficking in Human Beings, Supreme Public Prosecutor, the Supreme Court, the Ministry of Health, the Ministry of Labour and Social Welfare, the centre for social work, the Ministry of Interior, the Police Administration, representatives of the Shelter for Victims of Human Trafficking, as well as with representatives of all non-governmental organizations which directly or indirectly deal with the issues of fight against trafficking in human beings. The goal of the visit was drafting of an analysis on the functioning of the Shelter for Victims of Human Trafficking and giving recommendations for building the human resources and technical capacities of the shelter for the purpose of achieving alignment with EU standards in this area. By the end of July, we expect a written elaborate by the expert, which will form the basis for activities on technical and staff advancement of the Shelter for Victims of Human Trafficking. | Degree of implementation of recommendations determined by the analysis (3) 30/06/2014 [?] |

Recommendation 11 from the Screening Report – area “Fight against organised crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.81. * | Adopt the Strategy for Control and Reduction of small arms and light weapons (SALW), with an implementing action plan (1) 31 December 2013 [I] | MINISTRY OF INTERIOR Mira Radovic | I July 2013 | Strategy for Control and Reduction of small arms and light weapons (SALW) adopted, (1) 31 December 2013 [I] On its session held on 4 July 2013, the Government of Montenegro adopted the Strategy for control and reduction of small arms and light weapons (SALW), for the period 2013-2018. Action Plan for implementing Strategy adopted (1) 31 December 2013 [I] On its session held on 4 July 2013, the Government of Montenegro adopted the Action plan for implementation of the Strategy for control and reduction of small arms and light weapons (SALW), for the period 2013-2018. | Level and quality of implementation of measures of the Action Plan (1) 31 December 2013 [I] High level and quality of implementation of measures |
| 6.2.82. * | Establish a coordination body for monitoring the implementation of the Strategy for Control and Reduction of small arms and light weapons with a view to efficiently implementing the Strategy and the Action Plan. (1) 31 December 2013 [I] | POLICE ADMINISTRATION Mira Radovic | I September; 2013 | Coordination body for monitoring the implementation of the Strategy established (1) 31 December 2013 [I] Based on the Decision of the Minister of Interior No 01-220/13-59418/2 dated 12 September 2013, the Coordination body was formed for control and reduction of small and light weapons and ammunition, planning, coordinating, implementing and monitoring activities in this area. The chairman of the body is a representative of the Ministry of Interior – National Coordinator, and it consists of the representatives of: the Ministry of Interior, the Ministry of Foreign Affairs and European integrations, the Ministry of Defence, the Ministry of Economy, the Ministry of Finance and the Customs Administration. |  |
| 6.2.83. | Monitor implementation of the Strategy and the Action Plan (1) 31 December 2013 [IC] (2) 31 March 2014 [IC] (3) 30/06/2014 [IC] | MINISTRY OF DEFENCE Drazen Bozovic | IC Annually | Number of held meetings of the Coordination Body (1) 31 December 2013 [IC] Two meetings of the Coordination body were held. Note: In order to implement the Strategy and the Action Plan, the following activities are being carried out: - activities related to professional training and education of officers in order to provide professional basis for efficient implementation of the Strategy are continuously undertaken. In cooperation with the OSCE Mission and UNDP Office in Montenegro, in the period from 11 to 13 December 2013, regional workshop “Strategic access to control and reduction of SALW” was held in Budva. Members of Coordination body for implementation of the Strategy and experts from the region were present and experiences were exchanged. In the period from 23 to 25 December 2013, the study visit of the Coordination body to the Ministry of Interior and Customs Administration of the Republic of Serbia was organised in relation to the same issue. Within the above mentioned workshops, meetings and consultations of the Coordination body are held whereby the upcoming activities are agreed. State bodies work on the strengthening legal framework and administrative capacities in order to reduce SALW possessed by citizens, legal persons and state bodies. Ministry of Interior drafted the Law on Weapons which will be submitted to the EC (before the adoption procedure). Activities in relation to improvement of database on SALW are undertaken. Activities of reforming border police and Customs Administration are ongoing. (2) 31 March 2014 [NI] Coordination body held no meetings in first quarter. (3) 30/06/2014 [IC] Two meetings of the Coordination body were held. The focus of work: 1. Drafting of a report on the status in Montenegro, through the Template for reporting on implementation of the OSCE Document on Small Arms and Light Weapons and supplementary decisions - FSC.GAL/38/11, 2. Drafting of the report through UN template PoA on small arms and light weapons, 3. Conducting activities in accordance with the Council Decision 2013/730/CFSP of 9 December 2013 in support of SEESAC disarmament and arms control activities in South East Europe in the framework of the EU Strategy to Combat the Illicit Accumulation and Trafficking of SALW and their Ammunition. - preparation of annual report on implementation of the national strategy and the action plan for SALW, 4. Participation in regional and international seminars and workshops ---------------------------12.02.2014 meeting of the Regional steering (supervisory) group in Belgrade in the organization of UNDP-SEESAC, one representative of the Ministry of Interior - 13.02.2014 regional meeting of representatives of national SALW commission in Belgrade in the organization of SEESAC, one representative of the Ministry of Interior - 10th Meeting of the Regional Information Exchange Process held in Jahorina on 2 April 2014, in the organization of SEESAC. One representative of ME participated. | Annual report on implementation of Strategy and Action Plan submitted to the Government of Montenegro (1) 31 December 2013 [NI] The Coordination body was formed in the mid- 2013 and Work Report for 2013 will be submitted to the Government prior to 01 July 2014. (2) 31 March 2014 [?] (3) 30/06/2014 [NI] Note: 1. and 2. Responses were submitted, where Montenegro previously did not have completed questionnaires of OSCE and UN. The additions were related to: -national contact persons, - laws, regulations and/or administrative procedures that legally regulate production of SALW, - issuance of permits for production of SALW, - management and safety of supply, - confiscation, seizure and collection, - marking of SALW possessed by the armed forces and security forces, - cooperation with Interpol, -international cooperation for assistance. 3. With the Council Decision, in the next three years, Montenegro was provided support in the following activities: - for Brezovik warehouse – enhancing safety of the warehouse and development of a central registry of stored arms and ammunition, - approved funds for destruction of 4,000 pieces of weapons, - holding of regional meetings of SALW commissions twice a year, - carrying out campaign in collection of weapons and their ammunition and raising awareness on the importance of activities of disarmament and arms control. 4. Reports with proposals for further work. |

Recommendation 11 from the Screening Report – area “Fight against organised crime“

| No | Measure / Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 6.2.84. | Adopt a new Law on Weapons, which will regulate in details the issue of weapons possessed by natural and legal persons and define a legal framework harmonised with EU directives 91/477/EEC and 2008/51/EC, referring inter alia to: modification in some definitions given in the Law; clearer categorisation of weapons and special equipment for firearms in accordance with the EU standards; more precise procedure with weapons possessed by natural and legal persons; definition of the European Firearms Pass; simplification of procedures for procurement, possession, carrying and transfer of firearms for hunting and sport shooting, in accordance with the EU standards; definition of examination and marking of firearms; definition of ammunition loading for one’s own needs in hunting and sport shooting done by natural persons, which is not considered manufacturing of firearms and ammunition according to the EU standards; amendments to sanctioning provisions and their adjustment to the Criminal Code provisions; modification of existing and introduction of new registers; legalisation of weapons; definition of legal basis for adoption of the following implementing legislation: Rulebook on the procedure for and method of entry, transfer and exit of weapons across the state border; Method of keeping records on weapons entered, transferred and exited across the state border as well as on temporarily seized weapons and ammunition at the border crossing points. (1) 31/12/2013 [NI] The Draft Law on Weapons was made in December 2013 for which public discussion will be organised in the upcoming period. The Draft is being translated – in order to submit it to the EC. In order to achieve the objective of the Strategy- reduction of illegal weapons and registering or handing over legal categories of weapons, the legislator provided possibility: - of voluntarily handing over weapons and ammunition, while it is still in force without sanctions, - of legalisation of weapons, registration of weapons which are legal – in order to register it during two years from the date when the Law entered into force, also without sanctions, - of obligation of marking the weapons and - of European Firearms Pass according to the Decision of the Council of EU 51/2008, for the draft law. (2) 31 March 2014 [NI] The Draft Law on Weapons was made in December 2013 for which public discussion will be organised in the upcoming period. The Draft Law is submitted to the EC for opinion. In order to achieve the objective of the Strategy- reduction of illegal weapons and registering or handing over legal categories of weapons, the legislator provided possibility of: - voluntarily handing over weapons and ammunition, while it is still in force without sanctions, - legalisation of weapons, registration of weapons which are legal – in order to register it during two years from the date when the Law entered into force, also without sanctions, - obligation of marking the weapons and - European Firearms Pass according to the Decision of the Council of EU 51/2008, for the draft law. (3) 30/06/2014 [NI] The Draft Law on Weapons was drafted in December 2013, as was the secondary legislation for its implementation under the competence of the Ministry of Interior. Public discussion was held for the Draft Law, and justified objections and suggestions were incorporated in the text. The European Commission submitted comments on the Draft Law. The working group acted upon the comments of the European Commission (they were incorporated in the existing Draft Law). | MINISTRY OF INTERIOR Mira Radovic | NI December; 2013 | Proposal of the Law adopted, (1) 31 December 2013 [PI] The Draft Law on Weapons made in December 2013. Note: The Draft Law on Weapons was made in December 2013 for which public discussion will be organised in the upcoming period. The Draft is being translated – in order to submit it to the EC. In order to achieve the objective of the Strategy- reduction of illegal weapons and registering or handing over legal categories of weapons, the legislator provided possibility: - of voluntarily handing over weapons and ammunition, while it is still in force without sanctions, - of legalisation of weapons, registration of weapons which are legal – in order to register it during two years from the date when the Law entered into force, also without sanctions, - of obligation of marking the weapons and - of European Firearms Pass according to the Decision of the Council of EU 51/2008, for the draft law. (2) 31 March 2014 [?] (3) 30/06/2014 [?] More efficient system introduced in supervising and keeping records on (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30/06/2014 [?] procurement, possession, manufacturing, trade and transport of weapons and ammunition (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30/06/2014 [?] possessed by natural and legal persons, in accordance with the EU acquis (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30/06/2014 [?] | Results of the implementation of the Law (1) 31 December 2013 [NI] (2) 31 March 2014 [?] (3) 30/06/2014 [?] |

## 7.	FIGHT AGAINST TERRORISM                    	MI - Mladen Markovic

### TOPIC: Prevention of terrorism

Recommendation 1 from the Screening Report – area 'Fight against terrorism'

| No. | Measure/Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 7.1. | Adoption of the Draft Law on Compensation of damage to Victims of Criminal Offences It is aligned with the Framework decision 2002/475/JHA of 13 June 2002 on fight against terrorism32002F0475 (1) 31/12/2013 [NI] (2) 31/03/2014 [NI] (3) 30/06/2014 [NI] The adoption of the proposed law is currently halted due to the adoption of the new Directive by the EU. It is necessary to draft a new table of compliance with this directive. The reason for delay was the fact that the Council of the European Union has adopted the Directive on minimum standards for victims of criminal offences in EU, which the new law needs to be aligned with. The comments received from the European Commission were entered into the text of the draft. The text of the law in the procedure. The working group drafted the Proposal of the Law on Compensation of Damages for Victims of Criminal Acts of Violence and it is in the Governmental procedure. The Proposal of the Law is expected to be endorsed by the Government at the session on 10 July 2014. | MINISTRY OF JUSTICE Merima Bakovic | NI December 2013; | Proposal of the Law adopted and submitted to the Parliament (1) 31/12/2013 [NI] The adoption of the proposed law is currently halted due to the adoption of the new Directive by the EU. It is necessary to draft a new table of compliance with this directive. The reason for delay was the fact that the Council of the European Union has not yet adopted the Directive on minimum standards for victims of criminal offences in EU, which the new law needs to be aligned with. (2) 31/03/2014 [NR] The adoption of the proposed law is currently halted due to the adoption of the new Directive by the EU. It is necessary to draft a new table of compliance with this directive. The reason for delay was the fact that the Council of the European Union has adopted the Directive on minimum standards for victims of criminal offences in EU, which the new law needs to be aligned with. (3) 30/06/2014 [?] The working group drafted the Proposal of the Law on Compensation of Damages for Victims of Criminal Acts of Violence and it is in the Governmental procedure. The Proposal of the Law is expected to be endorsed by the Government at the session on 10 July 2014. | Results of the implementation of the Law (1) 31/12/2013 [?] (2) 31/03/2014 [?] 3) 30/06/2014 [?] |
| 7.2. * | Amendments to the Law on Explosive Substances It is aligned with the EU Action Plan on enhancing the security of explosives adopted by the Council on April 04, 2008. (1) 31/12/2013 [I] | MINISTRY OF INTERIOR Sandra Rackovic | I December 2013 | Proposal for Amendments to the Law adopted and submitted to the Parliament (1) 31/12/2013 [I] Proposal for Amendments to the Law on Explosive Substances adopted at the Government's session on 26 December 2013. | Results of the implementation of the Law (1) 31/12/2013 [NI] |
| 7.3. * | Amendments to the Law on Transport of Dangerous Substances It is aligned with the EU Action Plan on enhancing the security of explosives adopted by the Council on April 04, 2008. (1) 31/12/2013 [I] | MINISTRY OF INTERIOR Sandra Rackovic | I September 2013 | Proposal for Amendments to the Law adopted and submitted to the Parliament (1) 31/12/2013 [I] Proposal for Amendments to the Law on Transport of Dangerous Substances adopted at the Government's session on December 26, 2013. | Results of the implementation of the Law (1) 31/12/2013 [NI] |
| 7.5. * | Drafting of the innovated Action Plan for Prevention and Suppression of Terrorism, Money Laundering and Terrorism Financing for the period 2013-2014 (1) 31/12/2013 [I] | MINISTRY OF INTERIOR | I July 2013 | Innovated Action Plan drafted (1) 31/12/2013 [I] The Action Plan for the implementation of the Strategy for Prevention and Suppression of Terrorism, Money Laundering and Terrorism Financing 2010-2014, for the period 2013-2014 adopted at the Government’s session on August 01, 2013. The Government adopted the innovated Action Plan (1) 31/12/2013 [I] The Action Plan for the implementation of the Strategy for Prevention and Suppression of Terrorism, Money Laundering and Terrorism Financing 2010-2014, for the period 2013-2014 adopted at the Government's session on August 01, 2013. | Semi-annual reports on the implementation of objectives and measures from the Action Plan (1) 31/12/2013 [NI] The due date for drafting of the first semi-annual report on the implementation of objectives and measures from the Action Plan has not come yet. |
| 7.6. | Drafting of the Action Plan for the implementation of the Resolution SB UN 1540 (2) 31/03/2014 [PI] (3) 30/06/2014 [I] | MFAEI Stanica Andjic | I March 2014 | Action Plan for the implementation of the Resolution SB UN 1540 drafted (2) 31/03/2014 [PI] Draft Action Plan finalised, adoption is expected in April. (3) 30/06/2014 [I] At the 66th session on 8 May 2014, the Government of Montenegro adopted the National Report and the Action Plan on implementation of the United Nation Security Council Resolution 1540. The results in the strengthening of coordination partly shown in the measure 7.19 related to CBRN. Montenegro carries out activities and measures so as to meet in due time the obligations deriving from relevant international treaties banning weapons of mass destruction and builds a national legislative framework and administrative capacity, in accordance with the resolution. |  |
| 7.7. | Training of civil servants from judicial and law enforcement bodies, working on criminal offences of terrorism and related criminal offences. Remark: for more details, please see the Innovated Action Plan 2013-2014 (link: after its adoption by the National Commission, it will be available at the Government’s website) (1) 31/12/2013 [PI] (2) 31/03/2014 [PI] (3) 30/06/2014 [PI] | JUDICIAL COUNCIL Sanja Kalezic | Pi June 2013 – December 2014 | The number of trainings and the number of trained officers (1) 31/12/2013 [I] - 16.-20. September 2013 – Republic of Croatia/Zagreb, regional meeting was held on strengthening criminal justice institutions and the rule of law in the Central and South East Europe, accession to the EU and international cooperation in the fight against transnational crime. The meeting was organised by the USA Embassy in Zagreb – regional INL legal project. Through American Embassy in Podgorica, Deputy High Public Prosecutor in Podgorica, two representatives of the Ministry of Justice of Montenegro and one representative of Police Administration were present on behalf of Montenegro. - Within the implementation of the regional programme of the UNODC for better management, justice and security in South East Europe 2012-2015, with the financial support of the Government of the Republic of Slovakia, the workshop “International legal instruments in the fight against terrorism” was held in the period from 8 to 10 October 2013 in the premises of Human Resources Administration, in Podgorica. The workshop was organised by the Ministry of Interior, Police Administration, in cooperation with UNODC Office. Its basic objective was intensifying interagency cooperation and coordination through exchange of experiences and best practices, and then improvement of professional competences of representatives of relevant state bodies for efficient implementation of international instruments provided for the suppression of terrorism. On this occasion, renowned experts of the UNODC Office and OSCE as well as representatives of prosecutor’s organization from the Kingdom of Spain and Bosnia and Herzegovina presented international legal framework in the fight against terrorism, international conventions and resolutions of the Council of Security of UN in the area of the fight against terrorism, mechanisms of international cooperation related to prevention and suppression of financing terrorism, then experiences in the area of detection, prevention and suppression of financing terrorism and terrorist acts, as well as criminal prosecution i.e. punishment of perpetrators of these criminal offences. Representatives of the law enforcement agencies of Montenegro presented achieved results in the application of international instruments which refer to the fight against and prevention of financing terrorism. Participants at the workshop were representatives of the Ministry of Interior, the Ministry of Justice, the Ministry of Foreign Affairs and European integration, the Ministry of Defence, the Supreme Public Prosecutor’s Office - the Special Department for the fight against organised crime, the High Court, the Administration for prevention of money laundering and financing terrorism, the Agency for National Security and the Training Judicial Centre. - Fight against Terrorism-EUROPOL-Hague- Hague – the Netherlands – an officer of the Special Anti-terrorist unit. - Police officers Exchange Programme through CEPOL. Topic of exchange: Fight against terrorism and prevention of radicalism and extremism. Cyprus/two police officers, in the period from 13 to 18 October, and visit of the police officers from Cyprus in the period from 25 to 29 October. - Regional meeting in Sarajevo – B&H, topic: Establishment of better regional police cooperation in the area of EOD (Explosive Ordnance Disposal) - Training on topic “International workshop for fight against smuggling of weapons”, in the period from 1 to 2 October 2013 in Tirana, the Republic of Albania, where two representatives of Criminal Police Department participated. -Seminar “Improvement of regional and joint capacities of the fight against illegal trafficking in weapons”, in the period 26 to 28 November 2013 in Podgorica, where three representatives of the Criminal Police Department participated. -Training “Illegal trafficking in weapons and provision of explosive substances”, held in the period from 5 to 6 December 2013 in Vienna, the Republic of Austria, where two representatives of Criminal Police Department participated. In the period from June to December 2013, Special Anti-Terrorist Unit carried out: -the second regional gathering of elite police units – Sarajevo, June 2013 – six representatives of Special Anti-Terrorist Unit; -Financing terrorism, intervention of special units – Regional seminar – Belgrade - June 2013 – one officer of Special Anti-Terrorist Unit. -Security studies, programme related to terrorism - George C. Marshall-Garmisch-Partenkirchen – Germany - August 2013 – one officer of Special Anti-Terrorist Unit -Tactics of close fight – Gotenica – Slovenia – October 2013 – five officers of Special Anti-Terrorist Unit; -‘Shooting techniques and tactical action’ – Turkey – Eskisehir – TIKA – November 2013 - attended by seven officers of Special Anti-Terrorist Unit. Special police unit in requested period carried out the following: -Working visit to Gendarmerie of the Ministry of Interior of the Republic of Serbia – one officer; -Seminar “Surviving in the street” –ICITAP 10 officers; - Training “Shooting techniques and tactical actions” – TIKA – seven officers - Training within ILEA programme, Academy in Budapest – Hungary – one officer. Peace mission trainings: -International course for police officers participating in UN peace missions “UNPOC Croatia 2013” – Valbandon - Croatia - September-October 2013- one officer of Special Anti-Terrorist Unit; -Course for participation in UN peace missions – Butmir – Sarajevo – October 2013 – one officer of Special Anti-Terrorist Unit; Officers of the Ministry of Defence and the Army of Montenegro regularly and in planned manner participate in different joint trainings with representatives of other institutions in Montenegro, as well as NATO and other foreign armed forces. One member of the Army of Montenegro actively participates at the meetings of the Working sub-group for asymmetric threats – ATSG since 2006, which functions under the auspices of the “Conference of heads of General Staff of Balkan countries”. Meetings of the working sub-group are held two times a year in the host country of the Conference. Members of the Ministry of Defence and the Army of Montenegro in the second half of 2013 participated in several training programmes, directly related to the fight against terrorism: - IPK for exercise of special forces of Balkan EAGLE 2013, Turkey, 1 person, - Balkan EAGLE Special forces exercise2013, Serbia, 12 persons, - HUMINT course, Danilovgrad, 4 persons, - Demonstration exercise: fight and anti-terrorist actions against significant facilities and persons of the Army of Montenegro, ČVP, - Demonstration exercise: “Department of VP related to abductors and terrorists who use abducted vehicles” Danilovgrad, ČVP, - Special units for solving different hostage situations, Danilovgrad, 16 persons. - Combat shooting techniques with special effects, Danilovgrad, 4 persons. Within the area of chemical, biological, radioactive and nuclear (CBRN) protection, representatives of the Ministry of Defence and the Army of Montenegro participated at the following exercises (courses): - Course for officers ABHO, USA, 1 person, - Course of detection and identification of toxic chemicals, Serbia, 2 persons - Course "Detection and measurement of ionising radiation, Serbia, 2 persons - Course "Radiological, chemical and biological decontamination of people, land and assets”, Serbia, 2 persons -"NATO course ABHO", Germany, 1 person. - Basic course for analysis of radiological and chemical contaminated samples, Serbia, 2 persons. - Regional exercise “Initiative against expansion of weapons for mass destruction – PSI”, Croatia, 1 person. (2) 31/03/2014 [I] Ministry of Defence-Army of Montenegro: Conference on Terrorism. Maribor, Slovenia, 3-6 March 2014, 3 persons, Programme-terrorism and security studies, terrorism and security studies Garmisch-Partenkirchen, Germany, 1 person ’’Defence and Military Intelligence Executive Workshop’’ was held in Podgorica, from 10 to 14 February 2014. The workshop was organised in cooperation with United States European Command (US EUCOM), US Embassy in Podgorica and the Ministry of Defence of Montenegro. With support and mediation of representatives of US EUCOM, representatives of the National Security Agency, Ministry of Interior, Police Administration, Army of Montenegro and Military Intelligence and Security Department of the Ministry of Defence participated at the workshop on expert level. The workshop served as a platform for harmonisation and enhancement of cooperation of all elements of security intelligence sector of Montenegro. Police Administration- serial training in negotiating: Two-week training for 16 officers of Police Administration in Special Anti-Terrorist Unit base on the course of hostage negotiations/crisis situations. Organiser Tursa TIKA. 21. II 2014 the meeting held between negotiation team leader and psychologist in public administration bodies with the purpose of getting acquainted with the work of negotiation team and participation in crisis situations. 24. II 2014. One-day seminar ‘Negotiating and Acting of the First Negotiator at the Scene’ was held in Special Anti-Terrorist Unit base. The Seminar was attended by the participants of TIKA two-week training, as continuation of education. Finally, Seminar entitled: ‘Negotiation Team Organisation’ was held in the period from 24 to 28 March 2014 along with demonstration tactic exercise ‘Hostage situation’. Directorate for Prevention of Money Laundering and Terrorism Financing (DPMLTF)/ 24-26. March 2014initial workshop held in organisation of OSCE, TAIEX, World Bank and Ministry of Finances/ DPMLTF in drafting of the national risk assessment of money laundering and terrorism financing. The workshop was attended by all representatives of state institutions involved through the institutional framework for preventing money laundering and terrorism financing. (3) 30/06/2014 [I] The Ministry of Defence-Armed Forces of Montenegro: Conference on Terrorism. Maribor, Slovenia, 3-6 March 2014, 3 persons, Programme-terrorism and security studies, terrorism and security studies Garmisch-Partenkirchen, Germany, 1 person ’’Defence and Military Intelligence Executive Workshop’’ was held in Podgorica, from 10 to 14 February 2014. The workshop was organised in cooperation with United States European Command (US EUCOM), US Embassy in Podgorica and the Ministry of Defence of Montenegro. With support and mediation of representatives of US EUCOM, representatives of the National Security Agency, Ministry of Interior, Police Administration, Armed Forces of Montenegro and Military Intelligence and Security Department of the Ministry of Defence participated at the workshop on expert level. The workshop served as a platform for harmonisation and enhancement of cooperation of all elements of security intelligence sector of Montenegro. The Police Administration- serial training in negotiating: Two-week training for 16 officers of the Police Administration in the Special Anti-Terrorist Unit base on the course of hostage negotiations/crisis situations. Organiser Tursa TIKA. 21 February 2014 - the meeting held between negotiation team leader and psychologists in public administration bodies with the purpose of getting acquainted with the work of negotiation team and participation in crisis situations. 24 February 2014 - One-day seminar ‘Negotiating and Acting of the First Negotiator at the Scene’ was held in the Special Anti-Terrorist Unit base. The Seminar was attended by the participants of TIKA two-week training, as continuation of education. Finally, a seminar entitled: ‘Negotiation Team Organisation’ was held in the period from 24 to 28 March 2014 along with demonstration tactic exercise ‘Hostage situation’. The Directorate for Prevention of Money Laundering and Terrorism Financing (DPMLTF)/ 24-26 March 2014 initial workshop held in organisation of OSCE, TAIEX, World Bank and the Ministry of Finance/ DPMLTF in drafting of the national risk assessment of money laundering and terrorism financing. The workshop was attended by all representatives of state institutions involved through the institutional framework for preventing money laundering and terrorism financing. Training for the period April-June 2014 The Ministry of Defence: - Preparatory conference for exercise of special units of Balkan (B-9 CJSE 2014), Ankara, Turkey, 2 persons, - Course for training of instructors, Czech Republic, 1 person, - NATO workshop “Managing terrorist threats to critical infrastructure – Examples from SE Europe – Today and Tomorrow“, Belgrade, Serbia, 1 persons, - Course of Urban operation (cooperation with representatives of the armed forces of the USA), Danilovgrad, 20 persons, - Course for sniper training, (cooperation with representatives of the armed forces of the USA), Danilovgrad, 6 persons, - Course for anti-mine divers, Kopar, Slovenia, 6 persons, - Course for crime scene technicians, Police Academy, Danilovgrad, 1 person, - ISAF Intelligence Orientation Course, Federal Republic of Germany, 1 person, - Course Counter diversion control, Police Academy, Danilovgrad, 2 persons. In the area of nuclear, chemical and biological defence: - Course for RHB decontamination, Serbia, 2 persons, - Course for detection of toxic industrial chemicals, Serbia, 2 persons, - Advanced course for help and protection against chemical weapons, Serbia, 2 persons, - Workshop of the European Union concerning the drafting of a national action plan for protection against CBRN weapons, Hague, Netherlands, 1 person, - Participation in the seminar under Article X of the Chemical Weapons Convention, Rakitje, Croatia, 2 persons, - Participation in 2 workshops concerning drafting of a national action plan for protection against CBRN weapons, Montenegro, 3 persons, - Seminar on effective practices of the implementation of the United Nations Security Council Resolution 1540, Rakitje, Croatia, 1 person, - Participation of members of the CBRN defence team in the exercise “LEAD SHIELD 2014“, Slovenia, 10 persons, - Participation in the NATO CBRN Defence orientation course, Germany, 1 person, - Participation in the course for conducting sampling and analysis in a highly contaminated environment, Poland, 1 person, - Participation at the conferences for specification and planning of a multinational exercise “BALKAN RESPONSE 2015“, Serbia, 2 persons, - Participation at the 9th meeting of the international expert working group, Serbia, 1 person, The Ministry of Interior – Police Administration: Course of fire protection – Special Anti-Terrorist Unit base. The training was carried out on 10-14 March – performed by the instructors of the Service for Protection – Training attended by 34 employees. In the organization of the Swiss Government and OSCE, the Counter-Terrorism conference was held on 28-29 April 2014 in Interlaken entitled “The role of OSCE in addressing current terrorism challenges”, which was attended by one employee of the Criminal Police Department. Three trainings were organized for members of the diving group of the Special Anti-Terrorist Unit: - 17-22.02.2014 - 7 employees, - 07-11.04.2014 - 7 employees, - 06-15.06.2014 - 9 employees. • As a continuation of cooperation between the Special Anti-Terrorist Unit of the Police Administration and the Armed Forces of Montenegro, in the period from 7-12 April 20014, members of the Special Anti-Terrorist Unit had tactical and fire training with the troop of the special forces of the Armed Forces of Montenegro, after which a joint tactical –demonstration exercise was conducted in the barrack Milovan Šaranović in Danilovgrad, • Under the project of International police education, in the organization of the Turkish International Development and Cooperation Agency (TIKA), a training was organized in the period from 19 to 30 May in the police camp ``Zlatica” on the topic of ``Operative shooting techniques for special units”. The training was performed by the instructors of shooting training from Turkey – active members of the special police of Turkey. The training was attended y 20 members of the Police Administration. | Level of personnel qualification, efficiency and work quality (1) 31/12/2013 [?] (2) 31/03/2014 [?] (3) 30/06/2014 [PI] Teams trained in protection and elimination of consequences of fire, explosions and accidents. Participation in rescue missions in country and the region (more in 7.19) Participation in joint training with forces of other institutions in Montenegro; NATO forces and other foreign armed forces Exchange of best practices, procedures and organizations of joint exercises. Establishment of joint platforms for training and tactics. |

### TOPIC: Suppression of Terrorism

#### OBJECTIVE: Improving the mechanisms for detection, monitoring, research and disabling movement and stay of persons connected with terrorism in the territory of Montenegro

Recommendation 2 from the Screening Report - area ‘Fights against terrorism’

### TOPIC: Protection from Terrorism

Recommendation 3 from the Screening Report – area ‘Fight against Terrorism’

### TOPIC: Recovery of damage from terrorist attack

| No. | Measure/Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 7.18. | Conducting inter-generation exercises using different scenarios (2) 31/03/2014 [PI] (3) 30/06/2014 [PI] | MINISTRY OF INTERIOR | PI January 2014 -December 2015 | Existing plans checked (2) 31/03/2014 [?] (3) 30/06/2014 [?] Number of conducted exercises (2) 31/03/2014 [IC] A joint tactic rescue exercise was conducted on 01 March 2014 in organisation of the Ministry of Interior, Directorate for Emergency Situations. In exercise participated: Air Helicopter Unit of the Ministry of Interior, Police Administration, Capital City Protection and Rescue Service, Public Health Institution Health Centre and Ambulance, Mountain Rescue and Protection Service, divers of the Regional Centre for Demining - Bijela, Red Cross of Montenegro, etc. 27-31 March2014, Prijepolje, Republic of Serbia, within IPA Cross-border Cooperation between Montenegro and Serbia a training for members of special force units was held, followed by field exercise ‘Swift water rescue’. There were 20 persons from protection and rescue services in Podgorica and Berane who participated on the training, as well as representatives from the Red Cross of Montenegro, NGO ‘Extrem’ and Montenegro Rafting Association. (3) 30/06/2014 [IC] On the occasion of the Protection and Rescue day in Montenegro, as well as the international Civil Defence day, a protection and rescue exercise «Morača 2014» was carried out on 1 March 2014, in the organization of the Ministry of Interior and the Directorate for Emergency Situations. The following took part in the exercise: the Directorate for Emergency Situations, the Aviation Unit of the Ministry of Interior, the Police Administration, the Protection and Rescue Services of Podgorica and Danilovgrad, the Emergency Medical Assistance Institute, the Mountain Rescue Service, the Montenegro Rafting Association, divers of the Regional Centre for Divers Training and Underwater Demining from Bijela, the Red Cross of Montenegro and the KC “Morača”. The Ministry of Interior of Serbia, NGO Foundation for the Development of Northern Montenegro, in cooperation with the Ministry of Interior – Directorate for Emergency Situations, organized in the period from 27-31 March2014, in Prijepolje, Republic of Serbia, within IPA Cross-border Cooperation between Montenegro and Serbia, a training for members of special force units, followed by field exercise ‘Swift water rescue’. From Montenegro, there were 20 persons from protection and rescue services in Podgorica and Berane, the Red Cross of Montenegro, NGO ‘Extrem’ and Montenegro Rafting Association. | Innovated and new action plans drafted, (2) 31/03/2014 [DR] National plans for protection against fire and floods are updated. Five municipal plans for protection against floods with additional protection and rescue measures are finalised. (3) 30/06/2014 [?] Assessment of competence and efficient action in plan implementation (2) 31/03/2014 [?] (3) 30/06/2014 [?] Increased level of coordinated actions of bodies in the recovery of consequences (2) 31/03/2014 [I] Emergency response state capacities increased through trainings and exercises. Regionally- capacities of partner countries increased through training and exercises, organised within cross-border cooperation between our country and the Republic of Serbia The procedure of sending emergency response teams following the EU methods and standards has been facilitated through development of standard operational procedures (SOP) based on Agreement on Cooperation in Protection from natural and Other Disasters between the Government of the Republic of Serbia and Montenegro (signed on October 4, 2010). (3) 30/06/2014 [I] Regionally- capacities of partner countries increased through training and exercises, organised within cross-border cooperation between our country and the Republic of Serbia The procedure of sending emergency response teams following the EU methods and standards has been facilitated through development of standard operational procedures (SOP) based on Agreement on Cooperation in Protection from natural and Other Disasters between the Governments of the Republic of Serbia and Montenegro (signed on October 4, 2010). |
| 7.19. | Strengthening coordination and cooperation for the purpose of more efficient resource engagement of protection and rescue services (1) 31/12/2013 [IC] Constant communication and coordination with municipal protection and rescue services. (2) 31/03/2014 [IC] (3) 30/06/2014 [IC] | POLICE ADMINISTRATION | IC Continuous activity | Number of joint meetings in the country and abroad, (1) 31/12/2013 [?] (2) 31/03/2014 [IC] Ministry of Interior-Directorate for Emergency Situations (DES): 10.-14. III 2014. Belgrade, R. Serbia –presence of 3 officers at the International workshop for the training of UNICRI CoE Project 11 IM 3 (UN International and Regional Legal Institute)- TOPIC- Integrating several methodologies for the risk assessment of CBRN abuse (Chemical, Biological, Radiological, Nuclear) 18 and 19 March 2014, Podgorica-two officers of DES and one officer of Environment Protection Agency attended Regional CBRN workshop organised by UN and EC on topic – Preparation, readiness and response Meeting of Ministry of Defence - Army of Montenegro and Ministry of Interior-Department for Emergency Situations on the occasion of preparation for international simulation exercise - SEESIM 14. The exercise is planned to take place in III quarter of this year with the aim of enhancing national resources in rescue actions. Ministry of Interior-DES, within started cooperation through IPA II, held meeting in relation to the preparation of the international exercise entitled MNE- QUIAKE- rescue from ruins, which is planned to take place on 20-24 October 2014 (EC, Croatia, Slovenia, Italy, etc.) (3) 30/06/2014 [IC] From 1-3 March 2014, a workshop was held in Podgorica on “National Plan for CBRN” with discussions concerning methodology for drafting a plan on CBRN which will be in compliance with Resolution 1540 (Against proliferation of weapons of mass destruction). The workshop was held under the auspices of UNICRI and the European Commission and members of the Montenegrin National Team for CBRN took part in the workshop. Two employees of the Directorate for Emergency Situations participated. 10.-14 March 2014, Belgrade, R. Serbia –presence of 3 officers at the International workshop for the training of UNICRI CoE Project 11 IM 3 (UN International and Regional Legal Institute)- TOPIC- Integrating several methodologies for the risk assessment of CBRN abuse From 18-19 March 2014, the „Regional workshop for preparation and response to CBRN” was held in Podgorica, in the organization of the Centre of Excellence and UNICRI-Interregional Crime and Justice Research Institute. Representatives of Serbia, FYR Macedonia, Bosnia and Herzegovina, Republic of Albania and Montenegro were participants in the workshop. During the workshop, interactive discussion was held on specific topics for response and preparation for CBRN reflected in the experience of the countries. Meeting of the Ministry of Defence – the Armed Forces of Montenegro and the Ministry of Interior-Department for Emergency Situations on the occasion of preparation for international simulation exercise - SEESIM 14. The exercise is planned to take place in the third quarter of this year with the aim of enhancing national capacity for efficient action in case of emergency situation and at the same time combating all kinds of terrorism, cyber terrorism and other contemporary threats. The Ministry of Interior-DES, within started cooperation through IPA II, held a meeting in relation to the preparation of the international exercise entitled MNE- QUIAKE- rescue from ruins, which is planned to take place on 20-24 October 2014 (EC, Croatia, Slovenia, Italy, etc.) Within the project IM3 «Integrated Multi-Perspective methodology to Assess Risks of CBRN Misuse», a two-day workshop and a study visit were organized on Methodology of risk assessment and misuse of CBRN material, in the period from 17-21 June 2014 in the Hague, Netherlands. The project is part of the EU initiative CBRN Risk Mitigation Centres of Excellence Initiative (CoE Initiative), which is supported by the UNICRI – Interregional Crime and Justice Research Institute. Three employees of the Ministry of Interior-DES and one employee of the Ministry of Defence participated. Number of joint interventions (1) 31/12/2013 [?] (2) 31/03/2014 [?] (3) 30/06/2014 [IC] The Ministry of Interior-DES: rescue team were engaged in the evacuation of population from the flooded area, as well as in rescue of property and livestock, pumping water from basements and other premises, delivery of water and food to affected population, as well as register of population in coordination with the teams of the Sector for Emergency Management of the Republic of Serbia. 19 rescuers who passed training on swift water rescue within the project of cross-border cooperation between Serbia and Montenegro in the area of protection against floods were engaged in these activities. The equipment acquired through this programme was used (two inflatable boats, 10 sets for swift water rescue, rubber boots, etc.). The Ministry of Interior-Police Administration: Engagement of the diving group of the Special Anti-Terrorist Unit in floods in Serbia. Nine members with the accompanying equipment were engaged in total. The Ministry of Defence-Armed Forces of Montenegro: Seven teams of the Armed Forces of Montenegro participated in providing assistance to affected population of Serbia – five rescue teams, one diving team and one sanitary team. 43 members of the Armed Forces of Montenegro were engaged in total. | Review of basic results (1) 31/12/2013 [?] (2) 31/03/2014 [IC] 20 members of swift water rescue teams trained and qualified. Drafted standard operational procedures for easier crossing of state borders by rescue teams in order to provide cross-border assistance in natural and other disasters. CBRN- proposal by the Ministry of Interior-Department for Emergency Situations to train and equip team for CBRN on national level within follow-up activities (Regional CBRN workshop organised by UN and EC on topic – Preparation, Readiness and Response on 18 and 19 March 2014 in Podgorica). (3) 30/06/2014 [IC] 20 members of the swift water rescue team from Montenegro were trained. Standard operative procedures were done for facilitated national border crossing for rescue teams for the purpose of providing cross-border assistance in natural and other disasters. Exchange of experience of the countries of the region regarding the legal grounds for response to CBRN (planning and organization); Goals and basis (Assessment of threat from CBRN); Role and responsibility of organizations providing response; Enabled access to the Methodology for risk assessment from CBRN. Acquired additional knowledge in drafting of a comprehensive risk assessment from CBRN material through development of an innovative risk assessment methodology. In the rescue actions of the diving group of the Special Anti-Terrorist Unit, 400 residents of Obrenovac and 100 residents of the nearby villages in the municipality of Obrenovac were evacuated. Nine dead bodies were found and transported from the flooded facilities. In the rescue actions, 400 residents were evacuated from the flooded areas of Obrenovac, 20 tons of food and water were delivered, along with the delivery of sanitary and medical supplies. The diving group explored 5 locations in search for drowned persons. |

## 8.	COOPERATION IN THE FIELD OF DRUGS	MI - Miodrag Lakovic, MH Jasna Sekulić

Recommendation 1 from the Screening Report – area ’Cooperation in the field of Drugs’

| No. | Measure/Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 8.2. * | Provide material resources and technical equipment for the Division by purchasing official vehicles and replacing old official and motor vehicles (1) 31/12/2013 [IC] (3) 30/06/2014 [IC] | POLICE ADMINISTRATION Miodrag Lakovic | IC December 2013 ; December 2014 ; December 2015; | Motor vehicles provided (1) 31/12/2013 [IC] Within internal reallocation of the Ministry of Interior, the Division for the fight against drugs secured two official vehicles. (3) 30/06/2014 [IC] In the first half of 2014, there was no procurement of official vehicles for the Division for fight against drugs. | Increased number of cases, criminal charges, persons deprived of liberty, seizures and quantity of seized narcotic drugs. (1) 31/12/2013 [IC] (3) 30/06/2014 [IC] |
| 8.3. * | Provide material resources and technical equipment for the Division by purchasing specialised equipment and equipment for protection for officers of the Division for Fight against Drugs: equipment used for raising the level of security of officers when on duty (bulletproof vest) -equipment used for clear identification of police officers when taking arrest actions (jackets, vests and caps with visible police symbols) -technical equipment to be used on the crime scene (specialised equipment for search of premises such as CT35 sets, manual reflectors, LED torches, devices for daily and nightly long-distance surveillance, etc.) Need assessment carried out IPA 2010. (1) 31/12/2013 [IC] (3) 30/06/2014 [IC] | POLICE ADMINISTRATION Miodrag Lakovic | IC December 2013; December; 2014; December; 2015; December; 2016; | Equipment purchased (1) 31/12/2013 [IC] Procurement of equipment planned for 2013 carried out. Procured 6 personal computers for applying measures of secret surveillance. (3) 30/06/2014 [IC] In the first half of 2014, there was no procurement of official vehicles for the Division for the fights against drugs. Under IPA Project 2012 which is implemented with partners from the Republic of Ireland, specification was made of required equipment which is expected to be procured by the end of 2014. | Increased number of cases, criminal charges, persons deprived of liberty, seizures and quantity of seized narcotic drugs. (1) 31/12/2013 [?] (3) 30/06/2014 [IC] Within implementation of IPA project 2012, specification was made of equipment which will be procured for employees of the Division for the fight against drugs by the end of 2014. The specification was submitted to the project management, tender is expected to be announced and this activity implemented. In the period from 1 January to 1 June 2014, in 112 separate seizure actions, 321.25 kilograms of narcotics were seized on the territory of Montenegro as follows: - marijuana – 319,941.77 grams - cocaine – 191.03 grams - heroin – 679.33 grams - synthetic drugs – 443.57 grams In the same period, 76 persons were prosecuted by the competence public prosecutors, against whom 59 criminal charges were filed on grounds for suspicion that they committed 67 criminal offences in the area of drug abuse. In June 2014, a police action “Kvart”, launched in 2013, conducted in cooperation with the high public prosecutor, was carried out. The case was directed towards a criminal group which dealt in a longer period with smuggling, and, primarily, with street distribution of heroin, “Suboxon” tablets, and marijuana on the territory of Podgorica. The criminal charge covered 10 persons, accused in the criminal charge of a criminal offence of unauthorised production, keeping and releasing for circulation of narcotics. In the course of conducting this months-long investigation, the following was seized in total: - more than 560 grams of heroin, around 2 kilograms of skunk, more than 300 tablets of ``Suboxon”, around 900 grams intended for mixing with heroin. - also seized were two guns, several pieces of ammunition, as well as several motor vehicles. |
| 8.4. | a. Training of officer in the country and abroad for: -use of secret surveillance measures in collecting evidence against organised criminal groups (a part through IPA 2012) -international investigations and joint investigation teams -new types of drugs and method for their detection (particularly as regards synthetic drugs and laboratories for their production). (1) 31/12/2013 [IC] (2) 31/03/2014 [IC] (3) 30/06/2014 [IC] | POLICE ADMINISTRATION Miodrag Lakovic | IC a. and b. December 2013 – IV quarter 2015; c. continuously | Number of trained officers (1) 31/12/2013 [IC] Number of training held – 5, number of officers trained 8 for: 1.Handling of informants and associates (organised by OSCE) - 4 officers 2. Training for work with operational connections (organised by NCA, former SOCA) – 1 officer 3. Conducting financial investigations in the area of organised crime (organised by the USA Embassy in Zagreb) – 1 officer 4. Training at ILEA in Budapest – 1 officer 5. Use of police web sites for communication and investigations (organised by the EC) – 1 officer. Out of the above mentioned trainings, two trainings were delivered in the country and three abroad. (2) 31/03/2014 [IC] Number of training held - 4, number of officers trained - 13 for: 1. Specialised training for acting upon discovering criminal acts of drug abuse, held at the ILEA Academy in Budapest – 6 officers 2. Training "Undercover investigators"(organiser NCA G. Britain – 1officer 3. Training "Hiring undercover collaborator " (organiser USA – ICITAP programme) - 4 officers 4. Training Fight against Trans-national organised crime" (organiser US Embassy in Podgorica) - 2 officers Three of mentioned trainings were held in the country and one abroad. (3) 30/06/2014 [IC] 1. Application of secret surveillance measures: Regional training for undercover investigators and handlers (organizer NCA from Great Britain) - 1 employee 2. International legal aid and fight against transnational organized crime and other forms of organized crime (organizer the USA Embassy in Podgorica) - 2 employees 3. Suppression of organized crime related to drugs "Building and conducting long-term investigations " (IPA 2012, European Commission, experts of the Republic of Ireland) - 12 employees 4. Training for English language and 40-day course for suppression of criminal offences in the area of drugs (organizer George Marshall Centre in Germany) - 1 employee Police Academy: Planning and preparation of secret surveillance measures 20-21.02. – 14 employees of the Criminal Police sector Secret surveillance measures – secret monitoring and observation 24-25.04. – 16 employees of the Police Administration 26-30.05. – 16 employees of the Police Administration Methods for building cases in the area of fight against drugs 26-30.06. – 12 employees of the Division for Fight against Drugs and Smuggling | Increased number of cases resolved by applying secret surveillance measures (1) 31/12/2013 [IC] Officers of the Division for Fight against Drugs, with application of secret surveillance measures and in cooperation with High and Special Public Prosecutor, are currently working on 7 cases (investigations), three of which with international partners. (2) 31/03/2014 [IC] Number of trainings held - 4, number of officers trained 13. 1. Specialised training for acting upon discovering criminal acts of drug abuse, held at the ILEA Academy in Budapest – 6 officers 2. Training "Undercover investigators"(organiser NCA G. Britain – 1 officer 3. Training "Hiring undercover collaborator " (organiser USA – ICITAP programme) - 4 officers 4. Training Fight against Trans-National Organised Crime" (organiser US Embassy in Podgorica) - 2 officers Three of mentioned trainings were held in the country and one abroad. The first meeting with expert team from the Republic of Ireland, selected as partner in the implementation of IPA Project 2010 is planned for 10 April 2014. In the reporting period, officers in the Division for Fight against Drugs have been engaged in 7 cases conducted with the application of secret surveillance measures, three of which were conducted on international plan. (3) 30/06/2014 [IC] In the first half of 2014, officers of the Division for Fight against Drugs were engaged in 10 cases which are conducted with application of secret surveillance measures. Out of that, 5 cases are conducted with the Special Public Prosecutor for fight against organized crime ("Virus", "Atlantik", "Šetač 2", "Albatros" and "Kontejner"), and 5 with the High Public Prosecutor ("Kvart", "Čistač", "Kanal", "Rivijera" and "Klok"). |

Recommendation 1 and 3 from the Screening Report – area ‘Cooperation in the field of Drugs’

| No. | Measure/Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 8.5. | Strengthen cooperation between the Police Administration and the Customs Administration through joint controls at border crossing points (1) 31/12/2013 [IC] (2) 31/03/2014 [IC] (3) 30/06/2014 [IC] | Police Administration Milan Tomic | IC Continuous activity | Increased number of conducted joint controls at the border crossing points (1) 31/12/2013 [IC] There were 25627.00 of joint controls conducted by officers of Police and Customs Administrations of Montenegro. During these controls, in 2013 it was seized: MARIJUANA - 924, 017kg HEROIN - 4,260 kg The most important seizures: In February and March 2013, at border crossing point (BCP) Debeli brijeg three seizures of marihuana were made, in total quantity of about 160 kg. Also, in August, at border crossing point Scepan polje it was seized 25, in September 31.5 kg and at BCP Debeli brijeg 59 kg of this drug. In November, 30 kg of this drug was seized at BCP Božaj. In December 2013, 20kg of this drug was seized at BCP Debeli brijeg. (2) 31/03/2014 [IC] There were 2560 of joint controls carried out by officers of Police and Customs Administrations of Montenegro. During these controls in January and February 2014 it was seized 62.53 kg of drugs at border crossing points. (3) 30/06/2014 [IC] In the period from 1 January to 12 June 2014, through joint controls conducted by officers of the Police Administration and the Customs Administration of Montenegro, 18 seizures of narcotics were carried out as follows: - 17 seizures at the border crossing points Sukobin, Debeli Brijeg, Božaj and Šćepan Polje where 354.80 kilograms of marijuana were seized - 1 seizure in the customs duty branch office Free Zone Bar where 250 kilograms of cocaine were seized. | Increased number of seizures and quantities of seized drugs on border crossing points (1) 31/12/2013 [IC] During joint controls carried out by officers of Police and Customs Administrations in total it was seized: marihuana - 924,017 kg heroin - 4,260 kg The most important seizures: In February and March 2013, at border crossing point (BCP) Debeli brijeg three seizures of marihuana were made, in total quantity of about 160 kg. Also, in August, at border crossing point Scepan polje it was seized 25, in September 31.5 kg and at BCP Debeli brijeg 59 kg of this drug. In November, 30 kg of this drug was seized at BCP Božaj. In December 2013, 20kg of this drug was seized at BCP Debeli brijeg. The most important seizure: (2) 31/03/2014 [IC] Through joint controls of Police and Customs Administrations carried out at border crossing points it was seized 62.53 kg of narcotic drugs, which makes a significant share in total drug quantity seized on the territory of Montenegro, which amounts 107.71 kg. (3) 30/06/2014 [IC] By conducting joint controls by officers of the Police Administration and the Customs Administration, in the period from 1 January to 12 June 2014, 354.80 kilograms of marijuana (17 seizures) were seized at the border crossing points Sukobin, Debeli Brijeg, Božaj and Šćepan Polje On 4 June 2014, 250 kilograms of cocaine were seized in the customs duty branch office Free Zone Bar |
| 8.6. | Exchange of operational data with the EUROPOL and partner services from other countries (1) 31/12/2013 [IC] Direct exchange of operative data with EUROPOL did not start yet, given the fact that Operational Agreement on Cooperation with EUROPOL has still not been signed. Therefore, the exchange of operational data with the Europol is carried out through one of Europol state members. (2) 31/03/2014 [IC] (3) 30/06/2014 [IC] | POLICE ADMINISTRATION Miodrag Lakovic | IC Continuous activity | Increase in the number of international investigations (2) 31/03/2014 [IC] Officers in the Division for Fight against Drugs exchanged 55 pieces of information with police forces of the EU countries through NCB Interpol Office Podgorica. Also, in direct communication with liaison officers or police forces in partner countries we exchanged 44 pieces of information with operative data. There were 13 operational meetings held with representatives of police forces of the republic of Italy, G.Britain, R. Serbia and USA. (3) 30/06/2014 [IC] In the period from 1 January to 1 June 2014, officers of the Division for Fight against Drugs exchanged 70 pieces of information with police services of EU Member States through NCB Interpol Office Podgorica. We also exchanged 56 pieces of information with operative data in direct communication with liaison officers or police services of partner countries. 21 operative meetings were held with representatives of the police of the Republic of Italy, USA, B & H, Republic of Croatia, Republic of Serbia and Great Britain. | Increased number of international cases, number of seizures, number of prosecuted persons and quantity of seized drugs within international cooperation (2) 31/03/2014 [?] (3) 30/06/2014 [IC] In the first 5 months of 2014, officers of the Division for Fight against Drugs were engaged in 5 cases carried out with international partners: "Atlantik", "Virus", "Setač 2", "Albatros" and "Kontejner". The cases are conducted with the Special Public Prosecutor for fight against organized crime. Very significant is the participation of the Division for Fight against Drugs in the work of the EUROPOL Group “Mozzarella” founded on 7 December 2011, with the aim of combating organized crime groups of Western Balkan that smuggle cocaine from South America to Europe. At the last meeting of the Group held on 4 June 2014 in the Netherlands, a report was adopted stating that the results of Montenegro thus far had been very good, satisfaction was expressed with the cooperation thus far, manner of exchange and the quality of submitted data (for the purpose of illustration, in relation to a total number of SIM cards found in the EUROPOL database which are used by the persons involved in smuggling of cocaine, the Police Administration submitted data on 191 SIM cards, while other countries, except for the Republic of Serbia, submitted a significantly lower amount of data. On the basis of data submitted by the Police Administration of Montenegro, 400 kilograms of cocaine were seized in the Netherlands on 1 December 2013 within the case “White Bowl” |
| 8.7. | Initiate and participate in international investigations (1) 31/12/2013 [IC] (2) 31/03/2014 [IC] (3) 30/06/2014 [IC] | POLICE ADMINISTRATION Miodrag Lakovic | IC Regular activity; December 2013; December 2014; December 2015; December 2016; | Increase in the number of international investigations (1) 31/12/2013 [IC] Three international investigations were initiated, filed under code name “Atlantic” (carried out with SOCA), “Ocean” (carried out with the Ministry of interior of the Republic of Italy) and “Virus” (carried out by the Ministry of Interior of the Republic of Serbia and the Ministry of Interior of Bosnia and Herzegovina). (2) 31/03/2014 [IC] Officers in Division for Fight against Drugs are currently conducting 3 cases on international plan. (3) 30/06/2014 [IC] In the first half of 2014, a very intensive cooperation with international partners was continued, through exchange of operative information, conducting of joint investigations and carrying out of cases and police actions towards exposing and prosecuting organized criminal groups acting at the national and international level. 21 operative meetings were held in country and abroad with representatives of police services of the USA, Republic of Croatia, B&H, British Agency NCA, Federal Republic of Germany, Kingdom of Belgium, Kingdom of the Netherlands, Republic of Serbia, Republic of Albania, Australia, and with representatives of EUROPOL, DEA Office in Rome and SELEC Centre from Bucharest. | Increased number of international cases, number of seizures, number of prosecuted persons and quantity of seized drugs within international cooperation (1) 31/12/2013 [?] (2) 31/03/2014 [IC] Officers in Division for Fight against Drugs are currently conducting 3 cases on international plan. (3) 30/06/2014 [IC] In the first half of 2014, officers of the Division for Fight against Drugs, apart from the international investigations conducted from the previous period, initiated opening of 2 more international cases in June: “Albatros” and “Container”. |

Recommendation 2 from the Screening report – area ‘Cooperation in the Field of Drugs’ 	MF - Milena Durkovic

| No. | Measure/Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 8.8. * | Forming of the working group for the development of the Risk Analysis and the assessment of the required material and technical resources with the aim of more efficient surveillance over the Port of Bar (1) 31/12/2013 [I] (2) 31/03/2014 [I] (3) 30/06/2014 [I] | MINISTRY OF FINANCE Milena Durkovic | I September 2013; | Working group formed (1) 31/12/2013 [I] Decision 03/01 no. 11975/4 dated 18.10.2013 on establishing joint working group for drafting Risk analysis and assessment of the required material and technical resources for more efficient surveillance over the Port of Bar was adopted. It consists of three representatives from the Customs Administration and Police Administration. The group started to work immediately after its establishment. (3) 30/06/2014 [I] | More efficient cooperation between CA and MI (1) 31/12/2013 [I] Competent joint team of the Customs Administration and the Police Administration has made document containing knowledge, experiences and information from both services. (2) 31/03/2014 [I] Risk analysis drafted and it will be used for profiling risk during control of containers, goods and passengers at BCP Port of Bar. (3) 30/06/2014 [I] |
| 8.9. * | Development of the Risk analysis and the assessment of the required material and technical resources for the operative work on the improved surveillance over the Port of Bar (1) 31/12/2013 [I] | MINISTRY OF FINANCE Milena Durkovic | I December 2013 | Analysis developed (1) 31/12/2013 [I] Joint working group drafted a document “Risk analysis and the assessment of the required material and technical resources for more efficient surveillance over the Port of Bar”. The activity was completed on 25 December 2013. Risk profiles were entered into Risk Management System of the Customs Administration and are available to Police Administration. (2) 31/03/2014 [I] Risk profiles entered into Risk Management System of the Customs administration and made available to the Police Administration (1) 31/12/2013 [I] | More efficient control of goods and passengers, increase in the number of controlled containers (1) 31/12/2013 [IC] Implementation of measures and recommendations from the Risk Analysis will result in the increase of controlled containers. Increase in the number of seizures of drugs and smuggled goods (1) 31/12/2013 [IC] Increase in the number and quality of control will result in strengthening security and surveillance in the Port of Bar. |
| 8.10. | Selection and training of officers who will, when necessary, be engaged in the operative team for the control of goods and passengers in the Port of Bar (1) 31/12/2013 [IC] Joint operative team for the control of goods and passengers in the Port of Bar formed, Decision 04/01 no. D-16385/2 dated 25.12.2013. The Joint operative team for the control of goods and passengers in the Port of Bar was formed and consists of officers from the Customs Administration, Border Police Department and Criminal Police Department (2) 31/03/2014 [I] A Joint operative team for control of goods and passengers in the Port of Bar formed; Decision 04/01 No. D-16385/2 dated 25 December 2013 The Joint operative team for the control of goods and passengers in the Port of Bar was formed and consists of officers from the Customs Administration, Border Police Department and Criminal Police Department | MINISTRY OF FINANCE Milena Durkovic | I December 2013 – ; IV quarter 2015 |  | Increased number of conducted controls in the Port of Bar. (1) 31/12/2013 [IC] Activities of joint operative team will result in increased number of controlled container and passengers. (2) 31/03/2014 [I] Prerequisites for intensified control of container traffic in the Port of Bar created. Increase in the number of seizures and the quantity of seized drugs in the Port of Bar (1) 31/12/2013 [IC] Activities of joint operative team will result in increased number of controlled container and passengers. (2) 31/03/2014 [?] |
| 8.11. * | Providing premises and equipment for work of the joint operative team (2) 31/03/2014 [IC] (3) 30/06/2014 [IC] | MF Milena Durkovic | IC December 2014; | Provided material and technical conditions (2) 31/03/2014 [IC] The Customs Administration provided a premise for the needs of the joint operative team At the beginning of April, representatives of UNODC visited the Port of Bar with a view to overviewing the further implementation of activities, i.e. equipping of this premises that the Customs Administration designated for the work of the operative team. Note: At the beginning of April, representatives of UNODC visited the Port of Bar with a view to overviewing the implementation of activity of equipping the premises designated for the work of the operative team. (3) 30/06/2014 [IC] The Customs Administration provided premises for the work of the joint operative team of the Customs Administration and the Police Administration. Through the continuation of the Project of UNODC “Control of Containers”, adaptation and equipping of the premises will be carried out. | Increased number of controls conducted in the Port of Bar, (2) 31/03/2014 [IC] The next visit of representatives of UNODC, through the project of which this activity is implemented, is planned for April 2014 when the equipping of the premises for the work of the operative team will be discussed. (3) 30/06/2014 [?] In the period from 1 January to 12 June 2014, in the customs duty branch office Free Zone in the Port of Bar 263 containers were scanned, 441 thorough examinations of containers were carried out, as well as 200 partial examinations. Thus on 4 June 2014, 250 kilograms of cocaine were detected and seized in the customs duty branch office Free Zone Bar. Increased number of seizures and quantity of seized drugs in the Port of Bar (3) 30/06/2014 [IC] On 4 June 2014, 250 kilograms of cocaine were detected and seized in the customs duty branch office Free Zone Bar. |

Recommendations 4 and 5 from the Screening Report – area ‘Cooperation in the Field of Drugs’

| No. | Measure/Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 8.11. | Filling of the missing staff of the National focal point/National information unit for drugs in the Department for Drugs.[76] (3) 30/06/2014 [PI] | MINISTRY OF HEALTH Jasna Sekulic | PI June; 2014; | Employees in the labour relationship / two currently missing employees (3) 30/06/2014 [PI] - With Act No 11-27/2014 of 30 June 2014, one employee was designated for the position of Independent Advisor III in the Department for Drugs. - With Act No 11-29/2014-2 of 7 July, the Human Resources Administration was sent a required documentation for announcing an internal competition for filling the position of Independent Advisor II in the Department for Drugs, for an indefinite period of time. We point out that these obligations are in compliance with the recommendation of the European Commission and that they are fulfilled in accordance with the adopted and valid Rulebook on Internal Organization and Job Descriptions. | Employees of the focal point for drugs in the process of training in the programmes with EMCDDA. (3) 30/06/2014 [?] |
| 8.13. | Training of staff in the Focal Point for Drugs, with capacity building of national network for the information and data on drugs in line with the EMCDDA standards. (1) 31/12/2013 [IC] (2) 31/03/2014 [IC] (3) 30/06/2014 [IC] | MINISTRY OF HEALTH Jasna Sekulic | IC Continuously by phases; until membership; | Number of trainings and officers trained (1) 31/12/2013 [IC] Delivered 7 trainings and 5 officers trained. 1. Training in the Department for the drugs of the Republic of Croatia and other institutions competent in the field of drugs. 2. Training in the Ministry of Health of the Republic of Slovenia; bilateral cooperation through development technical assistance. 3. Training in the Department for the drugs of the Government of Republic of Italy; 4. Workshop with international and national participants organised by Ministry of Health of Montenegro and TAIEX. 5. International school for state administration for the field of drugs – the Government of the Republic of Italy. 6. Training with EMCDDA Reitox Academy.(monitoring drugs) 7. Training with EMCDDA Reitox Academy (infectious deceases) Remark: number of trained officers for now is 6, until we employ necessary staff into the Department for drugs in the Ministry of Health (2) 31/03/2014 [IC] Training with international participation in organisation of TAIEX "Workshop on improving the quality of drugs addiction treatment in the process of EU integration" (Sarajevo, 26-27 March 2014) participation of three experts. (3) 30/06/2014 [IC] Three seminars were organized attended by 28 employees/experts. 1.EMCDDA Reitox Academy "Drug Law offences in the WB : from definition to monitoring"(Podgorica,2-3.04.2014) 2.EMCDDA Reitox Academy "Effectiveness and efficiency of drugs use prevention programmes"(Ljubljana,28-29.04.2014) 3.International school on addiction illnesses of the European Centre for Peace and Development (Kotor,29.05-1.06.2014) | Adopted and applied standards and indicators for: (1) 31/12/2013 [IC] Standards will be adopted and applied continuously by phases until the membership in the EU. (2) 31/03/2014 [IC] Updating of application methods of specific types of treatment. (3) 30&06/2014 [IC] 1. Developed thematic material as a precondition for participation in Reitox Academies, are in line with EMCDDA indicators and standards, which represents part of the process of adoption and application of standards. 2. Continuous expert education and updating of expert knowledge in the areas of addiction illnesses. Collecting and analysis through operative national network. (1) 31/12/2013 [IC] Remark: Standards will be adopted and applied continuously by phases until the membership in the EU. (2) 31/03/2014 [?] (3) 30/06/2014 [IC] Standards are adopted and applied by stages continuously until the membership. |
| 8.15. | Training of participants in the Early Warning System (EWS) in case of new types of psychoactive substances (1) 31/12/2013 [IC] (2) 31/03/2014 [IC] (3) 30/06/2014 [IC] | MINISTRY OF HEALTH Jasna Sekulic | IC Continuously | Number of held trainings and participants trained (1) 31/12/2013 [IC] The first and initial training for 3 participants. Study visit to the National EWS of the Government of R. Italy (2) 31/03/2014 [NI] There were no trainings organised during the reporting period referring to I quarter of 2014. Division for drugs prepared thematic materials for participation in two Reitox Academy with EMCDDA to be held during April 2014. As requested, they were submitted to the EMCDDA as condition to be eligible to participate in the training. (3) 30/06/2014 [IC] Seminar/training with participation of 10 employees. EMCDDA Reitox Academy "Monitoring drug law offences and responding to new psychoactive substances"(Podgorica, 2-3.04.2014) | Application of the adopted standards. Capacity to monitor trends regarding the appearance of new synthetic substances and exchange of information with the international partners. (1) 31/12/2013 [IC] Standards will be adopted and applied continuously in phases until the membership to the EU and depending upon implementation of other measures. Remark: Full implementation of this indicator depends on measures 8.17; 8.6; 8.12; 8.13 (2) 31/03/2014 [?] (3) 30/06/2014 [IC] Prepared thematic materials as the precondition for participation at the seminar in accordance with the EMCDDA request. |
| 8.17. | Establish the functionality, through the stages, of the National Focal Point and the national information system, as a preparation for the participation in the European network (Reitox) and in reporting to the EMCDDA (1) 31/12/2013 [IC] (2) 31/03/2014 [IC] (3) 30/06/2014 [IC] | MINISTRY OF HEALTH Jasna Sekulic | IC Continuously by phases; until membership | Development of annual national reports in accordance with the EMCDDA standards (1) 31/12/2013 [IC] Division for Drugs participates in EMCDDA training programmes: Reitox Academy : "Prevention of infectious disease among people who inject drugs"; "National monitoring system". Remark: They are delivered in parallel with activities from measure 8.13.The indicator can be carried out after full adoption of EMCDDA standards. (2) 31/03/2014 [NI] There were no activities implemented in the reporting period, which refers to I quarter 2014. Division for drugs prepared thematic materials for participation in two Reitox Academy with EMCDDA to be held during April 2014. As requested, they were submitted to the EMCDDA as condition to be eligible to participate in the training. (3) 30/06/2014 [IC] With a view to establishing by stages the functionality of the national network for information and data on drugs, the Agreement was signed with EMCDDA on implementation of GPS (general population survey on drugs use) pilot phase, by EMCDDA standards. | Availability of data and information on the condition in the area of drugs for the purpose of planning national programmes and measures and participation in the international exchange of information and data. (1) 31/12/2013 [RK] Collected data from the area of “infectious disease among people who inject drugs” for the needs of Reitox Academy, organised by EMCDDA. Remark: Indicator of impact will be fully carried out after full application of adopted standards for reporting to EMCDDA. (2) 31/03/2014 [?] (3) 30/06/2014 [IC] Implementation of the GPS pilot phase (general population survey on drugs use) by EMCDDA standards leads to adoption and application of standards and prescribed indicators. |

Recommendation 6from the Screening Report – area ‘Cooperation in the Field of Drugs’

| No. | Measure/Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 8.18. | Forming of multi-sector working group with the task to develop annual report on implementation of objectives set out in the Action Plan for the period 2013 – 2016 (2) 31/03/2014 [I] (3) 30/06/2014 [I] | MINISTRY OF HEALTH Jasna Sekulic | I January - March; 2014 | The Government adopted the Information and Annual report on implemented objectives and activities set out in Action Plan for 2013 (2) 31/03/2014 [I] The working group tasked to develop annual report on implementation of objectives set out in Action Plan for the period 2013-2015 is formed by the Ministry of Health’s Decision No.. 51-1046/2013. The working group consists of the representatives of following institutions: Ministry of Health, Ministry of Justice, Ministry of Interior – Police Administration, Ministry of Finance – Customs Administration, Ministry of Labour and Social Welfare, NGO. The Government, at its session held on April 3, 2014 adopted the Report on implemented objectives and activities set out in Action plan for 2013 for the implementation of the Strategy of Montenegro for the Prevention of Drug Abuse2013-2020. (3) 30/06/2014 [?] | Improvements in area of preventing drug abuse, in accordance with the strategic framework through functional monitoring (2) 31/03/2014 [IC] The indicator of impact will be presented upon development of mid-term assessment of the strategic documents, in accordance with planned measure. (3) 30/06/2014 [?] |

OBJECTIVE: Aligning and implement legislation and strategic documents

| No. | Measure/Activity | Competent body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 8.21. * | Adopt the Law Amending the Law on Prohibition of Drug Abuse, transposing the Council Decision CD 2001/419/JHA (1) 31/12/2013 [I] (3) 30/06/2014 [I] | MINISTRY OF HEALTH Jasna Sekulic | I December 2013; | The Law adopted. (1) 31/12/2013 [R] Adopted the Law Amending the Law on Prohibition of Drug Abuse. It was published in the Official Gazette of Montenegro no. 35/2013 dated 23 August 2013. | Practical implementation of the concerned Decision regarding international official exchange and transmission of samples of drugs for the purpose of forensic analysis between police contact points of the involved countries. (1) 31/12/2013 [I] Conditions for practical implementation of the Decision 2001/419/JHA provided |

## 9.	CUSTOMS COOPERATION 	CA - Rade Lazovic

Recommendation 2 from the Screening Report – area “Customs Cooperation”

| No. | Measure/Activity | Competent Body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 9.1. * | Drafting of IT Strategy in accordance with Customs Administration Business Strategy by the company “Analysis for Economic Decisions (ADE) - Consulting & Advisory Services” - Belgium (1) 31/12/2013 [I] | CUSTOMS ADMINISTRATION Milena Durkovic | I October 2013; | IT Strategy drafted (1) 31/12/2013 [I] Experts of the company "Analysis for Economic Decisions" (ADE) - Belgium, developed IT Strategy in accordance with the Customs Administration Business Strategy, in October 2013–as provided by the Action Plan for Chapter 24: Freedom, Justice and Security | Customs Information System developed in accordance with the EU standards (1) 31/12/2013 [IC] After IT strategy is drafted, improvement of Customs Information system will be the subject of the IPA programme 2014 – 2016. |

Recommendation 3 from the Screening Report – area “Customs Cooperation”

| No. | Measure/Activity | Competent Body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 9.7. * | Amendment to the Rulebook on internal organisation and job description of the Customs Administration The Customs Administration has drafted a new Rulebook on internal organisation and job description of the Customs Administration, which is currently in the phase of adoption by the Ministry of Finance. The most important innovation in the organisational structure of the Customs Administration is establishment of a separate organisational unit – Section for International Customs Cooperation and European Integration, which will be held directly responsible to director of the Administration, with strengthened administrative capacities with a view to efficient functioning and meeting EU standards in the area of international customs cooperation. (1) 31/12/2013 [I] | CUSTOMS ADMINISTRATION Milena Durkovic | I Dec.13 | Rulebook on internal organisation and job description of the Customs Administration adopted (1) 31/12/2013 [I] Activity was carried out. New Rulebook on internal organization and job description of the Customs Administration was adopted (Ministry of Finance no. 08-5983/1 dated 10.06.2013). | Increased number of exchanged information within international cooperation, strengthening capacities of the Section for International Customs Cooperation (1) 31/12/2013 [I] Number of exchanged information in international cooperation is increased. Capacities of the Section for international customs cooperation are enhanced. |

## 10.	COUNTERFEITING OF THE EURO	MIA - Dragan Radonjic

Recommendation 1 from the Screening Report– area 'Counterfeiting of the euro'

| No. | Measure/Activity | Competent Body | Deadline Status | INDICATOR OF RESULT | INDICATOR OF IMPACT |
| --- | --- | --- | --- | --- | --- |
| 10.3. | Trainings on international and national level for the area of Counterfeiting of the euro (2) 31/03/2014 [NI] There were no trainings organised during the reporting period. (3) 30/06/2014 [IC] | POLICE ADMINISTRATION Dragan Radonjic | IC January 2014 -December 2018 | Number of trainings organised, (2) 31/03/2014 [NI] There were no trainings organised during the reporting period. (3) 30/06/2014 [IC] 19-23 May2014, hotel Splendid (Budva, “11th South-East Conference” – fight against counterfeiting of Euro, in the organization of OLAF and the Central Bank of Montenegro, attended by two employees of the Ministry of Interior-Police Administration. Police Administration: A letter was sent to the Police Academy in Croatia to provide expert assistance to us, we are awaiting the response. Number of officers trained (2) 31/03/2014 [NI] There were no trainings organised during the reporting period. (3) 30/06/2014 [IC] 19-23 May2014, hotel Splendid (Budva, “11th South-East Conference” – fight against counterfeiting of Euro, in the organization of OLAF and the Central Bank of Montenegro, attended by two employees of the Ministry of Interior-Police Administration. | Higher level of quality and efficiency in the ongoing investigations and filed criminal charges in area of counterfeiting of the euro (2) 31/03/2014 [NI] It is not possible to report on any indicator of impact at this moment. (3) 30/06/2014 [?] |